## Cover
QUARTELY PROJECT PROGRESS REPORT(Including FACE/Financial Reporting) |  |  | Q1/2014
Country: Tuvalu |  | Project: Increasing Resilience of Coastal Areas and Community Settlements to Climate Change in Tuvalu
Project no.: 00072222; Award ID: 00058214 (from Atlas)
UNDP Outcome: FJI_OUTCOME47 |  | Improved resilience of PICTs, with a particular focus on communities, through the integrated implementation of sustainable environmental management, climate change adaptation and/or mitigation and disaster risk management.
Strategic Plan | Provisional Corporate Outcome: | Development plans and programmes integrate environmentally sustainable solutions in a manner that promotes poverty reduction, MDG achievement and low-emission climate-resilient development
IWP | UNDAF Outcome Indicators: | Share of population with sustainable access to improved water sources and to renewable energy (disaggregated by gender and age)
All indicators disaggregated by sex and age
| 2015 UNDAF Outcome Target: Final year of UNDAF | Increase in % of population with improved access to safe drinking water in 3 PICs
| 20xx Outcome Target: | Annual UNDAF Target from UNDAF RRF
| UNDAF Outcome Baseline: | 97.9% have access to clean drinking water
(Name of Country) National Development Strategy |  | Te Kakeega II (National Strategy for Sustainable Development)
Details to be filled in by UNDP as part of programme formulation/implementation process and annexed to the project document/AWP as the monitoring tool to be used quarterly by the IP.
Annexes: 1. Risk Log 2. Quarterly Financial Report (FACE) Form
Please note that FACE Forms/Advance of Funds will not be processed unless attached to the Quarterly Progress Report (QPR)
Headings
UNDP to input data
Implementing Partner to input report

## Outcome 1
| Output Indicators | Baseline | Annual (yyyy) Target | On track, Off track or Partially on track | Annual Budget | Remaining Output Budget | Quarterly Delivery: (USD) |  | Balance: (USD) |  |  | Output Indicators | Baseline | Annual (yyyy) Target | On track, Off track or Partially on track | Annual Budget | Remaining Output Budget | Quarterly Delivery: (USD) |  | Balance: (USD) |  |  |  | Output Indicators | Baseline | Annual (yyyy) Target | On track, Off track or Partially on track | Annual Budget | Remaining Output Budget | Quarterly Delivery: (USD) |  | Balance: (USD)
Output 1.1 - National Development Plan (Te Kakeega II) and implementation matrix is reviewed to incorporate climate risk and resilience. |  |  |  |  | (USD): | (USD): |  |  |  |  | Output 1.2-- A National Climate Change Advisory Council is established, to support national policy making and planning |  |  |  |  | (USD): | (USD): | [5 empty] | Output 1.3 -- A national awareness campaign for local communities and kaupule is designed and implemented. |  |  |  |  | (USD): | (USD):
[5 empty] | (Output lump sum) | (Output lump sum) | [9 empty] | (Output lump sum) | (Output lump sum) | [10 empty] | (Output lump sum) | (Output lump sum)
| Percentage of national planners, kaupule, and communities (respectively) in Tuvalu able to identify climate-related risks and prioritize, plan, and implement effective adaptation measures; Number of coastal zone management –related policy documents formulated and approved as a result of the project | From AWP | National policies or action plans on coastal management are developed or revised to integrated climate-risks and resilience; the NCCAC is fully functional in coordinating climate change related policy and development processes, the 10 primary and 2 secondary schools functioning in Tuvalu are capacitated to conduct climate change related education programmes |  | 64500 | [6 empty] | Percentage of national planners, kaupule, and communities (respectively) in Tuvalu able to identify climate-related risks and prioritize, plan, and implement effective adaptation measures; Number of coastal zone management –related policy documents formulated and approved as a result of the project | From AWP | National policies or action plans on coastal management are developed or revised to integrated climate-risks and resilience; the NCCAC is fully functional in coordinating climate change related policy and development processes, the 10 primary and 2 secondary schools functioning in Tuvalu are capacitated to conduct climate change related education programmes |  | 12700 | [7 empty] | Percentage of national planners, kaupule, and communities (respectively) in Tuvalu able to identify climate-related risks and prioritize, plan, and implement effective adaptation measures; Number of coastal zone management –related policy documents formulated and approved as a result of the project | From AWP | National policies or action plans on coastal management are developed or revised to integrated climate-risks and resilience; the NCCAC is fully functional in coordinating climate change related policy and development processes, the 10 primary and 2 secondary schools functioning in Tuvalu are capacitated to conduct climate change related education programmes |  | 95000
Progress on quarterly activities (IP to complete this section) |  |  |  |  | Next quarter planned activities and budget | [5 empty] | Progress on quarterly activities (IP to complete this section) |  |  |  |  | Next quarter planned activities and budget | [6 empty] | Progress on quarterly activities (IP to complete this section) |  |  |  |  | Next quarter planned activities and budget
(Activities Scheduled and Results achieved)Note: All activities on AWP to be listed | [10 empty] | (Activities Scheduled and Results achieved)Note: All activities on AWP to be listed | [11 empty] | (Activities Scheduled and Results achieved)Note: All activities on AWP to be listed
Activity Result 1.1.1:Integration of Climate risk into the TeKakeega II and implementation matrix review in the overall development framework |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter | [5 empty] | Activity 1.2.1: Formalize the establishment of the NCCAC through revision of the NCCAC ToR to reflect recommendation of the SNAP and NCCP, confirmation of funding pool, and preparation of a cabinet paper for cabinet approval of this national body. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter | [6 empty] | Activity Result 1.3.1: to design and implement a project communication strategy for effective awareness campaign. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
This activity result is complete. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD | The establishment of the National Advisory Council on Climate Change (NACCC) was formally initiated and endorsed by Cabinet and was launched on 16th January 2014. While the project document suggested the Council to be called the National Climate Change Advisory Council (NCCAC), Cabinet named this Council the National Advisory Council on Climate Change (NACCC). Since its inception, the Council has met 4 times, three monthly meetings and an Emergency Meeting that was convened by the Prime Minister on 13th March 2014. The Emergency meeting was to formalise and confirm the Council members to ensure that directors are included in the Council. The Council comprises of the Secretary to Goverment (Chair), Director of Environment (Deputy Chair), Attorney General, Director of Budget and Planning, Director of Fisheries, Director of Meteorological Services, Director of Public Works Department, Director of Lands and Survey, Director of Agriculture, Director of Energy, Director of Women, Director of Home Affars and Rural Development, Director of Tuvalu Assoiation of NGOs (TANGO), Funafuti Kaupule Secretary, Ekalesia Kelisiano Tuvalu Secretary General, Representative from the Private Sector, and the NAPA Project Coordinator as observer. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD |  | This activity was reported in the Third Quarter Progress Report as having been completed. However, it was evident that the design and implementation of a project communication strategy for effective awareness campaign has not been completed. As alluded to in the NAPA Annual Progress Report 2013, this activity is the responsibility of the Knowledge and Information Management Officer that was supposed to have been recruited in the earlier part of 2013. The Project manager has indicatoed that the Knowledge and Information Management Officer will be recruited during the first half of the second quarter, so this activity can take place as soon as the officer is on board. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[16 empty] | Workshop costs (venue/refreshemnts |  |  | 75700 |  | 1200 | 3750 | [5 empty] | Travel |  |  | 71600 |  | 20000
[16 empty] | supplies |  |  | 72500 |  | 500 | [6 empty] | Training Officers Salary |  |  | 71300 |  | 5000
[28 empty] | supplies |  |  | 72500 |  | 500
[5 empty] | Total |  |  |  |  | 0 | [5 empty] | Total |  |  |  |  | 1700 | [6 empty] | Total |  |  |  |  | 25500
Activity Result 1.1.2:Conduct revision of the Public Works Department Sector Plans to reflect climate risk reduction |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter | [5 empty] | Activity 1.2.2: Undertake trainings of NCCAC members on climate change programming and policy mainstreaming. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter | [6 empty] | Activity Result 1.3.2: to develop posters, bookmarks etc on the Climate Change Policy and Strategic National Action Plan (SNAP) |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
This activity has not been carried out yet. A request was sent to the Permanent Secretary to Government for permission for PMU to conduct revision of the Public Works Department Sector Plans, and permission has been granted. What is needed now is for PMU to designate someone to be responsible for carrying this activity out in the second quarter 2014. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD | This activity is yet to be implemented. Now that the NACCC has been formally endorsed by cabinet, training of NACCC members on climate change programming and policy mainstreaming is expected to be carried out by the first week of the second quarter of 2014. An international Climate Change Expert is requested by the Chair of the National Advisory Council on Climate Change to deliver internationa negotiation skills at the traning together with the "Science of Climate Change" by the NTA. These topics are seen as essential elements for enhancing the understanding of Council members in order to better deliver policy advises to Cabinet. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD |  | Again developing posters and bbokmarks on the Climate Change Policy and Strategy National Action Plan (SNAP) is the responsibility of the Knowledge and Information Officer. The need to recruit a KIO is of paramount importance to the project and should be a priority activity for the project to be recruited in the first quarter of 2014. Once the officer is on board, this activity will commence in the second quarter and continue to the third quarter. |  |  |  |  | International consultant |  |  | Acct. code | Amt. LOC | Amt USD
[5 empty] | Miscellaneous |  |  | 74500 |  | 3000 | [5 empty] | Training, workshops and conferences |  |  | 75700 |  | 40000 | [6 empty] | Audio visual & print production |  |  | 74200 |  | 20000
[5 empty] | Travel |  |  | 71300 |  | 5000 | [5 empty] | Supplies |  |  | 72500 |  | 2000
[5 empty] | Total |  |  |  |  | 8000 | [5 empty] | Total |  |  |  |  | 42000 | [6 empty] | Total |  |  |  |  | 20000
Activity Result 1.1.3: Undertake training on how to mainstream climate change induced risks in professional sectors. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter | [17 empty] | Activity Result 1.3.3: Awareness Road Show on Climate Change Science and the National Policy on Climate Change completed. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
As reported in the last quarter report (Q4 2013) undertaking training on mainstreaming climate change induced risks in professional sectors has not been accomplished yet. While there was a training workshop of kaupule, falekaupule, youth, agriculture, and women representatives held in August 2013, professional sectors of the government including Public Works Department, Department of Environment, Home Affairs, Health, MET, were not involved in that training. They have not yet been trained on mainstreaming climate change induced risks into their sector plans. The recruitment of a “Knowledge and Information Officer (KIO)” will take on the role of delivering training for professional sectors of government. Given the urgency of completing these activities it is vital that this position be filled in as early as January 2014. The Project Manager should ensure that the recruitment of the KIO is a priority that should be attended to immediately. |  |  |  |  | Activity/event |  |  | Acct. code |  | Amt USD | [12 empty] | This activity was reported in the fourth Quarter Progress Report as having been completed. However, it was evident that the design and implementation of a project communication strategy for effective awareness campaign was never carried out. Once the Knowledge and Information Management Officer is recruited, he or she will be tasked to work closely with the International Climate Change Advisor to raise awareness Road Show on Climate Change Science and National Policy on Climate Change. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[5 empty] | Training, workshop, & conferences |  |  | 75700 |  | 20000 | [17 empty] | International consultant |  |  | 71200 |  | 30000
[28 empty] | Trainings, workshops & conferences |  |  | 75700 |  | 9000
[5 empty] | Supplies |  |  | 72500 |  | 2000 | [17 empty] | Travel |  |  | 71600 |  | 10000
[28 empty] | supplies |  |  | 72500 |  | 500
[5 empty] | Communication |  |  | 72400 |  | 1500
[5 empty] | Total |  |  |  |  | 23500 | [17 empty] | Total |  |  |  |  | 49500
This format should be repeated for each Activity contributing towards the Output
A new worksheet should be used for each project output
[23 empty] | Activity1.3.4 Integrating the sandwatch Programme in the Education Curriculum |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
[23 empty] | This activity is yet to be implemented. However, PMU has been dialoguing with the Director of Education in trying to fast track this activity. The Department of Education through its Technical Advisor from UNESCO is working on the process, and once it is confirmed, NAPA will be invited to assist in integrating the sandwatch programme in the Education Curriculum by the 3rd quarter. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[28 empty] | International consultant |  |  | 71200 |  | 30000
[28 empty] | Trainings, workshops & conferences |  |  | 75700 |  | 9000
[28 empty] | Travel |  |  | 71600 |  | 10000
[28 empty] | supplies |  |  | 72500 |  | 500
[28 empty] | Total |  |  |  |  | 49500

## Outcome 2
| Output Indicators | Baseline | Annual (yyyy) Target | On track, Off track or Partially on track | Annual Budget | Remaining Output Budget | Quarterly Delivery: (USD) |  | Balance: (USD) |  |  | Output Indicators | Baseline | Annual (yyyy) Target | On track, Off track or Partially on track | Annual Budget | Remaining Output Budget | Quarterly Delivery: (USD) |  | Balance: (USD) |  |  | Output Indicators | Baseline | Annual (yyyy) Target | On track, Off track or Partially on track | Annual Budget | Remaining Output Budget | Quarterly Delivery: (USD) |  | Balance: (USD)
Output 2.1: Community-based adaptation plans for coastal protection, water supply security, and agricultural livelihood sustainability are developed for all islands in Tuvalu. |  |  |  |  | (USD): | (USD): |  |  |  |  | Output 2.2: Community-based adaptation projects with a focus on participatory management of protective ecosystems and climate sensitive natural resources are designed and implemented in at least 1 pilot site on each of Tuvalu’s 9 Islands. |  |  |  |  | (USD): | (USD): |  |  |  |  | Output 2.3: The results of all community-based demonstration projects are analyzed and fed into the formulation of a government-endorsed replication programme. |  |  |  |  | (USD): | (USD):
[5 empty] | (Output lump sum) | (Output lump sum) | [9 empty] | (Output lump sum) | (Output lump sum) | [9 empty] | (Output lump sum) | (Output lump sum)
| Number of locally designed, sustainable adaptation measures demonstrated in vulnerable coastal communities ; | From AWP | By end of the project, over 80% of the community-based adaptation measures employed by the project demonstrate their utility for coastal communities and provide lessons for replication; |  | 93100 | [6 empty] | Number of locally designed, sustainable adaptation measures demonstrated in vulnerable coastal communities ; | From AWP | By end of the project, over 80% of the community-based adaptation measures employed by the project demonstrate their utility for coastal communities and provide lessons for replication; |  | 135304 | [6 empty] | Number of locally designed, sustainable adaptation measures demonstrated in vulnerable coastal communities ; | From AWP | By end of the project, over 80% of the community-based adaptation measures employed by the project demonstrate their utility for coastal communities and provide lessons for replication; |  | 35000
Progress on quarterly activities (IP to complete this section) |  |  |  |  | Next quarter planned activities and budget | [5 empty] | Progress on quarterly activities (IP to complete this section) |  |  |  |  | Next quarter planned activities and budget | [5 empty] | Progress on quarterly activities (IP to complete this section) |  |  |  |  | Next quarter planned activities and budget
(Activities Scheduled and Results achieved)Note: All activities on AWP to be listed | [10 empty] | (Activities Scheduled and Results achieved)Note: All activities on AWP to be listed | [10 empty] | (Activities Scheduled and Results achieved)Note: All activities on AWP to be listed
Activity 2.1.1: Develop a community level risk assessment and made available to national government and NGOs for dissemination and use in the planning of future projects. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter | [5 empty] | Activity 2.2.1: establish model demonstration projects on coastal protection measures (eg. Mangrove and non-mangrove species planting, soft technologies, protective structures) in Funafuti, Nukufetau, Niutao, Nukulaelae and Niulakita |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter | [5 empty] | Activity 2.3.1: Compilation and Publishing of lessons learned through the results of the community based demo projects and shared with Government and NGOs to be applied in future formulation work on adaptation and risk reduction projects on all islands. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
This target has not been achieved yet. As far as PMU is concerned, no risk assessment has been conducted yet for the project nor was there an activity planned to produce output 2.1. The best way to carry out a risk assessment is for PMU and UNDP to delegate this task either to the CTA or the NTA, incorporate it into their ToR and have one of them conduct a V&A for all islands. The CTA during his recent visit to Funafuti suggested that it would be ideal to collect all V&A risk assessments that have been conducted over the years and compile a consolidated report. In terms of developing community-based adaptation plans with active participation of local communities, this activity is yet to be carried out. As was envisaged in the logframe, that by the end of Year 1, at least 1 community-based adaptation plan in line with the Island Strategic Plans is developed in each island (9 total) and supported by detailed baseline data for each island, nothing has been done to achieve this target. It is the understanding of the PMU with interviews conducted by the NTA that also in principle there are Island Development Coordinating Committees on each island, in practice, these entities only perform their duties when there is a call from the DCC about a cyclone or a state of national emergency is declared. It is not sure who will take the leading role in developing community-based adaptation plans. Again, UNDP as a facilitator can recommend or task a consultant (either the CTA or NTA) or another consultant to carry out this activity by the middle of the second quarter 2014. The 4 Island Strategic Plans scheduled in the logframe as a target for the project was reported in the 2013 PIR as been removed by the Project Board in 2012. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD | 1. Construction of coastal protective measures as a result of the coastal assessment. • The Coastal Expert has just completed the assessment for Nukufetau and Nanumea. Accordingly, materials (sandbags, sand suction machine, etc) will be procured before the end of NAPA 1+ 2. Nukufetau and Nanumea coastal assessment sites. • The assessment of both islands is complete with the coastal expert visiting Nukufetau in mid-March. The Coastal Expert plans to visit Nanumea in May 3. JICA partnering with NAPA in putting up beach nourishment physical structure at Fongafale Funafuti. • This activity is still on hold. The EIA has not been carried out yet, but NAPA will fund these activities once they are moving 4. To train Government staff and community members on its maintenance. • Training of government staff will commence once the physical structure is in place 5. To produce a publication (adoption card, Lessons Learned Poster, etc.) on all coastal trees planted to date • This activity has not started. It will be produced once the CKO is on board. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD | This activity has not been carried out yet. The main setback in achieving this output is the late recruitment of the Knowledge and Information Officer (KIO). The KIO’s main role is to collect, collate, update, analyse and disseminate climate change information to sectoral planners and policy makers. It is therefore important that the KIO be recruited in the first quarter of 2014. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[5 empty] | International consultant (coastal) |  |  | 71200 |  | 30000 | [5 empty] | Materials and Goods |  |  | 72300 |  | 16000 | [5 empty] | Local consultant (NTA) |  |  | 71300 |  | 15000
[5 empty] | Local consultant (water) |  |  | 71300 |  | 20000 | [5 empty] | National coastal tree plantingday |  |  | 71300 |  | 18000 | [5 empty] | Contractual services (company) |  |  | 72100 |  | 15000
[16 empty] | Training workshops, & conferences |  |  | 75700 |  | 2000
[5 empty] | Miscellaneous |  |  | 74500 |  | 500
[5 empty] | Equipment |  |  | 72800 |  | 2500
[5 empty] | Travel |  |  | 71600 |  | 2500
[5 empty] | Training, workshops and conferences |  |  | 75700 |  | 2000
[5 empty] | Transport, shipping and Handling |  |  | 74700 |  | 1000
[5 empty] | Total |  |  |  |  | 58500 | [5 empty] | Total |  |  |  |  | 36000 | [5 empty] | Total |  |  |  |  | 30000
Activity 2.1.2: Scale up and expand activities on home gardenings |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter | [5 empty] | Activity 2.2.2: Secure additional freshwater supplies through enhanced capture, storage and water saving measures in Nanumea, Nui, Vaitupu and Nanumaga. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter | [5 empty] | Activity 2.3.2: Implementation of two replication project within Tuvalu are designed based on the replication plan developed during MTR and on the basis of the lessons learned. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
• This activity is on schedule, and this activity seems to be one of the main core activities of community organisers, assisting home gardeners with the distribution of garden fences, seeds, and garden tools. • Since October, after the COs returned to their home islands, they reopened registration for new home gardeners who are interested in having their home gardens. A total of 190 home gardeners including 72 new gardeners registered at Vaitupu alone, and 209 home gardeners were registered on Funafuti, 70 garderner registered for the competition at Nanumaga, and 73 from Nui. A complete list of new gardeners from around the country will be distributed later once the list from other COs is obtained by the WS. A total of 95 volunteers from 6 islands (Vaitupu, Nui, Niutao, Nanumaga, Nukufetau, and Nukulaelae) offered to have their harvests recorded by COs. • Over the next three months, PMU will procure fences for these new home gardeners. A proposal was also submitted to the Project Board requesting non-indigenous Funafuti residents to be able to receive garden fences from the project. The proposal was approved by the Board. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD | [5 empty] | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD | This activity has not been carried out yet. In the AWP, the design and implementation of the two replication projects are expected to be carried out by the NTA during the 3rd and 4th quarter of 2014. However, the NTA's contract will only go until the beginning of the 3rd quarter. In addition, this activity is not in the NTA's ToR. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[5 empty] | Equipment |  |  | 72800 |  | 10000 | [5 empty] | Materials and Goods |  |  | 72300 |  | 65000 | [5 empty] | Local consultant (NTA) |  |  | 71300 |  | 20000
[5 empty] | Miscellaneous |  |  | 74500 |  | 500 | [5 empty] | Training, workshops and conferences |  |  | 75700 |  | 2000
[10 empty] | 10500 | [5 empty] | Total |  |  |  |  | 67000 | [5 empty] | Total |  |  |  |  | 20000
Activity Result 2.1.3: To conduct an awareness-raising session for community island leaders and community participants |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter | [5 empty] | Activity 2.2.3: Establish saline protected pulaka, breadfruit, and banana plantations in Nanumea, Nui and Nanumaga |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
• This activity result was carried out in August 2013. However, there is a new development from UNDP suggesting that an awareness-raising workshop be conducted on each island by late April, when the Komawai visits all islands to deliver chippers. PMU staff and other technical personnel from government sectors (MET, PWD, Agriculture) will also be invited to join this tour to the outer islands. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD | Nanumaga 1. Work on the pulaka patches are still on hold as the procurement and shipment of materials from Fiji are still under negotiation. Plans to charter a vessel from Fiji to dispatch the materials to Nanumaga are on hold for the moment, and it is anticipated that the materials should get to Nanumaga before the end of the year. Niutao 2. Since the previous report, work on Niutao has been at a standstill. However, a proposal from the Kaupule to the NAPA, to assist them with the continuation of the work on Te Pela will be tabled at the next Board meeting for approval. The proposal requests that NAPA provide funding and labour to complete the road access to the pulaka plantations. Niulakita 3. The CO from Niulakita came in July for the workshop and took his annual leave after the workshop. He has not returned to the island since, and so, was not able to send in his report. It is understood that no further progress on the activities were carried out during this quarter. The CO is expected to return to his duty station on the next boat. i) Home Gardening 1. Due to the long delay in returning the workshop participants including Cos to their home islands, activities that were meant to be carried out in this quarter were put on hold. Participants from Nanumea, Nanumaga, Niutao, Nui, and Vaitupu left their home islands in mid-July to attend the workshop on Funafuti. The Nukufetau and Nukulaelae participants came on the NAPA’s chartered vessel on the 9th August. Some participants (Nukulaelae) returned at the end of July and returned at the end of last month. The Nanumea and Nanumaga participants left on the first week of October. Nui 2. A survey for the home garden been carried out,56 gardeners registered and ready to start as soon as possible. The CO on the island still waiting for the materials from the HQ. The main and the highly recommended material is the FENCE, chicken wire is required for each competitor, CO on the island is REQUESTING the PMU and HQ for their assistance so that the gardening may begin as soon as possible. As for the time being, the home gardeners will use local materials for fencing their home gardens. Nukulaelae 3. A total of 30 home gardeners have received their home garden fences, watering cans, 1250 cabbage seeds, 875 cucumber seedlings, 560 melons, 175 sweet peppers, and 100 pawpaws from NAPA. These seedlings are now beginning to grow in their own gardens. 4. Nursery: The NAPA and the Agricultural Department on the island are working together in promoting home gardening and the Agricultural officer on the island has built the nursery for the island. The CO will be using this nursery to plant his home garden seedlings for home gardeners. NAPA contributed to the building of the nursery by lending tools for the construction of the nursery. The NAPA also provided fly screens and one water tank to the nursery. The nursery is expected to be completed by mid-October. Nanumaga 5. Due to the long delay in returning the CO to their islands, the Nanumaga CO was not able to determine the status of home gardens on the island. There is also the problem of seed shortages on the island. Now that the CO has returned to Nanumaga, he took with him some cucumber and cabbage seeds from the PMU. The CO also took with him garden fences for the home owners who have enlisted for the home garden competition. A home garden competition is planned for the next quarter. Nukufetau 6. Home gardening competition was planned to commence in April, but was delayed because there is no suitable place to grow the seedlings for the competitors. So the CO decided to defer the competition until the nursery is completed. Now that the nursery is completed, competition will start shortly. The CO returned to Nukufetau with seeds to plant and distribute to competitors. Seeds were obtained from the Alofa Garden (Republic of China, Taiwan) and the PMU office, and include spring onion, wax gourd, eggplant, watermelon, hot pepper, cucumber, asparagus bean, Chinese cabbage, speedy and brisk green cucumbers, cabbages, tomatoes, and water melons. A total of 38 home gardeners have received fences for their gardens and the CO returned with another roll of fence wire. 7. Nukufetau Nursery: - Construction of the nursery began this quarter on the 8th July and continued for three weeks. The work was completed on 26th July, 2013. A total of 17 casual labourers and 2 permanent workers (1 foreman @$4/hr, 1 skilled labourer @$3/hr) were recruited to construct the nursery. On the 8th August 2013, the PMU chartered the MV Manufolau to Nukufetau. It arrived on Thursday 9th and PMU staff, and the 2 technical advisors went ashore to witness the official opening of the Nukufetau nursery. Now that the nursery is officially opened, local home-owners now have access to seeds for their home gardens. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[16 empty] | Materials and Goods |  |  | 72300 |  | 28304
[16 empty] | Contractual services |  |  | 72100 |  | 20000
[16 empty] | Training, workshops and conferences |  |  |  |  | 2000
[16 empty] | Total |  |  |  |  | 50304
This format should be repeated for each Activity contributing towards the Output
A new worksheet should be used for each project output
Activity Result 2.1.4: A country wide RWH survey on assessing water tanks whether working or not, capacity available and gutters malfunction |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
• Some COs carried out their RWH survey during the fourth quarter of 2013 and some islands had their surveys during the first quarter of 2014. • Nanumaga 175 households. 6 cement tanks need repairing and 37 houses need their gutterings repaired. • Nukulaelae. All 80 residential homes were include in the survey, 24 concrete tanks need to repair, 10 plastic tanks need to repair, 46 Household, half of their houses have no gutters & facia boards. • Nui: 167 private homes, 12 public buildings. 66 water tanks are leaking, 22 houses needs gutters repaired, 5 tanks need fittings. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[5 empty] | Training, Workshops and Conferences |  |  | 75700 |  | 2000
2000
Activity Result 2.1.5: Test of saline in soil from different parts of country, and have them tested in labs in NZ/Aust |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
•This activity is still on hold as there are no salinity tests. The CTA was scheduled to have returned in December for a follow-up workshop in which he will assist PMU in procuring salinity testing kits and training COs to use the kit. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
Activity Result 2.1.6: Japanese NGO ‘My Farm’ to rehabilitate tests of soil carried out. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
• The CTA (Geoff Dews) was dealing with this activity result and PMU will follow this up with the CTA in the next quarter |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD

## Outcome 3
| Output Indicators | Baseline | Annual (yyyy) Target | On track, Off track or Partially on track | Annual Budget | Remaining Output Budget | Quarterly Delivery: (USD) |  | Balance: (USD) |  |  | Output Indicators | Baseline | Annual (yyyy) Target | On track, Off track or Partially on track | Annual Budget | Remaining Output Budget | Quarterly Delivery: (USD) |  | Balance: (USD)
Output 3.1: Climate change information for Tuvalu are analysed, updated and disseminated to sectoral planners and policy makers. |  |  |  |  | (USD): | (USD): |  |  |  |  | Output 3.2 Lessons Learned from community-based adaptation projects are collated and disseminated to communities, sectoral planners and policy makers on a continuous basis |  |  |  |  | (USD): | (USD):
[5 empty] | (Output lump sum) | (Output lump sum) | [9 empty] | (Output lump sum) | (Output lump sum)
| Number of locally designed, sustainable adaptation measures demonstrated in vulnerable coastal communities Percent of households in Tuvalu that are participating in the implementation of community-based adaptation measures | From AWP | By end of the project, over 80% of the community-based adaptation measures employed by the project demonstrate their utility for coastal communities and provide lessons for replication |  | 51325 | [6 empty] | Number of locally designed, sustainable adaptation measures demonstrated in vulnerable coastal communities Percent of households in Tuvalu that are participating in the implementation of community-based adaptation measures | From AWP | By end of the project, over 80% of the community-based adaptation measures employed by the project demonstrate their utility for coastal communities and provide lessons for replication |  | 25000
Progress on quarterly activities (IP to complete this section) |  |  |  |  | Next quarter planned activities and budget | [5 empty] | Progress on quarterly activities (IP to complete this section) |  |  |  |  | Next quarter planned activities and budget
(Activities Scheduled and Results achieved)Note: All activities on AWP to be listed | [10 empty] | (Activities Scheduled and Results achieved)Note: All activities on AWP to be listed
Activity Result 3.1.1 Establish institutional links between Project Steering Committee, NCCAC, SNC, Meteorological Services process and other regional and international climate information and modeling processes relevant to Tuvalu and quality climate change impact projections and scenarios developed and produced. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter | [5 empty] | Activity Result 3.2.1: Brochures, posters, newsletters, photo stories, bookmarks, t-shirts, banners, audio visuals, etc. produced to highlight lessons learnt and best practices and disseminated to communities and national stakeholders. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
With the establishment of the NACCC, there is now institutional links between government departments at the directorate level. Since its inception in January, members of the NACC have met four (4) times to discuss climate change issues that affect Tuvalu as a nation. In light of these meetings and future dialogues, some members of the Council will be nominated to attend regional meetings (in Apia) and international meetings (Lima & at the UN Council) later in the year. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD | There has been no progress for this activity result since the last quarter. Some of these activities were reported in the first quarter 2013. Two photo stories on water security and food security were reported in the first quarter. T-shirts, banners, bookmarks have been ordered and are awaiting delivery from UNDP Suva office.PMU is still awaiting the arrival of t-shirts, brochures, bookmarks, pencils and usb sticks with the NAPA logo on them. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[5 empty] | Local consultant (NTA) |  |  | 71300 |  | 20000 | [5 empty] | Audio visual & Printing Production costs |  |  | 74200 |  | 20000
[5 empty] | International Consultant (CTA) |  |  | 71200 |  | 30000
[5 empty] | Communication |  |  | 72400 |  | 1325
[5 empty] | Total |  |  |  |  | 51325 | [5 empty] | Total |  |  |  |  | 20000
Activity Result 3.1.3 Proceedings of local and international climate change workshops and other relevant events that refers to the situation in Tuvalu are documented. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter | [5 empty] | Activity Result 3.2.2: To conduct one national workshop on coastal afforestation and other climate resilient livelihoods |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
These proceedings (both local and international climate change workshop) are yet to be documented. As with other activities, this activity result depends on the recruitment of the Knowledge and Information Management Officer (KIMO), who will have the leading role in collecting and collating information pertaining to local and international climate change workshops that refer to Tuvalu's situation. The CTA and the NTA are expected to assist and advise the KIMO on documenting these proceedings. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD | As reported in the last quarter of 2013, this activity result was scheduled for the first quarter 2014. The Works Supervisor and an Agricultural Officer will tour all the eight outer islands and conduct workshops on coastal afforestation and other climate resilient livelihoods. The idea of bringing representative from outer islands is not encouraged as this is more expensive than sending two (2) officers to the outer islands. The August 2013 Workshop experience has been learnt and PMU does not want to repeat the same experience. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[16 empty] | Workshop costs (venue/refreshemnts |  |  | 75700 |  | 5000
[16 empty] | Travel |  |  | 71600 |  | 5000
Note: Budget for this activity result
is included in the budget for activity
3.1.2 above
[5 empty] | Total |  |  |  |  | 0 | [5 empty] | Total |  |  |  |  | 10000
[11 empty] | Activity Result 3.2.3: Participated in an international workshop on coastal afforestation and other climate resilient livelihoods. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
[11 empty] | This activity depends on the active participation of the Department of Agriculture to international workshop on coastal afforestation and other climate resilient livelihoods. NAPA will then, together with Department of Agriculture nominate a representative to represent Tuvalu in such workshops. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[16 empty] | Travel |  |  | 71600 |  | 10000
[16 empty] | Total |  |  |  |  | 10000
This format should be repeated for each Activity contributing towards the Output
A new worksheet should be used for each project output
[11 empty] | Activity Result 3.2.4: A Project portal is established and routinely updated on project information and lessons leant. |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
[11 empty] | This activity result has not been carried out yet. As discussed in other activity results, the delay in implementing this activity is due to the delay in the recruiting of the Knowledge Information and Management Officer (KIMO). The KIMO will be responsible for establishing the project portal and routinely updating project information and lessons learnt. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[16 empty] | Contractual Services - Individual |  |  | 71400 |  | 5000
[16 empty] | Total |  |  |  |  | 5000

## Outcome 4
| Output Indicators | Baseline | Annual (yyyy) Target | On track, Off track or Partially on track | Annual Budget | Remaining Output Budget | Quarterly Delivery: (USD) |  | Balance: (USD)
Output 4.1 Project Management |  |  |  |  | (USD): | (USD):
[5 empty] | (Output lump sum) | (Output lump sum)
|  | From AWP |  |  | 206600
Progress on quarterly activities (IP to complete this section) |  |  |  |  | Next quarter planned activities and budget
(Activities Scheduled and Results achieved)Note: All activities on AWP to be listed
Activity Result 4.1.1: UNDP NIM external audit on 2012 accounts conducted |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
Completed |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[5 empty] | Workshop costs (venue/refreshemnts |  |  | 75xx
[5 empty] | Training Officers Salary |  |  | 71300
[5 empty] | Total |  |  |  |  | 0
Activity Result 4.1.2: Mid Term Review Completed |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
Completed in May 2013 |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[5 empty] | Workshop costs (venue/refreshemnts |  |  | 75xx |  | 2000
[5 empty] | Training Officers Salary |  |  | 71300 |  | 1800
[5 empty] | Total |  |  |  |  | 3800
Activity Result 4.1.3: Paid staff salary as per contractual agreement |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
Staff Contracts: Contracts of PMU staff all ended during this first quarter. The Project Coordinator's contract ended on 7th February. together with the Administrative Assistant, and their contracts were to be renewed. To date, their contracts have not been signed yet. The Works Supervisor and the Community Organisers' contracts are in line with th e life of NAPA. |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[5 empty] | Constractual Services - Project Coordinator |  |  | 71405 |  | 10007.69
[5 empty] | Constractual Services - Works Supervisor |  |  | 71405 |  | 8556.88
[5 empty] | Constractual Services - Administrative Assistant |  |  | 71405 |  | 7333.21
[5 empty] | Total |  |  |  |  | 25897.78
Activity Result 4.1.4: Direct Project Cost as per services rendered by UNDP |  |  |  |  | Details of activities for the next quarter from the AWP and any slippage from prior periods to be included together with estimated costs. This is required to justify any advance of funds for the next quarter
• In January, a Request for Direct Payment was made for UNDP to settle payment for the procurement of chippers from Brisbane, Australia. • In addition, PMU requested UNDP to nominate Trade Pacific as NAPA's shipping agent to handle all the project materials (documentation and loading) to Tuvalu. • Payment to the University of Tokyo was finally settled by UNDP in early March |  |  |  |  | Activity/event |  |  | Acct. code | Amt. LOC | Amt USD
[5 empty] | Workshop costs (venue/refreshemnts |  |  | 75xx |  | 2000
[5 empty] | Training Officers Salary |  |  | 71300 |  | 1800
[5 empty] | Total |  |  |  |  | 3800

## overall
Narrative: 2014 1st Quarterly progress reports on Key Drivers of Development (IP to complete this section)
Quarter 1, 2014:
1. Summary of Quarterly Progress including overall risk assessment and mitigation:
This report highlights the progress, key achievements of the project, and impacts on the project the hinder its progress in achieving its targets for the first quarter from the months of January to March 2014. Three main areas of environmental concerns are addressed in this report. They are adaptation to water security, food security, and coastal protection. Reports were obtained from the community organisers of Nanumaga, Niutao, Nui, Nukulaelae, Funafuti ,and Vaitupu. Nukufetau, Nanumea, and Niulakita did not have any reports for this quarter. COs for Nukufetau are on leave, while the Niulakita CO is currenlty working at the NAPA PMU office in Funafuti. Project Risks Risk: 1) Delay in disbursing funds from UNDP to PMU, and from PMU to COs at the outer islands. No funds were available for paying of outstanding payments to government departments, and private companies. In addition, outer island community organisers (Nui, Nukufetau, Vaitupu, Niutao, Nanumaga, Nanumea, Nukulaelae, and Funafuti did not any funds for implementing activities on their respective islands. This shortfall was mainly because of the delay in UNDP releasing funds to the PMU.Risk Type (H). Risk Reduction Strategy. Community Organisers are urging PMU to release funds at the end of each quarter for activities to be implemented in the next quarter. PMU in turn, is urging UNDP to kindly consider releasing funds at the their earliest conveniece so that they will not be any further delays in implementing the remaining activities of NAPA 1 & NAPA 1+. Risk 2) Communications with the outer island COs Internet connection to the islands has been out of service for a very long time. It has become very expensive to call PMU every time. Risk Type (H). Risk Reduction Strategy- PMU is urging the TTC to speed up the fixing of the problem so that communications with the islands is restored and more so to improve quarterly progress reporting from outer-islands. Risk:3)Inter-island vessels. Undertaking monitoring visits to the Islands is a serious probelme with the inconsistency of Government Shipping and unavailability and high cost of hiring vessels. Risk Type (H). Risk Reduction Strategy- Getting a vessel for the NAPA Project appeared to be a viable proposition. NEW risks/threats identified during the quarter: 1. Report Writing. It has become apparent during this quarter that COs still fail to capture the essence of their activities undertaken in each of their communities. Risk Type (M). Risk reduction Strategy: An in-house training schedule was conducted for COs to utilize Microsoft office (word, excel, powerpoint), and also to properly structure reports Project Issues Issue:The long delay in returning the participants to their respective islands after the workshop. Participants from the outer islands (except Nukufetau and Nukulaelae) were on Funafuti for more than three months. Nukulaelae and Nukufetau participants were on Funafuti for more than two months. Potential impact on the project, how dealt with and the result: This delay has caused much stress on the project’s budget allocations. • At the moment, the current DSA is $60/day. For 42 participants, the weekly DSA for all participants is $17,640.00. The actual expenditure for this training workshop is AUD$124,351.52. This is an enormous amount that has put much strain on the financial resources of the project. • Activities on the outer islands were put on hold as the Community Organisers were stranded on Funafuti for over 3 months. Issue: Delay in the procurement of materials for Nui, Nanumaga, Nukulaelae, and Vaitupu. Potential impact on the project, how dealt with and the result: Activities on Nui and Nanumaga are on hold as the materials needed for the construction of their top priority projects are still to be procured. • It is vital that the project sends someone from PMU immediately to procure and arrange for shipment of materials to the project sites as soon as practicable. During the training workshop, some good practices were revealed by a couple of participants from Nukulaelae and Nui. King tides are posing strenuous problems for agricultural practitioners on the outer islands. During King tides water seeps into the pulaka pits and kill the crops. A lady from Nukulaelae and the Nui Kaupule confirmed that their crops were not affected by king tides because they tend to their crops on a daily basis. These gardeners have shown that they can conquer the odds by being proactive. We should learn from these two local practitioners because being proactive means that we have avoided the possibility of being impacted by acting before it is too late. Another lesson learnt during this quarter is a more administrative matter; that proper and careful planning is an essential element of any project in the islands. During the workshop, 42 participants from the outer islands came to Funafuti. The workshop lasted 3 days only, but the participants stayed on Funafuti for over 3 months. The cost of maintaining the participants, together with other workshop-related expenses came to AUD$124,351.52, which could have been wisely used for other project expenses. Had there been an option to charter a vessel to return the participants soon after the workshop, the project would have saved tens of thousands of dollars. The PMU has learned from this and hope that future trainings would have to be planned in advance.
2. Contribution to Key Drivers of Development:
a. Capacity Building
During the fourth quarter, COs returned to their respective islands around October 2013 and conducted awareness raising to island communities. The awareness raising workshop entails the same content as the workshop that was conducted on Funafuti in August by the PMU and technical staff from UNDP and SPC. On Nukufetau, 104 participants attended the workshop where representatives of the comunities that attended the Funafuti workshop facilitated in the outer island workshops. On Niutao, 50 participants represented their respective organisations (Youths, Women's groups, Boys & Girls Brigade, Red Cross, and farmers). The Nanumaga CO reported that 63 participants attended theworkshop while Nukulaelae had 60 participants.
b. Gender Equality
The NAPA project continues to support and promote gender equality. Awareness raising is one area where gender equality is supported. In February 2014, the Project supported the World Women's Day with a $4,000 contribution to the Department of Women, Office of the Prime Minister. Officers from the Department of Environment took part in the week long celebrations
c. South-south Cooperation
The project has no South-south cooperation as yet. It is hope that there will be lessons learnt from around the region where NAPA can share experiences with other countries with similar situations.
d. Policy Update
As alluded to in the Kaniva - Tuvalu's National Climate Change Policy, the NAPA project will continue to support the implementation of the Strategic National Action Plan (SNAP), through the setting up of the National Advisory Council on Climate Change (NACCC), and training of members of the NACCC.

## UNDP Only
Cumulative Performance including financials of Project (UNDP CDM/MCO to complete)
Summary of Progress toward achievement of outcomes:
Progress towards achievement of outcomes
Impact on capacity building, South-south cooperation, Policy Up take and Gender Equality:

## Sheet1
Contractual Services - Project Coordinator | 71405 | 10007.69
Contractual Services - Works Supervisor | 71405 | 8556.88
Contractual Services - Administrative Assistant | 71405 | 7333.21
Rental & Maintenance of Premises | 73100 | 0
Miscellaneous | 74500 | 0
Supplies | 72505 | 0
Equipment | 72205 | 1697.54
SVC Co Trade & Business | 72120 | 0
Training, Workshops & Conferences | 75705 | 0
Land Telephone Charges | 72420 | 0
Communincations | 74500 | 0
Vehicle | 71635 | 0
Travel | 71610 | 0
Svc Co Construction & Engineer | 72105 | 150