## Sheet1
Expected Outputs | Planned Activities | Timeframe | [9 empty] | Responsible Party | Planned Budget
[13 empty] | Funding Source | Budget Description |  | Amount (USD)
|  | Quarter 1 | QTRLY BUDGET (USD) | Quarter 2 | QTRLY BUDGET (USD) | Quarter 3 |  | QTRLY BUDGET | Quarter 4 | QTRLY BUDGET | UNDP Code
[15 empty] | Disbursement to date |  |  | EIF | UNDP Total | EIF Total
Outcome 1: Sufficient institutional and management capacity built in Tanzania to formulate and implement pro-poor trade strategies and policies. Baseline: DTIS completed in 2005, strategy in place until 2013 Target: Implementation of priorities identified in capacity needs assessment. Indicator: # no of quality strategies and policies formulated Demonstrated good management of strategies and policies through achieving set targets in specified timeframes # of priorities addressed in the capacity assessment | 1.3.1.1.1 Purchase of data processing and analysis software for trade policy analysis | x | 8000 | [8 empty] | UNDP | UNDP | Software | 8000 | 8000 | 8000 | 8000 | 8000
| 1.3.1.1.2 Data processing and analysis training for 20 people |  |  | x | 15000 | [6 empty] | MIT | UNDP | Workshops | 15000 | 15000 | 15000 | 15000 | 15000
| 1.3.1.1.3 Conduct training on policy formulation, analysis and implementation, government budgeting and M&E for 15 people |  |  | x | 15000 | x |  | 30000 |  |  |  | MIT | UNDP | Workshops | 30000 | 45000 | 45000 | 45000 | 45000
| 1.3.1.1.4 Conduct training on modern human Resource, Change Management and Presentation skills for 20 people |  |  | x | 60000 | x | [5 empty] | MIT | UNDP | Workshops | 4000 | 60000 | 60000 | 60000 | 60000
| 1.3.1.1.5 Procurement of Heavy Duty Photocopier | x | 26000 | [8 empty] | UNDP | UNDP | Equipment | 20000 | 20000 | 20000 | 20000 | 20000
| 1.3.1.1.5 Procurement of 3 desktop computer | x | [9 empty] | UNDP | UNDP | Equipment | 6000 | 6000 | 6000 | 6000 | 6000
| 1.3.1.2.1 Develop a computerised file tracking system | x | n/a | x | 24000 | x | [5 empty] | MIT | UNDP | Consultants | 2470 | 40000 | 40000 | 40000 | 40000
| 1.3.1.2.2 Training to system users of the computerized file tracking system for 120 MIT staff |  |  |  |  | x |  | 20000 |  |  |  | MIT | UNDP | Workshops | - | 20000 | 20000 | 20000 | 20000
| 1.3.1.2.3 procurement of 5 desktop computers, 3 printers, 1 scanner, 1 projector, 2 laptops |  | 20000 |  |  | x | [5 empty] | UNDP | UNDP | Equipment | - | 20000 | 20000 | 20000 | 20000
| 1.3.1.2.4 Procurement of file racks by GoT |  |  |  |  | x | [5 empty] | MIT | UNDP | Equipment | - | 24000 | 24001 | 24002 | 24000
| 1.3.1.3.2 Review Effectiveness of Existing Trade Promotion Activities and develop communication strategy |  | 35000 |  |  | x |  |  | x |  |  | MIT | EIF | Communication materials, Consultants, Workshops | - | 35000 | 35000 | 35000 |  | 35000
| 1.3.6.1 Consultancy Fee for mapping of critical bottlenecks in the implementation of Trade Development policies and programmes |  | n/a |  | 24000 |  |  | 24000 | x |  |  | UNDP | EIF | Consultants | - | 24000 | 48000 | 48000 |  | 48000
| 1.3.6.2 Inception report meeting to document findings of the mapping exercise | [7 empty] | x | 6000 |  | MIT | EIF | Meetings | - | 6000 | 6000 | 6000 |  | 6000
| 1.3.6.3 National Stakeholders Workshop to present these findings in a zero draft | [7 empty] | x | 10000 |  | MIT | EIF | Workshops | - | 10000 | 10000 | 10000 |  | 10000
| 1.3.6.4 Validation Workshop for presenting results and agreeing on recommendations | [7 empty] | x | 10000 |  | MIT | EIF | Workshops | - | 10000 | 10000 | 10000 |  | 10000
| 1.3.7.1 Conduct 3 short term trainings for 10 NIU staff (project cycle management, M&E, report writing and presentation) |  |  |  |  | x |  | 20000 |  |  |  | MIT | UNDP | Workshops | - | 20000 | 20000 | 20000 | 20000
| 1.3.7.2 NIU attending negotiations and missions as part of south south learning | [6 empty] | 16000 | x | 16000 |  | MIT | UNDP | Meetings | - | 32000 | 32000 | 32000 | 32000
UNDP
UNDP
UNDP
| 1.3.8.2.1 Purchase of project equipment | x | [9 empty] | UNDP | UNDP | Equipment | 40000 | 40000 | 40000 | 40000 | 40000
| 1.3.8.2.2 Maintenance of project equipments in Mainland | x |  | x | x |  | x |  |  |  |  | UNDP | MIT | Equipment | 8700 | 17400 | 48000 | 48000 | 17400
| 1.3.8.2.3 Maintenance of project equipment in Zanzibar | x |  | x | x |  | x |  |  |  |  | UNDP | MTIM | Equipment | 3300 | 6600 | 24000 | 24000 | 6600
| 1.4.1.1 Hire national consultant to conduct Zanzibar capacity needs assessement |  | n/a | x | 33000 | x |  | 33000 |  |  |  | UNDP | UNDP | Consultants | 33000 | 66000 | 66000 | 66000 | 66000
| 1.4.1.2 Conduct stakeholders workshop to discuss draft Capacity Needs Assessement report |  |  | x | 15000 | [6 empty] | MTIM | UNDP | Workshops | 15000 | 15000 | 15000 | 15000 | 15000
| 1.4.1.3 Conduct validation workshop to discuss results and recommendations |  |  |  |  | x |  | 20000 |  |  |  | MTIM | UNDP | Workshops | - | 20000 | 20000 | 20000 | 20000
| 1.4.2.1 Procure 2 desktop computers for TTIS desk at MTIM | x | 6000 | [8 empty] | MTIM | UNDP | Equipment | 6000 | 6000 | 6000 | 6000 | 6000
| 1.4.2.2 Procure Printer for the TTIS desk at MTIM | x | 14000 | [8 empty] | UNDP | UNDP | Equipment | 3000 | 3000 | 3000 | 3000 | 3000
| 1.4.2.3 Procure Photocopier Machine | x | [9 empty] | UNDP | UNDP | Equipment | 16000 | 16000 | 11000 | 11000 | 16000
| 1.4.2.4 Conduct 4 short-term training on (project cycle management, M&E, report writing and presentation for 8 people) |  |  | x | 15000 |  |  |  | x |  |  | MIT | UNDP | Workshops | 15000 | 30000 | 60000 | 60000 | 30000
| 1.4.3.1 Support two participants from Zanzibar to attend quarterly Trade Integration Working Group (TIWG) for enhanced meeting planning and implementation skills | x | 2000 | x | 2000 | x |  | 2000 | x | 2000 |  | MIT | UNDP | Meetings | 4000 | 8000 | 8000 | 8000 | 8000
| 1.4.3.2 Support three participants from Zanzibar to attend quarterly Trade Integration Technical Committee (TITC) meetings for enhanced meeting planning and implementation skills | x | 4000 | x | 4000 | x |  | 4000 | x | 4000 |  | MIT | UNDP | Meetings | 8000 | 16000 | 16000 | 16000 | 16000
| 1.4.3.3 Support two participants from Zanzibar to attend bi-annual Trade Integration National Steering Committee (TINSC) for enhanced meeting planning and implementation skills |  |  | x | 2000 |  |  |  | x | 2000 |  | MIT | UNDP | Meetings | 2000 | 4000 | 4000 | 4000 | 4000
Outcome 2: Tanzania mainstream trade into national development strategies and plans Baseline: 2010 Country data (MKUKUTA II and MKUZA II) Target: National productive sector’s strategies aligned with trade development strategies and policies Indicator: # of national productive sector’s strategies aligned with trade development strategies and policies | 2.2.1.1 Conduct short term training for 6 people from 4 trade related MDAs on project cycle management |  |  |  |  | x |  | 90000 |  |  |  | MIT | UNDP | Workshops | - | 90000 | 90000 | 90000 | 90000
| 2.4.1 Create Request for Proposal for consulting firm for Zanzibar Trade Centre master plan | x | n/a | [7 empty] | n/a | UNDP/MTIM | UNDP | Consultants | - | 0 | 0 | 0 | 0
| 2.4.2 Issue and advertise RFP |  |  | x | n/a | [5 empty] | n/a | UNDP | UNDP | Communication materials, Consultants, | - | 0 | 0 | 0 | 0
| 2.4.3 Selection and Engagement of Contract Winner |  |  |  |  | x |  | n/a |  |  |  | UNDP/MTIM | UNDP | Meetings | - | 0 | 0 | 0 | 0
| 2.4.4 Twenty Percent of contract is awarded & Contract Signed/begins | [7 empty] | x | 30000 |  | UNDP | UNDP | Consultants | - | 26000 | 26000 | 26000 | 26000
| 2.4.5 Stakeholder Workshop | [7 empty] | x |  |  | UNDP | UNDP | Workshops | - | 10000 | 10000 | 10000 | 10000
| 2.4.6 Validation Workshop | [7 empty] | x |  |  | UNDP | UNDP | Workshops | - | 10000 | 10000 | 10000 | 10000
Outcome 3: Coordinated delivery of trade-related resources (funding, Technical Assistance, etc.) by donors and implementing agencies to implement country priorities. Baseline: Inactive TINSC, TITC, TIWG meetings Target: Mainstreamed and coordinated assessment and response to trade issues Indicator: # of trade related pilot projects implemented | 3.1.1.1 Bi annual field monitoring of indicators |  |  | x | 20000 |  |  |  | x | 20000 |  | MIT | UNDP | Travel | 20000 | 40000 | 40000 | 40000 | 40000
| 3.1.1.2 Quarterly Trade Integration Working Group (TIWG) | x | 3500 | x | 3500 | x |  | 3500 | x | 3500 |  | MIT | UNDP | Meetings | 7000 | 14000 | 14000 | 14000 | 14000
| 3.1.1.3 Quarterly Trade Integration Technical Committee (TITC) meetings | x | 3500 | x | 3500 | x |  | 3500 | x | 3500 |  | MIT | UNDP | Meetings | 7000 | 14000 | 14000 | 14000 | 14000
| 3.1.1.4 Bi-annual Trade Integration National Steering Committee (TINSC) |  |  | x | 3500 |  |  |  | x | 3500 |  | MIT | UNDP | Meetings | 3500 | 7000 | 7000 | 7000 | 7000
| 3.1.2 Project Auditing |  | n/a | [5 empty] | x | 45000 |  | MIT | UNDP | Travel | - | 5000 | 5001 | 5002 | 5000
| 3.2.1 Hire 2 Consultants Mapping and development of 2 value chains | x | n/a | x | 66000 | [6 empty] | UNDP | EIF | Consultants | 66000 | 66000 | 66000 | 66000 |  | 66000
| 3.2.2 Stakeholders and validation workshop to discuss findings |  |  | x | 5000 | [6 empty] | MIT | EIF | Workshops | 20000 | 20000 | 5000 | 5000 |  | 20000
Project Support | Recruitment of National Project Coordinator in Mainland |  |  | x | 15000 | x |  | 15000 | x | 15000 |  | UNDP | EIF | Consultants | 15000 | 45000 | 45000 | 45000 |  | 45000
| Recruitment of 2 project analysts (1 Mainland, 1 Zanzibar) |  |  | x | 9000 | x |  | 9000 | x | 9000 |  | UNDP | UNDP | Consultants | 18000 | 54000 | 49500 | 49500 | 54000
| Recruitment of 1 project assistant in Zanzibar |  |  | x | 12000 | x |  | 12000 | x | 12000 |  | UNDP | UNDP | Consultants | 6000 | 18000 | 18000 | 18000 | 18000
| In Kind Contribution | x | 20000 | x | 20000 | x |  | 20000 | x | 20000 |  | MIT | GOT | Utilities | 40000 | 80000 | 80000 | 80000
| Purchase of 2 project motor vehicles |  |  | x | [7 empty] | UNDP | UNDP | Vehicle | 100000 | 100000 | 100000 | 100000 | 100000
| Maintenance and fuel of 2 project motor vehicles | x |  | x |  | x |  |  | x |  |  | UNDP | UNDP | L/Sum | 12500 | 25000 | 25000 | 25000 | 25000
| Daily office expenses (Office sundries, stationary and NIU communication expenses combined) | x |  | x |  | x |  |  | x |  |  | MIT | UNDP | Sundries/Stationary | 31800 | 63600 | 63000 | 63000 | 63600
| UNDP General Management Support (GMS) 7% | x |  | x |  | x |  |  | x |  |  | UNDP | EIF | Admin | 10500 | 21000 | 21000 | 21000 |  | 21000
Total Funding for Year 1 | [14 empty] | 596770 | 1351600 | 1428502 |  | 1034600 | 261000
Note on W61: PC-7: Note: This is the same total 'for Q1&Q2 in 'Overall Budget'(cell I198)
Note on X61: PC-7: Note: This is the same total for year 1 total in Óverall Budget'(cell U194)