## Sheet1
Activity
outcome 1 | Provide financial support for networks and CSOs to conduct coordination meetings for KPs; Implement recommendations of the identified data gaps and quartely stakeholders meetings; | 01 Aug 2013 | 30 Jun 2014 | ZAC | 45,000.00
| Provide management support to ZAC, TAC and DACCOMs coordination meeting and field visits to track implementation of activities at National and local levels | 01 Aug 2013 | 31 Mar 2014 | ZAC | 30,700.00
| Engage a Consultancy firm to build capacity of CSO working with MARPs to develop and implement interventions for MARPs and Support NACOPHA Annual General Meeting | 01 Oct 2013 | 31 Mar 2014 | TACAIDS | 80,000.00
Outcome 2 | Conduct Mid Term Joint Review of the ZNSP II, Produce Zanzibar annual HIV report and dissemination and conduct biological and behavioral surveillance study among fishing communities, transport operators in Zanzibar | 01 Aug 2013 | 31 May 2014 | ZAC | 135,000.00
| Deploy web base application for non health data sytem | 01 Oct 2013 | 31 Dec 2013 | ZAC | 10,000.00
| Orient users on the tools and systems, conduct quarterly joint data audit and verification visits to HIV and AIDS implementers reporting through TOMSHA, Support electronic linkage of TOMSHA and LGMD and conduct bi annual joint mentoring visits to newly trained HIV and AIDS implementers on M&E | 01 Aug 2013 | 31 May 2014 | TACAIDS | 70,000.00
| Support ZAC staff and stakeholders to attend regional and international HIV conferences | 01 Oct 2013 | 31 Mar 2014 | ZAC | 22,000.00
| Provide ICT technical support to LGAs who are reporting TOMSHA data electronically and Strengthen capacity of TACAIDS staff on data analysis software and GIS use (ICT unit) | 01 Aug 2013 | 31 May 2014 | TACAIDS | 20,000.00
| Conduct training on mainstreaming of HIV to LGAs and MDAs | 01 Oct 2013 | 31 Oct 2013 | ZAC | 10,000.00
| TA for Capacity Building to address gaps and implement the action plan | 01 Aug 2013 | 31 Dec 2013 | TACAIDS | 50,000.00
| Engage Zanzibar legal service centre to implement legal literacy programme on HIV bill and hold advocay meeting with MoJ, HIV Activitst, Laywers associations and potential CSOs | 01 Aug 2013 | 31 May 2014 | ZAC | 20,000.00
| Consultancy to translate the National AIDS Policy and HAPCA into Kiswahili and to develop user-friendly versions - National AIDS Policy including printing and dissemination; to raise awareness through national dialogue and training of MPs, TAPAC and assess awareness on policies and laws related to HIV/AIDS among key actors | 01 Aug 2013 | 31 May 2014 | TACAIDS | 315,000.00
| Support commemoration of WAD and ZAPHA+ district coordination meetings and Recruitment of National Program Coordinator and District Support Officers (NUNVs) in 5 regions | 01 Aug 2013 | 31 May 2014 | ZAC | 120,000.00
| TA support on Human Resource capacity; TACAIDS – National Programme Coordinator and Gender Programme Officer, Conduct annual HIV and AIDS forum for research; Support Annual regional HIV and AIDS reviews, Joint National Response monitoring and conduct coordination meetings | 01 Aug 2013 | 15 Jun 2014 | TACAIDS | 245,000.00
Outcome 3 | Conduct ToT and sensitization workshop on gender, human rights and HIV mainstream and organize national meeting to advoacte to rights and gender issues of the people with disabilities and KPs; support the department of occupational safety and health to intergrate HIV in its core functions | 01 Aug 2013 | 31 May 2014 | ZAC | 41,000.00
| Technical assistance and capacity management support to sectors | 01 Aug 2013 | 31 May 2014 | TACAIDS | 50,000.00
Outcome 7