United Nations Development Programme – UN Environment

Poverty Environment Action for SDGs

Tanzania

Mainstreaming Poverty-Environment-Gender-Climate Change into LED and SDG Localization for Sustainable Development and Poverty Eradication in Tanzania

Annual Project Report (2019)

| Implementing Agency: | United Nations Development Programme (UNDP) |
| --- | --- |
| Country: | Country Name |
| Project Title and ID: | Title: Mainstreaming Poverty-Environment-Gender-Climate Change into LED and SDG Localization for Sustainable Development and Poverty Eradication in Tanzania Award ID – 00092476 Project ID - 00097169 |
| Project Duration: | September 2018 - August 2022 |
| Reporting Time Frame | July to December 2019 |
| Contact Person/s: | CO Management Project Team Leader: Amon Manyama Project Assistant: Leticia Kweba |
| Funded by: | PEA Donors (EU, Austria and UNEP pooled funds – Norway and SIDA) UNDP - TRAC Local Donors – N/A |

Acronyms

PEA	Poverty Environment Action for SDGs

Table of Contents

I.	Project Status Information	4

II.	Project Progress	6

III.	Indicators Based Performance Assessment	11

IV.	Partnerships, Visibility & Communication	12

V.	Challenges	13

VI.	Financial Overview	14

VII.	Plan for the next Quarter	15

ANNEX 1 Detailed Financial Report	16

# Project Status Information

| Project Title | Mainstreaming Poverty-Environment-Gender-Climate Change into LED and SDG Localization for Sustainable Development and Poverty Eradication in Tanzania |
| --- | --- |
| Project ID/Output ID | Award ID – 00092476 /Project ID – 00097169 / Output 1 |
| Reporting Timeframe Start Date/End Date | January 2019 – December 2019 |
| Implementing Modality | NIM – National Implementation with 100% CO Support |
| Implementing Partner(s) Responsible Party(ies) | Partners: Main IP: Simiyu Region Authority; RPs: Ministry of Finance & Planning, Institute of Rural Development Planning (IRDP); Economic and Social Research Foundation (ESRF) |
| Donors | PEA Donors (EU, Austria, and UNEP pooled funds – Norway, and SIDA) |
| UNDP Strategic Plan RRF Outcome | Outcome 1: Growth and development are inclusive and sustainable, incorporating productive capacities that create employment and livelihoods for the poor and excluded. |
| UNDP Strategic Plan RRF Output | N/A |
| UNDAF/ UNDP CPD Outcome (s) | UNDAP 2016 - 2021 The economy is increasingly transformed for greater pro-poor inclusiveness and increased opportunities for decent and productive employment. |

| Project Objective | The project aims at integrating poverty, environment, gender and climate change objectives in the overarching policies, guidelines and frameworks and their associated implementation mechanisms. At the sub-national level, the project aims at enhancing capacities in poverty analytics and gender analysis, business plan development, and resources mobilization. Further, the project will facilitate dialogues and collaboration between LGAs, private sector and CSOs to scale up the community nature-based livelihood improvement and poverty reduction initiatives from the previous PEI/pro-poor project and other partners initiatives. The project will pay specific attention to community level interventions to support women entrepreneurs to increase incomes from Environment and Natural Resources (ENR) sub-sectors-based enterprises. The indicative outputs of the project are: National and sub-national government entities have strengthened technical capacities in planning and budgeting to implement poverty-environment-gender-climate change programmes and relevant SDG targets in an integrated and coherent manner. LGAs enhanced capacities and partnerships with private sector leading to increased investments and resources that deliver gender responsive livelihood improvement and poverty eradication, ENR sustainability, and SDGs at sub-national level. Economic Productivity and incomes for women from Environment and Natural Resources (ENR) sub-sectors-based enterprises increased. |
| --- | --- |

| Donor (ID & Description) | Annual budget (USD) | Expenditure (USD) | Delivery Rate (%) |
| --- | --- | --- | --- |
|  | Approved AWP | FACE | FACE / AWP |

# Project Progress

PEA Joint Output 1: Development planning, budgeting and monitoring systems integrate environmental sustainability and climate objectives for poverty eradication

| CO Deliverables | Status as of Date xxx |
| --- | --- |
| CO Deliverable 1.1: (12) Application of poverty analytic tools for environmentally friendly poverty targeting and community reducing and livelihoods improvement interventions. 1.3 Capacitate MDAs & Selected LGAs in developing and applying poverty assessment and poverty reduction targeting tools for poverty targeting. Activity Result 1.3 working with IRDP, develop and test poverty analytical tools for targeting and implementation of environmentally sustainable community poverty reducing and livelihoods improvement interventions through eco-village model nature-based climate smart and gender responsive enterprises and innovations targeting youths and women. | During the reporting, the Institute of Rural Development Planning (IRDP) in collaboration with Simiyu region and UNDP implemented a study / research using a Multidimensional Poverty Analysis Tool (MPAT) to carry out two parts i.e. poverty diagnosis and a baseline survey and achieve twin objectives of poverty analysis and establishment of baseline in respective areas. the main products are: Report on Multidimensional Poverty Analysis and Socio-economic survey for echo-village / eco-shores climate smart and gender responsive interventions along the Lake Victoria shores in Bunda & Busega Districts. Stakeholder’s validation workshop – proceedings report for Bunda & Busega Districts. Report on Multidimensional Poverty Analysis and Socio-economic survey for echo-village / eco-shores climate smart and gender responsive interventions for Simiyu region. Stakeholder’s validation workshop – proceedings report for Simiyu region. During the implementation 2 training sessions for IRDP staff were conducted on how to access, utilize and analyse the Multidimensional Poverty Analysis Tool (MPAT) software, which is web-based, which was developed by IFAD & WB. Cost Benefit Analysis of Prioritized Interventions/ Solutions in Bunda and Busega Districts for the Eco shore project along the Lake Victoria Cost Benefit Analysis of Prioritized Interventions/ Solutions for Climate Smart Interventions in Meatu, Itilima, Maswa and Bariadi Districts Pre-Feasibility Study for climate smart interventions in Mara and Simiyu Regions |
| CO Deliverable 1.2 Develop 2 plans for Prioritized Interventions in Districts based on the baseline and CBA report for Bunda DC, Bunda TC, Busega, and Simiyu Region | The Institute of Rural Development Planning was able to develop implementation plans for prioritized interventions in Mara and Simiyu Regions. The plans include the following key interventions; Horticultural crop production Azolla and hydroponic farming Fish farming Paddy production Establishment of Tree Nurseries, Tree Planting and beekeeping Spirulina farming Itilima Agricultural Development Centre and e-extension services Improvement of animal production Conservation agriculture Increase access and utilization of water resources Nyalaja Salt Processing Industry Meatu Community Radio Open up of Ligangabilili Soper Lodge Road |
| Country Indicators | Baseline | Target | Target Status |
| Country indicator 1.1 (Links to PEA joint project indicator: Number of poverty analytics and assessment tools for gender responsive poverty targeting developed and applied. | Year: 2018 Status: National poverty assessment reports existed | Year: 2019 Value: 1 | Achieved The MPAT has been applied to two districts and one region. Moving forward is continuation of the in-depth poverty analysis and cost-benefit analysis of the proposed interventions. Cost Benefit Analysis has been applied for the Prioritized Interventions / Solutions in Bunda and Busega Districts for the Eco shore project along the Lake Victoria Cost Benefit Analysis has been applied for the Prioritized Interventions/ Solutions for Climate Smart Interventions in Meatu, Itilima, Maswa and Bariadi Districts Pre-feasibility Study has been applied for climate smart interventions in Mara and Simiyu Regions |
| Country indicator 1.2 (Links to PEA joint project indicator: 2. Poverty monitoring systems integrated and applying p-e-g-c indicators in context of SDGs. | Year: 2018 Status: 0 | Year: 2019 Value: 2 | partially achieved: The overall project supported development of National SDGs VNR 2019. On going implementation to produce AU 2063, Country progress report. |

PEA Joint Output 2: Public finance and investment frameworks incentivize shift in public and private investments towards environmental sustainability and climate objectives for poverty eradication

| CO Deliverables | Status as of Date xxx |
| --- | --- |
| CO Deliverable 2.1: XXX Links to PEA Global Output 2 ATLAS Activity 2.4: (=CO Deliverable 2.4): Support One LGA in Simiyu to formulate and implement climate smart and gender responsive targeted poverty eradication interventions that include p-e-g-c objectives. | Progress Report on Multidimensional Poverty Analysis and Socio-economic survey for climate smart and gender responsive interventions for three LGAs in Simiyu region. Stakeholder’s validation workshop – proceedings report for Simiyu region (LGAs). Report of Cost-Benefit Analysis of prioritized investments / interventions in LGAs in Simiyu Region Report of Pre-feasibility Study on investments / interventions in LGAs for Simiyu Region |
| Country Indicators | Baseline | Target | Target Status |
| Country indicator 2.1 (Links to PEA joint project indicator) : Number of gender responsive and climate smart poverty eradicating investments at the sub-national level. | Year: 2018 Status: 0 | Year: 2019 Value: 1 | Achieved: Prepared Reports on Multidimensional Poverty Analysis, Cost Benefit Analysis of Prioritized Interventions / Investments and Implementation Plan |

# Indicators Based Performance Assessment (until after the ROAR is done)

| Indicators | Baseline | Target | Target Status |
| --- | --- | --- | --- |
| UNDAF and Project Outcome Indicator: TEXT % of National budget allocated to address poverty, environment and gender | Year: 2016 Status: progress has not been established | Year: TBD The targets were not established. | Achievement, Progress, Limited Progress, No Progress: progress not measured |
| CPD and Project Outcome Indicator: Number of policies / plans that integrate and allocate resources for implementation of poverty, environment and gender | Year: 2016 Status: 1 | Year: 2021 Value: 10 | Achievement, Progress, Limited Progress, No Progress: 3 plans |
| CPD and Project Outcome Indicator: Number of new jobs/livelihoods created through management of natural resources in the 28 targeted districts. | Year: 2016 Status: 0 | Year: 2021 Value: 1,500 | Achievement, Progress, Limited Progress, No Progress: 800 |

# Partnerships, Visibility & Communication

Contacts with various partners were made during implementation, workshops and meetings.  Thanks to the funding donors.

The partnerships were also maintained, and new partnerships were development with 5 regions (Mwanza, Mara, Kagera, Simiyu & Geita) around the Lake Zone.

New partnerships with Regional Administrative Secretary Office of Simiyu - Implementing Partner of PEA project as well as Institute of Rural Development Planning (IRDP) as new RP.

Also, partnership between UNDP & UNHABITAT and Regional Administrative Secretariat Office in Mwanza – to review projects that were conceived during the preparation of Mwanza urban master plan and regional investment guide in line with the urban development 2030 agenda. UNHABITAT and UNDP worked together to review the environmental and social aspects of the projects under Mwanza Investment Guide and Master Plan.

Continued support to various regions in Tanzania Mainland on regional investments guides contributed to the partially achievements of output 2. In addition, working with the Ministry of Finance and Planning in the implementation of FYDPII and reporting on 2030 agenda for SDGs through the VNR 2019 including progress on poverty-environment and gender related SDGs.

Coordination between MoFP, UN Women and UNDP in identifying gender gaps addressed in the government document for poverty reduction – PRAP, which was informed by the inputs from the gender-based study report prepared by UN Women / UNDP.

# Challenges

| Risk Log |
| --- |
| # | Description and Date Identified | Type | Probability and Impact | Countermeasures / Management Response | Last Update |
| 1 | Description: The CTA left and project approval by Finance Ministry was delayed despite the approval by PAC meeting. Date Identified: Date: October 2017 | operational | High Impact = 4 Probability = 4 | Management Response: Decided to engage with Regional Authorities who wanted the activities of the project to start as early as 2019. Countermeasures: The CO engaged the regional authority that signed the project document on March 22, 2019 and the implementation started July 2019. | Date: July 2019 |
| 2 | Description: Funding is low, inadequate to finance the CTA post and same time implement project activities Date Identified: Date: July 2017 | Financial | Medium Impact = 2 Probability = 2 | Management Response: Decided that the Programme Coordinator (NOD) will take over and lead / supervise the project using about 40% as he has experience with PEI projects. And be supported by RSC Counter measures: The CO will charge to the project the Direct Project Cost for the time spent by the Programme Coordinator and other staff, with minimal burden to the project. | Date: September 2019 |

# Financial Overview

ATLAS Project ID:00092476

ATLAS Output  ID: 00115525

| Donor (Name & ID) | Budget (USD) | Expense (USD) | Balance (USD) | Delivery (%) |
| --- | --- | --- | --- | --- |
| EU | 35,816.00 | 302.00 | 35,514.00 | 0.84% |
| ADA | 14,000.00 | 6,265.00 | 7,735.00 | 44.75% |
| UNEP | 0.00 | 0.00 | 0.00 | N/A |
| Gov CS | 0.00 | 0.00 | 0.00 | N/A |
| One Fund | 0.00 | 0.00 | 0.00 | N/A |
| TRAC | 45,000.00 | 44,753.00 | 247.00 | 99.45% |
| TOTAL | 94,816 | 51,320 | 43,496 |  |

ATLAS Project ID:00092476

ATLAS Output  ID: 00115526

| Donor (Name & ID) | Budget (USD) | Expense (USD) | Balance (USD) | Delivery (%) |
| --- | --- | --- | --- | --- |
| EU | 114,184.00 | 88,959.00 | 25,225.00 | 78.78% |
| ADA | 0.00 | 0.00 | 0.00 | N/A |
| UNEP | 0.00 | 0.00 | 0.00 | N/A |
| Gov CS | 0.00 | 0.00 | 0.00 | N/A |
| One Fund | 0.00 | 0.00 | 0.00 | N/A |
| TRAC | 112,500.00 | 103,713.00 | 8,787.00 | 92.19% |
| TOTAL | 226,684 | 192,672 | 34,012 |  |

# Plan for the next Quarter

For the October – Dec 2019, the plan is to boost delivery of the project by ensuring that there is a good flow of activities from the previous quarter, and the follow up on implementation is tighten up – such that IP, RPs, consultants, etc are doing their parts on time.

# ANNEX 1 Detailed Financial Report

# Footnotes

Detailed Quarterly Expenditure Report can be found in Annex 1