## AWP 2013-14
FY 2013/2014 PROJECT ANNUAL WORK PLAN ( ENHANCING AID MANAGEMENT CAPACITY IN TANZANIA -00079142)
EXPECTED OUTPUTS | PLANNED ACTIVITIES | Description | Quantity | Rate (Tshs) | Days | Responsible | TIMEFRAME |  |  |  | Total (TZS) | Total (USD) | Exchange Rate USD/TZS
And baseline, associated indicators and annual targets | List activity results and associated actions | [5 empty] | Q1 | Q2 | Q3 | Q4 |  |  | Exchange Rate USD/TZS
Output 1: DCF approved and implemented with Mutual Accountability framework and coherence of GoT engagement in international AE fora strengthened.
(i) Develop DCF incl. Monitoring and Reporting framework; (ii) Roll-out of finalised DCF | DCF shared with MPs | Conference | 37 | 90000 | 2 | MoF | 6660000 |  |  |  | 6660000 | 4036.3636 | 1650
|  | Consultants Fees | 2 | 600000 | 4 |  | 4800000 |  |  |  | 4800000 | 2909.0909 | 1650
|  | Transport/Fuels/ Airtickets | 15 | 1000000 | 1 |  | 15000000 |  |  |  | 15000000 | 9090.9091 | 1650
|  | Transport | 20 | 50000 | 2 |  | 2000000 |  |  |  | 2000000 | 1212.1212 | 1650
| DCF shared with CSOs and Private Sector | Conference | 40 | 90000 | 2 | MoF | 7200000 |  |  |  | 7200000 | 4363.6364 | 1650
|  | Consultants Fees | 2 | 600000 | 2 |  | 2400000 |  |  |  | 2400000 | 1454.5455 | 1650
|  | Transport | 40 | 50000 | 2 |  | 4000000 |  |  |  | 4000000 | 2424.2424 | 1650
Translation of DCF (English to Kiswahili)
Editing and Proofing of DCF documents (English and Kiswahili)
Priting DCF
DCF Monitoring and Reporting Framework developed
DCF- Sensitized to DPP
DCF - Sensittized to LGAs
DCF- Sensitized to CSOs
| Sub Total Output 1: | [5 empty] | 42060000 | 0 | 0 | 0 | 42060000 | 25490.9091 | 1650
Output 2: Budgeting cycle, aid management systems and aid policy dialogue enhanced for stronger Government leadership of the national development framework.
Baseline: -Centralized AMP system and weak MTEF dialogue at sector level. -Dialogue Structure only partially implemented. Indicators: -Volume of ODA disbursed through Exchequer. -Number of DPs updating AMP on a quarterly basis. -Number of MKUKUTA/PER meetings per year.
(i) Strengthen roll-out and operationalisation of AMP to inform budgeting process and ODA management | Development Gateway Foundation Service Contract and implementation of AMP upgrade version (second installment) | Consultants Fees | 1 | 287284240 | 1 | UNDP |  | 287284240 |  |  | 287284240 | 174111.6606 | 1650
Targets 2013/14: -MDAs using AMP in data processing and management to inform budget process. -Annual AMP report and monthly flash reports published. - Assessment of AMP roll-out compliance. -5 MoF AMP administrators trained. | Discussions with MDAs on MTEF in order to enhance budget accuracy and quality of information | Conference | 90 | 90000 | 2 | MoF |  | 16200000 |  |  | 16200000 | 9818.1818 | 1650
|  | Transport | 90 | 50000 | 2 | MoF |  | 9000000 |  |  | 9000000 | 5454.5455 | 1650
|  | Stationary | 1 | 1000000 | 1 | MoF |  | 1000000 |  |  | 1000000 | 606.0606 | 1650
| Training MDAs AMP Focal Point | Conference | 90 | 90000 | 3 | MoF | 24300000 |  |  |  | 24300000 | 14727.2727 | 1650
|  | Transport | 90 | 50000 | 3 |  | 13500000 |  |  |  | 13500000 | 8181.8182 | 1650
| Training DPS on AMP | Breakfast/Lunch | 70 | 40000 | 3 | MoF | 8400000 |  |  |  | 8400000 | 5090.9091 | 1650
|  | Transport for Government staff Facilitators | 20 | 80000 | 3 | MoF | 4800000 |  |  |  | 4800000 | 2909.0909 | 1650
| 2012/13 Annual Report Writing for ODA | Conference and accommodation | 30 | 160000 | 6 | MoF | 28800000 |  |  |  | 28800000 | 17454.5455 | 1650
|  | Transport | 30 | 50000 | 2 |  | 3000000 |  |  |  | 3000000 | 1818.1818 | 1650
|  | Stationary | 1 | 2000000 | 1 |  | 2000000 |  |  |  | 2000000 | 1212.1212 | 1650
|  | Printing Report | 500 | 8500 | 1 |  | 4250000 |  |  |  | 4250000 | 2575.7576 | 1650
| Enhancing Capacity of AMP Administration | DSA Foreign | 5 | 831600 | 12 | MoF |  | 49896000 |  |  | 49896000 | 30240 | 1650
|  | Air ticket | 5 | 1500000 | 1 |  |  | 7500000 |  |  | 7500000 | 4545.4545 | 1650
|  | Ground transport | 5 | 100000 | 2 |  |  | 1000000 |  |  | 1000000 | 606.0606 | 1650
| Annual AMP knowledge sharing workshop | DSA Foreign | 2 | 831600 | 3 | MoF |  | 4989600 |  |  | 4989600 | 3024 | 1650
|  | Air ticket | 2 | 1500000 | 1 |  |  | 3000000 |  |  | 3000000 | 1818.1818 | 1650
|  | Ground transport | 2 | 100000 | 1 |  |  | 200000 |  |  | 200000 | 121.2121 | 1650
Strengthen GoT leadership cap & Institutional support to strengthen PER process | Secretariat support to PER | staffing | 2 | 6000000 | 12 | MoF | 36000000 | 36000000 | 36000000 | 36000000 | 144000000 | 87272.7273 | 1650
| Operational suport to PER Secretariat | Conference facilities, transport and stationeries | 1 | 13183333 | 4 | MoF | 13183333 | 13183333 | 13183333 | 13183333 | 52733332 | 31959.5952 | 1650
| Capacity and research support to PER Secretariat (DEP Economics/UDSM) | consultancy | 1 | 23588667 | 4 | MoF | 23588667 | 23588667 | 23588667 | 23588667 | 94354668 | 57184.6473 | 1650
| Sub Total Output 2: | [5 empty] | 161822000 | 452841840 | 72772000 | 72772000 | 760207840 | 460732.0242 | 1650
Output 3: Institutional capacity of Ministry of Finance to lead Aid Management & Project Implementation Enhanced.
Baseline: Uncoordinated use of exposure visits, peer-learning and institutional capacity building activities for MOF and external finance management.
Indicators: Evidence of effective institutional innovation and learning from exposure visits, peer learning and trainings.
Capacity of the MOF to participate in Regional Cooperation Matters strengthened and sustained. | Facilitating MOF to attend Regional meeting at EAC/SADC/AU | DSA Foreign | 3 | 831600 | 12 | MoF |  | 7484400 | 7484400 | 7484400 | 22453200 | 13608 | 1650
|  | Tickets | 3 | 1650000 | 1 |  |  | 1237500 | 1237500 | 1237500 | 3712500 | 2250 | 1650
Institutional capacity building of MoF to lead implementation enhanced. | Capacity Needs Asssessment: training on CD and methodology/approach | Conference facilities | 30 | 90000 | 1 | MoF/UNDP | 2700000 |  |  |  | 2700000
|  | Consultancy Fees | 1 | 600000 | 2 |  | 1200000 |  |  |  | 1200000
|  | transport | 30 | 30000 | 1 |  | 900000 |  |  |  | 900000
| Capacity Needs Asssessment | Conference facilities | 30 | 90000 | 1 | MoF/UNDP |  | 2700000 |  |  | 2700000 | 1636.3636 | 1650
|  | Consultancy Fees | 2 | 600000 | 20 |  |  | 24000000 |  |  | 24000000 | 14545.4545 | 1650
|  | transport | 30 | 30000 | 1 |  |  | 900000 |  |  | 900000 | 545.4545 | 1650
Capacity of the MOF to participate in international fora sustained. | Facilitate MOF to attend UNGA | DSA Foreign | 2 | 831600 | 24 | MoF | 39916800 |  |  |  | 39916800 | 24192 | 1650
|  | Tickets | 2 | 5775000 | 1 |  | 11550000 |  |  |  | 11550000 | 7000 | 1650
| Facilitate MOF to attend ECOSOC | DSA Foreign | 2 | 831600 | 24 | MoF |  |  |  | 39916800 | 39916800 | 24192 | 1650
|  | Tickets | 2 | 5775000 | 1 |  |  |  |  | 11550000 | 11550000 | 7000 | 1650
(i) UNDP funded projects implemented as planned. (ii) Implement measures to strengthen financial reporting as per audit comments. | Semi-annual meeting for Coordinators/ Managers/ financial controllers of UNDP funded projects (training in financial reporting) | Conference facilities and accommodation | 40 | 160000 | 6 | MoF |  | 19200000 |  | 19200000 | 38400000 | 23272.7273 | 1650
|  | transport | 40 | 50000 | 4 |  |  | 4000000 |  | 4000000 | 8000000 | 4848.4848 | 1650
|  | facilitation costs | 2 | 2000000 | 2 |  |  | 4000000 |  | 4000000 | 8000000 | 4848.4848 | 1650
|  | Half/Diem | 40 | 40000 | 6 |  |  | 4800000 |  | 4800000 | 9600000 | 5818.1818 | 1650
External Finance Department management retreat; discusses implementation progress and challenges including of planned annual activities, and proposed way forward are documented. | Management retreat to discuss department implementation of activities; progress, challenges and way forward including Semi Annual Report Writing | Conference and accommodation | 40 | 160000 | 6 | MoF |  | 19200000 |  | 19200000 | 38400000 | 23272.7273 | 1650
|  | Transport | 40 | 50000 | 4 |  |  | 4000000 |  | 4000000 | 8000000 | 4848.4848 | 1650
|  | Stationary | 1 | 1000000 | 2 |  |  | 1000000 |  | 1000000 | 2000000 | 1212.1212 | 1650
|  | DSA Local (half per/diem) | 40 | 40000 | 6 |  |  | 4800000 |  | 4800000 | 9600000 | 5818.1818 | 1650
UNDP Desk Supported | communication support | communication | 3 | 100000 | 12 | MoF | 900000 | 900000 | 900000 | 900000 | 3600000 | 2181.8182 | 1650
| Sub Total Output 3: | [5 empty] | 57166800 | 98221900 | 9621900 | 122088700 | 287099300 | 173999.5758 | 1650
TOTAL | [6 empty] | 261048800 | 551063740 | 82393900 | 194860700 | 1089367140 | 660222.5091
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
|  |  |  | Quaterly expenditure in USD: |  |  | #REF! | #REF! | #REF! | #REF!