## OCTOBER_DECEMBER_ 2015
SPANEST Project Activity Report for Second Quarter January -April, 2017)
Date: |  | 2017-04-27
PROJECT |  | SPANEST
Protected Areas: |  | KNP, MKGR and MRFNR
Name of the reporter: |  | Edmund Murashani
No. | Outputs-activities | Activity Progress indicators | Quarter |  |  | Remarks (Explain reasons if low rate of achievement and mitigation actions)
|  | (Number of trainings, number of people trained by sex, etc) | Planned | Achieved | Rate of achievement %
Output 1.1 : Inter-sectoral District land management coordination mechanism between Tanzania National Parks authority (TANAPA), district authorities and Wildlife Division (WD) is instituted, emplaced and enacted in the Greater Ruaha and Greater Kitulo-Kipengere landscapes of Southern Tanzania, to ensure that biodiversity management in National Parks, Game Reserves, wildlife migration corridors and dispersal areas is factored into decision-making governing land use management and coordinated action plans are followed.
1.1.4 | To design and produce KNP Outreach department broncures | Contracted firm to design and produce | 1 | 1 | 100 | ALLRICH Designing and Printing Firm in Mbeya were Contracted to execute the assignment. To be completed the next quarter.
|  | Designed Bronchures | 1 | 1 | 100
|  | Number of Bronchures Produced | 4000 | 4000 | 100
|  | Number of participating Institutions | 2 | 2 | 100 | KNP and SPANEST PROJECT
1.1,4 | To produce and print out Law enforcement summarized offences and penalties | Number of Produced summarised Offences and Penalties | 250 | 30 | 12
|  | Participating Institutions | 3 | 3 | 100 | KNP, SPANEST, MAKETE DC&MKGR
|  | Number of distributed documents | 250 | 30 | 12
| To review and Update Mpanaga Kipenegere Game Reserve Bronchure | Request Made for redesign and production | 1 | 1 | 100 | To be conducted early next quarter, The request and budget is submitted arleady
|  | Number of Request Processed | 1 | 0 | 0
|  | Number of bronchures requested for production (English Version) | 6000 | 0 | 0
|  | Number of bronchures requested for production (Kiswahili Version) | 8000 | 0 | 0
1.1.8 | To convene a meeting of GKKL for Njombe Region Stakeholders of Natural Resources and Tourism towards establishment of Landscape Coordination Committee (LCC) | Duration of the Meeting/working(no. of days) | 1 | 1 | 100 | To be conducted early next quarter
Number of Participants
|  | Participating Institutions | 5 | 5 | 100 | SPANEST, NJOMBE REGION, NJOMBE DC, LUDEWA DC, WANGINGOMBE DC, MAKETE DC and MAKAMBAKO TC
|  | Number of Implemented activity | 1 | 1 | 100
Output: 1.2 TANAPA, WD, 7 pilot District Authorities and civil society partners plan, implement, and monitor biodiversity management measures for these landscapes (systematic conservation plan is in place which (1) defines Greater Ruaha and Greater Kitulo-Kipengere landscapes wildlife corridors and dispersal areas, (2) EIA and impact management stipulations in place to avoid and/ or mitigate development impacts in sensitive areas, (3) monitoring and reporting systems are in place, and (4) as a result, enforcement measures are operational).
1.2.4 | To facilitate KNP to design and develop the Park Tourism Map | Participating Institutions | 2 | 1 | 50 | Delayed information from the Park to engage timely the Zonal GIS Officer
|  | Number of Participants (Stakeholders) | 6 | 0 | 0
|  | Field work executed | 5 | 0 | 0
|  | Number of Tourists Map developed | 1 | 0 | 0
1.2.4 | GIS, mapping and ground truthing of two landscapes | Duration of the Training (no. of days) | 5 | 0 | 0 | To be implemented in the next quarter
|  | Number of Participants (Stakeholders) | 6 | 0 | 0
|  | Field work executed | 5 | 0 | 0
|  | Number of Tourists Map developed | 1 | 0 | 0
|  | Participating Institutions | 3 | 0 | 0
1.2.7 | To draft TORS and Pay consultancy for ecological and hydrological studies on Nhumbe Wildlife Corridor | Awarded Contracts | 1 | 1 | 100
|  | Participanting institutions | 3 | 2 | 66.6667
|  | Duration of the Assignment | 30 | 10 | 33.3333
Output: 1.3 TANAPA has the competence and staff skills to lead land use planning, management and monitoring in landscapes; working with partners to assess hydrological dynamics, make predictions of climate change trends and gauge long term impacts on biodiversity conservation. Two specialist units are developed by TANAPA with partners; a land use planning unit and an ecological monitoring unit, and are in place.
1.3.1 | To convene GKKL and GRL land use stakeholders workshop and create Land use Management unit | Duration of the Training | 2 | 0
|  | Particiapnting Institutions | 6 | 0
|  | Number of Stakeholders attended | 30 | 0
|  | LUP Team formed | 1 | 0
|  | Number of implemented activity | 1 | 0
1.3.4 | Training for village leaders neighboring Kitulo National Park on Environmental Management (water sources conservation, Simple water quality management in Collaboration with MAKETEDC | Duration of the Training (No. of days) | 3 | 3 | 100
|  | Number of Participating stakehloders | 96 | 96 | 100 | SPANEST, MAKETE DC, MKGR, LNBWB, RBWB and ELIMISHA
|  | Participating Institutions | 6 | 6 | 100
|  | Number of Participating villages | 30 | 30 | 100
|  | Number of Agreed Resolutions | 5 | 5 | 100
1.3.6 | To facilitate Njombe Region Tourism Committee meet andvalidate the Region Tourism Stratergic Plan. | Duration of the meeting/working(no. of days) | 6 | 6 | 100
|  | Number of Participating institutions | 4 | 4 | 100 | SPANEST, NJOMBE REGION, MBEYA REGION, NJOMBE DC
|  | Number of Participants | 10 | 9 | 90
|  | Number of Participating Males | 4 | 1 | 25
|  | Number of Document produced | 2 | 2 | 100
|  | Number of agreed resolutions/Wayfoward | 3 | 3 | 100
Output:1.5 For Ruaha and Kitulo NPs, boundaries for recent/planned PA EXTENSIONS (BEING Usangu Game Reserve and Mpanga Kipengere Game Reserve respectively) are demarcated, associated public consulations are completed and respective management plans are completed, taking into account the outcomes for both.
1.5.1 | To engage District Land use Planning teams (Surveyors) in collaboration with Park Officials with communities to define shared boundaries and signify them with Concrete beacons. | Number of Participants | 25 | 0 | 0 | The assignment was postponed due to existing boundary conflict between KNP and neighbouring villages
|  | Female participants | 15 | 0 | 0
|  | Villages to be covered | 8 | 0 | 0
|  | Male particpants | 30 | 0 | 0
|  | Particpanting Institutions | 4 | 0 | 0
|  | Duration of the assignment (no. of days) | 12 | 0 | 0
1.5.4 | To clear 26 KM of boundary and install beacons & signposts around KNP | Materials Supplied (Gravel and Sand ) Tonnes | 48 | 48 | 100
|  | Materials supplied (Cement) | 248 | 248 | 100 | The exercise of beacons fabrication and installaton for KNP was finalised succeffuly as per requirements and guidelines
|  | Materials suplied (Iron Bars) 16 mm | 116 | 116 | 100
|  | Materials supplied (Iron Bars) 8 mm | 45 | 45 | 100
|  | Binding Wire Supplied (Roller) | 15 | 15 | 100
|  | Beacons Fabricated and Installed | 116 | 116 | 100
|  | Duration of training (days) | 30 | 90 | 300
| To Survey, clear KM of boundary and install beacons & signposts around MKGR | Materials Supplied (Gravel ) Tonnes | 42 | 42 | 100
|  | Materials supplied (Sand) Tonnes | 37 | 37 | 100
|  | Materials supplied (Cement) | 135 | 135 | 100
|  | Materials suplied (Iron Bars) 16 mm | 45 | 45 | 100
|  | Materials supplied (Iron Bars) 8 mm | 35 | 35 | 100
|  | Binding Wire Supplied (Roller) | 10 | 10 | 100
|  | Beacons Fabricated and Installed | 67 | 45 | 67.1642
|  | Duration of training of the exercise | 30 | 30 | 100
Component 3: Project Management to ensure effective project administration, M&E, and coordination has enabled timely and efficient implementation of project activities.
3.1.5 | Produce reports for GRL | Number of quarterly reports compiled and submitted | 1 | 1 | 100
3.1.7 | Maintain project machinery and equipment | Number of project vehicles mantained | 1 | 1 | 100
AREAS OF STRENGTH |  | Good cooperation from stakeholders especially the district authorities and conservation-based institutitons was key for reported achievements
Cite the factors that facilitated the implementation and/or completion of activities.
CHALLENGES ENCOUNTERED |  | Poor reporting from consultants and other stakeholders about the funds provided and executed activities progress. Other commitments of key stakeholders especially those from the parks. Receiving funds request from our 8key beneficiaries which was not budget for. Boundary Conflicts
Cite challenges encountered in the implementation/ completion of activities. |  | Delays in submitting proposal from key beneficiaries in particular parks authorities to request funds for implementation
ACTIONS TAKEN |  | Regular consultation and arrangements of technical meetings with key beneficiaries as well as simple reporting forms and Training on Project Proposal and Report writing (M& E)
Cite specific actions taken to address the challenges. |  | The implementation of the undone works to be carried forward for the reporting phase
SUPPORT REQUIREMENTS |  | Availability of stakeholders memebers, Provisioning of equipments during implementation from and Project coordination Unit
What were the common support requirements needed to accomplish the task? |  | Stakeholders, funds, transport, time and other office office equipment.
LESSONS LEARNED |  | Collaborative and timely planning between Project Management unit and stakeholders enhance efficiency in achieving project projected targets. It has been identified that to enhance Project Perforance and create sense of ownership it is important to plan jointly and set the intended achievement.
What are the specific lessons learned in the implementation of the activities?