## AWP&B
ANNUAL WORK PLAN
Project name: STRENGTHENING INSTITUTIONAL FRAMEWORK FOR SERVICE DELIVERY
Project number: 79645
Year: 2012
Implementing Partner: Ministry of Local Government
Expected Outputs | Planned activities | Time frame |  |  |  | Responsible party | Funding source | Budget description | Annual Budget in USD 1USD=2350 UGX | Annual Budget (UGX)
|  | Q1 | Q2 | Q3 | Q4
Output 1: Legal, policy and administrative framework for LG service delivery planning and management strengthened Baseline: Weak and inconsistent, legal, regulatory and coordination frameworks for service delivery. Indicators: Harmonized Local Government Act, NPA Act and Budget Act Targets: i Gaps and Inconsistencies in the LG Act, NPA Act and Budget Act identified; ii Revised LG planning and budgeting guidelines produced iii Inconsistencies in service delivery and program management approaches in LGS identified Related CP outcome: 1.3. Capacity of selected LGs and oversight entities build and delivering accountable, inclusive and demand driven social and economic services | 1. Activity Result: LG administrative set-up and structures of service delivery mandates revised
| Action: Commission a study involving dialogue at the national, LG and community levels to review and make recommendations on the appropriate LG administrative set-up |  |  |  |  | MoLG | UNDP
| Action Items: (i)Procure and commision a consultancy to carry out a study on the LG administrative set-up | X | X |  |  | MoLG | UNDP | Consultancy fee | 78724 | 185001400
| (ii)Conduct consultative (1) and validation (1) meetings at the LG level on LG administrative set-up | X | X |  |  | MoLG | UNDP | Meeting costs (Local travel, DSA, conference facilities) | 12000 | 28200000
| (iii)Conduct a national consultative and validation meetings on LG administrative set-up |  | X |  |  | MoLG | UNDP | Meeting costs (Local travel, DSA, conference facilities) | 8000 | 18800000
| (iv) Print final draft report on the appropriate LG administrative set-up |  |  | X |  | MoLG | UNDP | Printing costs | 5000 | 11750000
| Action: Commission a study to review LG structures and the respective service delivery mandates |  |  |  |  | MoLG | UNDP |  |  | 0
| Action Items: (i) Procure and commission consultancy to review the LG structures |  | X |  |  | MoLG | UNDP | Consultancy fee | 94000 | 220900000
| (ii) Conduct one national stakeholder consultative workshops |  |  | X |  | MoLG | UNDP | Workshops | 50000 | 117500000
| (iii) Conduct field visits to 40 Districts |  |  | X |  | MoLG | UNDP | Meeting costs (Local travel, DSA, conference facilities) | 55000 | 129250000
| (iv)Conduct four verification and validation workshops |  |  |  | X | MoLG | UNDP | Workshops | 50000 | 117500000
| (v) Printing final report on the LG structures |  |  |  | X | MoLG | UNDP | Printing costs | 10000 | 23500000
| 2. Activity Result: A report on inconsistencies in legal and policy framework approved | [5 empty] | UNDP |  |  | 0
| Action: Commission a consultancy to identify all inconsistencies/gaps in the legal and policy framework (LG Act, NPA, Budget Act). |  |  |  |  | NPA | UNDP |  |  | 0
| Action Items: (i) Hold meetings with stakeholders to determine the scope of and develop ToRs for the study to identify inconsistencies and gaps in the legal and policy framework | X |  |  |  | NPA | UNDP | Meeting costs (conference facilities) | 3000 | 7050000
| (ii)Procure and commission consultancy to identify inconsistencies in the legal and policy framework | X | X |  |  | NPA | UNDP | Consultancy fee | 20400 | 47940000
| (iii) Hold two stakeholder meetings to review the draft report on the inconsistencies |  | X |  |  | NPA | UNDP | Meeting costs (conference facilities) | 6000 | 14100000
| 3. Activity Result: Revised LG planning and budgeting guidelines that are aligned to the national development planning and budgeting framework and that accommodate all development initiatives in the LG sector. |  |  |  |  | NPA | UNDP |  |  | 0
| Action: Consultancy to revise the LG planning and budgeting guidelines focusing on, among others, alignment with the national development planning framework |  |  |  |  | NPA | UNDP |  |  | 0
| Action items: (i) Hold Stakeholders' meetings to finalise the ToRs for the consultancy to revise the LLG planning and budgeting guidelines. |  | X |  |  | NPA | UNDP | Meeting costs (Local travel & DSA) | 4000 | 9400000
| (ii) Procure and commission consultancy to review the guidelines for LLGs planning & budgeting and align them to the NDP |  |  | X | X | NPA | UNDP | Consultancy fee | 50000 | 117500000
| (iii) Consultations with LLG stakeholders |  |  | X | X | NPA | UNDP | Meeting costs (Local travel & DSA) | 45000 | 105750000
| (iv) Conduct four validation workshops on the draft revised LG planning and budgeting guidelines at the LLGs level |  |  |  | X | NPA | UNDP | Workshops | 24000 | 56400000
| 4. Activity Results: DPUs provided with tools | [8 empty] | 0
| Action: Procure tools for PDUs in LGs (e.g. computer, printer, photocopies, digital camera and scanner) to enable them effectively carry-out LG planning and budgeting processes | [8 empty] | 0
| Action Items: (i) Carry out a tools needs assessment in DPUs in a sample of 10 discricts | X |  |  |  | NPA | UNDP | Facilitation costs | 24000 | 56400000
| (ii) Procure and distribute computers, printers, photocopies, digital cameras and scanners for 50 Districts |  |  | X | X | NPA | UNDP | Equipment cost | 276000 | 648600000
| 5. Activity Result: A report on inconsistencies and best practices in service delivery and program management approaches being used by all stakeholders (including CSOs) in LGs produced. |  |  |  |  | MoLG | UNDP |  |  | 0
| Action: Commission a study to identify inconsistencies and best practices in service delivery and program management approaches in LGs |  |  |  |  | MoLG | UNDP |  |  | 0
| Action Items: (i) Procure and commission consultancy to identify inconsistencies and best practices in service delivery and management approaches | X |  |  |  | MoLG | UNDP | Consultancy fee | 17000 | 39950000
| (iii) Conduct one meeting of stakeholder to review the draft report |  | X |  |  | MoLG | UNDP | Meeting costs (conference facilities) | 4000 | 9400000
| 6. Activity Result: Principles to guide harmonization of development and service delivery programs in LGs produced | [8 empty] | 0
| Action:. Meeting with all stakeholders (including CSOs) and develop principles to guide harmonization of development and service delivery programs being implemented in LGs | [8 empty] | 0
| Action Items: (i) Stakeholder meetings to study report on the inconstancies and best practices in service delivery and management |  |  | X |  | MoLG | UNDP | Meeting costs (conference facilities) | 12000 | 28200000
| (ii) Constitute a team to develop principles to guide harmonization in the implementation of development and service delivery programmes |  |  | X |  | MoLG | UNDP | Resource persons | 8000 | 18800000
| (iii) Print the developed guide for harmonization of development and service delivery programmes |  |  |  | X | MoLG | UNDP | Printing costs | 5000 | 11750000
| 7. Activity Result: A Decentralized HIV/AIDS response strategic plan developed (for the decentralized response self coordinating entity) |  |  |  |  | MoLG | UNDP |  |  | 0
| Action: Commission a consultancy to develop the Decentralized HIV/AIDS response strategic plan |  |  |  |  | MoLG | UNDP |  |  | 0
| Action Items: (i) Final costing plan for the decentralized HIV/AIDS response strategic plan (the strategic response plan is in place) |  |  | X | X | MoLG | UNDP | Fees (consultants fee) | 10000 | 23500000
| 8. Activity Result: Capacity of the decentralized HIV/AIDS response self coordinating entity enhanced | [8 empty] | 0
| Action: Provide support including tools and operations to the HIV/AIDS response self coordinating entity | [8 empty] | 0
| Action Items: (i) Procure and distribute tools for the HIV/AIDS response self coordinating entities |  | X | X |  | MoLG | UNDP | Equipment costs | 150000 | 352500000
Output 2: National and LG capacity for service delivery enhanced Baseline: Inadequate capacity by LGs to deliver services Indicators: (a) Revised NLGCBP (capacity building strategy for LGs) in place (b) Number of LGs with revised Capacity Building Plans Targets: i. Revised NLGCBP addressing performance gaps in LGs ii. Capacity needs assessment report for MoLG and NPA Related CP outcome: 1.3. Capacity of selected LGs and oversight entities build and delivering accountable, inclusive and demand driven social and economic services. | 1. Activity Result: Draft revised National Local Government Capacity Building Policy produced |  |  |  |  | MoLG | UNDP |  |  | 0
| Action: Commission a consultancy to review the relevance and effectiveness of current capacity building strategies to improving service delivery in LGs and refine the NLGCBP based on the results of the study whilst addressing crosscutting issues (gender, HIV/AIDS etc..) |  |  |  |  | MoLG | UNDP |  |  | 0
| Action Items: (i) Procure and commission consultant to revise the NLGCBP | X | X |  |  | MoLG | UNDP | Consultancy fee | 33000 | 77550000 | 16500
| (ii) Conduct a stakeholder meeting to validate draft revised policy |  |  | X |  | MoLG | UNDP | Workshops | 12000 | 28200000
| (iii) Print the revised NLGCBP |  |  |  | X | MoLG | UNDP | Printing costs | 20000 | 47000000
| 2. Activity Result: A report on capacity needs assessment and capacity building plans of NPA and MOLG with regard to their role of planning for the LG sector |  |  |  |  | MoLG | UNDP |  |  | 0
| Action: Consultancy to conduct capacity needs assessment and formulate the capacity building plans of NPA and MoLG to support LG service delivery |  |  |  |  | MoLG | UNDP |  |  | 0
| Action Items: (i) Procure and commission consultant (s) to conduct a capacity needs assessment for MoLG and formulate the CB plans to support LG service delivery | X |  |  |  | MoLG | UNDP | Consultancy fee | 60000 | 141000000
| (ii) Conduct meeting to validate the draft capacity assessment report and capacity building plan for MoLG | X | X |  |  | MoLG | UNDP | Meeting costs (Local travel & DSA) | 8000 | 18800000
| 3. Activity Result: Capacity of MoLG and NPA enhanced for planning for the LG sector | [8 empty] | 0
| Action: Support the implementation of capacity building activities as identified in the capacity needs assessment and detailed in the capacity building plans which may include: short-term courses, exposure and re-tooling | [8 empty] | 0
| Action Items: (i) Implementation of the capacity building plan in MoLG |  |  | X | X | MoLG | UNDP | Training costs | 75000 | 176250000
| (ii) Implementation of the capacity building plan in NPA |  |  | X | X | NPA | UNDP | Training costs | 65000 | 152750000
Output 3: Public Private Partnership framework for enhancing service delivery in LGs developed and implemented Baseline: Limited use of PPP approach in LG service delivery Indicators: Number of LGs effectively utilizing PPP approaches for service delivery and Local Economic Development Targets: i. PPP Framework Policy for Uganda disseminated ii. PPP Tool kit/Guidelines for LGs developed Related CP outcome: 1.3. Capacity of selected LGs and oversight entities build and delivering accountable, inclusive and demand driven social and economic services. | 1. Activity Result: A Public Private Partnership (PPP) Tool kit/Guidelines for LGs in place |  |  |  |  | MoLG | UNDP |  |  | 0
| Action: Consultancy to develop the Public Private Partnership (PPP) Tool kit/Guidelines for LGs (refining the existing MoLG draft) – which is in line with the Public-Private Partnership Framework Policy for Uganda developed by MoFPED as well as the PPP Legislation (now a bill pending Cabinet Approval) and based on documented PPP experiences at LG level) |  |  |  |  | MoLG | UNDP |  |  | 0
| Action Items: (i) Procure and commission consultant to develop PPP tool kit/ guidelines on PPP for LGs | X | X |  |  | MoLG | UNDP | Consultancy fee | 28000 | 65800000
| (ii) Stakeholder meeting to review the draft PPP tool kit/ guidelines for LGs |  |  | X |  | MoLG | UNDP | Workshops | 10000 | 23500000
| (iii) Print final PPP tool kit/ guidelines |  |  | X |  | MoLG | UNDP | Printing costs | 20000 | 47000000
| (iv) Finalise consultations on the procurement guidelines on the management of taxi parks in LGs | X | X |  |  | MoLG | UNDP | Meeting costs (Local travel & DSA) | 25000 | 58750000
Administrative costs, audit, monitoring and evaluation | 1. Activity Result: Project implementation team supported to ensure effective project monitoring and evaluation and timely report and work plan production | [8 empty] | 0
| (i) Salary for Assistant Finance Officer | X | X | X | X | MoLG | UNDP | VLA | 12676 | 29788600
| (ii) Salary for Decentralized planning Specialist |  |  | X | X | NPA | UNDP | Salary | 27828 | 65395800
| (iii) Procurement of facilities (desk, chair, computer, printer) for the Finance Assistant |  | X |  |  | MoLG | UNDP | Procurement of equipment | 3000 | 7050000
| (iv) Procurement of facilities (desk, chair, computer, printer) for the Decentralisation planning specialist |  | X |  |  | NPA | UNDP | Procurement of equipment | 3000 | 7050000
| (v) Office Operations (email, stationery, tonner, fuel) | X | X | X | X | MoLG | UNDP | Office operations | 12000 | 28200000
| (vi) Office Operations (email, stationery, tonner, fuel) | X | X | X | X | NPA | UNDP | Office operations | 4000 | 9400000
| (vii) Monitoring of progress in implementation of activities | X | X | X | X | MoLG | UNDP | Project M&E | 12000 | 28200000
| (viii) HRM & procurement support to project implementation | X | X | X | X | UNDP | UNDP | Administrative cost | 43399 | 101987650
| (ix) Communication for project implementation | X | X | X | X | UNDP | UNDP | Communication cost | 15000 | 35250000
Total | [8 empty] | 1510027 | 3548563450