## Sheet1
ANNUAL WORK PLAN | [13 empty] | GEN INDICATORS
Strengthening Disaster Risk Reduction and Recovery in Ukraine
Project ID: 00129527 |  | Legend: | Implemented | Planned
Year: 2021 | Date: 01 September 2021
EXPECTED OUTPUTS | PLANNED ACTIVITIES | PLAN | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Baseline associated indicators and annual targets | Activity results and associated actions | [12 empty] | Men | Women | Survey Results | Blog | Report
OUTPUT 1: Target communities, including the most vulnerable, have improved capacity, knowledge tools and financing mechanisms to build resilience, and to prevent and better recover from natural disasters based on the principle of leaving no one behind. | Activity 1: National government has improved policy frameworks and plans for Disaster Risk Management, coherent with Climate Change Adaptation policies that respond to the needs of women and men from diverse groups, especially the most vulnerable.
| 71300 Local Consultants | 15,707.90
Policy & Legal Expert | bar: Mar to Nov
| 72100 Contractual Services-Companies | 1600
Public hearings in disaster-affected regions | bar: Mar to Apr; Sep to Oct
Stakeholder consultations with the Government | bar: May; Jul to Oct
A national training on Post Disaster Needs Assessment (PDNA), Sendai Framework, Disaster Recovery Framework (conference services) | bar: Sep
| 71600 Travel | 1000
| Local level needs assessment in disaster-affected regions - travel by project team members if applicable as per COVID-19 circumstances |  | Apr: Postponed due to COVID-19 situation
| 72400 Communic & Audio Visual Equip | 200
| 74500 Miscellaneous Expenses | 200
Activity 2. National and local authorities have capacities to integrate and implement gender-responsive DRR measures
| 71300 Local Consultants | 35,511.11
Technical Advisor on Civil Protection and Disaster Risk Management | bar: Apr to Jul
Recovery Advisor | bar: Mar to Nov
Gender and Human Rights Expert | bar: Mar to Jul; Sep to Nov
| Finance Expert, to support the development of a forecast based financing element for the Ivano-Frankivsk and Chernivtsi regions' early warning system |  | Jul: Portfolio level engagement, at no cost to the project
| 74200 Printing, Design, Translations | 1000
Translation of DRR/CCA integration thematic materials and project written products | bar: Feb to Oct
Video and audio production for project events involving DRR practitioners | bar: Jan to Feb; Apr
| 72100 Contractual Services-Companies | 46000
Development of a prototype model providing early warning signals for disasters in the Ivano-Frankivsk and Chernivtsi regions by CO SDTA | bar: Apr to Jun
Software development and infrastructure setup services for an early warning system integrating a forecast based financing element in the Ivano-Frankivsk and Chernivtsi regions | bar: Sep to Nov
Holding an inaugural donor forum on DRR under UNDP aegis (conference services, incl. speaking fees if applicable) | bar: Oct
Activity 3. Target communities, including the most vulnerable, have necessary capacity, knowledge tools and financing mechanisms to build resilience, and to prevent and better recover from natural disasters based on the principle of leaving no one behind
| 72100 Contractual Services-Companies | 44,021.24
Digitalization of regional early warning system in Chernivtsi Oblast; the Siret valley and upper Prut portions to improve the capacities of local communities
Development of technical specifications for communication equipment - digital communication sets for SESU local monitors and responders for emergency communications with the communities | bar: May to Jun
Procurement and handover of equipment to SESU Chernivtsi | bar: Aug to Nov
| 74200 Printing, Design, Translations | 2000
Production of a publication 'Connecting the Dots in Ukraine: Disaster Risk, Climate Change, and Civil Protection' dedicated to the International Day of DRR on the 13th of October | bar: Sep to Oct
| 74500 Miscellaneous Expenses | 200
Project Management
| 71400 Contractual services – Individ | 17783
Project Manager
| Total project implementation costs | 165,223.38
| GMS, 8% | 13,217.87
| Grand Total | 178,441.25 | Feb: Balance as of 25-Jun-21:; Apr: 107.424
| AWARD ID | ←Engagement Facility!
1. LPAC
2. Prodoc original and amendments
3. No Cost Extensions where applicable
4. Quarterly progress reports (FY21)
5. Annual progress report FY21
6. Signed CDR FY21
7. Project Board minutes FY21
8. Signed AWP FY17 and FY21
9. Evaluation reports completed mid term / final
10. Procurement plans FY21
11. Asset listing / verification completed FY21
12. Risk / issue logs if held external to Atlas
13. M&E framework
14. Monitoring visits - completed by Country Office
15. Monitoring visits - completed at project level
16. Copy of implementing partner - capacity or micro assessment
Note on B21: Swapping of funds from the 72100 Contractual Services line would be needed. A budget revision to be held as the exact amounts are precised.
Note on B29: Swapping funds to the 71300 Local Consultants line would be needed, leaving eventually ca. 25 K under this line. A budget revision to be held once the exact amounts are precised.