## Sheet1
ANNUAL WORK PLAN | [16 empty] | GEN INDICATORS
Strengthening Disaster Risk Reduction and Recovery in Ukraine
Project ID: 00129527
Year: 2021
EXPECTED OUTPUTS | PLANNED ACTIVITIES
Baseline associated indicators and annual targets | Activity results and associated actions | PLAN | Jan | Feb | March | April | May | June | July | August | September | October | November | December | RESULT | DIFFERENCE | Men | Women | Survey Results | Blog | Report
OUTPUT 1: Target communities, including the most vulnerable, have improved capacity, knowledge tools and financing mechanisms to build resilience, and to prevent and better recover from natural disasters based on the principle of leaving no one behind. | Activity 1: National government has improved policy frameworks and plans for Disaster Risk Management, coherent with Climate Change Adaptation policies that respond to the needs of women and men from diverse groups, especially the most vulnerable.
| 71300 Local Consultants | 15,707.90 | [12 empty] | 0 | 15707.9
Recovery Advisor | bar: March to June
Policy & Legal Expert | bar: March to June
| 72100 Contractual Services-Companies | 1600 | [12 empty] | 0 | 1600
Public hearings in disaster-affected regions | bar: March to May
| 71600 Travel | 1000 | [12 empty] | 0 | 1000
Local level needs assessment in disaster-affected regions | bar: March to May
| 72400 Communic & Audio Visual Equip | 200
| 74500 Miscellaneous Expenses | 200 | [12 empty] | 0 | 200
Activity 2. National and local authorities have capacities to integrate and implement gender-responsive DRR measures
| 71300 Local Consultants | 35,511.11 | [12 empty] | 0 | 35511.11
Technical Advisor on Civil Protection and Disaster Risk Management | bar: March to June
Gender and Human Rights Expert | bar: March to June
Finance Expert | bar: May to June
| 74200 Printing, Design, Translations | 1000 | [12 empty] | 0 | 1000
Printing training materials and manual on risk assessment | bar: April to June
| 72100 Contractual Services-Companies | 46000 | [12 empty] | 0 | 46000
Development and implementation of IT solution for flooding risk assessment and emergency preparedness in three target regions | bar: March to June
Activity 3. Target communities, including the most vulnerable, have necessary capacity, knowledge tools and financing mechanisms to build resilience, and to prevent and better recover from natural disasters based on the principle of leaving no one behind
| 72100 Contractual Services-Companies | 44,021.24 | [12 empty] | 0 | 44021.24
Development and implementation of early warning system for a pilot target community | bar: March to June
| 74200 Printing, Design, Translations | 2000 | [12 empty] | 0 | 2000
Production of training materials and guildeines on DRR financing and data collaborations | bar: May to June
| 74500 Miscellaneous Expenses | 200 | [12 empty] | 0 | 200
Project Management
| 71400 Contractual services – Individ | 17,783.13 | [12 empty] | 0 | 17783.13 | bar: Jan to June
Project Manager
| Total implementation | 165,223.38 | [13 empty] | #REF!
| GMS | 13,217.87
| Grand total | 178,441.25