MONITORING VISIT REPORT

PROJECT ID AND TITLE: “Strengthening national capacities to address emerging challenges in response to the three diseases (AIDS, TB, Malaria)” 00084647

PROJECT DURATION: 2012-2014

DATE OF THE VISIT: 2-6 August 2014

PARTICIPANTS:

National Monitoring and Evaluation Group under MEC visiting Ferghana region comprised of:

Liya Perepada, UNDP

Batir Kurbanov, Republican AIDS Center

Dilnoza Avazova, MEC Secretariat

UNAIDS colleagues (Lev Zohrabyan, Charos Maksudova)

UNICEF colleagues (Komiljon Karimov)

REGION/CITIES VISITED: Ferghana;

ORGANIZATIONS VISITED/ ACTIVITIES CONDUCTED:

- Day 1: AIDS Center met: follow up on quality data collection pilot

- Day 2: following organizations met:

- Oblast Healthcare department

- AIDS Center, Friendly Cabinet, Center for HIV positive children and parents (established by UNICEF)

- TB Dispensary

- Ferghana Khokimiat

- Two trust points

- Day 3. Joint Round table with participation of government and non government organizations to review progress reached and challenges faced in the region in the fight with HIV, TB and Malaria

| COMPONENT OF THE MONITORING | FINDINGS & RECOMMENDATIONS |
| --- | --- |
| - Background | Population is around 3,388,234 with about 48% men and 52% women. Intensive indicator – prevalence or incidence?? (per 100 thousand population)= 9.7 Total people living with HIV – 2042 with 52% being men and 48% women 987 people are on ARV treatment As per official data 90 children were newly infected with HIV in 2013 Prevalence rates by SS study: IDU 8.5%, SW 1.7%, migrants 0.5% TB falls from 1559 in 2010 to 716 cases in 2014 (55% among men and 45% among women). Among those 6.4% TB are detected in migrants. From 366 amnestied people 23 were detected to be with TB making about 6%. |
| - Outstanding issues / challenges faced by the sub-project: - Programmatic - Procurement - Finance - M&E (reports) - Administrative - Overall management | - Authorities claim that newly identified children are those infected back in 2006 -7 when incidents of intrahospital infection revealed in Namangan and other areas of Ferghana valley leading to massive infection among newborn children. - Syndrome treatment that is currently being implemented at Friendly cabinet (located in AIDS Center) requires further study in approach overall by medical experts in light of dangers and risks to public health (as came out during discussions). - Psychologists. Despite the new staffing position created by the Government at each AIDS Center, apparently there are no qualified psychologists in the region since the position is not filled to date. Representative of people living with HIV thinks that they require psychologists who would be specializing in HIV area and proposed the issue to be advocated with the Ministry of Higher Education to revise the approach and educate more expensively psychologists on the issue of HIV/AIDS. |
| - Synergies with other projects/programmes - Other projects in the area of HIV in a particular region | More interaction and communication with NGOs is recommended. |
| - Capacity Development issues and needs | Cooperation and work on HIV/TB co-infection needs to be strengthened in the region by two services in charge. Building capacities (increasing knowledge) of law enforcement authorities in the regions could potentially positively influence prevention activities in the region. Stock: AIDS Center reports having at the moment the buffer stock of ARVs for the next 6 months which is being updated with the most recent delivery. The region is fully equipped with the single used medical disposables. Trust points: Two trust points visited: one based in living four floor building and second based in rayon policlinic. Clearly it was observed that the one placed in the living area is much more efficient and has a lot of clients which the group had a chance to talk to. According to the Assistant of the TP the number of women (IDUs) started rising for the past 6 months. While the second one seemed to be not functioning well having about 7 clients visiting per day as per the registry, however when the group was there at 12 o’clock right after visiting the first trust point, there were no clients at all visiting the TP. Visited TPs did not have express tests that could enhance prevention and diagnostic services. |
| - Recommendations/ suggestions raised by organizations and beneficiaries. | A person living with HIV expressed the need to pay attention and do more about stigma and discrimination. Khokimiat could consider creating additional employment opportunities for people living with HIV. Cooperation among organizations (NGO and government organizations) needs to be further strengthened. Especially from the Khokimiat side. Lack of opportunities for NGOs to implement projects: lack of announced grants/ donors. Makhalla Foundation has been missed from discussions during the monitoring visit. |
| NEXT STEPS / FOLLOW-UP ACTIONS | Report to be consolidated by the Chairperson of the National Monitoring Group and shared among members. Further annual consolidated report will be shared with the MEC at the MEC meeting for further decisions and actions. |

- Prepared by Liya Perepada