## Multi-year AWP-2015-2019
Adaptation to Climate Change in the Coastal Zone in Vanuatu (V-CAP) VANUATU Multi-Year Annual Work Plan 2015-2019
Country |  |  | Vanuatu
Programme |  |  | Adaptation to Climate Change in the Coastal Zone in Vanuatu
Award ID |  |  | 00082472
Project Id |  |  | 00091375
UNDAF Program Country Output |  |  | Outcome Area 1: Integrated Community Approaches to Climate Change Adaptation
Priority Area |  |  | UNDAF Outcome(s): Outcome 1.1: Improved resilience of Pacific Island Countries and Territories (PICTs), with particular focus on communities, through integrated implementation of sustainable environmental management, climate change adaptation/mitigation, and disaster risk management. UNDP Environment and Sustainable Development Primary Corporate Outcome: Growth is inclusive and sustainable, incorporating productive capacities that create employment and livelihoods for the poor and excluded (Strategic Plan 2014-2017, Outcome 1) UNDP Secondary Corporate Outcome: Countries are able to reduce the likelihood of conflict and lower the risk of natural disasters, including from climate change (Strategic Plan 2014-2017, Outcome 5) Expected Country Program Outcomes: • Sub-Regional Program Outcome 4 (UNDAF Outcome 1.1): Improved resilience of PICTs, with particular focus on communities, through integrated implementation of sustainable environment management, climate change adaptation/mitigation and disaster risk management • Sub-Regional Program Outcome 2 (UNDAF Outcome 5.1): Regional, national, local and traditional governance systems are strengthened, respecting and upholding human rights, especially women’s rights in line with international standards.
Outcome/Output |  |  | Planned Activities | Timeframe
|  |  |  | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | Budget Description and Amount 2015 | Budget Description and Amount 2016 | Budget Description and Amount 2017 | Amount 2018 | Amount 2019
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Outcome 1.1: CC adaptation plans, including risk management, preparedness and response plans, formulated in the context of ICM and in relation to site-specific vulnerabilities, subsequently adopted and mainstreamed in planning processes | [23 empty] | 1770510 | 1603360 | 1153540 | 956680 | 515910
Output | Target Indicators | a | Establishment of field capability – co-located with Area Council Offices in the six-targeted provinces including “climate-proofed” field office facilities, transport and communication including a full-time Field Officer in each site to support Area Secretaries; | [20 empty] | 71200 International Consultants 319,300 71300 Local Consultants 369,250 71600 Travel 81,900 72100 Contractual Services - Companies 650,440 72200 Equipment & Furniture 53,940 72800 Information Technology Equipment 4,686 72500 Supplies 9,486 73400 Rental & Maint of Equip 72,760 74200 Audiovisual & Printing 13,700 72100 Contractual Services -Companies 130,800 74500 Miscellaneous - 75700 Training, Workshop & Conference 64,248 | 71200 International Consultants 255,300 71300 Local Consultants 368,750 71600 Travel 72,450 72100 Contractual Services - Companies 602,440 72200 Equipment & Furniture 53,940 72800 Information Technology Equipment 4,686 72500 Supplies 9,486 73400 Rental & Maint of Equip 19,560 74200 Audiovisual & Printing 22,700 72100 Contractual Services -Companies 130,800 74500 Miscellaneous - 75700 Training, Workshop & Conference 63,248 | 71200 International Consultants 54,500 71300 Local Consultants 302,000 71600 Travel 62,550 72100 Contractual Services - Companies 400,960 72200 Equipment & Furniture 53,940 72800 Information Technology Equipment 4,686 72500 Supplies 9,486 73400 Rental & Maint of Equip 20,760 74200 Audiovisual & Printing 41,610 72100 Contractual Services -Companies 130,800 74500 Miscellaneous - 75700 Training, Workshop & Conference 72,248 | 71200 International Consultants 25,500 71300 Local Consultants 189,000 71600 Travel 41,550 72100 Contractual Services - Companies 385,960 72200 Equipment & Furniture 53,940 72800 Information Technology Equipment 4,686 72500 Supplies 9,486 73400 Rental & Maint of Equip 18,600 74200 Audiovisual & Printing 24,910 72100 Contractual Services -Companies 130,800 74500 Miscellaneous 9,000 75700 Training, Workshop & Conference 63,248 | 71200 International Consultants 14,000 71300 Local Consultants 101,400 71600 Travel 43,650 72100 Contractual Services - Companies 71,000 72200 Equipment & Furniture 53,940 72800 Information Technology Equipment 4,686 72500 Supplies 9,486 73400 Rental & Maint of Equip 19,800 74200 Audiovisual & Printing 7,700 72100 Contractual Services -Companies 130,800 74500 Miscellaneous 6,000 75700 Training, Workshop & Conference 53,448 | bar: 2015 Q1 to 2015 Q3
1.1.1 Integrated CC-Adaptation Plans mainstreamed in the coastal zone | ·• Development of Community CC-Development Adaption Strategies (CCCADS) at the village level using common indicators across all project sites • Community Disaster Committees established and operational with specific plans developed in targeted communities and at Area Council level | bar: 2015 Q1 to 2015 Q3
|  | b | Undertake pilot in CC vulnerability assessment and climate change adaptation planning processes in selected communities and replication of these models to other sites to ensure government officials, traditional leaders, community members are able to fully engage in the process at each site; | bar: 2015 Q4 to 2016 Q1
|  | c | Completion of comprehensive vulnerability assessments for each targeted community identifying key risk, vulnerabilities and proposed actions to build resilience to climate change forward; | bar: 2016 Q1 to 2016 Q3
|  | d | Development of Coastal Climate Change Adaptation Development Strategies (CCCAD Strategies) in each community in each of the target sites and at the Area Council– all six provinces linking to specific plans for DRR, and under 1.2.1 and 1.2.2 incorporating upland management (including water resource management, forestry and agriculture), and coastal and marine management; | bar: 2016 Q1 to 2016 Q3
|  | e | Implementation of the mainstreamed CCCAD Strategies at community and Area Council levels supported by appropriate funding, monitoring and evaluation and compilation of lesson learnt | bar: 2016 Q4 to 2019 Q2
Outcome 1.2: Improved climate resilience of coastal areas through integrated approaches
Output | Target Indicators | a | Build upon initial PPG assessments to develop detailed marine ecosystem health baselines, with quantitate and qualitative data on fisheries including coral and mangrove health at all six target sites and identify key issues in management of these sites. (note baseline will be re-surveyed in final year | bar: 2015 Q3 to 2016 Q1
1.2.1 Threatened coastal ecosystems and resources such as mangroves, coral reefs, and fisheries rehabilitated to support livelihoods and food production and increase climate resilience | 1.2.1 : Length of coastline placed under improved integrated coastal management to improve ecosystem-based adaptation | bar: 2015 Q3 to 2016 Q1
|  | b | Develop Community Integrated Coastal Zone Management Plans (CICZM Plans) through a participatory approach integrating fisheries, traditional management regimes at the village/ community and areas council levels identifying time-bound actions for long-term management to include tabu and Community Conservation Areas. | bar: 2015 Q4 to 2016 Q3
|  | c | Implementation of the CICZM Plans including deployment of FADs, monitoring on a regular basis, COT monitoring surveys and removal, management of fishing activities and other associated measures. | bar: 2016 Q2 to 2018 Q4
|  | d | Support the site-based network of marine managed areas throughout Vanuatu which include V-CAP sites and existing CCAs to facilitate learning between resource monitors, communities and government. Training for men, women and youth will be delivered through this network. | bar: 2016 Q2 to 2019 Q2
|  | e | Monitoring and evaluation of the implementation of these plans will be completed annually by Field Officer from V-CAP sites and submitted annually to the Coordinator for this Component and the Project Implementation Unit. | bar: 2015 Q4; 2016 Q4; 2017 Q4; 2018 Q4; 2019 Q4
1.2.2 Coastal areas stabilized through re-vegetation and other ‘soft’ approaches to complement ‘hard’ measures | 1.2.2 Enhanced resilience of terrestrial coastal areas to minimize erosion, provide clean water resources to both communities and ecosystems enhancing the livelihoods of coastal communities
|  | a | Develop baselines of issues and threats of terrestrial upland and coastal ecosystems with a particular focus on impacts of climate change on agriculture, water supply, forestry and protected area management and related resources at all six V-CAP sites; | bar: 2015 Q3 to 2016 Q1
|  | b | Develop Integrated Upland Management and Climate Change Adaptation Plan (UMCCAP) through a participatory approach integrating forestry, agriculture, and water resource and traditional management regimes at the village, community and areas council level identifying time-bound actions for long-term management to include tabu and Community Conservation Areas. | bar: 2015 Q4 to 2016 Q3
|  | c | Implementation of the Upland Management and Climate Change Adaptation Plan (UMCCAP) including nurseries, agricultural training and extension, provision of climate-resilient crops, soft measures, etc, though development of time bound annual work plans ; | bar: 2016 Q3 to 2019 Q2
|  | d | As part of the implementation of Upland Management and Climate Change Adaptation Plan (UMCCAP) develop specific cooperative programs with forestry, agriculture and water resources agencies to deliver an agreed series of comprehensive work plans with time bound outputs to be delivered in conjunction with Field Officers, Area Council and appropriate provincial officials and extension staff from key national agencies; | bar: 2017 Q1 to 2019 Q2
|  | e | Monitoring, evaluation and work planning will be based on the UMCCAP prepared in Year one, and annual participatory reviews will identify progress and lessons learnt to be incorporated into the workplan of the following year. | bar: 2015 Q4; 2016 Q4; 2017 Q4; 2018 Q4; 2019 Q4
1.2.3 Improved resilience through climate proofing of selected public conveyance infrastructure in the coastal zone in at least 6 priority vulnerable coastal communities | • 1.2.3 Number of public conveyances climate proofed to provide long-term use by vulnerable coastal communities
|  | a | Undertake further in-depth community mapping, in particular transport routes and use of secondary conveyances, to access markets and health and education facilities particularly in Pentecost, Ambae, Santo and Epi project sites. | bar: 2015 Q1 to 2016 Q2
|  | b | Develop an integrated and detailed workplan for the implementation of the works, including detailed costing of the various designs and the identifications of suitable methods of delivery of the proposed works | bar: 2015 Q4 to 2017 Q4
|  | c | Develop and finalise an agreements between PWD, communities, provincial governments and V-CAP on implementation arrangements with a particular focus on responsibilities for long-term maintenance, management and repairs of roads, bridges and public walkways and associated infrastructures. | bar: 2016 Q1 to 2017 Q4
|  | d | Develop and implement an overall monitoring and evaluation plans for the roll out of works in each of the site, incorporating training and capacity building activities for local communities and provincial authorities. | bar: 2016 Q1 to 2017 Q4
|  | e | Training of students from the RTC in Ambae and communities from V-CAP sites in construction and maintenance of primary and secondary conveyance networks to provide long-term management and opportunities for scaling up approaches. | bar: 2016 Q1 to 2017 Q4
Outcome 2: Information and early warning systems on coastal hazards | [23 empty] | 734100 | 106500 | 94500 | 64900 | -
Outcome 2.1: Reduced exposure to flood-related risks and hazards in the target coastal communities. | [23 empty] | 71200 International Consultants 19,000 71300 National Consultants 24,000 71600 Travel 4,200 72200 Equipment & Furniture 673,400 72800 Information Technology Equipment 1,000 72500 Supplies 1,000 73400 Rental & Maint of Equip 1,500 75700 Training, Workshop & Conference 10,000 | 71200 International Consultants 64,000 71300 National Consultants 24,000 71600 Travel 9,000 72200 Equipment & Furniture 1,000 72800 Information Technology Equipment 1,000 72500 Supplies 1,000 73400 Rental & Maint of Equip 1,500 75700 Training, Workshop & Conference 5,000 | 71200 International Consultants 57,000 71300 National Consultants 24,000 71600 Travel 9,000 72200 Equipment & Furniture 1,000 72800 Information Technology Equipment 1,000 72500 Supplies 1,000 73400 Rental & Maint of Equip 1,500 75700 Training, Workshop & Conference - | 71200 International Consultants 7,000 71300 National Consultants 12,000 71600 Travel 2,400 72200 Equipment & Furniture 1,000 72800 Information Technology Equipment - 72500 Supplies 1,000 73400 Rental & Maint of Equip 1,500 75700 Training, Workshop & Conference 40,000
Output | Target Indicator | a | Procurement and installation of five (5) Automatic Weather Stations composed of wind, temperature, rainfall, barometer, cloud coverage and others for Weather Forecast Observations Sites of Whitegrass, Lamap, Sola, Analguahat and Saratamata | bar: 2015 Q1 to 2016 Q4
2.1.1 Automated system for real time monitoring of climate-related hazards such as coastal flooding, storm surges, sea-level rise designed, installed and maintained | • Better quality accuracy and timeliness in weather forecasting, particularly for extreme events such as extreme rainfall events, storm surges, tropical depressions and cyclones informing EWS • Strengthened capacity within VMGD to deliver timely climate related information to all communities in Vanuatu | bar: 2015 Q1 to 2016 Q4
|  | b | Procurement and installation of two (2) Automatic Ceilometer Stations for cloud coverage in Bauerfield and Pekoa Airports | bar: 2015 Q1 to 2016 Q4
|  | c | Procurement, upgrade and installation of real-time transmission system based on the extension of the current Vanuatu Government Broadband Network from each station to the Port-Vila main office | bar: 2016 Q1 to 2017 Q2
|  | d | Procurement and installation of Automatic Weather Forecast Software Data Analysis / Weather Data Display and Server equipment for data storage and data handling | bar: 2015 Q3 to 2017 Q2
|  | e | Procurement and installation of Climate Data Analysis equipment for the VMGD Climate Division | bar: 2016 Q1 to 2017 Q3
|  | f | Maintenance mission for the next five years (and the entire economic life of the Stations) to all the outer islands Automatic Weather Stations. This will be carried out by engineers/technicians from Vanuatu Meteorological and Geohazards Department VMGD | bar: 2015 Q4; 2016 Q4; 2017 Q4; 2018 Q4; 2019 Q4
|  | g | Incorporation of operations and maintenance costs of the information and early warning systems into VMGD budget starting in year 4. | bar: 2018 Q3; 2019 Q3
2.1.2 Timely releases of early warnings against coastal flooding and storm surges through various public media |  | a | Procurement and Installation of Warning Dissemination System in the premises of the five (5) Weather Observation Stations of Whitegrass, Lamap, Sola, Analguahat and Saratamata. This will include solar powered system units; robust computer system; radio HF system upgrades; and construction/upgrade of an equipment shelter | bar: 2015 Q2 to 2016 Q4
|  | b | Procurement and Installation of Warning Dissemination System in the premises of each six (6) Vanuatu Provinces consisting on solar powered units, TV screens and ICT equipment (Robust field computer and VOIP phone) | bar: 2016 Q1 to 2017 Q4
|  | c | Procurement and Installation of Warning Dissemination System in the premises of each two (2) Major Vanuatu Airport (Bauerfield and Pekoa) consisting on solar powered units, TV screens and ICT equipment (Robust field computer and VOIP phone) | bar: 2016 Q1 to 2017 Q2
|  | d | Development of an Automatic Messaging Broadcast System to disseminate automatically information/advisory/warning to each remote warning dissemination system (as defined above in 2.1.2.1, 2.1.2.2 and 2.1.2.3). A medium-term international consultant will be hired for this purpose. | bar: 2017 Q1 to 2018 Q2
|  | e | Procurement and Installation of HF Alert System for seven (7) communities (project targeted communities) connected to existing HF Radio Station. | bar: 2016 Q1 to 2017 Q4
|  | f | Organize at least two mock drill exercises in the year 3 of the project. Those events will be coordinated by the VMGD and involve NDMO, appropriate NGOs and other relevant stakeholders, and at the outer island level, coordination will be supported by local VMGD staffs and provincial officers from respective islands. | bar: 2017 Q3; 2018 Q4
|  | g | Develop Public Private Partnerships with (Digicell and TVL) for the dissemination of early warnings to its subscribers | bar: 2016 Q3 to 2019 Q3
2.1.3 Capacity of 18 VMGD staffs in the operation and maintenance of AWS and in the analysis of data strengthened |  | a | Organize technical training sessions for VMGD Observation Division Staff for installation, use and maintenance of the Automatic Weather System equipment. A short-term international consultant will be hired for this purpose. | bar: 2016 Q1 to 2017 Q4
|  | b | Organize technical training sessions for VMGD Weather Forecast Division Staff for the use of Meteorological Display software. A short-term international consultant will be hired for this purpose. | bar: 2016 Q3 to 2018 Q2
|  | c | Organize a refresher training session for VMGD Observation Division Staff for use and maintenance of the communication equipment. A short-term international consultant will be hired for this purpose. | bar: 2018 Q1 to 2018 Q4
|  | d | Organize technical training sessions for VMGD Weather Forecast Division and Observation Division Staff for the use and maintenance of Warning Dissemination System Framework. A short-term international consultant will be hired for this purpose | bar: 2018 Q1 to 2018 Q4
Outcome 3.1 Climate change adaptation enabling policies and supportive institutions in place | [23 empty] | 116025 | 98675 | 49925 | 18700 | 16675
Output | Target Indicator | [22 empty] | 71200 International Consultants 56,800 71300 Local Consultants 32,500 71600 Travel 8,300 72800 Information Technology Equipment 340 72500 Supplies 710 74200 Audiovisual & Printing 6,975 74500 Miscellaneous 400 75700 Training, Workshop & Conference 10,000 | 71200 International Consultants 12,000 71300 Local Consultants 51,250 71600 Travel 10,500 72800 Information Technology Equipment 340 72500 Supplies 710 74200 Audiovisual & Printing 6,975 74500 Miscellaneous 400 75700 Training, Workshop & Conference 16,500 | 71200 International Consultants - 71300 Local Consultants 20,000 71600 Travel 6,500 72800 Information Technology Equipment 340 72500 Supplies 710 74200 Audiovisual & Printing 5,975 74500 Miscellaneous 400 75700 Training, Workshop & Conference 16,000 | 71200 International Consultants - 71300 Local Consultants 3,750 71600 Travel 4,000 72800 Information Technology Equipment 340 72500 Supplies 710 74200 Audiovisual & Printing - 74500 Miscellaneous 400 75700 Training, Workshop & Conference 9,500 | 71200 International Consultants - 71300 Local Consultants 1,250 71600 Travel 3,000 72800 Information Technology Equipment 340 72500 Supplies 710 74200 Audiovisual & Printing 4,975 74500 Miscellaneous 400 75700 Training, Workshop & Conference 6,000
3.1.1 Legislation and national/sector policies with impacts on climate change adaptation reviewed and a policy reform agenda developed and implemented (e.g., finalization of draft National CC Policy; incorporation of CC into the EIA Policy, and sector policies in forestry, coastal fisheries, agriculture, water and sanitation; localization of existing policies). | • Number of sectoral policies, plans and strategies explicitly recognising approaches to climate change adaption and a reform agenda adopted | a | Support the NAB through the PMU to develop a stocktake of the current sectoral policies and plans in place at the national, provincial and local levels currently incorporating climate change and those in need of review to ensure community-approaches to climate change are incorporated and support the production of policy reform agenda | bar: 2015 Q1 to 2016 Q2
|  | b | Support the finalization of the Draft National Integrated Coastal Management Framework in conjunction with the Fisheries and Environment Departments and related agencies and departments, to ensure the NICMF is developed to support appropriate local delivery. | bar: 2015 Q2 to 2016 Q2
|  | c | Support the integration of climate change adaptation into relevant sector policies and plans, including but not limited to: | bar: 2015 Q3 to 2018 Q2
|  | d | Maintain on-going dialogue with the NAB and related members to ensure V-CAP sites are able to serve as case-studies and field testing sites for the delivery and implementation of new and modified policies and plans. | bar: 2016 Q1 to 2019 Q3
Outcome 3.2 Human resources in place at the national, provincial and community levels
3.2.1 Capacity building of key national and provincial government agencies (DEPC, PWD, Department of Internal Affairs, Departments of Fisheries, Forestry, Water) in areas of compliance and enforcement, monitoring and evaluation and mainstreaming of climate-related policies and regulations. | • Number of trained staff with sufficient resources to implement CC resilience and adaptation at the national, provincial and community levels | a | Based on a Training Needs Assessment (TNA) develop an innovative and comprehensive 5-year Capacity Building Program for key national, provincial and local officials in community involvement in the delivery of climate change adaptation solutions to be delivered through V-CAP | bar: 2015 Q1 to 2015 Q4
|  | b | Based on the TNA deliver the 5- year capacity building program for key national, provincial and local government officials and key field staff working with local communities.
|  | c | Ensure consistency in the delivery of the of the training through the appointment Communication and Training Coordinator to ensure integration of the training and ensuring training is meeting the needs of project related activities, particularly at the field sites.
|  | d | Regular monitoring and evaluation of the training and adjustment of the training plans through the annual work planning process.
3.2.2 Communities empowered to deal with climate change impacts in the coastal zone through participatory approaches in vulnerability assessments, planning and community-based adaptation measures and capacity building | Number of trained staff with sufficient resources to implement CC resilience and adaptation at the national, provincial and community levels | a | Assist DLA in identifying and drafting initial guidance on the “best practice” governance at the community and village level to support community climate change adaptation through CCCA Planning processes and ensure integration of those plans under the various other levels of community planning, e.g. water, coastal management, agriculture, fisheries and upland management | bar: 2015 Q2 to 2016 Q4
|  | b | Develop community level model demonstrations of integrated governance approaches to support community adaption to climate change in each of the V-CAP field sites. | bar: 2015 Q2 to 2017 Q4
|  | c | Based on the above in year 3, provide technical support to DLA and partner agencies, through the NAB, to deliver guidance in the form of policy, on integration of climate change adaption to existing and developing community structures to enhance resilience to climate change. | bar: 2017 Q2 to 2019 Q1
Outcome 4.1 Increased awareness and ownership of climate risk reduction processes at the national and local levels. | [23 empty] | 93740 | 61140 | 74540 | 60040 | 60540
Output | Target Indicator | a | Baseline survey on community awareness of climate change, past successful communication programs and reviews of existing materials to contribute to an education and awareness programs. | [20 empty] | 71200 International Consultants 26,800 71300 Local Consultants 18,000 71600 Travel 6,000 72400 Communication and Audio visual equipments 2,400 72200 Equipment & Furniture 1,840 72800 Information Technology Equipment 700 72500 Supplies 400 73400 Rental & Maint of Equip 2,400 72200 Equipment & Furniture 3,300 74200 Audiovisual & Printing 8,000 74500 Miscellaneous 15,000 75700 Training, Workshop & Conference 8,900 | 71200 International Consultants - 71300 Local Consultants 18,000 71600 Travel 5,300 72400 Communication and Audio visual equipments 2,400 72200 Equipment & Furniture 1,840 72800 Information Technology Equipment 700 72500 Supplies 400 73400 Rental & Maint of Equip 2,400 72200 Equipment & Furniture 3,300 74200 Audiovisual & Printing 12,000 74500 Miscellaneous 5,000 75700 Training, Workshop & Conference 9,800 | 71200 International Consultants 13,400 71300 Local Consultants 18,000 71600 Travel 4,200 72400 Communication and Audio visual equipments 2,400 72200 Equipment & Furniture 1,840 72800 Information Technology Equipment 700 72500 Supplies 400 73400 Rental & Maint of Equip 2,400 72200 Equipment & Furniture 3,300 74200 Audiovisual & Printing 14,000 74500 Miscellaneous 5,000 75700 Training, Workshop & Conference 8,900 | 71200 International Consultants - 71300 Local Consultants 18,000 71600 Travel 3,500 72400 Communication and Audio visual equipments 2,400 72200 Equipment & Furniture 1,840 72800 Information Technology Equipment 700 72500 Supplies - 73400 Rental & Maint of Equip 2,400 72200 Equipment & Furniture 3,300 74200 Audiovisual & Printing 14,000 74500 Miscellaneous 5,000 75700 Training, Workshop & Conference 8,900 | 71200 International Consultants - 71300 Local Consultants 18,000 71600 Travel 2,900 72400 Communication and Audio visual equipments 2,400 72200 Equipment & Furniture 1,840 72800 Information Technology Equipment 700 72500 Supplies - 73400 Rental & Maint of Equip 2,400 72200 Equipment & Furniture 3,300 74200 Audiovisual & Printing 16,000 74500 Miscellaneous 5,000 75700 Training, Workshop & Conference 8,000 | bar: 2015 Q1 to 2015 Q4
4.1.1 Best practices are captured, documented, and distributed to all local and national stakeholders and shared globally in appropriate mechanisms (development, populating and maintenance of national website for CC) through the NAB (National Advisory Board) | • Practices demonstrated and shared by the project adopted by other parties (replication) and adopted by local communities • Development of 10 sets of training and awareness materials | bar: 2015 Q1 to 2015 Q4
|  | b | Development of a time bound and costed comprehensive communication strategy for V-CAP incorporating capturing, documenting and distributing of lessons learnt with a focus on full involvement of local communities in the process. | bar: 2015 Q3 to 2016 Q1
|  | c | Implementation of the communication strategy by the Communication and Training Coordinator with full engagement of local communities through training, equipment; and | bar: 2016 Q1 to 2019 Q4
|  | d | Monitor implementation of the communication strategy on an annual basis and at the end of year two undertake a comprehensive review and evaluation to ensure long-term effective delivery with full community consultation | bar: 2016 Q4; 2017 Q4; 2018 Q4; 2019 Q4
4.1.2 Awareness, training and education programs developed and implemented for e.g. schools, households and the private sector; translated into Bislama and French as applicable and working with ongoing initiative. |  | a | Develop an annual “Private Sector and climate change dialogue’ to identify opportunities for collaboration between the private sector and communities in climate change adaptation based on a framework developed in yea 1 of the project. | bar: 2015 Q4; 2016 Q4; 2017 Q4; 2018 Q4; 2019 Q4
|  | b | Based on the communication strategy developed in activity 4.1.1.2 implement a school education program supported by appropriate materials and equipment including 3D monitoring. | bar: 2016 Q1 to 2018 Q2
|  | c | Document and share lessons learnt and best practices through the communication strategy developed in activity 4.1.1.2 | bar: 2017 Q1 to 2019 Q2
|  | d | Maintain a project website, linked to the main climate change PMU operated portal for Vanuatu, with up-to-date information on the progress of implementation of V-CAP with all appropriate communication materials available to the wider community.
Outcome 5: Programme Execution | [23 empty] | 87829 | 87829 | 71500 | 68671 | 64171
PIU established and operational |  | a | Project Staff recruited | [20 empty] | 71200 International Consultants 18,000 71300 Local Consultants 25,200 71600 Travel 4,600 74100 Professional Services 15,000 72400 Communication and Audio visual equipments 4,800 72500 Supplies 1,200 72800 Information Technology Equipment 1,740 72200 Equipment & Furniture 2,280 74500 UNDP DPC 8,487 75700 Training, Workshop and Conference 6,522 | 71200 International Consultants 18,000 71300 Local Consultants 25,200 71600 Travel 4,600 74100 Professional Services 15,000 72400 Communication and Audio visual equipments 4,800 72500 Supplies 1,200 72800 Information Technology Equipment 1,740 72200 Equipment & Furniture 2,280 74500 UNDP DPC 8,487 75700 Training, Workshop and Conference 6,522 | 71200 International Consultants 4,500 71300 Local Consultants 25,200 71600 Travel 4,600 74100 Professional Services 15,000 72400 Communication and Audio visual equipments 4,800 72500 Supplies 1,200 72800 Information Technology Equipment 1,740 72200 Equipment & Furniture 2,280 74500 UNDP DPC 5,658 75700 Training, Workshop and Conference 6,522 | 71200 International Consultants 4,500 71300 Local Consultants 25,200 71600 Travel 4,600 74100 Professional Services 15,000 72400 Communication and Audio visual equipments 4,800 72500 Supplies 1,200 72800 Information Technology Equipment 1,740 72200 Equipment & Furniture 2,280 74500 UNDP DPC 2,829 75700 Training, Workshop and Conference 6,522 | 71200 International Consultants - 71300 Local Consultants 25,200 71600 Travel 4,600 74100 Professional Services 15,000 72400 Communication and Audio visual equipments 4,800 72500 Supplies 1,200 72800 Information Technology Equipment 1,740 72200 Equipment & Furniture 2,280 74500 UNDP DPC 2,829 75700 Training, Workshop and Conference 6,522 | bar: 2015 Q1
|  | b | Inception Workshop | bar: 2015 Q1
|  | c | Equipment procured office established
|  | d | PMU operational and managing programme implementation
Project Monitoring and Evaluation |  | a | Inception report | bar: 2015 Q2
|  | b | Quartely reports
|  | c | Annual technical monitoring report | bar: 2015 Q3; 2016 Q3; 2017 Q3; 2018 Q3; 2019 Q3
|  | d | Meetings of Project Steering Committee | bar: 2015 Q2; 2015 Q4; 2016 Q2; 2016 Q4; 2017 Q2; 2017 Q4; 2018 Q2; 2018 Q4; 2019 Q2; 2019 Q4
|  | e | Meetings of Thematic Working Groups | bar: 2015 Q2 to 2015 Q3; 2016 Q1; 2016 Q3; 2017 Q1; 2017 Q3; 2018 Q1; 2018 Q3; 2019 Q1; 2019 Q3
|  | f | Mid-term Evaluation | bar: 2017 Q2 to 2017 Q3
|  | g | Final Project Evaluation | bar: 2019 Q3 to 2019 Q4
|  | h | Project Terminal Report | bar: 2019 Q3 to 2019 Q4
|  | i | Audits | bar: 2017 Q3; 2019 Q4