## Classic guidelines
Project General Information | [7 empty] | Implementation plan | [7 empty] | GRANT DISBURSEMENT DATA
Country | Grant Agreement Number | UNDP ID | Implementation Start Date | Date of First Disbursement Received from the GCF | Tranche number of the committed funding during the reporting period | Reporting Period | Anticipated duration per approved proposal | Baseline summary per the GCF Guidebook | Variance from Baseline Summary (i.e. change from original proposal) | Milestones and deliverables achieved | Current estimated Implementation End Date | Reason for Delay | Steps that will be taken to address performance in the next six months | Narrative on progress made in the past six months, challenges, lessons learned and outline measures (both long term and short tem) to address the challenges | Key activities to be undertaken with corresponding milestones/deliverables in the next six months against which progress will be reported in the next report. | [7 empty] | h =(c+d)/b
[16 empty] | a | b | c | d | e | f = (c+d+e) | g= (b-f)
[16 empty] | Total Approved Grant Amount (USD) | Cumulative Funds received as of as of the end of the reporting period | Prior reporting periods cumulative expenditure | Current reporting period Expenditure | Commitments/ Obligations | Total | Fund Balance | Utilization %
Azerbaijan | AZE-RS-001 | 6151 | 2018-02-27 | 2018-02-06 | First | 1 January to 30 June 2018 | 18 months | [8 empty] | 300000 | 150000 | 0 | 15146 | 43702 | 58848 | 91152 | 10.1%
Outcome 1: Strengthening of NDA | [15 empty] | 92936 | 46468 | 0 | 11847 | 17999 | 29846 | 16622 | 25.49%
Output 1.1 NDA/focal point lead effective coordination mechanism | [7 empty] | 1= NDA is in the process of establishing a coordination mechanism, meetings are conducted, but not regularly. | No deviation from original proposal | The Inception Workshop was conducted on June 5th with the participation of all key stakeholders, including private sector and civil society. The First Steering Commitee Meeting took place on 6 June to make recommendations to the Project Team on implementation of the project's work plan. The questionnaire to conduct a survey for the MENR as the NDA for the GCF has been prepared. • The TORs for the following key positions were prepared, and hired: - Lead International Technical advisor (LITA) - Local capacity building support and logistic consultant - Institutional and Legal Expert - Senior Local Consultant on designing and managing capacity building programs for NDA and other national stakeholders | Q2 2019 | No delays from original plan. | Activities are on track; procurement is in progress and project team will continue with implementation as planned. | The actual project implementation started in late February and within less than two months, the Project Coordinator was hired. Currently, 4 experts (Please see K7) were contracted by the Project and started performing their assignments . On June 5th 2018, the Inception Workshop has been organized with participation of more than 30 stakeholders from public and private institutions. The participants demonstrated a high level of interest in the Readiness project. In addition, during the first Steering Committee meeting, the project team had the opportunity to start a dialogue with the newly appointed NFP for the UNFCCC, with UNDP and NDA officials. Both the Inception Workshop and the SC Meeting were used to brainstorm on project activities, address pending issues and questions. Recent changes in political appointments may impact the pace of the activities of the project, overall. A new Minister was appointed to the Ministry of Ecology and Natural Resources (NDA) in April 2018. In addition, the National Focal Point for the UNFCCC has also been replaced. Also, currently, the Ministry is undergoing the process of Structural Optimization. All of these may impact the speed of project implementation. | 1.1.1. In close consultation with the Ministry of Ecology and Natural Resources acting as the NDA for Azerbaijan, carry out needs assessment of MENR to identify its main needs in regards to institutional and individual capacity building. Deliverable: Needs Assessment Report including roles and responsibilities of NDA 1.1.2. Develop Terms of Reference (TOR) forNDA coordination based on multi-stakeholder partnerships including with women groups, and State Committee on Family, Women, and Children’s issues Deliverable: Terms of Reference (ToRs) for key positions, both local and international consultants, including on work with women groups and the SCFWCI - ToRs 1.1.3. Based on the assessment done under 1.1.1, design and execute capacity building workshops/trainings Deliverable: at least one training conducted based on the needs assessment, including on GCF policies and procedures – Training materials, reports, participation lists, and documented feedback/evaluation by the participants
Output 1.2 No objection procedure established and implemented | [7 empty] | 0 = No objection procedure is not established. | No deviation from original proposal | TOR for Institutional And Legal Expert has been developed, the consultant hired. | Q2 2019 | No delays from original plan | Activities are on track; procurement is in progress and project team will continue with implementation as planned. | Legislative and institutional research is underway to analyze national legislation, institutional and technical capacities within the country in relation to the work with the GCF, which are parts of the Needs Assessment process of NDA and will be the basis for future coordination of "no- objection" process. Issues raised and questions posed during the Inception workshop will guide the Project Team in designing the entire process of developing guidelines for "no-objection" procedure and for the respective trainings and awareness-raising sessions. | 1.2.1. In close consultation with the NDA, develop, validate, and disseminate guidelines for effective no-objection process Deliverable 1: Guidelines on No Objection procedure – Document validated by the NDA in Azeri and English languages. At lease one training and/or awareness events organised on No-Objection procedure
Output 1.3 Bilateral agreements between the country and the GCF executed | [7 empty] | 0 = Discussions on the bilateral agreements have not been advanced | No deviation from original proposal | No milestones or deliverables achieved yet. | Q2 2019 | No delays from original plan | Activities are on track; procurement is in progress and project team will continue with implementation as planned. | No specific challenges and lessons learned yet. | No activities and milestones planned for the next six months. Work on this output will start in 2019.
Output 1.4 Monitoring, oversight, and streamlining of climate finance | [7 empty] | 0=Monitoring and oversight of climate finance flows is not established yet | No deviation from original proposal | TORs for the following key positions were prepared, and hired: - Lead International Technical advisor (LITA) - Institutional and Legal Expert -Tor for Climate Finance expert has been developed. | Q3 2019 | No delays from original plan | Activities are on track; procurement is in progress and project team will continue with implementation as planned. | No specific challenges and lessons learned yet. | No activities and milestones planned for the next six months. Work on this output will start in 2019.
Outcome 2: Stakeholders engaged in consultative processes | [15 empty] | 118200 | 59100 | 0 | 188 | 23476 | 23664 | 35436 | 0.3181%
Output 2.1 Stakeholders engaged in consultative processes | [7 empty] | 1 = Some stakeholders are being consulted on an ad-hoc basis, however a formal consultation process is not established | No deviation from original proposal | No milestones or deliverables achieved yet. | Q3 2019 | No delays from original plan | Activities are on track; procurement is in progress and project team will continue with implementation as planned. | Most of the consultations usually take place when specialists meet to discuss implementation of particular programs and projects. Therefore, those meetings have rather sectoral orientation and lack a holystic approach. Currently, there is a lack of comprehensive consultations with the participation of major stakeholders devoted specifically to the national climate change initiatives. Consultations conducted within the country still either do not take place at all, or just started taking into account such issues as the NDCs, NAMAs and NAPs. The Inception workshop presented an opportunity to start addressing these issues. it included multi-stakeholder presentations and how the Readiness project could contribute to them. The project will continue supporting such consultations in order to raise general public awareness of the GCF. | 2.1.1. Mapping of the current practices on stakeholder engagement processes for climate change related policies and strategies with recommendations for improvement endorsed by the NDA; Deliverable: Standard Operating Procedures, SOP document validated by NDA, for stakeholder engagement process focusing on GCF. Gaps in engagement identified and addressed with establishment of SOP. 2.1.3. Develop a communications/advocacy strategy to inform key stakeholders (government and non-government) on progress in the country’s engagement with the GCF. Deliverable: The Engagement Plan with the list of major participants and contact information both at the central and local level, what is and/or could be their role, which resources they may bring in, what type of organization they are, like state agencies, civil society organizations, including women groups; The Plan will include also an established platform for communication, timeline for recurring convening opportunities, and input (government and non-government) on progress in the country’s engagement with the GCF
Output 2.2 Country programmes, including adaptation priorities, developed and continuously updated | [7 empty] | formal consultation process has not been established. |  |  | Q3 2019
Output 2.3 Stakeholder consultations conducted with equal representation of women
Output 2.2 Country programmes, including adaptation priorities, developed and continuously updated | [7 empty] | 0 = No country programme developed | No deviation from original proposal | No milestones or deliverables achieved yet. | Q1 2019 | No delays from original plan | Activities are on track; procurement is in progress and project team will continue with implementation as planned. | No specific challenges and lessons learned yet | Deliverable: Initial draft of Country Programme
Outcome 3: Private sector mobilization | [15 empty] | 33690 | 16845 |  |  | 2227 | 2227 | 14618 | 0%
Private sector engaged in country consultative processes | [7 empty] | 0= No private sector engagement in the country yet | No deviation from original proposal | No milestones or deliverables achieved yet. | Q2 2019 | No delays from original plan | Activities are on track; procurement is in progress and project team will continue with implementation as planned. | No specific challenges and lessons learned yet. | Activity: Conduct an awareness raising session with the private sector representatives with regards to the GCF. Deliverables: One multi-stakeholder private sector meeting report.
Contingency | [15 empty] | 12241 | 6120.5 |  |  |  | 0 | 6120.5 | 0%
Project Management | [15 empty] | 15660 | 7830 |  | 2779 |  | 2779 | 5051 | 35.49%
DP Fee | [15 empty] | 27273 | 13636.5 |  | 331 |  | 331 | 13305.5 | 2.427%

## COUNTRY 1
COUNTRY

## COUNTRY 3
COUNTRY 3