## AccLab Working Plan
Accelerator Lab Work Plan
Action plan for the first 100 days of Accelerator Lab Azerbaijan
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | TEAM MEMBER | PERCENT COMPLETE
DEFINING WORK SCOPE OF ACCELERATOR LAB
| Prepare pitch deck for AccLab | 2019-08-26 | 26 | 2019-09-05 | Team | DONE
| Present AccLab to UNDP team | 2019-08-26 | 26 | 2019-09-11 | Team | On-going
| Budget Planning & Strategy | 2019-08-26 | 26 | 2019-09-07 | Team | On-going
| Meeting with operations & procurement | 2019-08-26 | 26 | 2019-09-15 | Team | DONE
SETTING TEAM DYNAMMICS
| Operational Framework | 2019-08-19 | 19 | 2019-08-30 | Team | DONE
| Individual roles, responsibilities matrix | 2019-08-19 | 19 | 2019-08-30 | Team | DONE
| Team capabilities mapping | 2019-08-19 | 19 | 2019-08-30 | HSM | DONE
| Team values workshop | 2019-08-26 | 26 | 2019-08-30 | HER | DONE
| Exploring tools and platforms | 2019-08-26 | 26 | 2019-10-01 | Team | On-going
INTRODUCING ACCELERATOR LAB
| Soft launch with key donors | 2019-09-09 | 9 | 2019-09-27 | Team | On-going
| AccLab big launch event | 2019-08-19 | 19 | 2019-10-01 | Team | On-going
| Embed new methodologies with CO portfolio | 2019-10-01 | 1 | 2019-12-30 | Team | On-going | `
| Horizon Scanning | 2019-09-09 | 9 | 2019-12-30 | Team | Planned
| Design communication plan | 2019-08-26 | 26 | 2019-10-01 | HEL | On-going
EXPLORING UNDP FOCUS AREAS
| Portfolio sense-making on focus areas | 2019-08-26 | 26 | 2019-09-30 | Team | On-going
| Project data review | 2019-08-26 | 26 | 2019-09-30 | Team | On-going
| Field visits and issues mapping | 2019-08-27 | 27 | 2019-11-01 | Team | Planned
BUILDING PORTFOLIO OF EXPERIMENTS
| Defining areas of intervention | 2019-09-15 | 15 | 2019-09-30 | Team | On-going
| Solutions mapping (finding local solutions) | 2019-09-15 | 15 | 2019-10-30 | HSM | Planned
| Developing portfolio of experiments | 2019-09-15 | 15 | 2019-11-01 | HER | Planned
| Network learning | 2019-09-15 | 15 | 2019-12-30 | HEL | Planned
| Experimentation (explore, trial-error, validate) | 2019-09-30 | 30 | 2019-11-30 | HER | Planned
| Results assessment | 2019-10-15 | 15 | 2019-12-15 | Team | Planned
COLLABORATING WITH ACCELERATION LABS NETWORK
| Participate in calls | 2019-08-26 | 26 | 2019-12-30 | Team | On-going
| Working out loud (blogging, share & reapply best experiments) | 2019-08-26 | 26 | 2019-12-30 | Team | Planned
HSM - Head of Solutions Mapping
HER - Head of Experimentation
HEL - Head of Exploration
CO - Country Office