## Sheet1
Project General Information | [7 empty] | Implementation plan | [7 empty] | GRANT DISBURSEMENT DATA
Country | Grant Agreement Number | UNDP ID | Implementation Start Date | Date of First Disbursement Received from the GCF | Tranche number of the committed funding during the reporting period | Reporting Period | Anticipated Duration per approved proposal | Baseline summary per the GCF Guidebook | Variance from Baseline Summary (i.e. change from original proposal) | Milestones and deliverables achieved based on those milestones in the approved project proposal. | Current estimated Implementation End Date | Reason for Delay | Steps that will be taken to address performance in the next six months | Narrative on progress made in the past six months, challenges, lessons learned and outline measures (both long term and short tem) to address the challenges | Key activities to be undertaken with corresponding milestones/deliverables in the next six months against which progress will be reported in the next report | [7 empty] | h =(c+d)/b
[16 empty] | a | b | c | d | e | f = (c+d+e) | g= (b-f)
[16 empty] | Total Approved Grant Amount (USD) | Cumulative Funds received as of as of the end of the reporting period | Prior reporting periods cumulative expenditure | Current reporting period Expenditure | Commitments/ Obligations | Total | Fund Balance | Utilization %
Burundi | BDI-RS-001 | 6055 | 2018-03-07 | 2018-02-06 | First | 1 Jul to 31 Dec 2019 | 24 months | [8 empty] | 434545 | 217272.73 | 29330 | 45359 | 44410 | 119099 | 98173.73 | 34.38%
Outcome 1: Country capacity strengthened | [15 empty] | 110620 | 55310.0585 | 29330 | 31609 | 43855 | 104794 | -49483.9415 | 110.2%
Output 1.1 NDA/focal point lead effective coordination mechanism | [7 empty] | 1= NDA is in the process of establishing a coordination mechanism, meetings are conducted, but not regularly. | No variance from original proposal. | Milestones and deliverables achieved: - NDA team capacities have been enhanced on climate project conception, gender meanstreaming (Annex 1: Workshop report on project conception, annex 3: Retreat report on projects formulation) - Information on the GCF guidlines have been disseminated to different stakeholders (Annex 2: Workshop report on dissemination of project criteria) | Q1.2020 | Enhancing NDA's capacities is a progressive mechanisme and it has been achieved at 75 %, In fact, during this reporting period,NDA team has been operational. Four concepts notes have been evaluted,letters of non objection have been issuied, it provided guidance to other stakeholders on GCF process, project submission processes. In the next quarter Q1 2020, the evaluation session for NGO concepts notes will be carried out. | In the next report period, much focus will be made on strengthening capacities of NDA team on continue on organising five days training on climate finance and in carrying out a Climate Public Expenditure and Institutional Review (CPEIR); assessing concepts notes from private sector and civil society. | The strengthening of NDA team capacities has been made through different sessions/workshop and retreat which have been organised. These were related in developing concept notes to be submietted to GCF for funding, gender mainstreaming in climate projects conception, understanding of climate profile of Burundi (7-10/10/2019). The NDA team has been involved in activities planning of second semester 2019 5(annex 4: Planning session with NDA team and other sectoral ministries). Two national Consultants have been recruited and contributed in strengtjening NDA teaam capacities. The International cabinet is being recruited that will help in training on climate finance and carrying out a CPEIR. Lessons learned: To put in place an effective coordination mechanism, It is more important to organise consultation session so as different stakeholders could discuss institutional arrangement to be made. Challenges: As climate change is a cross-cutting theme, it has been observed a lack of coordination between various government departments which leads to duplication of activities. As the NDA team was supposed to include people from different ministries as stated in INDC, but those apointed are from one ministry of environment. The reason behind this, is the DNA had to appoint most of people from his general direction of environment as it might be easier for him to meet them anytime as needed. However, other sectoral ministries will be invited in some working sessions as needed. | In the next reporting period, NDA team will be supported in assessing concepts notes from civil society and private sector organization, five days training on climate finance.
Output 1.2 No objection procedure established and implemented | [7 empty] | 0 = No objection procedure is not established. | No variance from original proposal. | Milestones and deliverables achieved: - No-objection procedures have been developed. - Training to the NDA team on the no-objection procedures has been conducted succesfully. - A workshop was organised to disseminate guides for issuing the no objection letter | Q1.2020 | Activities are on track | In next period, the NDA team will be enhanced in their capacities (learning by doing) to consider the non objection procedures while assessing projects concepts notes from different stakeholders. In addition, these process of no objection procedure will be disseminated to all stakeholders at sub national level and published on website of the ministry in charge of environment. | A workshop (from 27-30.08.2019 in Kayanza province) had been organised in order to disseminate guides for issuing the letter of no objection, evaluation tools for funding criteria and selection of projects (annex 2). This included 30 NGOs and provided stakeholders guidelines in oder to submit projects to the GCF. This workshop has been conducted jointly with the workshop planned on identification of pepiline projects which will be included in Country Document Programme. Lessons learned: It has been realized that NGOs are willing to develop climate projects in differents areas but accredity entities are still few to work with them. Challenges: The New NDA team members need to be trained so as they could assume their responsaility of being on driven seat. | Activities: In the upcoming period, the non objection procedures, evaluation tools and criteria of projects selection will continue to be disseminated to other relevant stekeholders at sub national level.
Output 1.3 Bilateral agreements between the country and the GCF executed | [7 empty] | 0 = Discussions on the bilateral agreements have not been advanced. | No variance from original proposal. | Milestones and deliverables achieved: Guide on structural dialogue for NDA and the interministerial committee with stakeholders in climate sector of Burundi | Q1.2020 | These bilateral agreements were going to be based on the content of Burundi Country Programme, As we could not finalize this document, facilitation face-to-face meetings between Burundi and GCF could not take place | In this next period, bilateral aggreements between country and GCF will be undertaken while finalising the Country programme of Burundi to be engaged with GCF. It will be carried out jointly with establishment of a systematic approach of engagement in a structured dialogue with different partners through workshop consultation. | This activity has been carried out with a national consultant who developed the guide. Lessons learned: Through two documents which are Country Programme of Burundi to be engaged with GCF and Climate Public Expenditure and Institutional Review (CPEIR), bilateral agreemen would be developed Challenges: Regarding climate finance management and oversight, there are challenges in strengthening coordination through inter-sectoral mechanisms. One option could be to move overall coordination functions into a central body with convening/decision-making power vis-à-vis line Ministries. | In the next period, the planned activities will support the engagement of members of the NDA and inter-ministerial working group with the GCF by facilitating face-to-face meetings to advance in bilteral agreements process.
Output 1.4 Monitoring, oversight, and streamlining of climate finance | [7 empty] | 0= Monitoring and verification of climate finance flows is not established. | No variance from original proposal. | No milestones or deliverables achieved yet. | Q3 2020 | The recruitment of international cabinet for CPEIR has been finalised but due to lack of budget in the second semester of 2019, the contract could not be issued so as activities implementation couldn't start | Recruting an international cabinet which will carry out the public expenditure on climate and institutional review of climate finance is on its final stage . However, unless the extension timeline is accepted, in fact, the process of CPEIR could take up six months. The current estimated implementation end date goes beyond the planned end date of the project. | In this reporting period, the recruitment of needed expertise is in progress. It is expected to engange an international cabinet which will align one international consultant and two national consultants. Lessons learned: Through a planning session, it has been noticed that there is no much local expertise to carry out such mission. So participants suggested that one unternational consultant and two national consultant could be recruited by the project so as they can conduct this mission. Moreover, these shall work closely with NDA team so as these can be enhanced in their capacities in climate finance. Challenges: Regarding the planned end date of the project, there is no enough time to implement all required activities. | Key activities that will be undertaken are: - Five days training (with giving certificates) to relavant staff from UNDP and sectoral ministries and NDA team on climate finance with focus on analyse of institutional arrangements for integrating climate change policy priorities into budgeting and expenditure management processes; an analysis of public expenditure and its relevance to climate change. - The CPEIR methodology mentioned in cell N10 will include three main elements: (i) an assessment of current policy priorities and strategies as these relate to climate change; (ii) a review of institutional arrangements for integrating climate change policy priorities into budgeting and expenditure management processes; and (iii) an analysis of public expenditure and its relevance to climate change. This will serve as basis of advocating on creation of budget line for climate change in NDC sectors.
Outcome 2: Stakeholders engaged in consultative process | [15 empty] | 114000 | 57000.0603 | 0 | 2269 | 0 | 2269 | 54731.0603 | 3.981%
Output 2.1 Stakeholders engaged in consultative processes | [7 empty] | 1 = Some stakeholders are being consulted on an ad-hoc basis, however a formal consultation process has not been established yet | No variance from original proposal. | In this reporting period: No milestones or deliverables achieved yet. | Q1 2020 | The consultation workshops were planned but due to lack of funding (second disbursement) of the project, activities have been suspended up to now. | In the upcoming periods, activities which are going to be carried out are the following products: (i) Needed additional support funds, (ii) Key UNDP-supported analysis, (iii) UNDP-supported stakeholder consultations, (iv) CO final review and validation of NDC. The products to be delivered are 1) A report on the implementation status of the 2015-2019 INDC in the relevant sectors, on Financing, Measurement, Notification and Verification, proposing recommendations to be incorporated into the new document for define new mitigation and adaptation objectives as well as measurement and monitoring tools; 2) Elaboration of the National Contribution (NDC) document indicating mitigation objectives, priority adaptation programs for all sectors vulnerable to CC with gender mainstreaming. The sectoral programs should present the medium and long-term objectives, illustrating how different sectors will contribute to the implementation of the NDC at national level (Two versions of the document (French and English version)); 3) An Implementation Plan incorporating a governance, Measurement, Notification and Verification and intersectoral coordination framework. However, the current estimated implementation end date goes beyond the planned end date of the project. | In this reporting period, a national consultant has been recruited so as he could carry out the revision of NDC and its impementation. The consultation workshops were planned but due to lack of funding (second disbursement) of the project, activities have been suspended up to now. However the revision of NDC has now gone beyond activitiy being implemented by one project. At global scale, UNDP is willing to help Burundi (as many other countries) to undertake an inclusive and transparent process to revise and submit enhanced Nationally Determined Contributions (NDCs) by 2020. Building on UNDP’s extensive climate and sustainable development portfolio and partnerships with the UN, NDC Partnership, coalitions, private sector, academia and civil society groups, the initiative will provide technical and financial support across a tailored set of services to address bottlenecks and scale-up key success factors. So far, UNDP CO has finalised a workplan which has been submitted (annex A). The communication strategy has been finalised and is curenntly been implemented by UNDP communication unity. Communication kits are being produced, these are 600 leaflets (folded in three), 7 roll up, 2 banners, 500 note pads with color logo and 500 folders. All these tools convey messages on the evaluation criteria, selection of projects, non-objection procedures, policy and modalities of funding by the GCF, etc. In addition, an IT platform is being created online to make the necessary information available to users. The target audience is technicians from ministries, political decision-makers, civil society, the private sector. Finally, a documentary film is being prepared to show the harmful effects of climate change in Burundi. Challenges: There is a need of timeline extension for project GCF Readiness and Preparatory Support-Burundi. The most important challenges is time of conducting all planned activities. In fact the planned end date of project is by 28 February 2020 while the timeline and key milestones to be delivered goes beyond the end date. Lessons learned: there is need for doing the INDC update. At global scale, UNDP has made a promise of helping 100 countries to enhance their Nationally Determined Contributions by 2020, with demonstrated increase in ambition. It has noticed an international consultant will be recruited to support national team revising NDC. UNDP has suggested a new framework for service offer: (i) build political will and societal ownership at national and sub-national levels (ii) review, align and update existing targets, policies and measures, (iii) incorporate new sectors and/or Greenhouse Gases, (iv) assess costs and investment opportunities and (v) Monitor progress and strengthen TRANSPARENCY. Regarding the Burundi Country Programme, through discussion, It has been noticed that there is need of recruiting another national consultant to finalise the document. He will have to conduct workshops of consultation of stakeholders at national and sub national levels. | Key activities are (i) Multi-stakeholders and multi-sectors consultation and validation workshops for the Country Program, (ii) a updated INDC and its implementation plan, (iii) implement of the communication strategy. Deliverables: Burundi country program document and revised of NDC and its implementation plan
Output 2.2 Country programmes, including adaptation priorities, developed and continuously updated | [7 empty] | 1 = Development of country programme has started. | No variance from original proposal. | One workshop has been held to identify pepiline of project in compliance with national strategies (Annex 2 and Annex 5: List of project ideas from NGO). Deliverable: - Draft of Burundi country program document | Q2 2019 | Activities are on track | In this next period, one national consultant shall be recruited so as he could finalise the Burundi Country programme. However, the current estimated implementation end date goes beyond the planned end date of the project. | This activity was conducted jointly with the workshop with NGO on dissemination of no objection procedures, selection criteria of project to be submitted to GCF. Challenges: Regarding to the remaining time before the planned end date of project,It is still a challenge to capitalise all the available information of projects on climate change since all stakeholders were not consulted. There is a need of more trainings, sensetization workshops towards NGO and private sector abd other accredited entities so as they can involved in GCF process. Lessons learned: It is very important to establish a physical adress of the NDA and capitalise the information by feeding the website so that the stekeholders can be well informations. | Key activities: (i) Recruitment of national consultant to finalise the Burundi Country Programme, (ii) Consolidate indicative pipeline of projects in compliance with national strategies and plans as well as in line with the GCF investment criteria and results areas. (iii) train/endow the NDA team and intersectoral coordination mechanism with tools to help identify suitable instruction for specific projects as well as for appraising project and programme across the country. Deliverables: (i) Revised of NDC and its implementation plan, (ii) Climate Country Programme of Burundi
Output 2.3 Stakeholder consultations conducted with equal representation of women | [7 empty] | 1 = Gender equality measures are considered in parts of stakeholder consultation processes. | No variance from original proposal. | Gender dimension has been taken into account in projects formulation (annex 5: Workshop report on four days training on project formulation) | Q1.2020 | After the consultant was recruited, Terms of reference were made, invitations were in signatory and the activities have been planned but its implementation could not be possible due to lack of budget | In the upcoming period, the gender consultant is going to be involved in consultation workshops while revising NDC and finalise Burundi Country programme. Workshops will be organised jointly. However, the current estimated implementation end date goes beyond the planned end date of the project. | In this reporting period, the recruitment process was finalised. The Consultant worked on proposing a gender mainstreaming approach in project planning; (ii) facilitate advanced training workshops for project proponents on results planning: practical applications, planning, results-based monitoring and evaluation, project cycle and gender mainstreaming. in the development of projects, determine whether the relationship between gender and climate change has been taken into account in the context of the main objectives of the project; ensure that the project meets the practical and strategic needs of men and women related to climate change. | As planned activities were not implemented over last six months, the same activities are planned for upcoming six months. Activities: Start developing sustainable consultation mechanism with all sectors and with all catagories of stakeholders, organize consultations with gender focal in key ministries in order to ensure the mainstreaming of gender in the GCF portofolio. Deliverables: concept of consultation mechanism.
Output 2.4 Annual Participatory review of GCF portfolio in the country organized | [7 empty] | 0 =No process established for periodic participatory review and updating established. | No variance from original proposal. | No milestones or deliverables achieved yet. | Q1.2020 | Delays from updated period. As the Burundi Country programme could not be finalised, It could not be possible to make a meeting on GCF portfolio in the country | Regarding to the remaining time, this activity may not be carried out. | Challenges: Regarding to the remaining time before the planned end date of project, we cannot plan this activity.
Outcome 4: Access to finance | [15 empty] | 87000 | 43500.046 | 0 | 0 | 0 | 0 | 43500.046 | 0%
Output 4.1 Structured dialogue between the NDA/Accredited Entities and the GCF Secretariat organized | [7 empty] | 1 = Separate ad-hoc dialogue existing between NDA/FP and some accredited entities | No variance from original proposal. | (i) Final Document guide on conducting of a structered dialogue with Burundi climate stakeholders (annex 6), NDA and government member have been supported to participate in Conference of Parties (COP25), (ii) Ad hoc dialogue between NDA and accredited entities on GCF initaitives in Burundi (Annex 7). | Q2.2020 | Activities are on track. The dialogue with Accredited entities has been made but with GCF was not yet made. As the Country Programme document was not finalised, the dialogue with GCF has been postponed. | In the upcoming period, depending on time availability, national dialogue on climate change shall be organized jointly with national resitution workshop on COP25 restitution. | (i) Guidance document has been provided to support the NDA and his team to be able to be on driven seat when engaging in structured dialogue, (ii) Discussion meeting between the accredited entities chosen or potentially to be chosen by the country in order to ensure coordination in the development and implementation of the GCF portfolio has been organized (annex 7: Discussion report with accredited entities), (iii) the project has supported the participation of the NDA, members of the interministerial committee or other national institutions involved in climate finance to participate in COP25 involving the dialogues with the GCF secretariat members. Progress was made in the last six months on producing a final guide on conducting a structered dialogue with climate change related entities in Burundi. A meeting with accredited entities has been organized (02/08/2019) (Annex 7). The identified accredited entities in Burundi are World Bank, African Development Bank, GIZ, FAO and IFAD. These Accredited Entities will be involved in project development in order to channel resources. Taking into account previous experiences of participation in conferences of the parties (COP), this time, the Burundian team organized under the support of Readiness project a preparation workshop for COP in Madrid (Annex 14:. Discussions focused on (i) general overview of major decisions on international climate negotiations, (ii) Doha amendment and related decisions, (iii) general overview on international climate negotiations, lessons learned for Burundi and negotiators, (iv) international climate negotiations: Nationally Determined Contribution (CDN). The conclusions of this workshop were among others (i) to prepare on the stakes of negotiation and the position of the strategic groups of negotiation, (ii) to target themes of negotiation to follow compared to the needs for the country and to decide to participate in parallel sessions, (iv) conduct informal contacts on financing mechanisms (GCF, GEF, and FA, etc.) with a view to accessing climate finance which is lacking, (v) ratify the Doha amendment to the Protocol of Kyoto to give a precious boost to the climate ambition by the end of 2020 and to take a position regarding the transition of the achievements of the Kyoto Protocol to the Paris Agreement on certain negotiation issues (Annex 6). The project supported NDA and members from government to participate in COP25. Challenges: There is a need of more time so as all stakeholders can get involved in GCF process in Burundi.The accredited entities have been working with different funds such as GEF, AF. It has been observed that it is very important to initiate an effective coordination mechanism of all initiatives in climate sector at national level to share climate related information. Lessons learned: Regarding to previous experiences of participation in conferences of the parties (COP), country delegation has to prepare itself and go as a team. So it is important to have coordination mechanism in climate sector. | Activities: One national restitution workshop on COP25 recommandations Deliverables: Report of national restitution workshop on COP25
Output 4.2 Country programmes, concept notes, including on adaptation, developed that implement high-impact priorities identified in INDCs and other national strategies or plans | [7 empty] | 1 = Development of country programme has started. | No variance from original proposal. | In this reporting period: - A draft of Burundi country program has been developed -Two (02) programmes and two (02) projects have been developed and submitted to GCF secretariat (Annex 8: Project 1, Annex 9: Project 2, Annex 10: Programme 1, annex 11: Programme 2) | Q1.2020 | Activities are on track | In this next period, one national consultant shall be recruited so as he could consolidate the Burundi Country programme. | As of the expected impacts of the program, there are well-formulated GCF funding proposals. It is in this context that actions have been undertaken to develop projects / programs that respond to the problem of climate change in Burundi. Sectors concerned are the environment, agriculture, energy, public health, infrastructure and disaster risk reduction. Actions carried out are workshops to raise awareness, identify and consolidate project / program ideas. A strategic retreat to accelerate the formulation of project documents, certification training on the process of developing climate projects. Thus, two projects and two programs have been developed and submitted to the GCF secretariat. The titles of the projects / programs are (i) Program to reduce greenhouse gas emissions through large-scale reforestation and development of alternative measures to limit pressure on wood in Burundi; (ii) Climate change adaptation program by mananging floods in the city of Bujumbura; (iii) Project to strengthen the resilience of communities to the effects of climate change for food security in the regions of Bugesera, Bweru, Buyenzi and Imbo in Burundi and (iv) Project to improve the Early Warning System (EWS) hydrometeorological at the service of the resilience of sectors affected by climate change in Burundi). One workshop has been held in Kayanza to identify indicative pipeline projects from NGO. 30 NGO were invited and 5 new projects ideas have been developed. 5 consortia have been developed from the invited NGO so as synergies could be made (Annex 12: Inventory of the indicative pipeline climate change projects from NGO). | Activities: (i) Finalise and publish country program of Burundi, track the implementation of priorities projects and concepts. Deliverables: At least two additional GCF project ideas evaluated by the NDA.
Output 4.3 Project/programme preparation support, including for adaptation, to develop funding proposals provided | [7 empty] | 0 = no project / programme preparation is sought from GCF | No variance from original proposal. | In this reporting period: -Four days of retreat to accelerate projects/programme formulation to be submitted to GCF secretrait (Annex 3: Retreat workshop) - Four days certification training on adaptation and mitigation project formulation with taking into account of gender dimension (Annex 5: Workshop report on four days days training on project formulation) -Primary data collection from local communities, local administration and decentralized services with consideration of the gender dimension (annex 13: Field report on primary data collection). - Two (02) programmes and two (02) projects have been developed and submitted to GCF secretariat (Annexes 8-11). | Q1.2020 | Activities are on track | In this upcoming period, the steps to be undertaken are related to follow up the concepts notes submitted and NGO concepts notes | In this reporting period, actions carried out are a strategic retreat to accelerate the formulation of project documents Annex 9: Report of the retreat), certification training on the process of developing climate projects (Annex 10: report of the training workshop), primary data collection (Annex 11: report of fiels activities on primary data collection) whose aim is to take into account the considerations of local communities, to inquire about the situation on the ground experienced by the population on a daily basis, the impacts of climate change and the measures put into practice by the communities, the local administration and decentralized services with consideration of the gender dimension. Thus, two projects and two programs have been developed and submitted to the GCF secretariat. The titles of the projects / programs are (i) Program to reduce greenhouse gas emissions through large-scale reforestation and development of alternative measures to limit pressure on wood in Burundi; (ii) Climate change adaptation program by mananging floods in the city of Bujumbura; (iii) Project to strengthen the resilience of communities to the effects of climate change for food security in the regions of Bugesera, Bweru, Buyenzi and Imbo in Burundi and (iv) Project to improve the Early Warning System (EWS) hydrometeorological at the service of the resilience of sectors affected by climate change in Burundi (Annex 7: Projects/programme documents). Challenges: There is still need of studies which require more funding. These studies are related feasibility study, vulnerabilities assessment, environmental and social impact assessment. There is a need of more working session with NGO and private sector so as they can as well produce bancable projects. Lessons learned: It has been observed that people in charge of formulation of climate projects need significant support in terms of capacity building on co-funding aspects of their projects. | Activities: (i) Follow up submitted concepts notes. Deliverable: -
Outcome 5: Private sector mobilization | [15 empty] | 76000 | 38000.0402 | 0 | 0 | 0 | 0 | 38000.0402 | 0%
Output 5.1 Private sector engaged in country consultative processes | [7 empty] | 0= No private sector engagement in the country. | No variance from original proposal. | In this reporting period: - Draft of framework for private sector engagement in climate finance decision making to include periodic consultations between business service organisations and the NDA and other national stakeholders. | Q1.2020 | Activities are on track | In the upcoming period, depending on timeline extension, consultation processes could be carried out jointly with consultative process regarding to NDC and Country Programme. This will include commercial banks and informative meetings on GCF modalities, requirements and process of accreditation . | This activity has been conducted jointly with activity 4.1 &nd 2.1. A meeting has been organized jointly with the Accredited entities including banking institutions so as they can get involved in GCF initiatives in Burundi (02/08/2019). Moreover a framework for private sector engagement in climate finance decision making to include periodic consultations between business service organisations and the NDA and other national stakeholders has been improved by a national consultant. Challenges: As stated in previous report, the same chalenges and lessons learned are still on: Investments in climate change sector are not yet well understood by the private sector, so there is a need for more awareness raising to achieve broad buy-in from the private sector on climate investments. The banking sector is not yet aware of climate-related opportunities and how to access GCF funds, even more given that there is no national accredited entity in Burundi yet. Lessons learned: The private sector is struggling to integrate GCF initiatives at national level in Burundi. How the Concessionary loans, guarantee will be provided, etc. It has been noticed that there is a need of national accredited entity. | Activities: Consultative process through workshops with private sector so as is involved in GCF initiatives in Burundi. Deliverables: Validation of a framework for private sector engagement in climate finance decision making to include periodic consultations between business service organisations and the NDA and other national stakeholders.
Output 5.2. Enabling environment for crowding-in private sector investments at national, regional and international levels exists | [7 empty] | 0=No enabling environment exist for private sector investments. | No variance from original proposal. | In this reporting period: - Four Concept notes have been developed but Three have submitted to GCF inlovling partnership with the private sector. - Workshops previously mentioned in 4.3., and 4.4 to train the private sector. | Q1.2020 | Activities are on track, The fourth could not be submitted because it is related to resilience of agriculture. Discussion are being made so as FAO could be an accredited entity, | In the upcoming period, depending on timeline extension, consultation processes could be carried out jointly with consultative process so as environment for crowding-in private sector investments can be improved. | Due to lack of entry visa in Spain, members of private sector could not be supported to participate in COP25.This activity has been carried out jointly with 4.3., and 4.4 through trainings with private sector. For this output, actions carried out are a strategic retreat to accelerate the formulation of project documents Annex 3: Report of the retreat), certification training on the process of developing climate projects (Annex 1: report of the training workshop), primary data collection (Annex 11: report of fiels activities on primary data collection) whose aim is to take into account the considerations of local communities, to inquire about the situation on the ground experienced by the population on a daily basis, the impacts of climate change and the measures put into practice by the communities, the local administration and decentralized services with consideration of the gender dimension. Challenges: As stated in previous report, the same challenges and lessons learned are still on: Investments in climate change sector are not yet well understood by the private sector, so there is a need for more awareness raising to achieve broad buy-in from the private sector on climate investments. The banking sector is not yet aware of climate-related opportunities and how to access GCF funds, even more given that there is no national accredited entity in Burundi yet. Lessons learned: The private sector is struggling to integrate GCF initiatives at national level in Burundi. How the Concessionary loans, guarantee will be provided, etc. It has been noticed that there is a need of national accredited entity | Activities: Follow up submitted three concepts notes and submit the fourth one Deliverables: Report of consultative process including private sector
Contingency | [15 empty] | 19925 | 9962.5105 | 0 | 0 | 0 | 0 | 9962.5105 | 0%
Project Management | [15 empty] | 27000 | 13500.0143 | 0 | 11481 | 555 | 12036 | 1464.0143 | 85.04%