PROPOSAL SUBMISSION SUMMARY FORM (PSF)

For

BUREAU FOR CRISIS PREVENTION AND RECOVERY (BCPR)

PROJECT APPRAISAL COMMITTEE (BPAC)

(To be completed by submitting Country Office)

Date of Submission:       3 September 2009

Country: Burkina Faso

Project Title: Emergency Response to Unprecedented Flooding in the city of Ouagadougou

Linkage to UNDAF Outcome 6.2 Le dispositif de prévention et de gestion des crises dues aux aléas climatiques et aux catastrophes est renforcé

Focal Point: Mme Mariam Pangah, Directrice Pays Adjointe (P)

Total Project Budget: 4 months, USD 50,000

Amount Funded by Country Office: Non applicable

Amount Requested from BCPR: 4 months: US $ 50,000

Expected Project Duration:  4 months

Executing Agent: UNDP

Implementing Partner(s): Conseil National de Secours d’Urgence et de Réhabilitation (CONASUR)

Proposal Summary:

Background and context On September 1, heavy rainfall triggered flooding in Burkina Faso’s capital Ouagadougou. The country has on average 1,200mm of rainfall annually. Within only hours on 1 September, the city was deluged with 263 mm. Five people were killed and about 150,000 left homeless in five neighborhoods in and around the capital (Bogodogo, Boulmiougou, Baskuy, Nongremassom et Sigh-Noghin). The infrastructure has been severely damaged. Many houses collapsed, bridges and roads have been destroyed. The main hospital in Ouagadougou which is close to a dam was inundated and some patients including about 60 children were evacuated. An electrical plant was also destroyed and power supply problems are expected in the coming days and weeks. Schools and churches at 193 sites across Ouagadougou are sheltering 110,000 flood victims, based on a preliminary government count. Those who have lost homes and possessions urgently need access to shelter, food, water, clothes and medicines. There are fears that the stagnant water will cause outbreaks of cholera and malaria. Given the scope of the disaster and the limited capacity of the national authorities to respond to the identified needs, the Government launched on September 2 an international appeal for disaster relief. Justification. The Government of Burkina Faso, through its National Council for Crisis Emergency and Recovery (Conseil National de Secours d’Urgence et de Réhabilitation, CONASUR) has already provided some assistance (food, clothes, shelter in 30 public sites) and donors have started mobilizing funds to assist the Government in its response. The scope of the assistance needed is way beyond the Government’s current capacity and this is why the Government launched an international appeal for disaster relief. This proposal seeks US$50,000 to allow UNDP to assist the Government of Burkina Faso to respond to the urgent needs of those affected by this natural disaster. With the immediate support from BCPR, the proposed project will strive within the next 4 months to achieve the following : Enhanced capacity for conducting early recovery needs assessment and coordinated early recovery activities; Formulate a continued early recovery/recovery programme beyond the initial 4-month period.

Deliverables/Activities that will funded from BCPR Resources:

USD 50,000 will applied to support the following : Early Recovery Needs Assessment. Early Recovery coordination and technical assistance. Proposal Development for further response.

RESULTS AND RESOURCE FRAMEWORK, September 2009 – December 2009

Project Title:   Emergency Response to Unprecedented Flooding in the city of Ouagadougou

| Expected Output | Key Activities | Timeframe | Responsible Party |
| --- | --- | --- | --- |
|  |  | Q3 | Q4 |  | Budget Description | Amount |
| 1. Enhanced capacity for coordinated Early Recovery Response | 1.1 Assessment | x |  | UNDP in support of CONASUR | National consultant. Professional services including the cost for meetings, communication and local travel costs | 15,000 |
|  | 1.2 Coordination | x | x | UNDP in support of CONASUR | National consultant. Professional services including cost for meetings, communication and local travel. | 20,000 |
|  | 1.3 Proposal development for further response. |  | x | UNDP in support of CONASUR | Cost for stakeholder consultation and communication. | 15,000 |
| Total |  |  |  |  |  | USD$50,000 |