Quarterly Progress Report

January – March 2022

Title of Project: Social Protection Policy Support (SPPS) Programme Atlas Project ID: 00090394

List of Acronyms

| CMC | Central Management Committee |
| --- | --- |
| DFAT | Department of Foreign Affairs and Trade |
| GoB | Government of Bangladesh |
| NSSS | National Social Security Strategy |
| SSPS | Social Security Policy Support |
| OAA | Old Age Allowance |
| OPD | Organisation of Person with Disabilities |
| PWD | Person with Disabilities |
| NSSS | National Social Security Strategy |
| UNDP | United Nations Development Programme |
| OAA | Old Age Allowance |

Project Information

| Funded by: | DFAT |
| --- | --- |
| National Counterparts: | Cabinet Division and General Economics Division ,Planning Commission. |
| Partnerships: | Sightsavers -Disability Alliance on SDGs Bangladesh, and the Centre for Disability in Development (CDD) |
| Project Locations: | Cabinet Division, Dhaka; General Economics Division, Planning Commission, Dhaka |
| CPD Output: | 1.3 Policy and regulatory frameworks enabling greater access to and utilization of inclusive, gender-responsive and resilient basic social and protection services are strengthened |
| SP Output: | 1.2 Social Protection Services and system strengthened across sectors with increased investment. |
| SDG Target: | 1.3: Implement nationally appropriate social protection systems and measures for all, including floors, and by 2030 achieve substantial coverage of the poor and the vulnerable. 5.4: Recognize and value unpaid care and domestic work through the provision of public services, infrastructure and social protection policies and the promotion of shared responsibility within the household and the family as nationally appropriate. 10.4: Adopt policies, especially fiscal, wage and social protection policies, and progressively achieve greater equality. |
| Project Starting Date (DD/MM/YYYY): | 01/01/2014 |
| Original Completion Date as per approved ProDoc (DD/MM/YYYY): | 30/06/2020 | Expected Completion Date as per revised ProDoc, if any (DD/MM/YYYY): | 31/12/2025 |
| Project Total Budget (USD): | $12,448,649 | Fund Received (USD) till to date: | $9,852,356 |

Narratives

| Key Results achieved |
| --- |
| List the top 3-5 key results that the project has achieved during Q1 (January-March) of 2022. A Project Implementation Committee (PIC) was held ,jointly chaired by the Secretary, Coordination and Reforms, Cabinet Division and Member, General Economics Division (GED) of Planning Commission. Discussion centered around the project implementation progress, formulation of the NSSS Action Plan Phase 2 and SPPS detailed Annual Work Plan (2021-2023). Annual reflection Meeting held with DFAT on the progress of NSSS Action Plan 2 Reforms and updated on future programmes. ToR developed and study commissioned to an individual firm on NSSS- M&E and MIS assessment, identification of indicators, and outline of M&E dashboard. Field visit to Gopalganj on Single Registry MIS initiated by DC using National Household Database and Geographical code by BBS. Visit to Asharayan Project to see the multidimensional Poverty. Nonstate Actor Platform initiated with OPDS sharing mapping on social protection. |
| Gender Leaving No One Behind (if any) |
| Gender Briefly narrate Project’s contribution to achieving gender equality (only report on the progress made between January and March 2022) Revised NSSS Action Plan 2021-25 incorporates set of gender focused indicators addressing practical and strategic needs of women for social security. Leave No One Behind (LNOB)/Persons with Disabilities (PWD) Mapping of Social Protection Programmes held on 21st March 2022 with disability inclusive presentation shared by 12 Organizations of Person with Disabilities(OPDs) and session on stories of Lives of PWDS across lifecycle attended by Principal Coordinator (SDG ) Affairs PMO office. |
| COVID-19 Responses (if any) |
| If the project had activities relating to COVID-19 during the reporting period, please share here briefly. A Brief Analysis of Social Protection Program Response to Covid-19 Pandemic in Bangladesh (Draft) prepared by consultant. |
| Innovation (if any) |
| N/A |
| Monitoring |
| Impact monitoring is being conducted through regular minute minutes after all consultation meetings and workshops and shared with the concerned ministries with proper and regular feedback on the discussions. |
| Project Risks & Mitigation Measures |
| Sr | Project Risk | Risk Category and Sub-category | Likelihood (High/Substantial Moderate/Low) | Mitigation Measure |
| 1 | Social and Environmental Risk : Covid Pandemic affected policy development and continued implementation of NSSS action plans on social protection. | Low | Low | Activities moved to hybrid model where necessary . |
| 2 | Organizational: Frequent transfer of government officials | Moderate | Moderate | Orientation to the concerned officials |
| 3 | Operational: Coordination and Communication problem among ministries | Moderate | Moderate | Regular weekly meetings. |
| Project Issues & Remedial Actions |
| Sr | Project Issue | Remedial Action |
| 1 | COVID-19 Pandemic: The ability to meet with individuals for both policy discussions and internal administrative issues has slowed down work. | Regarding the policy outputs, the project shifted discussions to Zoom, which has worked well. Regarding the PIC, annual reflection meeting to Donor , many discussions have happened by Zoom and phone call, with limited physical contact at the Government offices. |
| Lessons Learned |
| Zoom is not always feasible for working on extremely technical pieces due to less face-to-face contact and unclear communication and individuals are required to collaborate in personas a result the project has used a designated working space, social distanced and with necessary precautions and cleaning tools, limited to two individuals per technical area for better feedback. |

Indicator Progress

| Output 1 | By 2025, Government has significantly increased social security coverage of old age persons and Person with disabilities by adopting a universal approach (sex and age disaggregated data) |
| --- | --- |
| Indicator | Baseline | End of Project Target | Annual Target (2022) | Progress (Q1-2022) |
| 1.1. Four policy proposals (OAA, Persons with Disabilities, NSIS) submitted for Govt. approval | 2020 |  | Concept notes OAA, DA developed (January 2022) | Developed |
| Output 2 | Research and pilot generated evidence available to and utilized by policymakers and other stakeholders |
| M&E Dashboard research study initiated | 2020 |  | Initiated(February 2022) | Initiated . First Draft to be submitted in May 2022 |
| Output 3 | Gender-responsive policy advice and accountability tools are made available to the line ministries to demonstrate their accountability for social protection reforms |
| 3.1. Single registry MIS field visit completed | 2020 |  | March 2022 | Completed |
| Output 4 | Broadened knowledge base and influence of NGOs working for marginalized and excluded groups, including persons with disabilities in social protection decision-making |
| Disability social protection programming workshop from supply and demand perspective completed | 2020 |  | March 2022 | Completed |

Activity Progress

| Output wise Progress against Activities |
| --- |
| Output 1 |
| Planned Activities of Q1, 2022 | Progress Achieved | Challenges and Measures |
| 1.1. Four concept notes developed | Approved by Cabinet | Challenges: Frequent changes in line ministry officials e.g GED,Cabinet Division often limits institutional capacity building and hampers relationships to be built for quicker progress of the project Measures: Frequent Meetings with ministries for better understanding. |
| Output 2 |
| M&E Study Dashboard ToR developed and awarded to private firm for commissioning. | To be submitted in May 2022 | Challenges: Only One firm has bid out for the study . Measures: Thorough background check done of the firm before awarding. |
| Output 3 |  |  |
| Workshop held with 12 OPDS who shared their presentation on social Protecting Mapping on disabilities | A platform has been initiated with OPDS ,two workshops completed, and report is being drafted. | Challenges: Braille PowerPoint , written materials and resources suggested by OPDs Measures : Braille and visually friendly resources to be taken into consideration. |

Financial Progress

Currency: USD

| Output | Total Annual Budget (2022) | Budget for Q1 (2022) | Expenditure in Q1 (2022) | Balance | Delivery Rate |
| --- | --- | --- | --- | --- | --- |
| Output1,2,3 & 4 | 1,360,815 | 340204 | 322,000 | 18,204 | 24% |
| Grand Total | 1360815 |  |  |  |  |

(As of 31 March 2022)

Annex

Please insert picture, case story or any other relevant information and illustration.

Workshop On Mapping of  Social Protection Programs and Listening to the Lives of Person with Disabilities Across Lifecycle held on 21st March 2022

# Footnotes

Please make sure to include Social and Environmental risks

Use the ‘ERM Risk Categories Sub-categories and Risk Matrix’ as a reference