United Nations Development Programme

The Bahamas

January to December 2009

| Project Title: | Enabling Activities for the Preparation of The Bahamas’ Second National Communication to the UNFCCC |
| --- | --- |
| Project Number: | PIMS 3212 CC EA SNC Bahamas |
| Project Budget: | USD 405,000 |
| Award No./Date of PO/ etc.: | [Award no. in ATLAS, or date of PO]. |
| Partnership Strategy: | BEST Commission, National Climate Change Committee |
| Duration: | 36 months (October 2006 – October 2009) |
| Reporting Period: | 01 January 2009 – 31 December 2009 |
| Contact: | Nicole Brown, Project Manager/Programme Specialist/Officer UNDP Jamaica T: F: E: nicole.brown@undp.org |
| Related Documents: | First National Communication on Climate Change |
| Record Ref.: |  |

EXECUTIVE SUMMARY:

| Award Total: | USD 405,000 |
| --- | --- |
| Expenditure to Date: | USD 179,071.73 |
| Delivery: | 44.22% |
| Partnership Strategy: | Achievements – Project initiation workshop, project inception report, impact assessment framework workshop, GHG inventory, National circumstances completed, V&A initiated, Mitigation initiated Problems – Timely disbursement of funds by Implementing Agency, communication (UNDP) |
| Update on Outcome: | Outcomes related to implementation arrangements, project inception, and GHG Inventory have been completed. Outcomes related to national circumstances and V&A assessment have been initiated. |
| Update on Outputs: | 1. National circumstances – NTC established to gather data, chapter completed, Impact Assessment Framework (IAF) workshop completed 2. V&A – positions advertised locally and internationally, candidates interviewed, V&A Team Leader selected, equipment purchased to conduct climate modeling needed as a part of the assessment, two workshops held (training and methodologies), V&A sectoral analysis begun. 3. National GHG inventory – review of first inventory begun, training session completed on developing GHG inventory, review of methodologies completed, inventory circulated for peer review and data validated, GHG inventory completed and approved 4. Mitigation – Expert engaged to complete this work. Initial stakeholder meeting held 5. Other relevant information – no activities to date 6. Constraints and gaps – no activities to date 7. Technical assistance – some guidance has been provided by NCSP on developing IAF and finding a V&A expert; assistance in finding V&A expert also provided by UNDP. 8. SNC compilation – no activities to date 9. Project management – Project Steering Committee established, project coordinator contracted, GHG Team leader selected, V&A Team Leader selected, Mitigation expert selected, National Technical Team established for national circumstances |
| Activities: | See listing above and section 4 below. |
| Lessons Learned: | Positive: Progress is being made, reporting is more regular, structure of the project has improved to provide more guidance to those involved. Communication has improved with Implementing Agency. Disbursement received after long delay. Negative: In the first 6 months of 2009, project affected by inefficiencies in administrative procedures at Implementing Agency mainly related to disbursement of funds. Disbursement was received in July 2009 and good progress has been made since then. |
| Risk Assessment: | As with many Small Island Developing States, The Bahamas has issues related to capacity and resources, both of which are limited and have many priorities competing for their attention and commitment. Climate change will have to compete as well. SIDS are faced with the reality that they can do their best to adapt, but climate change as a threat cannot be addressed without commitment of countries with high GHG emissions. |
| Recommendations: | Communication between UNDP and BEST has improved with an effort to hold conference calls on a quarterly basis to discuss any issues and try to come up with solutions to them. Disbursements of funds by UNDP were delayed in the first half of 2009 (similar problem was faced in 2007 and 2009) and this negatively impacted project implementation with months going by and activities not happening due to lack of funding. A disbursement was received in July 2009 which enabled good progress to be made on project activities. It is hoped that such long delays in disbursements are a thing of the past so the project can be completed in 2010 calendar year. Disbursements need to be in a timely manner and responsive to cash advance requests as indicated in financial reports; reasons should be given for delays or any reduction in disbursement from what has been requested so project team can plan accordingly and make adjustments where necessary. Higher profile needs to be given to climate change with decision makers through media and regular communication with them so they are aware of project activities throughout project implementation and this is not left until SNC is completed. |

1.	INTRODUCTION

  - Background

Funding for The Bahamas project was awarded in October 2006. The project will enable The Bahamas to prepare its Second National Communication (SNC) for presentation to the Conference of the Parties of the United Nation Framework Convention on Climate Change (UNFCCC). The Second National Communication project activities will build on and continue the work done under the First National Communication (FNC).

The main components of the SNC project are: (a) assessment of potential impacts of climate change on the most vulnerable sectors, (b) preparation of an inventory of GHG in accordance with the UNFCCC, (c) identification of mitigation measures being undertaken, (d) identification of other information relevant to implementation of the UNFCCC, and preparation of a National Strategy and Action Plan to address climate change and its adverse impacts.

Under the Bahamas Environment, Science and Technology (BEST) Commission that serves as the national climate change office, the Project will strengthen the national capacities for addressing climate change and for fulfilling commitments and obligations to the UNFCCC. It is anticipated that the project will increase the public’s knowledge and awareness of climate change. The development of a national policy will also contribute to putting climate change issues into the national planning and development mechanisms.

The Bahamas is highly vulnerable to the potential impacts of climate change even though its contribution to greenhouse gas (GHG) emissions is low by global standards. Nevertheless, recognizing the importance of climate change as an environmental issue and of the need to integrate climate change issues into its environmental and economic development objectives, The Bahamas ratified the United Nations Framework Convention on Climate Change (UNFCCC) on 9 April, 1999. Having ratified the UNFCCC, The Bahamas is obliged to submit periodic national communications. To facilitate this, there is a pressing need for assistance in developing and sustaining a process by which The Bahamas can complete a greenhouse gas inventory, assess its vulnerability to climate change, and develop adaptation and mitigation strategies.

  - Current Situation

Project activities began in earnest in July 2007 with the Project Initiation Workshop. Since awarding of project funding, activities have included:

- Drafting of National Circumstances component of SNC

- Engagement of Project Coordinator

- Engagement of GHG Team Leader

- Establishment of Project Steering Committee

- Establishment of National Technical Team

- Completion of Impact Assessment Framework workshop

- Completion of GHG Inventory

- Engagement of V&A Team Leader

- Participation in regional V&A training activities

- Completion of National Circumstances chapter

- Initiation of V&A sectoral analysis

- Completion of V&A training and methodologies workshops

  - Update on expenditure and delivery (refer to financial report and progress reports for 2009)

Expenditures to date are outlined in the quarterly financial reports for 2009. Deliverables in 2009 include:

- Completed national circumstances component of SNC

- Contract for V&A Team Leader

- V&A training and methodologies workshops

- Stakeholder meeting on mitigation

Details on these can be found annexed to the quarterly 2009 progress reports.

  - Update on partnership strategy

The coordination strategy amongst Executing Agency, Project Steering Committee, Project Coordinator, National Technical Team and GHG Team Leader has greatly improved with more regular meetings and communication.

Project stakeholders committed at the end of 2007 to take steps to address problems and ensure the project receives the priority it needs through:

- Dedicated financial officer for Executing Agency to expedite disbursements

- Adherence to reporting deadlines through regular reminders and support to stakeholders as is necessary

- Commitment to attend meetings regularly so that project stays on track

Stakeholders have fulfilled these commitments and problems cited in 2007 no longer exist though there are still time delays whenever a response is needed from the Ministry of the Environment.

Good progress is being made by the V&A Team Leader through working in partnership with persons in relevant sectors including energy, agriculture, tourism, housing and population settlement, water resources and forestry.

- OUTCOMES:

Outcomes completed in 2009:

- 1. National Circumstances

Outcomes initiated in 2009:

- 2. Vulnerability and adaptation assessment – engaged V&A Team Leader, held V&A training and methodologies workshops, initiated V&A sectoral analysis, began collecting data for climate modeling.

- OUTPUTS:

Outputs initiated or continued in 2009:

- Output 1: National circumstances (completed)

- Output 2.1A: Procedures for assessing vulnerability

- Output 2.1B: Procedures for identifying and evaluating adaptation options

- Output 4: Mitigation

- ACTIVITIES:

Activities initiated or completed in 2009:

1.1.3 Collect data and information from different sources in the course of project implementation.

1.1.4 Fill the gaps, update and add the new information in accordance to the TORs for National Circumstances section of The Bahamas’ SNC.

1.1.5 Draft national circumstances sections that would be relevant to each thematic area.

1.1.7 Circulate the National Circumstances section for comments and receive comments to incorporate them into the report.

Output 2.1A:

2.1.1 Develop indicators

2.1.2 Assess vulnerability for sectors

2.1.3. Develop climate baseline

2.1.5 Assess any previous adaptation experience

Output 2.1B:

2.1.1 Review policy process and development context

2.1.2 Collect data and information

2.1.3 Adapt training materials

3.2.8 Finalize the inventory to be submitted as a part of the SNC of The Bahamas.

4.1.1 Define range of options

4.1.3 Analyse GHG inventory

9 Project management

Completed numerous reports for The Bahamas SNC project inclusive of partial ASL, annual work plan, procurement plan and annual operational plan (AOP).

- LESSONS LEARNED:

a. Positive

- Improved communication with implementing agency through quarterly conference calls.

b. Negative

- The project can be negatively impacted if disbursements are not made in a timely manner. This has resulted in a changing end date with each report. If disbursements can be made in a timely manner, the project can be successfully completed by the end of 2010.

- RISK ASSESSMENT:

Political and Economic

As with many Small Island Developing States, The Bahamas has issues related to capacity and resources - both of which are limited and have many priorities competing for their attention and commitment. Climate change will have to compete as well. Economy is dependent on touristic development with large-scale projects existing or planned in coastal areas.

Socio-cultural

Awareness and understanding of climate change is limited across all sectors of society.

Environmental

As a low-lying SIDS, The Bahamas is faced with the reality that they can do their best to adapt, but climate change as a threat cannot be addressed without commitment of countries with high GHG emissions.

- RECOMMENDATIONS:

- Regular communication between UNDP and project should continue including timely request for information; project should also be advised if there will be problems with disbursements so efforts can be made to plan accordingly. With very prolonged delays in disbursement, negative impacts to project implementation cannot be avoided, but every effort should be made to avoid this.

- Disbursements of funds by UNDP need to be made in a timely fashion to avoid negative impacts to project implementation.

- Higher profile needs to be given to climate change with decision makers through media and regular communication with them so they are aware of project activities throughout project implementation and this is not left until SNC is completed.