## Accelerator Lab AWP Aug-Dec 19
Accelerator Lab Bosnia and Herzegovina (AccLab BiH) ANNUAL WORK PLAN FOR 2019
No. | ACTIVITY | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | Deliverable | Responsible party/Lead party | Budget activity | Budget
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Output 2: Identify and elevate new solutions
I. Onboarding Objective: Embedding the AccLab team into the organization
1.1 | Administrative on-boarding | [29 empty] | AL/UNDP Operations | Activity 3 | bar: JUL 4 to AUG 3
1.2 | Office setup | [29 empty] | AL/UNDP Operations | Activity 3 | bar: AUG 3 to AUG 4
1.3 | Accelerator Lab Bootcamp | [29 empty] | AL/MD | Activity 3 | bar: JUL 4 to AUG 1
1.4 | Team work norming (define roles, set up coworking tools, team building, etc.) | [29 empty] | AL/MD | Activity 3 | bar: AUG 3 to SEP 1
1.5 | Orientation with Operations, Communications and M&E | [29 empty] | SN/MD/AL | Activity 3 | bar: AUG 4 to SEP 1
1.6 | Getting to know the organization (UNDP/CPD/SDGs/UNCT/ and other key docs.) | [29 empty] | AL | Activity 3 | bar: AUG 3 to SEP 1
II. In-house sensemaking Objective: Identifying opportunities for accelerated learning by assessing the current CO portfolio for patterns, commonalities and gaps
2.1 | Internal AccLab launch at the UNDP Team Building Retreat | [29 empty] | AL/Communication Unit/MD/SN | Activity 1 | bar: SEP 4
2.2 | Participation in regular meetings (senior staff meetings, sector meetings, project meetings, LG Practitioners' Network meetings, Step up team etc.) | [29 empty] | AL | Activity 1 | bar: SEP 1 to DEC 4
2.3 | Meeting the sector leaders and selected projects to introduce the AccLab | [29 empty] | AL | Activity 1 | bar: AUG 4 to DEC 4
2.4 | Digesting the sense-making report | [29 empty] | AL | Activity 1 | bar: AUG 4 to SEP 1
2.5 | Expanding the sensemaking tool for a deeper understanding of the portfolio and identifying broader impacts and signals of change | [29 empty] | AD/AL | Activity 2 | bar: AUG 3 to SEP 1
2.6 | Applying the customized sensemaking tool to a selected number of projects | [29 empty] | AL | Activity 2 | bar: SEP 2 to OCT 1
2.7 | Acceleration potential map of the portfolio: what's there and what's not | [29 empty] | KB/AL/MD | Activity 2 | bar: OCT 2
2.8 | Acceleration potential map of the portfolio validated with the core team | [29 empty] | AL/MD/SN | Activity 2 | bar: OCT 2 to OCT 3
2.9 | Applying design thinking tools and practices in new project development (i.e. MZ, Smart City, GEF, MEG) | [29 empty] | AL | Activity 1 | bar: SEP 1 to DEC 4
2.10. | Participating in design thinking process in development of the new UNDP strategy (2025); | [29 empty] | AL | Activity 1 | bar: SEP 1 to DEC 4
III. Mapping the outdoors Objective: Assessing the acceleration needs around emerging developmet topics and unusual players in the external environment
3.1 | Draft the initial plan of targeted meetings with external actors/agents of change | [29 empty] | AL | Activity 2 | bar: AUG 4 to SEP 1
3.2 | Participating in project's events (incl. COPs) to learn about the local innovation ecosystem(s) | [29 empty] | AL | Activity 2 | bar: SEP 1 to DEC 4
3.3 | Meeting with the selected external actors/agents of change for a rapid scanning of the horizon | [29 empty] | AL | Activity 2 | bar: SEP 2 to DEC 4
3.4 | External acceleration intel map to identify untackled development solutions. | [29 empty] | AL | Activity 2 | bar: OCT 3 to OCT 4
3.5 | External acceleration intel map validated with the core team. | [29 empty] | AL/MD/SN | Activity 2 | bar: NOV 1 to NOV 2
IV. Experiments! Objective: Answering the acceleration needs through running a portfolio of experiments
4.1 | At least two test experiments AccLab learning cycles (experiments) conducted | [29 empty] | AL/MD | Activity 2 | bar: SEP 2 to DEC 4
4.2 | Birds eye perspective: Master map of acceleration opportunities between existing portfolio and signals from external environment | [29 empty] | AD/AL | Activity 2 | bar: NOV 1 to NOV 2
4.3 | Formulation of an 2020 Acceleration Plan to outline the framework of portfolio of experiments. | [29 empty] | AL/MD | Activity 2 | bar: NOV 3 to NOV 4
4.4 | Validation of the 2020 Acceleration Plan with the CO. | [29 empty] | AL/MD/SN | Activity 2 | bar: NOV 4 to DEC 1
V. Working out loud Objective: Communicating the Lab's work with the external environment and the Global Team/AL Network
5.1 | Public launch of the AccLab | [29 empty] | AL/Communication Unit/MD/SN | Activity 1 | bar: OCT 2
5.2 | Monthly blog posts | [29 empty] | AD/AL | Activity 1 | bar: AUG 4; SEP 4; OCT 4; NOV 4; DEC 4
5.3 | AccLab pitch and presentation formulation | [29 empty] | AL | Activity 1 | bar: AUG 4
5.4 | Active participation and lab presentation at outside events (i.e. Innovation summit, Sarajevo unlimited…) | [29 empty] | AL | Activity 1 | bar: AUG 3 to DEC 4
5.5 | Producing innovative visibility and communication tools and materials | [29 empty] | AD/AL | Activity 1 | bar: SEP 1 to DEC 4
VI. Learning Objective: Training and coaching for the Lab and by the Lab on mindset, values, principles, practices, tools and techniques that support innovation and acceleration
6.1 | Design an innovative and interactive learning journey for the Lab and CO staff. | [29 empty] | AL | Activity 3 | bar: AUG 3 to DEC 4
6.2 | Learning journey stops on a monthly basis | [29 empty] | KB/AL | Activity 1 | bar: SEP 3; OCT 3; NOV 3
6.3 | Weekly reflections for the team and updating of the journey journal | [29 empty] | AO/AL | Activity 3 | bar: AUG 4 to DEC 4
6.5 | Encouraging in house conversation and sharing on successes and failures. | [29 empty] | AO/AL | Activity 1 | bar: SEP 1 to DEC 4
6.6 | Bulletin/newsletter (3 bullet Friday newsletter) | [29 empty] | AD/AL | Activity 1 | bar: SEP 1 to DEC 4
Legend
AD - Arijana Drinić, Head of Exploration
AO - Amina Omićević, Head of Solution Mapping
AL - Accelerator Lab team
KB - Kemal Bajramović, Head of Experimentation
MD - Marina Dimova, Governance Chief Technical Specialist / Accelerator Lab Focal Point
SN - Steliana Nedera, UNDP Resident Representative in Bosnia and Herzegovina

## 00115686 - Accelerator Lab BDG
AWP | EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year |  |  | RESPONSIBLE PARTY | PLANNED BUDGET
|  |  | Y1 | Y2 | Y3 |  | Funding Source | Budget Description | Amount | Year 1 | Year 2 | Year 3
| Output 2: Identify and elevate new solutions GEN Marker 1 | Activity 1: Communications and local engagement | 33815 | 31000 | 31000 | UNDP CO BIH | Qatar Fund for Development; German Cooperation; Italy | 71300 - Individual consultant | 15000 | 5000 | 5000 | 5000 | 15000 | 0
[6 empty] | UNDP CO BIH | Qatar Fund for Development; German Cooperation; Italy | 71600 - Travel | 15500 | 7500 | 4000 | 4000 | 15500 | 0
[6 empty] | UNDP CO BIH | Qatar Fund for Development; German Cooperation; Italy | 74200 - Communication, audio-video | 19000 | 5000 | 7000 | 7000 | 19000 | 0
[6 empty] | UNDP CO BIH | Qatar Fund for Development; German Cooperation; Italy | 75700 - Workshops and events | 46315 | 16315 | 15000 | 15000 | 46315 | 0
|  | Activity 2: Experiments and Solutions Mapping | 40837 | 40000 | 40000 | UNDP CO BIH | Qatar Fund for Development; German Cooperation; Italy | 71600 - Travel | 5000 | 5000 | 0 | 0 | 5000 | 0
[6 empty] | UNDP CO BIH | Qatar Fund for Development; German Cooperation; Italy | 72100 - Subcontract - software solution | 45000 | 20000 | 10000 | 15000 | 45000 | 0
[6 empty] | UNDP CO BIH | Qatar Fund for Development; German Cooperation; Italy | 71300 - Individual consultant | 25000 |  | 15000 | 10000 | 25000 | 0
[6 empty] | UNDP CO BIH | Qatar Fund for Development; German Cooperation; Italy | 75700 - Workshops and events | 45837 | 15837 | 15000 | 15000 | 45837 | 0
|  | Activity 3: Country Accelerator Lab Teams | 136136.5 | 250576 | 250576 | UNDP CO BIH | Qatar Fund for Development; German Cooperation; Italy | 61100 - Salaries for the lab staff | 553940 | 110788 | 221576 | 221576 | 553940 | 0
[6 empty] | UNDP CO BIH | Qatar Fund for Development; German Cooperation; Italy | 73100 - Office and utilities for the staff | 26300 | 6300 | 10000 | 10000 | 26300 | 0
[6 empty] | UNDP CO BIH | Qatar Fund for Development; German Cooperation; Italy | 72200, 72800 - IT Equipment for the lab staff | 5260 | 1260 | 2000 | 2000 | 5260 | 0
[6 empty] | UNDP CO BIH | Qatar Fund for Development; German Cooperation; Italy | 75700 - Workshops/ training/ learning | 51788.5 | 17800 | 17000 | 17000 | 51800 | -11.5
|  | Sub-Total for Output 2 | [6 empty] | 853940.5 | 210800 | 321576 | 321576 | 853952 | -11.5
| Monitoring | MONITORING | [10 empty] | 0 | 0
| Evaluation (as relevant) | EVALUATION | [10 empty] | 0 | 0
| General Management Support |  | 16863.08 | 25726.08 | 25726.08 |  |  |  | 68315.24 | 16864 | 25726.08 | 25726.08 | 68316.16 | -0.92
| TOTAL | [7 empty] | 922255.74 | 227664 | 347302.08 | 347302.08 | 922268.16 | -12.42
Authorized Spending Limit - ASL
|  |  |  | FUND | Donor | USD
|  |  | AX1_DP | 30000 | 00117 | 141264 |  | 130800 | 10464 |  | 141264 | 0
|  |  |  | 30000 | 12298 | 86400 |  | 80000 | 6400 |  | 86400 | 0
[6 empty] | 227664 |  | 210800 | 16864
Budget in Atlas and COAs | Account | Operating Unit | Fund Code | Department | Activity | Analysis Type | Implementing Agent | Donor | Budget Item | Amount | Currency
| 71300 | BIH | 30000 | B0542 | ACTIVITY1 | BUD | 001981 | 12298 | 71300 | 5000 | USD
| 71600 | BIH | 30000 | B0542 | ACTIVITY1 | BUD | 001981 | 12298 | 71600 | 7500 | USD
| 74200 | BIH | 30000 | B0542 | ACTIVITY1 | BUD | 001981 | 12298 | 74200 | 5000 | USD
| 75700 | BIH | 30000 | B0542 | ACTIVITY1 | BUD | 001981 | 12298 | 75700 | 16315 | USD
| 75100 | BIH | 30000 | B0542 | ACTIVITY1 | BUD | 001981 | 12298 | 75100 | 2705.2 | USD | GMS lines
| 71600 | BIH | 30000 | B0542 | ACTIVITY2 | BUD | 001981 | 12298 | 71600 | 5000 | USD
| 72100 | BIH | 30000 | B0542 | ACTIVITY2 | BUD | 001981 | 12298 | 72100 | 20000 | USD
| 71300 | BIH | 30000 | B0542 | ACTIVITY2 | BUD | 001981 | 12298 | 71300 |  | USD
| 75700 | BIH | 30000 | B0542 | ACTIVITY2 | BUD | 001981 | 12298 | 75700 | 15837 | USD
| 75100 | BIH | 30000 | B0542 | ACTIVITY2 | BUD | 001981 | 12298 | 75100 | 3266.96 | USD | GMS lines
| 61100 | BIH | 30000 | B0542 | ACTIVITY3 | BUD | 001981 | 00117 | 61100 | 110788 | USD
| 73100 | BIH | 30000 | B0542 | ACTIVITY3 | BUD | 001981 | 00117 | 73100 | 952 | USD
| 73100 | BIH | 30000 | B0542 | ACTIVITY3 | BUD | 001981 | 12298 | 73100 | 5348 | USD
| 72800 | BIH | 30000 | B0542 | ACTIVITY3 | BUD | 001981 | 00117 | 72800 | 1260 | USD
| 75700 | BIH | 30000 | B0542 | ACTIVITY3 | BUD | 001981 | 00117 | 75700 | 17800 | USD
| 75100 | BIH | 30000 | B0542 | ACTIVITY3 | BUD | 001981 | 00117 | 75100 | 10464 | USD | GMS lines
| 75100 | BIH | 30000 | B0542 | ACTIVITY3 | BUD | 001981 | 12298 | 75100 | 427.84 | USD | GMS lines
227664
|  | Department ID |  | Expenditure department
|  | B0542 |  | 54201
COA | GL | OU | Fund | Dept. | Project | Activity | Imp.Ag. | Donor |  | Expense account |  |  |  |  | 71205 | Intl Consultants-Sht Term-Tech
| UNDP1 | BIH | 30000 | 54201 | 00115686 | based on AWP | 1981 | based on above distribution |  | depending on the nature of expense |  |  |  |  | 71210 | Intl Consultants-Sht Term-Supp
[15 empty] | 71305 | Local Consult.-Sht Term-Tech
[15 empty] | 71310 | Local Consult.-Short Term-Supp
[15 empty] | 71605 | Travel Tickets-International
[15 empty] | 71610 | Travel Tickets-Local
[15 empty] | 71615 | Daily Subsistence Allow-Intl
[15 empty] | 71620 | Daily Subsistence Allow-Local
[15 empty] | 71625 | Daily Subsist Allow-Mtg Partic
[15 empty] | 71630 | Shipment
[15 empty] | 71635 | Travel - Other
[15 empty] | 72105 | Svc Co-Construction & Engineer
[15 empty] | 72110 | Svc Co-Agricultural Management
[15 empty] | 72115 | Svc Co-Natural Resources & Env
[15 empty] | 72120 | Svc Co-Trade and Business Serv
[15 empty] | 72125 | Svc Co-Studies & Research Serv
[15 empty] | 72126 | Svc Co-Security blast assessme
[15 empty] | 72130 | Svc Co-Transportation Services
[15 empty] | 72135 | Svc Co-Communications Service
[15 empty] | 72140 | Svc Co-Information Technology
[15 empty] | 72145 | Svc Co-Training and Educ Serv
[15 empty] | 72150 | Svc Co-Manufacturing Services
[15 empty] | 72155 | Svc Co-Public Admin, Politics
[15 empty] | 72160 | Svc Co-Education & Health Serv
[15 empty] | 72165 | Svc Co-Social Svcs, Social Sci
[15 empty] | 72170 | Svc Co-Humanitarian Aid & Relf
[15 empty] | 72175 | Svc Co-Urban, Rural & Regional
[15 empty] | 74205 | Audio Visual Productions
[15 empty] | 74210 | Printing and Publications
[15 empty] | 74215 | Promotional Materials and Dist
[15 empty] | 74220 | Translation Costs
[15 empty] | 74225 | Other Media Costs
[15 empty] | 74230 | Audio & Visual Equipment
[15 empty] | 75705 | Learning costs
[15 empty] | 75706 | Learning - ticket costs
[15 empty] | 75707 | Learning – subsistence allowan
[15 empty] | 75708 | Learning - subcontracts
[15 empty] | 75709 | Learning - training of counter
[15 empty] | 75710 | Participation of counterparts
[15 empty] | 75711 | TrnWrkshp&Conf - Stipends
[15 empty] | 75712 | TrnWrkshp&Conf - Honorariums