Appendix A

Schedule of Activities and Facilities

2021: BELIZE: Support to Good Governance in Belize TRAC 2

Attachment 3

Schedule of Activities and Facilities

Work Plan Support to Good Governance in Belize

Period September 2021 t0 December 2021

|  | Chronogram |  | Budget |
| --- | --- | --- | --- |
|  |  | Responsible Party | SourceofFunding |
|  | Q42021_ |  |  |
|  |  |  | Planned Activities |
| Expected Outputs |  |  |  |
| Based on discussions with the GoB and particularly the MPSCPR and the AG, the |  |  |  |
| area of support by UNDP will be in three key areas: |  |  |  |
| i. Legislative Reform; |  |  |  |
| ii. Institutional Capacity Development; and |  |  |  |
| iii. Assessment and Strategy Development |  |  |  |
| Conduct assessment of the current asset recovery processes in |  |  |  | Consultant to conduct desk |
| Belize to identify how civil asset recovery would work in practice (15 |  |  |  | based research to baseline and |
|  |  |  |  | map Belize asset recovery |
| days) 1st September – 13th October 2021 |  |  |  |  |
|  |  |  |  | processes |
|  | x | Attorney General Ministry | UNDP | mapping the process from |
|  |  |  |  | inception of intelligence |
|  |  |  |  | through to obtaining the final |
|  |  |  |  | order |
| Conduct consultation: require a series of meetings with |  |  |  |  |
| stakeholders to understand operational realities, challenges and |  |  |  | explore findings and test |
|  |  |  |  | options for civil asset recovery |
| opportunities (5days) 18th – 22nd October 2021 |  |  |  |  |
|  |  |  |  | implementation in Belize |
|  | x | Attorney General Ministry | UNDP | Devise a civil asset recovery |
|  |  |  |  | strategy |
|  |  |  |  | Roundtable Meeting sessions |
|  |  |  |  | with stakeholders to present |
|  |  |  |  | verified findings |
| Produce a report on the findings of Phase 1 and a plan to Phase 2, |  |  |  | Draft report detailing the |
| which will include the recommendations for the Civil Recovery |  |  |  | findings and outcomes of Phase |
|  |  |  |  | 1 and a plan for Phase 2 |
| legislation (5days) 25th – 29th October 2021 |  |  |  |  |
|  | x |  |  | including detailed |
|  |  |  |  | recommendations for the Civil |
|  |  |  |  | Recovery legislation |
|  |  |  |  | Draft Civil Recovery Strategy |
| Produce draft legislation and subsidiary rules, to include cash |  | Attorney General Ministry | UNDP |  |
| seizure, detention, and forfeiture (25days) 1st November – 13th |  |  |  | including legislation, subsidiary |
|  |  |  |  | legislation and accompanying |
| December |  |  |  |  |
|  |  |  |  | rules (cash seizure, detention |
|  | x |  |  | and forfeiture rules need to be |
|  |  |  |  | implemented) |

| Q4 2021 | Total |
| --- | --- |

| $14,937.77 | $14,937.77 |
| --- | --- |

| $7,468.88 | $7,468.88 |
| --- | --- |

| $7,468.88 | $7,468.88 |
| --- | --- |

| $29,875.54 | $29,875.54 |
| --- | --- |

Total

$	59,751.07

$59,751.07