PROJECT DOCUMENTATION

Q2-3 2015 STAGE PLAN

| Projects: “Self-assessment for the TNC to the Framework Convention on Climate Change” - 00076372 |  |
| --- | --- |
| Date: June 29th, 2015 |  |
| PRINCE2 |  |
| Author: Safira Vasquez |  |
| Owner: National Climate Change Office |  |
| Client: Government of Belize (supported by the European Union, Global Environment Facility and UNDP) |  |
| Document Ref: 2.SP.Q2-3.2015a |  |

# Stage Plan History

## 1.1	Document Location

This document is only valid on the day it was approved.

The source of the document will be found on the Project Administrative Assistant PC at National Climate Change Office in Belmopan, Cayo.

## 1.2	Revision History

Date of this revision:	29 June 2015

Date of Next revision:	N/A

| Revision date | Previous revision date | Summary of Changes | Changes marked |
| --- | --- | --- | --- |
| 29/06/2015 | N/A | First issue |  |

## 1.3	Approvals

This document requires the following approvals.

Signed approval forms are filed in the Management section of the project files.

| Name | Signature | Title | Date of Issue | Version |
| --- | --- | --- | --- | --- |
| Ann Gordon |  | Project Director |  | SP.Q2-3.2015a |
| Adele Catzim-Sanchez |  | CEO - MFFSD |  | SP.Q2-3.2015a |

## 1.4	Distribution

This document has been distributed to:

| Name | Title | Date of Issue | Version |
| --- | --- | --- | --- |
| TNC-PEG |
| Adele Catzim-Sanchez | Chief Executive Officer, Ministry of Forestry, Fisheries and Sustainable Development |  | SP.Q2-3.2015a |
| Audrey Wallace | Chief Executive Officer, Office of the Prime Minister |  | SP.Q2-3.2015a |
| Ann Gordon | UNFCCC Focal Point/National Climate Change Coordinator, National Climate Change Office |  | SP.Q2-3.2015a |
| Diane Wade Moore | Environmental Programme Analyst, United Nations Development Programme |  | SP.Q2-3.2015a |
| Carlos Fuller | International and Regional Officer, Caribbean Community Climate Change Office |  | SP.Q2-3.2015a |
| Edilberto Romero | Executive Director, Programme for Belize |  | SP.Q2-3.2015a |
| Beverly Wade | GEF Focal Point/Chief Environmental Officer, Department of the Environment |  | SP.Q2-3.2015a |
| Dennis Gonguez | IPCC Focal Point/Chief Meteorologist, National Meteorological Service |  | SP.Q2-3.2015a |
| Emily Waight Aldana | Economist, Ministry of Finance and Economic Development |  | SP.Q2-3.2015a |
| Andrew Harrison | Marketing Officer, Ministry of Natural Resources and Agriculture |  | SP.Q2-3.2015a |
| Ambrose Tillett | Ministry of Energy, Science and Technology and Public Utilities |  | SP.Q2-3.2015a |

# 2	Table of Contents

Page

### 1	Stage Plan History									1

1.1	Document Location								1

1.2	Revision History

1.3	Approvals

1.4	Distribution

### 2	Table of Contents

### 3	Purpose

### 4	Plan Description

### 5	Quality Plan

### 6	Plan Prerequisites

### 7	External Dependencies

### 8	Tolerances

### 9	Monitoring and Control

### 10	Reporting

### 11	Planning Assumptions

### 12	Graphical Plan

12.1	Product Breakdown Structure

12.2	Risk Assessment

### 13	Product Descriptions

# Stage Plan

## 3	Purpose

## The purpose of this document is to identify and schedule the activities that should be initiated and/or completed during the period of the project (1st April to 30th September, 2015). It provides adequate information for the Project Manager (PM) and the Project Board (PB)/ Project Execution Group (PEG) to manage and direct the stage.

- Complete the following activities/consultancies:

        - GHGI Coordinator

        - GHGI Data Collection and Programmes Containing Measures to Mitigate Climate Change Identified

        - National Circumstance of the National Communication

        - Climate Change Communication Strategy

        - NCCO Website

        - Third National Communication report compiler/ editor

- Climate Change Education, Awareness, Outreach, Capacity Building/Training

        - Printing of Climate Change awareness/information documents including:

          - Copies of the final Vulnerability and Adaptation Reports (In-depth and summary reports)

          - Copies of the final Climate Change Policy, Strategy and Action Plan

          - Copies of the final Third National Communication Report

        - Production of Climate Change awareness tools including

          - Banners

          - Displays

        - Product placement at sector specific events (Reef Week, National Agriculture and trade show, Public service day, other expositions, etc.)

Project activities are directly managed by a dedicated Project staff and execution of actions will be carried out with the support of MFFSD extended staff complementing the PMU and/or UNDP support. The NCCO Project Manager will serve as the initial point of project quality assurance. Quality of work programme delivery will be monitored and reported on a monthly basis the governing project bodies set in place such as the TNC PEG.

This is the initial stage plan; project baseline is as suggested in the approved document.

## 4	Plan Description

- Complete the following activities/consultancies:

        - GHGI Coordinator – Database and Management System for Archiving Data (including the back-up of data collected), Final Summary Report to be used as the Biennial Update Report, Final GHGI Report Chapter for the National Communication

        - GHGI Data Collection and Programmes Containing Measures to Mitigate Climate Change Identified - GHGI data collected, Recommendations on Mitigation Options, GHGI Sector Reports, Final Chapter reporting on programmes containing measures to mitigate climate change for the National Communication Report.

        - National Circumstance of the National Communication – To be validated and approved

        - Climate Change Communication Strategy – buy-in from stakeholders, presentation to and approval from the BNCCC

        - NCCO Website – live website, ease of access to climate change information

        - Third National Communication report compiler/editor- submission to the UNFCCC

- Climate Change Education, Awareness, Outreach, Capacity Building/Training

        - Printing of Climate Change awareness/information documents including:

          - Copies of the final Vulnerability and Adaptation Report – circulation to stakeholders for information sharing

          - Copies of the final Climate Change Policy, Strategy and Action Plan - circulation to stakeholders for information sharing

        - Copies of the final Third National Communication Report - circulation to stakeholders for information sharing

        - Production of Climate Change awareness tools including

          - Banners

          - Displays

          - Videos on strategic messages on Climate Change and its impact on Belize

          - promotional items

        - Product placement at sector specific events (La Ruta Maya, expositions, etc.)

Resources and Responsibilities

Total funds for 2015 TNC = $ 155,000.00 (based on Atlas) Funds for Q2-3 2015 TNC = $ 96,766.16

## 5	Quality Plan

| GHGI Coordinator TNC OUTCOME 2: Completed National GHGI Assessments |
| --- |
| Activity 1: Database and Management System for Archiving Data (including the back-up of data collected) | Start Date: February 2013 End Date: August 2015 |
| To support effective implementation of approved project interventions |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of delivery | Data in organized usable form | July 2015 |
|  | Database and training for up keeping handed over to the NCCO | August 2015 |
| Activity 2: Final Summary Report to be used as the Biennial Update Report | Start Date: February 2015 End Date: July 2015 |
| To support effective implementation of approved project interventions |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of delivery | Report accepted and approved by the TAC | July 2015 |
|  | Reports following validation meeting held with stakeholders | July 2015 |
| Activity 3: Final GHGI Report Chapter for the National Communication | Start Date: February 2015 End Date: July 2015 |
| To support effective implementation of approved project interventions |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of delivery | Assessment of data based on IPCC guidelines | July 2015 |
|  | Report accepted and approved by respective Sectors | July 2015 |
|  | Report presented and approved by the mitigation subcommittee | August 2015 |
| GHGI Data Collection and Programmes Containing Measures to Mitigate Climate Change Identified TNC OUTCOME 2: Completed National GHGI Assessments TNC Outcome 4: Programmes Containing Measures to abate (mitigate) Climate Change |
| Activity 1: GHGI data collected | Start Date: February 2015 End Date: July 2015 |  |
| To support effective implementation of approved project interventions |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of deliverable | Assessment of data based on IPCC guidelines | July 2015 |
|  | Validation of datasets and modules by respective sectors | July 2015 |
| Activity 2: Recommendations on Mitigation Options | Start Date: January 2015 End Date: August 2015 |  |
| To support effective implementation of approved project interventions |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of deliverable | Recommendations accepted and approved by the mitigation subcommittee | August 2015 |
| Activity 3: GHGI Sector Reports | Start Date: February 2015 End Date: July 2015 |  |
| To support effective implementation of approved project interventions |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of deliverable | Report validated by the respective sectors and the information matches with approved datasets and modules validated by respective sectors | July 2015 |
|  | Reports presented to and approved by the mitigation subcommittee | July 2015 |
| Activity 4: Final Chapter reporting on programmes containing measures to mitigate climate change for the National Communication Report | Start Date: February 2015 End Date: July 2015 |  |
| To support effective implementation of approved project interventions |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of deliverable | Report accepted and approved by the mitigation subcommittee | July 2015 |
| National Circumstances of the National Communication TNC OUTCOME 1: Updating of the National Circumstances |
| Activity 1: National Circumstances completed | Start Date: March 2015 End Date: July 2015 |  |
| To support effective implementation of approved project interventions |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of deliverable | Report submitted to and reviewed by the NCCO | July 2015 |
|  | Chapter validated and approved by nationals | July 2015 |
| Climate Change Communication Strategy TNC OUTCOME 5: Public Education and awareness information dissemination and capacity building programme being supported |
| Activity 1: Finalization of a climate Change Communication Strategy | Start Date: February 2015 End Date: July 2015 |  |
| To support effective implementation of approved project interventions |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of deliverable | Acceptance and approval from PEG and BNCCC | July 2015 |
| NCCO Website TNC OUTCOME 5: Public Education and awareness information dissemination and capacity building programme being supported |
| Activity 1: Finalization of the NCCO Website | Start Date: February 2015 End Date: July 2015 |  |
| To support effective implementation of approved project interventions |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of deliverable | Website content and layout finalized | May 2015 |
|  | Website is live | July 2015 |
|  | Ease of access to climate change information to stakeholders/public | July 2015 |
|  | Final training on management of the website for continuous updating, etc. | August 2015 |
| Compilation and completion of the Third National Communication report TNC OUTCOME 5: Public Education and awareness information dissemination and capacity building programme being supported |
| Activity 1: Completion and submission of Belize’s TNC to the UNFCCC | Start Date: June 2015 End Date: September 2015 |  |
| To support effective implementation of approved project interventions |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of deliverable | Terms of reference developed and approved by NCCO | June 2015 |
|  | Solicitation of proposed IC offerors by roster | June 2015 |
|  | Selection of the best IC offer based on the selection criteria (evaluation) | July 2015 |
|  | Validation of the TNC report by relevant stakeholders | August 2015 |
|  | TNC report approved and accepted by the PEG and/or BNCCC | August 2015 |
|  | Submission of the TNC report to the UNFCCC | August 2015 |
|  | Revised and edited 2014 V&A accepted and approved by key sectors | September 2015 |
| Climate Change Education, Awareness, Outreach and Capacity Building Training TNC OUTCOME 5: Public Education and awareness information dissemination and capacity building programme being supported |
| Activity 1: Printing of climate change awareness/information documents | Start Date: March 2015 End Date: July 2015 |  |
| To support effective implementation of approved project interventions |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of deliverable | Selection of vendor based on quotations submitted | July 2015 |
|  | Printing of CC awareness/information documents | July 2015 |
|  | Dissemination of the CC awareness/information documents | Following receipt from the printers |
| Activity 2: Copies of final vulnerability and adaptation assessments, national climate change policy, strategy and action plan, and the Third National Communication Report | Start Date: March 2015 End Date: September 2015 |  |
| To support effective implementation of approved project interventions |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of deliverable | Selection of vendor based on quotations submitted | August 2015 |
|  | Printing of report | September 2015 |
|  | Dissemination of the Report | September 2015 |
| Activity 3: Production of Climate Change Awareness tools | Start Date: February 2015 End Date: August 2015 |  |
| To support effective implementation of approved project interventions |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of deliverable | Selection of vendor based on quotations submitted | July 2015 |
|  | Production of CC awareness tools | August 2015 |
| Activity 4: Product placement at sector specific events | Start Date: Ongoing End Date: Ongoing |  |
| To support effective implementation of approved project interventions |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Quality of deliverable | Events identified | Ongoing |
|  | Messaging for event is finalized | Ongoing |
|  | Product is showcased at event | Ongoing |
|  | Information shared to stakeholders/public | Ongoing |

## 6	Plan Prerequisite

- Project overarching communication strategy must be elaborated and socialized with sub- projects.

- Quotations needed by various service providers in order to complete procurement of goods / services for the elaboration of CC information, tools, reporting, etc. to be produced/purchased.

- Payment issues with CITO clarified and NCCO staff to be trained on managing the NCCO website.

- Endorsement of GHGI and programmes containing measures to abate (mitigate) CC by key partners/stakeholders.

## 7	External Dependencies/ Linkages

- Buy-in from key Ministries is essential for the realization of project outputs.

- All reports need to be accepted and approved by the PEG and to an extent some needs to be accepted and approved by the BNCCC and/or its subcommittees.  This may require additional dedication and prioritization of the work being presented/circulated by the NCCO by members.  Adequate time determined by the PMU which is dictated by the time remaining for project closure may not seem sufficient to members.

## 8	Tolerances

Project Manager is allowed 20% deviation from approved stage plan budget. 75% budget delivery is considered acceptable. Deviations in project timeline must not exceed 1 month.

## 9	Monitoring and Control

Monitoring and Evaluation of this stage plan will be accomplished by:

- Monthly meetings between/among project staff to track progress against approved stage plan.

- As per normal, expenditure will be controlled primarily through UNDP’s Request for Direct Payment mechanism for payment and close monitoring of the stage budget by the Project Manager.

- Preparation of Quarterly End Stage Report and Submission to TNC: PEG and UNDP

Control of stage boundaries will be accomplished by:

- PEG Meeting to approve the plan.

- Production of risk logs, lessons learned log, & end of stage report.

## 10	Reporting

Plan will be reported upon at the end of this stage period.

## 11	Planning Assumptions

- Quarterly PEG meetings may assist the project in implementing its work plan.

- Development of the Communication Strategy requires further consultations with various sectors to establish a baseline.  This process is costly and time consuming.  At this stage of the project, there are not sufficient funds or time for a baseline to be established through consultations.  Due to the lack of time and funds, this may not be realistic.  Therefore, the strategy may not be able to meet the needs of its target audience and may need to be revised as soon as more financing are available to do so.  Currently, the finalization of the strategy is being done by a volunteer of whom the office has not been able to provide any financial assistance to for the completion of this activity.

- Based on quotations submitted and proven quality, public awareness tools and information documents will be produced.

## 12	Graphical Plan

### 12.1	Financial Budget

- Complete the following activities/consultancies:

        - GHGI Coordinator – Database and Management System for Archiving Data (including the back-up of data collected), Final Summary Report to be used as the Biennial Update Report, Final GHGI Report Chapter for the National Communication

        - GHGI Data Collection and Programmes Containing Measures to Mitigate Climate Change Identified - GHGI data collected, Recommendations on Mitigation Options, GHGI Sector Reports, Final Chapter reporting on programmes containing measures to mitigate climate change for the National Communication Report.

        - National Circumstance of the National Communication – To be validated and approved

        - Climate Change Communication Strategy – buy-in from stakeholders, presentation to and approval from the BNCCC

        - NCCO Website – live website, ease of access to climate change information

        - Third National Communication report compiler/editor- submission to the UNFCCC

- Climate Change Education, Awareness, Outreach, Capacity Building/Training

        - Printing of Climate Change awareness/information documents including:

          - Copies of the final Vulnerability and Adaptation Report – circulation to stakeholders for information sharing

          - Copies of the final Climate Change Policy, Strategy and Action Plan - circulation to stakeholders for information sharing

        - Copies of the final Third National Communication Report - circulation to stakeholders for information sharing

        - Production of Climate Change awareness tools including

          - Banners

          - Displays

          - Videos on strategic messages on Climate Change and its impact on Belize

          - promotional items

        - Product placement at sector specific events (La Ruta Maya, expositions, etc.)

### 12.2	Risk Assessment

|  | To provide a repository of information about risks, their analysis, countermeasures and status. |
| --- | --- |
| Risks: |  |

| Id. | Description | Category | Impact | Probability | Proximity | Counter-measures | Owner | Author | Date Identified | Date last updated | Current status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Due to the institutionalization of the GHG Inventory and the limited human resources the Policy Coordination and Planning Unit of the Ministry of Natural Resources and the Environment were identified to undertake the Data collection of the Green House Gas Inventory Process. | Political | Very high | Low | Medium | The Project Director along with UNDP has identified Government counterparts (with the technical background) to support the MNRE-PCPU. | CEO- MNRE/UNDP | S. Vasquez | 07.12.11 | 13.01.12 | Improving |
|  | Time constraints on work plan due to lack of technical experience in GHG inventory. | Operational | Very high | Medium | Medium | The Project Manager (PM) continues to work along with other Government technical experts to support the Data Collectors. | PM | S. Vasquez | 13.01.12 | 20.02.12 | Stable |
|  |  | Operational | Very High | Medium | Medium | On 3rd May 2012, a meeting was held with Mr. Green the former project manager of the SNC and a statistical expert used to validate past GHG inventory worksheets to validate data submitted to the PMU by previous data collectors. In validating the data it was determined that the number and quality of data was deficient. | PM | S. Vasquez |  | 08.5.12 |  |
| 3. | Large membership of the NCCC results in lack of direction to the PMU due to unavailability of members; therefore, no quorum is attained. quorum. | Operational Political | Extremely High | High | Medium | The PM continues to call officers to meet. Urgent matters were addressed via email (round-robin). |  | S. Vasquez | 12.04.12 | 17.04.12 |  |
|  |  | Operational Political | Medium | Low | Immediate to Short Term | Under new Ministry the NCCC membership is being revised. The PMU currently establishing a PEG. |  | S. Vasquez | 15.06.12 | 15.06.12 | Stable |
|  |  | Operational Political | Medium | Low | Immediate to Short Term | Under the new Ministry, the NCCC membership has been revised along with the channel of communication. Sub-committees are being activated and a Project Execution Group is being formalized. | PM | S. Vasquez | 23.08.12 | 23.08.12 | improving |
| 4. | Belize General Elections has impacted project activities | Political Operational | Extremely high | High | Immediate to short term | General Elections for the country took place on7th March 2012, a re-shuffling in ministries occurred and new Ministries formed. The project is now under the newly formed Ministry of Forestry, Fisheries and Sustainable Development. The project will need to re-locate and sensitize the new Minister and CEO. Project may have a change in direction and flow of activities. The institutionalization of the Green House Gas Inventory Process may also be altered. | PM | S. Vasquez | 29.03.12 | 29.03.12 | Improving |
| 5. | Housing of the Project in new Ministry has changed the project direction. | Operational | High | Low | Medium to long term | A presentation was made by the PMU on the project document, finances, lessons learnt to the new Minister and CEO. This determined the best way forward for the project especially for Outcome 2 – Green House Gas Inventory Thematic Area. | PM | S. Vasquez | 18.05.12 | 18.05.12 | Improving |
|  |  | Operational | High | Low | Medium to long term | The PMU along with CEO in consultation with Mr. Earl Green, former project manager to the SNC, had a meeting on the 23rd May 2012 recommending that consultants in past GHG inventories be contacted to bid for available consultancies. TOR’s will be adjusted for a government technical person to work closely with the consultant so as to institutionalize the process and train the government officers. This better allow sustainability of the reporting process. |  | S. Vasquez |  | 23.5.12 | Improving |
| 6. | Finances under Outcome 2 will disallow the number of days needed for a detailed inventory to be produced. | Operational | Very High | Low | Immediate | In consultation with Mr. Earl Green , former Project Manager for the SNC, on the way forward, the number of consultants hired would be six for the inventory and one for the biomass. In calculating the number of days needed and consultancy rate it was observed that the finance presently available will fall short. To address this risk, the PMU was able to contact a Belizean Student who has been researching on biomass data in various plot areas throughout Belize. The student has agreed to assist the project with data. This will save cost for Outcome 2. Another Belizean scientist currently working with CATALAC has agreed to assist in biomass and LUCF data analysis and report with a low cost attached. This person will also be able to assist in training the Government Officers to use the program for the GHG Inventory Analysis. | PM | S. Vasquez | 04.05.12 | 29.06.12 | Improving |
|  |  | Operational | Very High | Low | Immediate | The PEG agreed to the hiring of the CCCCC as the GHGI Coordinator to facilitate training of National counterparts to build those capacities to conduct the GHGI. The CCCCC has been hired as the GHGI coordinator and will provide the necessary support need to train national and to ensure the completion of the GHGI component of the TNC. | PM | S. Vasquez |  | 27.11.12 | Stable |
| 7. | Additional responsibilities assigned to the PM will cause a delay in delivery of project outputs | Operational Organizational | Very High | Moderate | Immediate to Short term | The PA will take-over some of the responsibilities of the PM pending the return of the PD from medical leave | PM | S. Vasquez | 24.09.2012 | 24.09.2012 | Stable |
| 8 | Flow of communication from technical advisory committee (TAC) and PEG members result in delay | Strategic | High | Medium | Immediate to Short Term | An agreement should be made that all approvals or comments need to be submitted within a specified timeframe given. If there is no response it should be agreed that there is no objection to the request | PM | S. Vasquez | Aug 2012 |  |  |
| 9 | Monthly travels to CC seminars, although beneficial, result in delay of project deliveries | Operational | Med | High | Immediate to short term | Travel need to be indicated within timeframe so that PMU is able to plan properly | PM | S. Vasquez | Aug 2012 |  |  |
|  |  |  |  |  |  | If a technical staff is needed for the completion of an activity (requested by the PMU) then that technical staff will not be sent to participate in that meeting. This allowed for more timely delivery of activities under the project. |  |  |  | January 2014 | stable |
| 10 | Capacity being built in project staff, no measure is currently available to ensure capacity is not lost | Operational | High | Low | Immediate to short term | Measures need to be put in place for capacity to stay within government | PM | S. Vasquez | Aug 2012 |  |  |
| 11 | National needs requires a maximization of project results. | OperationalPolitical | High | Medium | Immediate to short term | When there is a change in the Ministry housing the project it is recommended that the project outcomes be revisited by the new Ministry and donors to see how best the results can accommodate the Ministry's needs. | PM | S. Vasquez | 4 March 2013 |  |  |
| 12 | Indecisiveness on the way forward with consultancy | Operational, strategic | high | medium | Immediate to short term | Written legal position from both UNDP and GOB needs to be recorded. | PM | S. Vasquez | 30-11-2014 | 30-11-2014 | Resolved |
| 13 | Resignation of Officers | Operational | High | Medium | Immediate to short term | Re-advertisement of vacant post. The vacant post(s) TOR should be revisited to ensure adequacy in delivery of project outputs. If TOR is adequate then it should be re-advertised so that post can be filled immediately | PM | S. Vasquez | 20-03-2014 | 24-03-2014 | resolved |
| 14 | Review of Deliverables by the TAC | OperationalRegulatory | High | High | Immediate | Will address this issue at the PEG and BNCCC level; CEO will address at the CEO Caucus level | PM | S. Vasquez | 25-06-2014 | 25-06-2014 | Will be addressed at decision making level |
| 15 | Relocation of the NCCO to a new space | operational |  |  |  | Relocation may pose some problems. Better planning is recommended to avoid delays in communication with partners. | PM | S. Vasquez |  |  | improving |
| 16 | Change of CEO (PEG Chair) | Operational |  |  |  | Although may be a risk to the project and can pose some delays, if the PMU gains early buy-in from the new CEO then there will be no delay. As such, the new CEO was briefed within the first week of her assignment to the post of the NCCO and its ongoing activities/projects. | PM | S. Vasquez |  |  |  |
| 17 | The lack of time and human resources within the sectors of focus for the GHGI to dedicate to the process | operational | high | high | Medium | Since 2012, various attempts for training and for the completion of this activity were conducted. The efforts put out to institutionalize this process did not receive the expected outcome. After realizing that this process was not effective and in an effort to save time, the PMU presented to the PEG another alternative which was to contract the training institution with experience in conducting this exercise to facilitate the process. The institution agreed to complete this exercise on the behalf of the Government but will ensure that there is sector buy-in on the reports coming out of this activity. | PM | S. Vasquez | 12-12-2014 | 07-01-2015 | improving |
| 18 | The lack of a systematic approach of data collection at a national level | Operational regulatory | high | high | high | A recommendation will be made to the GOB through the TNC report that there is a need to develop a nationwide systematic and scientific approach to data collection. The importance of data collection and its use needs to have buy-in at the policy-makers level. A second recommendation will also be made for capacities to be built in this area. It will also be useful if it can be emphasize to agencies/institutions, etc. the importance of having data to inform our national decision-making processes. | PM | S. Vasquez | 18-06-2015 | 18-06-2015 | To be presented at the next BNCCC meeting |

Environmental; organizational; operational, political, financial, Strategic; regulatory; security

## 13	Product Descriptions

Annex 1: Monthly Work and Expenditure Plan for Q2-3 2015

| Outcome 2 | Completed National Green House Inventory Assessments |
| --- | --- |
| Outputs | Planned activities for coming year | Chronogram |  |  | Budget 2015 |
|  |  | Start | End | Person Responsible | GEF | CO |
| Output 2.3 Methodologies for GHG inventory estimates analyzed, selected and validated | 2.2.1 Final IPCC Excel Workbook sheets validated and approved | July | July | PM | 15,205 | 4500 |
| Subtotal output 2.3 |  | 15,205 | 4,500 |
| Output 2.4 Collect GHG inventory data and complete the IPCC workbooks | 2.4.1 Acceptance of Final Summary of Biennial Report Summary, Final GHGI Report Chapter for the National Communication | July | July | PM | 7,000 | 3,000.00 |
| Subtotal output 2.4 |  | 7,000 | 3,000 |
| Output 2.5 Database and management system for archiving data | 2.5.1 Database and Management Systems completed | August | August | PM | 12,250.00 | 2250 |
| Subtotal output 2.5 |  | 12,250 | 2,250 |
| TOTAL per budget line | Locked in contract with CCCCC | 34,455 | 9,750 |
| Outcome 3 | Programmes containing measures to facilitate adequate adaptation to climate change (Integrated Vulnerability & Adaptation Coastal development, water, agriculture sector, Resilience of NPAS; National Adaptation Strategy) |
| Outputs | Planned activities for coming year | Chronogram |  | Budget 2015 |
|  |  | Start (month) | End (month) | Person Responsible | GEF | CO |
| Outpu t 3.2 Adaptation Policy and strategy development | 3.1.1 Printing of V&A Assessment | September | September | PM/PA | 5,000.00 |  |
|  | 3.1.2 Printing of CC Policy, Strategy and Action Plan | July | July | PM/PA | 3,000.00 |  |
|  | 3.1.3 Support staff | July | Sept | PM/PA | 10,791.16 |  |
|  | 3.1.4 Validation meetings (BNCCC/Mitigation/V&A sub comm) | July | Sept | NCCO | 3,000.00 |  |
|  | 3.1.5 Office sundries/supplies | July | July | Pm/PA | 300.00 |  |
|  | 3.1.6 Website design changes | July | July | CO/PM | 400.00 |  |
|  | 3.1.7 Transportation Cost | July | Sept | Pm/PA | 800.00 |  |
| Subtotal output 3.2 |  | 23,291.16 | 0.00 |
| TOTAL per budget line |  | 23,291.16 | 0.00 |
| Outcome 4 | Programmes containing measure to abate (mitigate) climate change |
| Outputs | Planned activities for coming year | Chronogram |  | Budget 2015 |
|  |  | Start (month) | End (month) | Person Responsible | GEF | CO |
| Output 4.1 Identify programmes containing measures to mitigate CC | 4.1.1 Final Summary Report detailing the methodology, results/findings and conclusions/recommendations for the assessment | July | August | PM | 13,050 |  |
|  | 4.1.3 Final Chapter reporting on programmes containing measures to mitigate climate change for the National Communication | July | August | PM | 8,970 |  |
| Subtotal output 4.1 |  | 22,020 | 0 |
| TOTAL per budget line | Locked in contract with CCCCC | 22,020 | 0 |
| Outcome 5 | Public Education and awareness information Dissemination and Capacity Building Programme being supported |  |
| Outputs | Planned activities for coming year | Chronogram |  | Budget 2015 |
|  |  | Start (month) | End (month) | Person Responsible | GEF | CO |
| Output 5.1 Public Education & Awareness information dissemination and capacity building | 5.1.1 Printing of CC awareness documents | July | August | PM/PA | 6,000 |  |
|  | 5.1.2 Purchase of CC awareness tools (displays, banners, etc) | July | August | PM/PA | 4,000 |  |
| Subtotal output 5.1 |  | 10,000 | 0 |
| TOTAL per budget line |  | 10,000 |  |
| Outcome 6 | Compilation, Drafting, Production and Dissemination, processing for acceptance as national report |  |
| Outputs | Planned activities for coming year | Chronogram |  | Budget 2015 |
|  |  | Start (month) | End (month) | Person Responsible | GEF | CO |
| Output 6.1 Compilation, Drafting, Production & Dissemination, processing for acceptance as national report | 6.1.1 Compilation and drafting of national report for acceptance as national report by consultant | July | September | PM | 7,000 |  |
|  | 6.1.2 Printing of third national communication report | September | September | PM | 3,000 |  |
| Subtotal output 5.1 |  | 7,000 | 0 |
| TOTAL per budget line |  | 7,000 |  |
|  |  |  |  | TOTAL | 96,766.16 |  |