| 1. **Strategic Priority (1) MDG/IADG Achievement**

***Support countries in accelerating achievement of the MDGs and internationally agreed development goals and treaty obligations with equity by assigning priority to poverty eradication guided by national development priorities*** |
| --- |
| **Outputs** | **Lead** | **Role of Partners** | **Performance Indicators** | **QCPR** |
| 1. UNDAFs in the AP region highlight efforts to accelerate achievement of the MDGs and IADGs
 | PSG | * PSG to review CCAs and UNDAFs to ensure MDGs and IADGs highlighted
 | * Number of CCAs and UNDAFs revised on the basis of PSG feedback
 | 10, 14, 15, 42, 70-73, 81, 82, 84, 89, 117-120, 145-151 |
| * Joint missions conducted to roll out countries to support integration of MAF in UNDAFs
 | * Number of MAF missions to UNDAF roll out countries
 |
| 1. Regional good practices and lessons on incorporation of MDGs and IADGs shared with UNCTs
 | PSG | * PSG working with RCOs to identify and document best practice case studies
 | * Number of best practice cases documented.
* Number of UNCTs that request / utilize best practice examples from UNDG AP
 |  |

| 1. **Strategic Priority (2) Post-2015 Agenda**

***Facilitate broad-based engagement in the global dialogue on the post-2015 development agenda building on the experience of the MDGs and core UN principles of human rights, equality and sustainability, linking to national development priorities and strategies*** |
| --- |
| **Outputs** | **Lead** | **Role of Partners** | **Performance Indicators** | **QCPR** |
| 1. Regional level inputs contribute to the Post 2015 development agenda (in coordination with RCM/ESCAP)
 | UNDG | * Regional meetings and consultations organized
 | * Number of regional meetings on Post 2015 conducted in consultation with or facilitated by UNDG AP
* Successful launching of UNDG AP project on Post 2015
 | 10, 14, 15, 73 |
| 1. Regional Working Group / Task Team papers (and case studies) are utilized by UNCTs as part of UN contribution to post 2015 debate

  | Working Groups / Task Teams | * Country case studies developed and circulated
* Follow up country missions conducted
 | * Number of case studies related to WG/TT papers developed and disseminated
* Number of requests for follow up support at the country level
 | 10, 14, 15, 73 |

|  |
| --- |
| 1. **Strategic Priority (3) Crisis/Post-Crisis Transition**

***Help build resilient societies and deliver effective support for sustainable recovery in crisis and post-crisis countries by ensuring mutually reinforcing linkages between the political, development, humanitarian, rule of law, human rights and social and security dimensions of UN engagement*** |
| **Outputs** | **Lead** | **Role of Partners** | **Performance Indicators** | **QCPR** |
| 1. Quality support and advice provided to countries in transition and in particular those rolling out UNDAFs in 2013/14
 | UNDG AP | * High level interagency mission to transition countries conducted under the auspices of the UNDG AP
* UNDG members-led training
 | * Number of UNDG-facilitated engagements with transition countries
* Number of dedicated trainings on conflict and transition, and disaster risk reduction and preparedness, supported (directly or indirectly) through the UNDG AP members
 | 94-108 |

|  |
| --- |
| 1. **Strategic Priority (4) National Capacity Development and Development Effectiveness**

***Strengthen support for national capacity development, including through “upstream” policy and programme advice, incentivizing the use of national systems, sharing of good practices and lessons learned, and strengthening the normative approach and operational linkages, including human rights and gender equality*** |
| **Outputs** | **Lead** | **Role of Partners** | **Performance Indicators** | **QCPR** |
| 1. **Capacity Development**

UNDG AP is better able to support UNCTs ability to engage with national systems esp. around core normative principles (through the UNDAF process) | PSG | * PSG to identify good examples of UNDAFs utilizing national data sources and coordinating with national planning cycles
 | * Number of UNDAFs indicator frameworks revised to make greater use of national data sources
* % of UNDAF Reviews that are held in conjunction with review of national development plans
 | 57, 58, 61, 62, 63, 64, 66, 67, 68, 95 116, 157, 158 |
|  | OHCHR | * Regional HR Advisor provides technical advice and support to UNDAF roll out countries
 | * Number of missions / trainings / meetings led by Regional HR Advisor
 | ibid.Preamble |

|  |
| --- |
| 1. **Strategic Approach (1) Promote a coherent results culture across the entire UN development system**
 |
| **Outputs** | **Lead** | **Role of Partners** | **Performance Indicators** | **QCPR** |
| 1. **UNDAF Results Monitoring**

Quality support and advice provided to the UNCTs in implementing and monitoring the UNDAF | PSG | * DOCO global guidance package shared with UNCTs
* PSG (CAs) follow up with UNCTs on SOPs implementation and other joint programming modalities
* RM and M&E frameworks reviewed in depth by PSG [and PSG support for Annual Review process codified]
 | * Number of UNCTs implementing the new SOPs (in consultation with or with support from UNDG AP)
* % of UNDAF RM and M&E frameworks that were reviewed in depth by the PSG (detailed feedback on individual Indicators) out of all UNDAF reviews
* % of UNDAF Annual Reviews held with PSG participation (on request)
* Number of Annual Review reports submitted / shared by the UNCT with the UNDG AP and other colleagues.
 | 134, 137-142, 164-171, 174182, |

|  |
| --- |
| **6. Strategic Approach (2) Ensure the functioning of the RC system as participatory, collegial and mutually accountable** |
| **Outputs** | **Lead** | **Activities** | **Performance Indicators** | **QCPR** |
| 1. **Oversight, performance appraisal and leadership development**

The Management & Accountability System fully implemented, with senior leadership engagements | UNDG AP Chair | * RCARs submission monitored and collected
* One80 roll-out monitored and reports collected for both RCs and UNCTs, and results analyzed
* UNDG AP’s annual RC/UNCT performance appraisal meeting organized, and results conveyed to RC/UNCTs
 | * % of RCs/UNCTs receiving quality feedback from by UNDG AP on their performances, 2012/2013 annual reports and/or 2013/2014 WP
* Effective roll-out of the One80 for the year 2013/2014 (with target of at least 80% average RC/UNCT completion rate of the One80 Full exercise)
 | 112, 122-124, 130 |

|  |
| --- |
| **7. Strategic Approach (3) Accelerate simplification and harmonization of business practices in conjunction with HLCM** |
| **Outputs** | **Lead** | **Role of Partners** | **Performance Indicators** | **QCPR** |
| 1. **Harmonization of business practices**

Quality support and advice provided to the UNCTs in implementing the recommendations from the UNDG-HLCM on harmonization of business practices, upon request | UNDG AP  | * DOCO to provide technical support as needed
* Status of HACT compliance in the region monitored
* Good practices and lessons learnt about business practice harmonization shared with UNCTs
 | * Number of UNCTs receiving advice or feedback from UNDG AP on business practice harmonization
* Percentage of eligible UNCTs that are HACT compliant
 | 152-163 |

|  |
| --- |
| 8. Strategic Approach (4) Foster effective partnerships |
| **Outputs** | **Lead** | **Role of Partners** | **Performance Indicators** | **QCPR** |
| 1. Coordination and cooperation among development partners strengthened
 |  |  |  |  |