## Updated AWP
AWP 2018 : Biogas Project - Promoting Production and Utilisation of Biogas from Agro-waste in South-Eastern Botswana ID:00098758, GEN:01
National Priorities & Goals | Vision 2036:
NDP10 MTR: Sustainable Management of Natural Resources; Pollution Prevention and Control; Climate Change/Global Warming
SDGs: GOAL 7 - Affordable and Clean Energy
Other SGDs contributing to: GOAL 11 - Sustainable Cities and Communities; GOAL12 - Responsible consumption and production and GOAL 13 - Climate Action, GOAL 2 - Promotes Sustainable Agriculture
SDGs Indicators:
SGDs Targets:
Outcome | Output | Indicators, baseline and targets | Activities | Implementing Partner | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Responsible UN Agency | Funding UN | Revised Budget
[5 empty] | J | F | M | A | M | J | J | A | S | O | N | D
Outcome 1.1: Increased capacity of Government, private sector and community stakeholders to develop, finance and implement PPPs in the agro-waste sector. | 1.1 Specific guidelines and standards on low-carbon alternatives and utilisation technologies for agro-waste and wastewater developed and disseminated to all relevant stakeholders in the sector. | Output indicator: Existence of guidelines and standards (on low-carbon alternatives) BL: None T(2019): draft guidelines and standards T(2020): Approved guidelines and standards | 1.1.1 Organise short workshops with sector experts to introduce new approaches on low carbon technologies for better guidelines and standards to be developed | PMU, DWMPC | [12 empty] | UNDP | 15000 | 0 | bar: Q1 F; Q2 A; Q2 J
|  |  | 1.1.2 Establish of a multi-stakeholder platform (MSP) to develop guidelines and standards for low-carbon alternatives and technologies for agro waste | PMU | [12 empty] | UNDP | 5000 | 0 | bar: Q2 M to Q3 S
| 1.2 Framework agreement for public-private partnerships (PPPs) in the waste sector adopted and disseminated. | Output indicator: Existence of Framework Agreement for public-private partnerships (PPPs) in the waste sector BL: None T(2019): draft Framework Agreement T(2020): Approved Framework Agreement | 1.2.1 Develop waste to energy PPP framework agreement for use in PPPs | PMU | [12 empty] | UNDP | 10000 | 8000 | bar: Q1 F to Q2 J
|  |  | 1.2.2 Invite waste to energy PPPs Experts from other countries to share latest developments/practices on waste management | PMU | [12 empty] | UNDP | 5000 | 5000 | bar: Q1 M; Q2 M; Q3 J; Q3 S; Q4 N
Outcome 1.2: Increased capacity of Government authorities to properly monitor and enforce waste management regulations in the agro-industrial sector. | 1.3 Training conducted for all relevant stakeholders on the new guidelines and PPP framework agreement | Output indicator 1: No. of people trained (public & private) BL: 0 T(2019): 20 T(2020): 40 Output indicator 2: Extent to which trained stakeholders are able to implement the guidelines and standards BL: Low (guidelines are yet to be developed) T(2019): medium T(2020): high NB: a score card for measuring utilization will be developed Output indicator 3: No. of stakeholders benefiting from PPP framework BL: 0 T(2019): 1 T(2020): 3 | 1.3.1 Meetings conducted to finalise MoU with Training Institute that will facilitate training and capacity development on PPPs. | PMU | [12 empty] | UNDP | 1000 | 0 | bar: Q1 J to Q1 F
|  |  | 1.3.2 Develop training materials on the new guidelines and waste to energy PPP framework agreement | PMU | [12 empty] | UNDP | 8000 | 0 | bar: Q1 F to Q2 J
|  |  | 1.3.3 Print training materials on the new guidelines and waste to energy PPP framework agreement | PMU | [12 empty] | UNDP | 5000 | 0 | bar: Q2 J to Q3 J
|  |  | 1.3.4 Conduct training on the developed PPP framework and guidelines | PMU | [12 empty] | UNDP | 7000 | 0 | bar: Q3 J to Q4 O
| Training conducted for training institution facilitators and masons for small scale digester construction | Output indicator 1: Existence of mason training curriculum BL: None T(2019): Draft curriculum T(2020): Approved curriculum Output indicator 2: No. of trained masons BL: 0 T(2019): 40 T(2020): 75 | Meetings conducted to finalise MoU with CITF to conduct training in biogas. | PMU | [12 empty] | UNDP | 1000 | 1000 | bar: Q1 J
|  |  | Develop curriculum for training masons on biogas digester construction, operation and maintenance of small scale digesters. | CITF, BITRI, PMU | [12 empty] | UNDP | 6000 | 6000 | bar: Q1 J to Q1 M
|  |  | Capacitate 40 masons to construct, operate and maintain small scale biogas digesters at CITF. | CITF | [12 empty] | UNDP | 28000 | 28000 | bar: Q1 F to Q4 N
|  |  | Facilitate training of CITF Instructors on construction, operation and maintenance of small scale digesters | CITF | [12 empty] | UNDP | 7000 | 7000 | bar: Q1 J to Q1 M
| Robust research undertaken for the biogas technology | Output indicator: No. of research projects on biogas BL: 0 T(2020): 5 research papers | Develop a research agenda on the biogas technology | BITRI | [12 empty] | UNDP | 2000 | 2000 | bar: Q1 J to Q1 M
|  |  | Undertake research on the technical, social and economic aspects of the technology | BITRI | [12 empty] | UNDP | 5000 | 3000 | bar: Q1 F to Q4 D
| 1.4 Updated regulations developed and adopted for the successful monitoring of effluent flows and by-product waste in all abattoirs in the country, including launch of a “green certification” waste management award for industry actors | Output indicator 1: Effluent regulations BL: draft Regulations T(2020): Approved Regulations Output indicator 2: Level of monitoring and enforcement of regulations BL: unsatisfactory T(2020): satisfactory NB: scorecard to be developed to measure the level of satisfaction Output indicator 3: Green certification framework in place BL: No T(2020): Yes | 1.4.1 Develop regulations and monitor effluent flows and by-product waste in all abattoirs | WUC | [12 empty] | UNDP | 10000 | 5000 | bar: Q2 A to Q3 A
|  |  | 1.4.2 Develop and pilot green certification protocol to be adopted by sector stakeholders. | PMU | [12 empty] | UNDP | 20000 | 2000 | bar: Q1 F to Q4 D
| 1.5 Support provided to the Department of Waste Management and Pollution Control (DWMPC) and District Council authorities to improve monitoring and enforcement of Trade Effluent Agreements between industries and local authorities | Output indicator: Level of monitoring and enforcement of TEAs BL: unsatisfactory T(2020): satisfactory NB: scorecard to be developed to measure the extent of monitoring and enforcement | 1.5.1 Capacitate DWMPC/WUC/Councils to monitor and enforce trade effluent agreements | DWMPC | [12 empty] | UNDP | 10000 | 7000 | bar: Q1 J to Q2 A
|  |  | 1.5.2 Support DWMPC/WUC/Councils activities that strengthen monitoring and enforcement of trade effluent agreements | DWMPC | [12 empty] | UNDP | 17000 | 10000 | bar: Q2 A to Q4 N
| 1.7 Corrective EIA measures implemented | Output indicator: Level of compliance to EIA measures during construction of biodigesters BL: None (dependent on construction of bio-digesters) T(2020): full compliance | 1.7.1 DWMPC and Councils to monitor the implementation of EIA through project visits. | PMU/DWMPC/DEA | [12 empty] | UNDP | 5000 | 0 | bar: Q2 A; Q2 J; Q3 A
Outcome 1.3: Autonomous support systems in place for replication and scale-up of agrowaste technologies post project | 1.9 Dedicated investment facilitation platform on low-carbon waste-utilisation technologies established at BITRI, and operational with independent budget | Output indicator: Existence of investment facilitation platform BL: No T(2020): Yes (at BITRI) | 1.9.1 Train Financing Institutions and Project stakeholders on agro-waste-to-energy projects to enhance best practices in assessing and financing agrowaste projects | PMU/BITRI | [12 empty] | UNDP | 30000 | 6000 | bar: Q1 M; Q2 M; Q3 J; Q3 S
|  |  | 1.9.2 Organize consultation workshops to identify options for the setting up of an investment-facilitation platform or similar structure. | PMU/BITRI | [12 empty] | UNDP | 10000 | 9000 | bar: Q1 J to Q4 D
| 1.10 Level playing field created for all energy providers and REFIT in place | Output indicator: REFIT tariffs BL: draft REFIT tariff guidelines T(2020): approved tariff guidelines | 1.10.1 Facilitate development and implementation of REFIT | BERA/PMU | [12 empty] | UNDP | 25000 | 25000 | bar: Q1 J; Q2 A; Q3 J; Q4 D
|  |  | 1.10.2 Engage REFIT Experts to share experiences from other countries on REFIT | BERA/PMU | [12 empty] | UNDP | 15000 | 10000 | bar: Q1 M to Q3 S
|  |  | Contractual Services -Individual (PM,PE &Admin) | PMU | [12 empty] | UNDP | 43000 | 43000 | bar: Q1 J; Q2 A; Q3 J; Q4 D
Total Outcome 1 | [17 empty] | 290000
Outcome 2.1: Increased investment in clean-energy | 2.1 Sensitisation campaign conducted with district councils, stakeholder and community groups in targeted biogas plant sites | Output indicator 1: No sensitisation campaigns BL: 0 T(2019): 15 T(2020): 30 (2 per sub-district) Output indicator 2: Level of awareness BL: low T(2019): medium T(2020): high | 2.1.1 Raise awareness on biogas production and utilisation, employment opportunities, agriculture and energy use. | PMU | [12 empty] | UNDP | 22000 | 22000 | bar: Q1 F to Q4 D
| 2.2 Feasibility study undertaken for small-scale biogas digester component | Output indicator: Existence of knowledge product on feasibility biogas BL: pre-feasibility study report T(2020): feasibility study report | 2.2.1 Undertake market/feasibility study for small scale digesters. | PMU | [12 empty] | UNDP | 64000 | 40000 | bar: Q1 J to Q2 A
| 2.3 Business plan developed for the three potential medium-scale biogas sites near agro-industrial plants with potential off-take uses analysed. | Output indicator: No. business plans for medium-scale biogas sites BL: 0 T(2019): 1 T(2020): 3 | 2.3.1 Develop business plans for potential sites identified for medium sized digesters (3 per site). The most suitable proposal will be selected by PPPs to undertake a complete feasibility study. | PMU | [12 empty] | UNDP | 15000 | 0 | bar: Q1 J; Q2 A
|  |  | 2.3.2 Advert made for Consultants (international and local) to develop business plans at the three sites. | PMU | [12 empty] | UNDP | 2000 | 2000 | bar: Q1 J; Q2 A
|  |  | 2.3..3 Consultants or technology providers identified to perform feasibility study for each of the 3 medium sized digesters. | PMU | [12 empty] | UNDP | 45000 | 45000 | bar: Q2 A; Q3 J
| 2.5 Environmental impact assessment of selected biogas sites completed | Output indicator: No of EIA for Medium Scale biogas sites BL: 0 T(2019): 1 T(2020): 3 | 2.5.1 EIAs conducted for each medium sized digester site in line with Government policy. | PMU | [12 empty] | UNDP | 30000 | 15000 | bar: Q3 J; Q4 O
| 2.7 Legal establishment of biogas operators based on public-private partnerships and concessional agreements with chosen agro-industrial partners (including guaranteed supply of substrate and purchase agreement for supply of biogas). | Output indicator: No of legally registered Biogas Operators BL: 0 T(2019): 1 T(2020): 2 | 2.7.1 Facilitate establishment of PPPs and capacitate partners on the PPP model when required. | PMU | [12 empty] | UNDP | 12000 | 0 | bar: Q1 F; Q2 A; Q3 J
|  |  | 2.7.2 Prepare and develop sample PPP contracts and incorporate best practices from similar projects | PMU | [12 empty] | UNDP | 10000 | 0 | bar: Q1 M; Q2 M; Q3 A; Q4 O
| 2.8 Technology agreement signed on North-South or South-South cooperation with selected international biogas equipment providers | Output indicator: No of (Mid-scale) Technology Agreements BL: NS - 0 SSC - 0 T(2020): NS - 2 SSC- 1 | 2.8.1 Facilitate the signing of medium sized biogas construction agreements and support negotiations where required. | PMU | [12 empty] | UNDP | 2000 | 0 | bar: Q3 J; Q4 O
| Construction and commissioning of small scale biogas plants | Baseline:0 Indicator: Number of biogas digesters constructed and in use. Target:28 | Construct 28 small scale digesters for demonstration of the technology in all sub districts (2 per sub district) | PMU | [12 empty] | UNDP | 50000 | 50000 | bar: Q1 J to Q2 M
|  | Baseline:0 Indicator: Number of biogas digesters constructed and in use. Target:300 | Facilitate monitoring construction of 300 small scale biogas plants, ensure commissioning and operation. | PMU | [12 empty] | UNDP | 5000 | 0 | bar: Q2 A to Q4 D
| 2.9 Construction and commissioning of medium scale biogas plants | Output indicator: No. of operational biogas plants (medium-scale) BL: 0 T(2019): 1 T(2020): 3 | Facilitate monitoring the construction of 3 medium scale biogas plants, ensure commissioning and operation. | PMU | [12 empty] | UNDP | 5000 | 0 | bar: Q1 F to Q4 N
| Contractual Services -Individual (PM,PE &Admin) |  |  | PMU | [12 empty] | UNDP | 65000 | 65000 | bar: Q1 J to Q4 D
Total Outcome 2 | [17 empty] | 327000
Outcome 3: Increased investment in less GHG-intensive energy systems using biogas. | 3.1 Partnership established between biogas plant operators and selected district councils for supply and purchase of biogas from the plants | Output indicator: No. of partnership on biogas sales BL: 0 T(2019): 1 T(2020): 3 | 3.1.1 Facilitate meetings with operators, councils, BERA, BPC and other stakeholders to forge agreements on purchase of biogas | PMU | [12 empty] | UNDP | 7000 | 1000 | bar: Q1 J; Q2 A; Q3 J; Q4 D
|  |  | 3.1.2 Facilitate capacity building on utilization of biogas (technical and financial) within the partnership forged between stakeholders | PMU | [12 empty] | UNDP | 12000 | 0 | bar: Q2 A; Q3 J; Q4 D
| 3.2 District council staff trained on the biogas-utilisation technologies selected for investment, including operations and maintenance | Output indicator: No. stakeholders trained BL: 0 T(2019): 10 (BMC) T(2020): 30 (inclusive of other stakeholders to be identified) | 3.2.1 Facilitate training of stakeholders implementing medium sized digesters on the technology/design selected used. | PMU | [12 empty] | UNDP | 10000 | 10000 | bar: Q2 A; Q3 J; Q4 D
|  |  | 3.2.2 Develop and print gender-sensitive training materials to be used to train male and female masons. | PMU | [12 empty] | UNDP | 8000 | 2000 | bar: Q2 A; Q3 J; Q4 D
| Contractual Services -Individual (PM,PE &Admin) |  |  | PMU | [13 empty] | 37000 | 37000 | bar: Q1 J to Q4 D
Total Outcome 3 | [17 empty] | 74000
Project Management | Travel |  |  | PMU | [13 empty] | 9000 | 9000 | bar: Q1 J; Q2 A; Q3 J; Q4 D
| Supplies |  |  | PMU | [13 empty] | 8000 | 8000 | bar: Q1 J; Q2 A; Q3 J; Q4 D
| Direct project costs |  |  | PMU | [13 empty] | 7650 | 7650 | bar: Q4 D
Total Project Management | [17 empty] | 24650
Project Budget Total | [17 empty] | 715650 | 490650

## Original AWP
AWP 2017 : Bio-Methane Project - Promoting Production and Utilisation of Biogas from Agro-waste in South-Eastern Botswana
Results Group: Environment and Climate Change Report
National Priorities & Goals
NDP10 MTR: Sustainable Management of Natural Resources; Pollution Prevention and Control; Climate Change/Global Warming
MDGs: Ensure Environment Sustainability: Eradicate Extreme poverty and hunger
Activity outputs/result | Indicators, baseline and targets | Activities | Implementing Partner | Q1 | Q2 | Q3 | Q4 | TOTAL EXP
Outcome 1.1: Increased capacity of Government, private sector and community stakeholders to develop, finance and implement PPPs in the agro-waste sector. | Baseline: Indicator: Target: | Establishment of a multi-stakeholder platform (MSP) to define guidelines and standards (national level); regular stakeholder meetings. | PMU, Gov - Ips |  | x | x |  | 2000
| Baseline: Indicator: Target: | Organise short workshops with sector experts to introduce new approaches and technologies | PMU |  | x | x |  | 1000
| Baseline: Indicator: Target: | Study tours in Botswana and to an African country (Ethopia/Kenya/Tanzania) that has been successful in developing the biogas sector. | PMU/BITRI |  |  | x |  | 14000
| Baseline: Indicator: Target: | Key stakeholders facilitate MSP at district level. | PMU |  |  | x |  | 1000
| Baseline: Indicator: Target: | Workshop and follow-up meetings to identify framework agreement. | PMU |  |  | x |  | 500
Outcome 1.2: Increased capacity of Government authorities to properly monitor and enforce waste management regulations in the agro-industrial sector. | Baseline: Indicator: Target: | A training institute is identified and contracted to facilitate training and capacity development. | PMU |  | x | x |  | 500
| Baseline: Indicator: Target: | Establishment of MSP for regulations and monitoring. | PMU |  | x | x |  | 400
| Baseline: Indicator: Target: | Contractul Servises -Individual (PM,PE &Admin) | PMU |  | x | x | x | 25400
| Baseline: Indicator: Target: | Project Vehicle | PMU |  | x |  |  | 43000
Outcome 2.1: Increased investment in clean-energy | Baseline: Indicator: Target: | A series of meetings is organised to provide information on the pros and cons of biogas, as well as opportunities for employment and agriculture and energy use. | PMU |  | x | x |  | 5000
| Baseline: Indicator: Target: | Consultants (international) identified to perform market study. | PMU |  |  | x |  | 30000
| Baseline: Indicator: Target: | Consultants ( local) identified to perform market study. | PMU |  |  | x |  | 20000
| Baseline: Indicator: Target: | Consultants or technology providers identified to perform feasibility study. | PMU |  |  | x |  | 15000
| Baseline: Indicator: Target: | EIAs conducted for medium scale digesters in line with Government policy | PMU |  | x | x |  | 50000
| Baseline: Indicator: Target: | Procure Part time Biogas Digester Expert | PMU |  | x | x | x | 10000
| Baseline: Indicator: Target: | Contractul Services -Individual (PM,PE &Admin) | PMU |  | x | x | x | 50800
| Baseline: Indicator: Target: | Project Vehicle | PMU |  | x |  |  | 37000
Outcome 3: Increased investment in less GHG-intensive energy systems using biogas. | Baseline: Indicator: Target: | Facilitate meetings with operators, councils and other stakeholders to forge partnerships. | PMU |  | x | x |  | 5000
| Baseline: Indicator: Target: | Technical and financial advice on utilisation of biogas within the partnership. | PMU |  | x | x |  | 3500
| Baseline: Indicator: Target: | Identify training institute to conduct training in biogas | PMU |  | x | x |  | 0
| Baseline: Indicator: Target: | Identify and contract consultant/technology providers to conduct feasibility study. | PMU |  | x | x |  | 7000
| Baseline: Indicator: Target: | BITRI and project office to ensure quality of feasibility study and its relevance to local context through screening of proposals. | PMU |  |  |  |  | 0
| Baseline: Indicator: Target: | Contractual Services (PM,PE&Admin) | PMU |  | x | x | x | 38100
Project Management | Baseline: Indicator: Target: | Information Technology Equipment | PMU |  | x |  |  | 10000
| Baseline: Indicator: Target: | Travel | PMU |  | x | x | x | 6000
| Baseline: Indicator: Target: | Direct project Cost | PMU |  | x | x | x | 7120
|  | Total | [5 empty] | 382320
5180