# Basic Project Information

| Project Title: |
| --- |
| UNDP Award ID | PIMS 3675 |
| UNDP Project ID | 3091 |
| CRIS Contract Number |  |
| Project Duration | May, 2010-April, 2015 |
| Reporting Period | January,2012-December,2012 |
| Total Approved Project Budget | USD7,000,000 |
| Participating UN agencies |  |
| Implementing Partners/ National collaborating agencies | Ministry of Agriculture of People`s Republic of China |
| International collaborating agencies |  |
| Cost-sharing third parties |  |
| UNDP Contact officer | Shijun LIU |
| Project website | www.mtebrb.org |

# Executive Summary

- Summarise the report (<500 words), highlighting

- key outcomes,

- management issues,

- and management recommendations.

- Shorter reports may not require an Executive Summary.

The report covers the overall project implementation in 2012, including implementation environment, main activities, outputs, outcomes, main measures taken to enhance project sustainability and development efficiency, preliminary macro impacts, project management (financial management, monitoring and evaluation, human resource management, risk management, inter-agency coordination and communication), etc. Besides, on basis of experiences and lessons learnt from the project implementation in 2012, the report has also proposed recommendations to UNDP with regard to general management of GEF/UNDP projects.

The project progress generally met the requirements of the work plan with activities carried out in full swing and the delivery rate of 79.2%. According to the project progress at present, the project is expected to accomplish all intended outcomes by completion as designed in ProDoc. During the reporting period, the project made breakthroughs in developing sustainable information dissemination mechanism, promoting market transformation policy system synthetically. The project has also made innovative institutional arrangement in 2012.

# 1. Background

## Development Context

- Provide a brief assessment (<250 words) of the development context, including

- development challenges;

- relevant Chinese policies/priorities;

- institutional context;

- and operational environment.

- Note any significant contextual changes since the beginning of project/ last annual report.

China has exceeded US as the world’s biggest energy consumer and top GHG emission country. Energy consumed in building sector in China takes up 30% of the total energy consumption, with rural area accounting for over 50% of the nation’s building market. Therefore, huge potential of energy saving exists in China’s rural area that lags much behind the urban area in energy efficiency in building sector.

Implementation of this project experiences both good opportunities and harsh challenges. On the one hand, as one of the focal areas of the energy saving and GHG emission reduction (ESER) act imposed by the Chinese government, energy efficiency in building sector has acquired great attention from the government. By end of 2012, with great support from related international organizations (such as GEF/UNDP EUEEP projects), energy efficient (EE) building standards have been continued by the Chinese government on newly constructed urban buildings, and also in advancing progress in existing urban buildings. Besides, improvement of living conditions for rural residents is also one focus of the governmental Socialism New Rural Construction campaign. On the other hand, Chinese government has paid more attention to application and extension of EE brick and EE building in rural areas and is ready to carry out related works. The obstacles and challenges faced by application and extension of EE bricks and rural EE buildings differ from those in urban area. Practical long-term mechanisms of information, policy, financing and technology shall be established in rural area to popularize applicable EE bricks and EE building techniques that can be extensively recognized and accepted by farmers and the rural market. This is the biggest challenge faced by the project.

## Project Objectives and Strategy

- Provide a brief description (<250 words) of the project, assuming the reader has no prior knowledge.  
Consider the following questions:
	What are the objectives of the project?
	How is the project relevant to the development priorities of the Chinese government, UNDP 	and, if appropriate, other partners? Why is UNDP involved in this sector?
	Who are the beneficiaries of the project? 
	What strategy, approaches and modalities are being used to deliver the project?

The objective of the project is to promote energy efficiency and greenhouse gas (GHG) emission reduction in rural brick-making industry and residential/commercial building sector through such technical assistance activities as information dissemination, policy development, financial support, technology demonstration and replication so as to remove the barriers that persistently hinder the development and application of EE bricks and EE buildings in rural China.

The project will carry out targeted capacity building activities through technical assistance, to 1) support and promote acts such as the governmental Socialism New Rural Construction campaign and energy saving in building sector 2) facilitate the MDG requirement of ‘Ensure Environmental Sustainability’; 3) contribute directly to UNDAF Outcome 1  (Government institutions and other stakeholders ensure environmental sustainability, address climate change, and promote a green, low carbon economy )  and  Outcome 3（China`s enhanced participation in the global community brings wider mutual benefits）.

Farmers in China that take up over 50% of the total population are the direct beneficiaries of this project. Besides, this project will also build the capacity of other stakeholders (countryside enterprises, local governments, financial institutions, technical service providers, etc.) and further improve related regulations and policies of the Chinese government.

# 2. Key Results

- In 1-2 paragraphs (<250 words) introduce this section.  Make a judgement as to how the project is progressing in relation to expected high-level objectives/outcomes. 
Consider the following questions:
	Overall, is progress on track or not?  
	Is the project achieving the outcomes expected at this stage and is it likely to achieve its 	intended outcomes by completion?  
	Is there evidence at this stage of the project’s contribution to any higher-level objectives (of the 	project or more broadly of UNDP/Chinese government)?

- You may also wish to use these introductory paragraphs to highlight key issues discussed elsewhere in this section (ie relating to sustainability, MDG goals, cross-cutting issues).

The project progress generally met the requirements of the work plan with activities carried out in full swing and the delivery rate of 79.2%. According to the project progress at present, the project is expected to accomplish all intended outcomes by completion as designed in ProDoc. During the reporting period, the project made breakthroughs in developing sustainable information dissemination mechanism, promoting market transformation policy system synthetically. The project has also made innovative institutional arrangement in 2012.

During the reporting period, activities were carried out in the following aspects:

- Information dissemination: 1) Continued with construction of EE bricks and EE buildings information systems; 2) Continued footage shot for the advocacy and training films; 3) Various information dissemination activities were extensively carried out ( including workshop on project demonstration outcomes, project column in a journal, EE wall materials museum, project trainings, etc.)

- Policy improvement: National Standards of Fired Perforated Bricks/Blocks (GB13544-2011) supported by the project was formally promulgated on April 1, 2012. It stated that only perforated bricks/blocks with rectangle cores were qualified products, which means that market access of EE bricks and market elimination system of traditional wall materials were initially established. 2) Conducted studies on financial and tax policy of rural EE buildings application and replication. The policy proposal of “supporting EE brick sand rural EE buildings with wall material reformation funds” was submitted to MoF. 3) Standard system of EE bricks and rural EE buildings was initially established. 4) Application and replication of rural EE buildings was integrated into the 12th Five-Year Plan of the Xianyang construction department. The Management Rules of New Wall Materials Application and Energy Efficiency of Buildings of Xianyang City were issued.

- Financial support: 1) Accomplished assessment on financing capabilities of pilot brick makers and financial institutes; 2) Studied and designed the financial incentive mechanism on rural EE buildings and initially applied in demonstration sites construction.

- Technical demonstration and capacity building:1) Construction of EE brick factories: 9 pilot brick factories have started to produce EE bricks meet the project requirements; 2) construction of demonstration EE buildings is in full swing: planning and design has almost been completed; construction of demonstration buildings is expected to complete in 2013; demonstration EE buildings in Xianyang, Shaanxi province was completed and residences already moved to the new houses; 3) Replication of EE bricks and EE buildings in rural area was initially started: on the basis of extensive studies and consultancy of experts, design of general replication plan and institutional arrangement has been initially completed; Replication activities started first in Shaanxi and Sichuan with better demonstration basis and faster progress. Screening of replication sites and the design of replication plan in Shaanxi have been completed. Screening of replication sites and the design of replication plan in Sichuan is ongoing. The construction of some replication sites has started. 4) Technical support: Training materials of EE bricks and EE buildings have been developed; M&E of demonstration EE buildings and EE brick factories has been started based on the M&E method developed by the project.

The number of activities and outcomes in information dissemination, policy development and demonstration sites construction were much more than the original design of the project document.

## Project Outcomes

- This section should assess progress in the reporting period against each of the project’s expected outcomes. For each outcome, identify key factors accounting for progress/lack of progress.  Identify any problems and discuss what steps are needed to rectify them.  Identify any expected outcomes that seem unclear or realistic, and discuss what action is needed to develop more appropriate objectives.

- Include results that were not planned for, if they demonstrate important achievements.  For example, replication into government and other programs can be an important sign of development impact.  Also note any negative unplanned outcomes.

- Even in the early stages of project implementation, your assessment should focus on achieving development outcomes, not just on delivering outputs.  If there is not much to say, then keep it brief!

Progress and accomplishments at outcome level in 2012

| Component 1: Information Dissemination and Awareness Enhancement |
| --- |
| Indicator | Target | Progress and Accomplishments |
| 1) Establishment of information dissemination networks on EE bricks and EE buildings by the third year; 2) The number of multimedia products that are developed and disseminated from the 3rd year; 3) The number of promotion activities ever conducted by the end of the project; 4) The number of people involved in information dissemination and awareness enhancement activities from the start of this project | 1) The network is expected to operate from the 3rd year; 2) 5个; 3) 1个; 4) at least 1 million person time | 1）reviewed the system software on EE bricks and rural EE buildings; signed subcontracts of EE bricks and rural EE buildings information system construction; organized experts to review and assess the workplans of the subcontractors; the networks will be put into operation as planned 2）Footage has been collected for project films as planned; relevant outcomes will be completed in time 3）Jointly held the International Forum of Energy Efficiency and Emission Reduction in Brick & Tile Industry and MTEBRB Project Promotion Workshop with China Brick & Tile Industry Association. Around 400 international and national participants from brick & tile industry attended the meeting and visited the project demonstration factory and EE buildings; Cooperated with the Building Council of Shanxi Province and Xianyang City, a wall material exhibition room was built, which works as a new and sustainable information dissemination platform for EE bricks and rural EE buildings; Cooperated with the journal of Agricultural Engineering Technology—New Energy Industry, a project publicity column has been developed to disseminate project progress and technologies of EE brick and rural EE building in time. 4）This number should be accumulated number from the beginning of the project. The tracking and recording has started |
| Component 2: Policy Development and Institutional Support |
| Indicator | Target | Progress and Accomplishments |
| 1) Upon the completion of this project, the number of policy proposals that are taken into the national EE building and rural development 2) Upon the completion of this project, the number of approved rural EE building standards and codes; 3) Upon the completion of this project, the number of local governments that take the EE building and EE brick production into their local development plan; | 1)one; 2) at least one 3) at least ten | 1）Conducted studies on financial and tax policy of rural EE buildings application and replication. Policy proposal of “supporting EE brick sand rural EE buildings with wall material reformation funds” was submitted to MoF. 2）National Standards of Fired Perforated Bricks/Blocks (GB13544-2011) supported by the project was formally promulgated on April 1, 2012. It stated that only perforated bricks/blocks with rectangle cores were qualified products, which means that market access of EE bricks and market elimination system of traditional wall materials were initially established; standard system of EE brick and rural EE building were initially established 3）Application and replication of rural EE buildings was integrated into the 12th Five-Year Plan of the Xianyang construction department. The Management Rules of New Wall Materials Application and Energy Efficiency of Buildings of Xianyang City were issued. |
| Component 3: Financial Support & Accessibility Improvement |
| Indicator | Target | Progress and Accomplishments |
| 1) The number of financial institutions involved in this project by the end of this project; 2) the total amount of fund leveraged to the rural EE building construction and EE brick project | 1) at least 40 institutions; 2）at least RMB50m | 1）Accomplished assessment on financing capabilities of pilot brick factories and financial institutes； 2）The demonstration progress in 2012 indicated that the achievement will be well beyond the expectations of the ProDoc |
| Component 4: Demonstration and Technology Support |
| Indicator | Target | Progress and Accomplishments |
| 1) the number of EE brick factories in rural areas upon the completion of this project 2)by the end of this project, the total output of EE bricks in rural areas; 3) the total number of EE buildings in rural areas by the end of project; | 1) at least 28 enterprises; 2) at least 1.4 billion standard bricks; 3) at least 1760 EE buildings being built | 1）Number of demonstration EE brick factories has already exceeded the planned number in ProDoc, with the total number still yet to be identified according to the project replication at latter phase; 2）Related targets will be reached as planned 3）Related targets will be reached as planned |

## Activities and Outputs

Activities and outputs in 2012

| Output 1.1 Establishment and operational of information dissemination network |
| --- |
| Indicator | Annual Targets | Activities and Accomplishments |
| 1) Establishment of the information networks on EE bricks and EE buildings 2) Since the third year, at least 76 stakeholders have ever used this information network 3) Since the third year, the No. of annual visit to this website is at least 10,000 | information networks of EE bricks and rural EE buildings are established and start to operate | reviewed system software on EE bricks and rural EE buildings organized experts to review and assess the workplan of the subcontractors; the networks will be put into operation as planned click rate of the project website reached the requirements |
| Output 1.2: Development of a full package of multi-media products |
| Indicator | Annual Targets | Activities and Accomplishments |
| 1) from the 3rd year, at least 2 sets of CDs developed and 1000 copies each have been distributed 2) 2 sets of books/training materials will be disseminated 3) At least one audio program will be produced and broadcasted in the rural broadcasting network | Completion of the film of EE bricks; start the production of the film of rural EE buildings | material collection of the media products related to Indicator 1) has been finished; EE brick film will be completed in 2013 the training materials have been developed; Annual targets have been reached and the objectives of this output will be achieved as planned in the ProDoc. |
| Output 1.3: Completed promotion and advocacy program |
| Indicator | Annual Targets | Activities and Accomplishments |
| 1) Since the first year, at least 100 villages in 20 counties of 10 provinces will be covered by this project 2) Since the third year, at least 500 field missions to pilot and replication sites will be conducted 3) By the end of the project, 6 project promotion workshops have been conducted | complete the construction of Shaanxi wall material museum (EE brick part) | Jointly held the International Forum of Energy Efficiency and Emission Reduction in Brick & Tile Industry and MTEBRB Project Promotion Workshop with China Brick & Tile Industry Association. Around 400 international and national participants from brick & tile industry attended the meeting and visited the project demonstration factory and EE buildings Cooperated with the Building Council of Shanxi Province and Xianyang City, a wall material exhibition room was built, which works as a new and sustainable information dissemination platform for EE bricks and rural EE buildings. Cooperated with the journal of Agricultural Engineering Technology—New Energy Industry, a project publicity column has been developed to disseminate project progress and technologies of EE brick and rural EE building in time. the component and number of information dissemination activities carried out by the project were beyond requirements of the ProDoc |
| Output 2.1 Formulated policies, and associated implementing rules on EE building materials production and utilization |
| Indicator | Annual Targets | Activities and Accomplishments |
| 1) By the end of the project, study on relevant policy being conducted at least once 2) By the end of the project, at least one activity being conducted to facilitate the approval of policy 3) By the end of the project, at least one policy developed under this project being recommended or approved by the government | 1）accomplish formulation of relevant technology standards and application guidelines 2）accomplish an international study tours on relevant policies and practices | National Standards of Fired Perforated Bricks/Blocks (GB13544-2011) supported by the project was formally promulgated on April 1, 2012. It stated that only perforated bricks/blocks with rectangle cores were qualified products, which means that market access of EE bricks and market elimination system of traditional wall materials were initially established Standard system of EE bricks and rural EE buildings was initially established, technology standards that completed and promulgated will be more than designed by the ProDoc Conducted studies on financial and tax policy of rural EE buildings application and replication. Policy proposal of “supporting EE brick sand rural EE buildings with wall material reformation funds” was submitted to MoF. the international study tour was postponed to 2013 according to the actual needs |
| Output 2.2：Improved local governments` policy enforcement capacity and implemented action plans |
| Indicator | Annual Targets | Activities and Accomplishments |
| 1) 8 times By the end of the project, capacity building activities (including training materials) being conducted: 8 times 2) By the end of the project, at least 200 local officials being trained 3) By the end of the project, the No. of policies and action plans formulated and implemented under this project will reach 10 | accomplish the formulation of local government`s action plans | guideline of the local government`s action plan was drafted and reviewed Application and replication of rural EE buildings was integrated into the 12th Five-Year Plan of the Xianyang construction department. The Management Rules of New Wall Materials Application and Energy Efficiency of Buildings of Xianyang City were issued. |
| Output 3.1:Completed Financial and Business Development Assessments for Rural Brick Makers and Building Developers; and public the assessment |
| Indicator | Annual Targets | Activities and Accomplishments |
| 1) The minimum No. of local building developers and brick makers trained under this project: 200 2) The minimum No. of completed financing and business plans: 60 | Completion of the development of business plans for 9 pilot EE brick makers | Development of business plan of the demonstration brick makers at 9 pilot sites was completed |
| Output 3.2：Developed and Implemented New Business Models for Local Banks and Financial Institutions for Financing EE Brick Making and EE Buildings Projects in Rural Areas |
| Indicator | Annual Targets | Activities and Accomplishments |
| 1) By the end of the project, the minimum No. of information exchange and knowledge sharing activities conducted : 5 2) By the end of the project, at least 100 people in local financial sectors being involved in or trained under this project | Completion of assessment on the financing and finance incentive mode | Accomplished assessment on financing capabilities of pilot brick makers and financial institutes; developed study and design of financing incentive mechanism on rural EE buildings and initially applied in the construction of demonstration project |
| Output 4.1：Completed demonstration of rural EE buildings and EE bricks production |
| Indicator | Annual Targets | Activities and Accomplishments |
| 1) By the end of third year, the No. of conducted feasibility studies: at least 9 feasibility studies on EE bricks production and 8 feasibility studies on EE buildings 2)By the end of third year, the No. of EE building projects and EE brick making projects that can reach the energy efficient goals: 8 EE brick making projects, 8 EE building projects 3)By the end of the third year, the No. of information dissemination activities: at least once | 1) Completion of Planning of Village and Township Development and Energy Efficiency and Emission Reduction for 9 pilot sites.； 2）Completion of reform of brick-making techniques for 3 pilot brick-making plants； 3）launch construction of EE buildings at 10 pilot sites； | Energy efficiency and emission reduction plans for most of the demonstration villages were completed. Up to now, all demonstration brick making factories have the ability of volume production of EE bricks selected by the project (the demonstration factory in Gansu has successfully produced EE bricks since April 2012) .Revised the construction plans of the EE buildings in Changde, Hunan Province, Nongan, Jilin Province, Pinghu, Zhejiang Province and Pengshan, Sichuan Province. The construction of demonstration EE buildings is in full swing and is expected to complete in 2013. Demonstration EE buildings in Xianyang, Shaanxi Province have been completed and residents have moved in. The annul targets have been achieved, with the indicators expected to be met as designed in ProDoc (the number of demonstration sites will be more than originally designed). Besides, energy efficiency and emission reduction plans are additional outputs which will improve the project sustainability |
| Output 4.2: Developed and disseminated technical guidelines and templates for the development and implementation of rural EE brick and EE building applications |
| Indicator | Annual Targets | Activities and Accomplishments |
| 1) The No. of reports on lessons learnt and experience of rural EE building and EE brick making projects at home and abroad: 2; 2) The No. of feasibility study report on the EE brick product standardization: 1; 3) One data base on rural EE building information being established and relevant report being submitted; 4) The No. of information dissemination activity: 1; 5) The No. of training materials on rural EE brick and EE building technology: at least 2 sets; 6) The No. of trainees at the end of the project: 200 | 1) Develop and printed training materials of EE bricks and EE buildings; 2) Organize 1 Experience Exchange Meeting on Project Demonstration and Forum of Development, Application and Energy Efficiency and Emission Reduction of New-Type Energy Efficient Wall and Roof Material s | Developed and printed training materials of EE brick and EE buildings Successfully organized ‘National Energy Conservation High-Level Forum & Project of Market Transformation of Energy Efficient Bricks and Rural Buildings Promotion Conference’, with over 400 representatives from brick & tile industries in and out of China taking part in the meeting and visit the pilot brick-making plant and EE buildings of the project. Besides activities designed in the ProDoc, subcontracts for studying of M&E of the energy efficiency of the rural EE buildings and EE bricks were awarded to technical institutes through bidding. Investigation and study of M&E methodologies in and out of China and their effects were carried out. M&E methodologies targeted at rural areas in China were designed and developed , with an implementation plan designed and trainings carried out to related staff at pilot sites; The annul targets have been achieved; with the indicators expected to be met as designed in ProDoc (some of the indicators have been achieved). Besides what have been designed in ProDoc, the project has also designed and carried out M&E of the energy efficiency of EE bricks and rural EE buildings in order to further identify demonstration effects and increase possibilities for replication and the sustainability of project outcomes. |
| Output 4.3：Construction of replication sites |
| Indicator | Annual Targets | Activities and Accomplishments |
| 1) No. of evaluation reports of the demonstration projects at the end of the project: 16 ; 2) the Number of the replication projects constructed at the end of the project: 60 | Selection of project replication sites being carried out | Initially designed the replication plan Replication in Shaanxi and Sichuan has started: the replication plan of Xianyang, Shaanxi Province was initially designed Screening of replication sites and implementation plan in Chengdu, Sichuan Province is under developing, and the construction in Qionglai has started |

## Sustainability

- (<250 words) Describe what measures were taken in the reporting period to promote the sustainability of the project.  How confident is UNDP at this stage that any benefits/changes the project is generating will endure? Are specific constraints to sustainability of the activity identified and being addressed?

To secure the project sustainability, attention must be paid on integration of and balance between the bottom-up micro-effects and top-down macro-system and impacts during project implementation. First, as the most important stakeholder, farmers focus on real effects and benefits. To ensure the sustainability, real effects and benefits must be generated and acknowledged by farmers to encourage their spontaneous application. On the other hand, as it is a cross-sector, trans-industry and interdisciplinary mission to develop EE bricks and rural EE buildings, a comprehensive and long-term system and mechanism must be established to make the project sustainable.

The marketization of EE bricks and rural EE buildings is a dynamic and inevitable development progress with many stages (adoption, scaling-up and mainstreaming of the technologies). As the intervention of the project is a systematic intervention at all dimensions throughout the whole progress of the marketization, the project shall not only carry out activities at the micro level, but also pay attention to comprehensive establishment of a sustainable marketization mechanism (information, policy, financing mechanism, etc.).

Measures taken in developing the top-down macro-system in 2012 include:

- Policy support system:  1) National Standards of Fired Perforated Bricks/Blocks (GB13544-2011) supported by the project was formally promulgated on April 1, 2012. It stated that only perforated bricks/blocks with rectangle cores were qualified products, which means that market access of EE bricks and market elimination system of traditional wall materials were initially established; 2) Conducted studies on financial and tax policy of rural EE buildings application and replication. Policy proposals of “supporting EE brick sand rural EE buildings with wall material reformation funds” were submitted to MoF; 3)Standard system of EE bricks and rural EE buildings was initially established; 4) Application and replication of  rural EE buildings was integrated into the 12th Five-Year Plan of the Xianyang construction department. The Management Rules of New Wall Materials Application and Energy Efficiency of Buildings of Xianyang City were issued.

- Financial incentive mechanism: The project studies showed that financial incentive mechanisms are commonly adopted both in and out of China as a successful tool to promote EE buildings in the market and encourage users’ preference in EE buildings.  In order to explore applicable subsidy models in rural areas, related study was conducted and subsidy plans were designed. The plans has been implemented in the demonstration sites and will be improved after assessment;

- Information dissemination mechanism at multi channels: 1) Continued with establishment of the information systems of EE bricks and EE buildings; 2) Carried on with footage shooting for development of the project propaganda and training films; 3) Widely carried out various information dissemination activities (including project demonstration outcomes promotion workshop, project columns in journals, exhibition room of EE wall materials, project technical training, etc.)

## MDG Targets

- (<250 words) Assess how the project is contributing to relevant MDG targets.

- Note: This section may not be required if the project’s contribution to specific MDG target/s is obvious and has already been addressed elsewhere.

As mentioned in section 1, the project implementation will facilitate MDG7 “Ensure Environmental Sustainability”.

The project implementation will also facilitate MDG8 “Develop a global partnership for development”. Based on the experience from GEF/UNDP TVE project, as a pioneer in energy conservation and emission reduction (ECER) among developing countries, the practice of China in technology, policy and mechanism is typical and replicable in other developing countries. For example, the energy efficiency brick manufacturing technologies in the TVE project were widely promoted in South Asia and Southeast Asia via bilateral and multilateral cooperation, such as GEF and UNDP. As the first practice of applying EE buildings in rural areas of a developing country, the project is valuable in demonstration not only in China, but also all over the world. In order to further promote the experience of TVE project, to expand the impacts of GEF/UNDP funds and to contribute to MDG of “Develop a global partnership for development”, the project designed the following contents: 1) The project will develop bilingual films for promotion and technical trainings and share via the project website and GEF/UNDP regional offices; 2) Information dissemination and knowledge sharing events will be organized in 2013 with the participation of multilateral agencies and developing countries. Practical experiences, technologies, service providers and resources, project developing and management resources will be shared and more stakeholders will be reached through participants, thus the project will establish a sustainable global partnership and contribute to South-South cooperation in ECER.

## Partnership Effectiveness

- (<250 words) Comment on the extent to which the project is consistent with the principles of development effectiveness. Describe the significance of project partnership, reflecting mutual ownership and accountability, coordination/collaboration with other local, national and/or international agencies working in the similar sector beyond the project partnerships etc.

The main indicators for measuring development effectiveness are relevance, performance and success. Success relies on impact, sustainability, contribution to capacity building, etc.

- Relevance: The progress in 2012 well proved that the project objectives and activities are in line with and have promoted the nationals targets and campaigns and effectively contributed to MDG and UNDAF.

- Performance: It is too early to evaluate the performance via results and efficiency at this stage, but so far the project implementation result is positive. In addition to the 18 replication sites promised in PPG, the project added 60 replication sites without increasing the budget. Based on the implementation in 2012, it is practical though challenging (number of pilot projects and sites all exceeded ProDoc. design). This will greatly increase the ECER amount and improve the efficiency of GEF funds.

- Impact: the project focuses not only on the bottom-up micro results such as the amount of energy conserved, GHG emission reduced and people trained, but also on the top-down macro impacts on the social, political and economic system. Therefore, the project added the following contents to the original designed activities in 2012:

  - The standard/code of EE bricks promised is enhanced to systematic standards and codes of EE bricks and rural EE buildings. A complete technical and policy system will be preliminary established, including rural EE building materials and the application, EE building design, construction, monitoring and evaluation;

  - The budget of 2013 has prepared to ensure the project objective as well as to consider the possibility of South-South cooperation, thus to enlarge the regional and global impacts of GEF/UNDP funds;

  - Additional information dissemination activity to ProDoc. Design: Successfully organized ‘National Energy Conservation High-Level Forum & Project of Market Transformation of Energy Efficient Bricks and Rural Buildings Promotion Conference’, with over 400 representatives from brick & tile industries in and out of China taking part in the meeting and visiting the pilot brick-making plant and EE buildings of the project. Establish exhibition hall of Shaanxi Xianyang wall materials jointly with committees of Shaanxi province and Xianyang to open a new dissemination platform for information of EE bricks and EE buildings. Set a project column in the periodical named Agricultural Engineering Technologies— The New Energy Industry to publicize project activities and disseminate knowledge of EE bricks and rural EE buildings.

- Sustainability: Please refer to the “Sustainability” section;

- Contribution to capacity building: Footage shooting for the project science film of EE brick-making techniques was completed, with the film expected to be produced in 2013; additionally, the technical training materials of EE brick-making and rural EE buildings were developed and distributed nation-wide through the promotion workshop of project demonstration achievements. All these activities played a positive role in enhancement of the sustainability of the project capacity building.

## Cross-cutting Issues

- Comment on how effectively the project is addressing relevant cross-cutting issues  (no more than one paragraph per issue).  These may include:
Environment (are environmental, climate and disaster issues being addressed in project implementation? How is the project ensuring no significant negative environmental impacts?)
Gender equality (How well does the project integrate gender equality into its objectives? What progress has been made to address/resolve any gender equality issues identified at design or subsequently? What progress has been made to develop the gender capacity of program staff; counterparts; development partners; and/or the broader community?)
Other issues such as HIV/AIDS, disability, anti-corruption, etc.

Besides ECER and improving global and local air quality, the project also: 1) improved the indoor air quality through building energy conservation and reduction of coal firing for house heating; 2) greatly reduced the consumption of clay and land resources through technical improvement and EE brick production.

The investigation in 2010 showed that just like other rural areas in China, women in the project sites were left home while men went to work in the cities. Lack of labour is a common problem. However, traditional brick making requires hard labour in poor working environment, which is not suitable for women. Thus, lack of labour and raising cost of labour force restricted the development of rural brick making sector. The project has improved the technology and the working condition, thus provided women with working opportunities in EE brick production sector. In the future monitoring and evaluation, the project will record and assess the change of employment of men and women, and quantify the contribution of the project in improving women employment and gender equity.

# 3. Project Management and Oversight

- Briefly introduce this section (<250 words).  Provide UNDP’s judgement as to whether during the reporting period, management and oversight of the project was of sufficient quality to effectively support progress of the project.  Has project management been responsive to changing needs and managed risks adequately?

The management strategy of 2012 includes scientific decision-making, timely adjustment, integration and opening, adaptation to local conditions, and public participation.

- Scientific and rigorous working procedure: According to the GEF/UNDP rules and based on PMO’s over 10-year experience in implementing GEF/UNDP projects, the project is managed normatively, systematically and comprehensively: 1) Based on the investigation, study and expert consultation, the annual workplan was made with full consideration of the logical connection between activities and various possible restrains; 2) the procurement of services and equipments; 3) rigorous monitoring and supervision of project implementation; 4) results evaluation and assessment and quality control by expert team; 5) develop scientific and practical monitoring and evaluation plan, as well as recording and reporting system; 6) regular communication with UNDP and the financial service provider to be guided timely; 7) continuous management capacity building of the project teams, especially local project teams.

- Flexible and quick adjustment: As mentioned in section 2, new project activities and management mechanism were added based on the changed situation and deepening understanding, thus the project sustainability and GEF/UNDP impacts are enhanced and the project objectives and outcomes are ensured.

- The implementation strategy of being integration and opening is the key to guarantee project success and expansion of the GEF macro-impact (timely adjustment with project objectives unchanged, open selection of technologies and products, open management arrangements);

- Adaptation to local conditions: With project objectives kept unchanged, technical implementation and management methods were made flexibly to be targeted and adapted to different local conditions (differences in management capacity, economic development levels, resources of wall materials, living habits of local people, etc.) of the pilot sites.

- Public participation: As the application and replication of EE bricks and rural EE buildings involves actual benefits of the mass rural residents, farmers’ participation in project implementation is necessary to ensure smooth project implementation and sustainable project results. The project made encouraging fruits in this aspect in 2012. For example, in construction of the pilot project in Chengdu, farmers were involved via Dam Meetings organized by the local project team throughout the whole process of planning, design and construction of the EE buildings. Besides, farmers were also organized to visit the brick-making plants to see the whole process of EE brick-making to learn the good quality of EE bricks, thus they would become more active and initiative in adopting EE bricks and EE buildings.

## Implementation Status

- Comment (<250 words) on whether progress against the annual plan was satisfactory during the reporting period, and assess the quality of implementation arrangements.

Consider the following questions:
	Were project activities delivered on time? If there were delays, explain why, assess the likely
	consequences of the delays for the project’s objectives, and describe any remedial action 	undertaken or proposed.  
	Is an extension required? 
	Are additional project inputs needed?

	Do implementation arrangements remain high quality, appropriate to the context and good 	value for money?  

	Where relevant, are implementation arrangements harmonised with other donors and aligned 	with partner government systems?

The national and local project teams have basically implemented the project according to the workplan in 2012. Delayed tasks and countermeasures were listed in section 2 Activities and Outputs. It will not affect the achievement of project objective and outcomes.

According to the progress, the project will meet the requirements of the project document and achieve the designed objective and outcomes. A relatively significant project achievement in 2012 is the breakthrough in establishment of the market system of EE bricks and rural EE buildings (information, policy, financial and technical systems)

## Monitoring and Evaluation

- Assess the adequacy of M&E arrangements during the reporting period (<250 words).

Consider the following questions:
	What M&E work was conducted during the reporting period (eg, evaluation? MTR?)
	Did M&E arrangements provide timely and meaningful information?  	
	Does evidence exist to show that objectives are on track to being achieved? 
	Do M&E arrangements use, or contribute to strengthening, local M&E systems and/or capacity? 
	Given all these considerations, is M&E adequately resourced?

Daily M&E system:

- Institutional arrangement: The project M&E was carried out under the leadership and supervision of TPR and PSC. The daily M&E was organized by the national PMO and carried out by the national PMO, the expert consultation committee, local PMOs and the construction management partners.

- Procedure: 1) According to the requirements in the project document, the national PMO developed the annual workplan with detailed M&E indicators and plan; 2) The expert consultation committee, local PMOs and the construction management partners submitted progress reports to the national PMO; 3) The national PMO organized supervision and monitoring of project activities progress and quality, as well as the evaluation and assessment of important activities; 4) The APR was prepared by the national PMO and submitted to PSC and TPR for approval.

M&E in 2012 includes:

  - Further refined the indicator system in 2012 annual workplan based on the ProDoc;

  - Developed M&E methodology and implementation plan of energy efficiency of EE bricks and rural EE buildings and carried out M&E activities accordingly;

  - Organized review of outputs of key activities of 2012

  - PMO carried out more than twice site visits to each pilot and on-going replication sites;

  - Organized TPR&PSC meeting with 2012 project progress report reviewed and approved.

Project implementation in 2012 has proved the timeliness and effectiveness of the M&E system, with the budget and implementation of M&E activities soundly guaranteed by the workplan.

## Human Resource Management

Assess the quality of human resource management (<250 words).  Were human resources effectively managed and adequate to support progress against the project’s objectives? Note any significant human resources issues during the reporting period that require the attention of senior management or donors.  Describe any remedial action taken/required.

Human resource management of the project includes PMO staff, CTA and experts. Following measures were taken in 2012:

- Based on the experience in 2011, positions of staff and experts were specialized and TORs were developed for the tasks in 2012;

- Based on the assessment of their work in 2011, contracts with some of the PMO staff and experts were renewed;

- Recruited local experts in EE bricks and EE buildings at pilot sites in addition to national experts, who played a positive role in successful project implementation at each pilot site.

In 2012, the project was well managed with high efficiency. The coordination and cooperation was smooth and the results were satisfying.

## Risk Management

- Assess (<250 words) the extent to which identified risks are being managed, and identify any new risks that have emerged during the reporting period.

- Highlight specific risks requiring higher-level management attention.  This should include reputational risks such as environmental, social, child protection, or corruption.

- UNDP’s role in managing and mitigating these risks should be made clear.

Main risks in 2012 were basically the same with those in 2011, which were: 1) How to achieve and identify the demonstration effects and promote to stakeholders; 2) How to realize effective management, with the consideration of different regions, sectors, departments, fields, objectives and levels, especially to encourage local project teams and to ensure the full-cycle-quality-control of project implementation. However, all risks were timely and effectively controlled by the PMO with the guide of UNDP (see section 1 and section 2). The project was smoothly implemented

## Inter-Agency Coordination and Delivering as One

- Comment briefly on whether the project is in line with the UNDAF.  If not, is it consistent with national strategies?

- If relevant, describe what measures have been taken to ensure inter-agency coordination.

The project objective and outcomes directly contribute to UNDAF outcome 1 (Government institutions and other stakeholders ensure environmental sustainability, address climate change, and promote a green, low carbon economy) and outcome 3 (China’s enhanced participation in the global community brings wider mutual benefits), thus the project is totally in line with UNDAF.

PMO participated GEF projects management meeting organized by MOF in 2012, submitted a report of practices and findings and exchanged experiences with other PMOs.

## Communication and Advocacy

- Briefly (<250 words) highlight significant communications and advocacy efforts undertaken during the reporting period.  Does the project have a communication and advocacy strategy?  If not, is one required?

Communication and advocacy (C&A) is one of the 4 components of the project and systematic and specific activities were designed. C&A is also one of the major project management procedure and methods. For both project activities and management, C&A has carried out activities focus on the following aspects: 1) to remove the barriers that hinder the stakeholders, especially farmers and rural companies, accessing related information and to establish sustainable information dissemination mechanism; 2) for the project management, to establish efficient institutional arrangement and normative operation system, including PSC, expert consultation committee, website, etc.; 3) to visit the project sites regularly and to discover and involve important stakeholders, thus to improve the project activity design and to enlarge the impacts and partnership base.

Special note: The project has carried out series of information dissemination activities beyond the original design of the project documents and achieved initial outcomes, which further strengthened the project impacts and sustainability (please refer the section 2 for details).

# 4. Financial Management

- Provide a brief narrative summarising key financial management issues (<300 words).  State whether the project is being delivered on budget.  Account for under/overspends.  Comment on whether the project is providing good value for money. If any remedial action is required, describe what action UNDP proposes to take.

- Provide a summary of key financial information using the tables below as a guide.  Add other tables as appropriate. Put very detailed information in an annex.

- If relevant, provide information on how donor financing has been used (eg list specific activities funded by the donor’s contribution).

Based on the UNDP/GEF projects experience, the PMO realized that the financial management is one of the major methods and contents of project management. The success of the project relies on the financial management. The financial management of this project includes budget, procurement and payment, audit, etc.

The main methods of financial management are: 1) to establish strict and normative financial management system, which includes annual work and budget planning system, normative procurement and payment documents and procedure, and detailed and normative original documents and recording system for audit; 2) clear assignment of responsibility: the budget management, service procurement and payment was assigned to different persons who cooperate with each other and report to the manager; 3) regular and timely coordination system: the PMO has established a regular and timely coordination system with UNDP, the financial service provider and the National Audit Office to discuss problems, technical principles and be guided; 4) staff trainings: since the project initiation, experts from UNDP, the financial service provider and other projects were invited to train the project team on project management and financial management; 5) strict supervision of the financial management by the project manager.

Because of the successful financial management in 2012, the budget was efficiently spent: 1) the delivery rate is 79.2%; 2) Besides the original design, the project has implemented extra activities with important impacts; 3) The project has explored new sources of co-financing and the amount of co-financing will be much more than expected, thus the effect of GEF/UNDP fund as synergy and leverage will be greatly improved.

|  | Source of Fund | Budget | Expenditure |
| --- | --- | --- | --- |
| Expenditure Vs. Approved project budget by source of funding | UNDP | 1,289,502.32 | 1,037,865.20 |
|  | Government Cost Sharing |  |  |
|  | Third Party Cost-sharing |  |  |
|  | Other (please specify) |  |  |
|  | Total |  |  |

| Output | Activities | Source of Funding | Budget Description | Annual Budget (USD) | Annual Expenditure (USD) | Note |
| --- | --- | --- | --- | --- | --- | --- |
| Component 1 | Information Dissemination and Awareness Enhancement | UNDP | 71300 | 10800.00 | 10,800.00 |  |
|  |  | UNDP | 72100 | 70000.00 | 62,000.00 |  |
|  |  | UNDP | 75700 | 0.00 | 3,934.27 |  |
|  |  | UNDP | 74500 | 2424.00 | 2,302.03 |  |
|  |  |  | Subtotal | 83224.00 | 9,036.29 |  |
| Component 2 | Policy Development and Institutional Support | UNDP | 72100 | 53,800.00 | 84,600.00 |  |
|  |  | UNDP | 74500 | 5298.00 | 2,537.95 |  |
|  |  | UNDP | 75700 | 122800.00 | 0.00 |  |
|  |  |  | Subtotal | 181,898.00 | 87,137.95 |  |
| Component 3 | Financial Support & Accessibility Improvement | UNDP | 72100 | 46000.00 | 45,473.00 |  |
|  |  | UNDP | 74500 | 1,380.00 | 1,602.28 |  |
|  |  |  | Subtotal | 47380.00 | 47,075.28 |  |
| Component 4 | Demonstration and Technology Support | UNDP | 71200 | 75600.00 | 88,200.00 |  |
|  |  | UNDP | 71300 | 60600.00 | 42,600.00 |  |
|  |  | UNDP | 72100 | 577324 | 514,378.16 |  |
|  |  | UNDP | 74500 | 54,561.72 | 21,254.44 |  |
|  |  | UNDP | 75700 | 105000.00 | 56,994.85 |  |
|  |  |  | Subtotal | 873,085.72 | 723,427.45 |  |
| Component 5 | Project Management | UNDP | 71300 | 68820.00 | 68,820.00 |  |
|  |  | UNDP | 71600 | 27067.96 | 29,075.8 |  |
|  |  | UNDP | 74500 | 8026.64 | 3,292.40 |  |
|  |  |  | Subtotal | 103,914.60 | 101,188.21 |  |
|  | Total | 1,289,502.32 | 1,037,865.20 |  |

# 5. Management Recommendations

- This section should highlight any key lessons learned and list any recommendations that require the attention of UNDP senior management or donors.

- Ensure you have reviewed the key judgements made in the report, noted lessons learned from all significant problems identified, and used these judgements and lessons to make appropriate recommendations of action required.

Both GEF and UNDP were involved in this project as development agencies, so the management rules and procedure are complicated. As full sized project, this project is with large amount of funds and related to different fields, departments, sectors, goals and levels, thus challenging to the project management team. Effective management according to GEF/UNDP rules is the key of success. The method applied in this project is to organize continuous trainings for the project team to improve the understanding and application capacity of GEF/UNDP management rules. Satisfying results were achieved. Therefore, it is recommended to UNDP that the experience gained in this project should be summarized as normative procedure and practice in the projects initiation stage, and normative training materials or project management manuals should be developed and shared via UNDP website. Related trainings should be held for project teams by UNDP or authorized agencies or experts. Workshops should be organized for experience sharing among similar projects.

# 6. Conclusion

- Briefly (<250 words) reiterate any key results, issues or proposed actions. Use the preceding assessments to help make clear what difference the project is making or has made, and what UNDP’s contribution has been to the project.

- Be selective, highlighting key achievements that tell a story, rather than long lists.

- Make sure your conclusion is consistent with the Executive Summary.

2012 is the first year of the project demonstration construction. The success of this year is very important to the project objective and outcomes. Under the supervision of UNDP, the PMO has strictly followed the GEF/UNDP management rules and efficiently carried out the project management. The project implementation in 2012 is smooth and successful. The progress met or exceeded the annual workplan and the original design. The delivery rate is 79.2%.

Also, 2012 was full of opportunities and challenges. On the one hand, the PMO has successfully controlled the risks; On the other hand, the PMO has taken advantage of positive factors and adjusted activities. The project activities are enriched without changing the budget or tasks, which has laid a solid foundation for enlarging GEF/UNDP impacts.

# 7. Annexe/s

- Include any detailed project information here (financial details, activity level details, maps, brochures, M&E framework, subsidiary reports, catalogue listing of publications/ knowledge products produced in Chinese and English etc).

Workplan 2012.