Basic Project Information

| Project Title: Strengthening the Capacity of the International Poverty Reduction Center in China for South-South Cooperation |
| --- |
| UNDP Award ID | CPR/09/210 |
| UNDP Project ID | 00069270 |
| Project Duration | 01/09-12/15 |
| Reporting Period | 01/13-12/15 |
| Total Approved Project Budget | US$4 million |
| Participating UN agencies | UNDP |
| Implementing Partners/ National collaborating agencies | China International Centre for Economic and Technical Exchanges (CICETE) International Poverty Reduction Centre in China (IPRCC) |
| International collaborating agencies | N/A |
| Cost-sharing third parties | Australian Agency for International Development (AusAID) |
| UNDP Contact officer | Zhang Yan |
| Project website | www.iprcc.org.cn |

Executive Summary

The IPRCC Project is proceeding smoothly and on the right track to achieve the expected outcomes. Over the past years, IPRCC has gradually become one of the top flagship organizations in China for South-South Cooperation (SSC) with a close mandate on poverty reduction. Cooperation and coordination between IPRCC and the receiving countries/governments/organizations has been strengthened through concrete activities. China’s experiences and lessons learnt in poverty reduction and development have been introduced to interested parties through exchange activities. As in the case of two-way exchanges, project participants get to know about China’s development contexts and likewise, IPRCC has accumulated abundant first-hand knowledge of other developing countries, as a stock-taking and preparation for China’s overall engagement in the world realm, aside from its rising role in the development community.

Over the course of 2015, IPRCC has further strengthened its institutional capacity for effective knowledge sharing and mutual learning on poverty reduction. Meanwhile, it also enhanced awareness and dialogue on pro-poor policy and presented policy options to policymakers, academics and practitioners in China and other developing/transition economies. Project management and oversight has been generally satisfactory.  The project delivery rate in 2015 was around 45%. To further increase its impact and consolidate its position on sharing China’s development experiences, IPRCC has to be more proactive, apply the demand-driven approach and improve its operations and project management.

1. Background

Development Context

Over one billion people around the world are poor, living on less than one dollar a day, trying to survive the vulnerability that goes with hunger, poor health, homelessness and lack of access to clean water. Globally, about 800 million people are food insecure, undermining their ability to live healthy, productive lives.

China’s outstanding record in reducing poverty has caught the attention of the entire world, particularly those countries in the South that wish to capture and apply lessons from the China experience. At the Global Conference on Scaling up Poverty Reduction, held in Shanghai in May 2004, the Chinese government, UNDP, the World Bank, DFID and other donors reached a consensus that there is a need for an international programme that examines China’s poverty reduction record to learn what might be replicated by other developing countries. The International Poverty Reduction Centre in China (IPRCC) is the result, intended to serve as a hub of knowledge and information on poverty reduction globally.

By the year of 2008, while there had been significant progress in establishing the IPRCC as an operational institution, and while also commending results in the area of training and activities related to exchange of experiences, little capacity has been built to date within the centre itself to fulfil its mandate. Many gaps still remain in the overall goal of making the IPRCC a truly global hub of excellence. The second phase of this jointly initiated project would require an emphasis on creating, expanding and deepening partnerships with countries in the South and their institutions, and as critically, professionalizing the institution in order for it to reach international quality standards with respect to management, administration, research and training.

Project Objectives and Strategy

The Project of Strengthening the Capacity of the International Poverty Reduction Centre in China for South-South Cooperation aims at further strengthening IPRCC’s institutional development and help further promote South-South Cooperation (SSC) for poverty reduction of other developing countries, through providing tailored training, collaborating on applied research and comparative study, fostering networking and facilitating professional exchanges. It also actively engages in organizing high level policy dialogues between China and other countries on poverty reduction.

This project would mainstream some common dimensions such as gender, pro-poor development, South-South Cooperation and environment sustainability into the project activities. Common themes and synergies would also be explored between activities in order to maximise effective use of resources including: training activities; technical assistance; publications; project dissemination, e.g. website, briefs, bulletins, training manuals, guidelines etc. At the completion of this project, it should have facilitated the IPRCC in formulating and adopting a set of systematic mechanisms for institutional sustainability and operation on its own.

This project would add to the momentum of investments made by UNDP to support achievement of MDG targets by developing countries. Moreover, as a founding stakeholder of IPRCC, coordinated aid is seen by UNDP as critical to

(i) ensure that developing countries can usefully access lessons to be taken from China’s experience in pro-poor, inclusive and balanced development; and

(ii) effective partnering with the Government of China and the Chinese agencies responsible for the delivery of development assistance from China to other developing countries.

Beneficiaries are developing country governments, institutions, particularly in the South as well as the IPRCC and the Government of the People’s Republic of China. The two primary outcomes of this project covering capacity development of the IPRCC and enhanced South-South Cooperation are:

(i) training, research & knowledge management capacity of IPRCC improved and meets international quality standards;

(ii) South-South Cooperation for poverty reduction enhanced, expanded and institutionalized.

2. Key Results

Overall, the project is on track to achieve its expected outcomes.

Institutional mechanisms of IPRCC (i.e., staffing support and funding support) have facilitated the progressing of the project, and collaboration with like-minded institutions on SSC has been also intensified. IPRCC has taken great efforts in terms of building the capacity of its staff and facilitate institutional development, and its brand as a knowledge hub on poverty alleviation and development, as well as a platform of South South exchange has been further consolidated.

At the output level, IPRCC, together with UNDP, has promoted quality research in line with the central government’s policies on poverty and development; while taking abreast of trends of poverty and development related theories and practices all over the world, organized a series of international exchange activities to boost international cooperation and broaden its network and visibility.

Project Outcomes

Outcome 1: Training, Research & Knowledge Management Capacity of IPRCC Improved and Meets International Quality Standards

In this Outcome, it is expected that the internal capacity of the IPRCC is strengthened and improved. In order to achieve this outcome, among other results, internal capacity assessments on training, administrative, knowledge management will be undertaken. Training manual, curricula and packages, based on country assessments will be systematized and rolled out, standardized as well as differentiated based on needs of participating countries. A set of core elements will be included in the training modules such as gender equality, gender dimension in poverty and poverty reduction, sustainability of environment linking to poverty and sustained poverty reduction. A high quality team of trainers (in-house and on the spot) will be developed to deliver the training courses. Gender balance of trainees will be ensured. Knowledge and document management platforms, dissemination, publications and communications strategies and capacities will be upgraded. Advisers of both short term and longer term will be attached to the Centre. The Advisory Board is expected to play a greater role as well as in capacity development.

Output 1.1: IPRCC Capacity building needs assessed and recurrent internal training programme established.

Output 1.2: Knowledge & document management guidelines, systems and platforms created and upgraded.

Output 1.3: Training practices, schedules and delivery systems established and professionalized.

Output 1.4: Management, monitoring & advisory services to IPRCC upgraded and strengthened.

Outcome 2: South-South Cooperation for Poverty Reduction Enhanced, Expanded and Institutionalized

At the end of the project cycle, it is expected that firm institutional relationships and dynamic working arrangements will be established with similar think tanks, academic and research entities, from the South and North. Selective and limited cross-comparative research will be undertaken on cutting edge issues related to development and poverty reduction. Follow up micro demonstration projects in select developing countries tied to research and knowledge generation will be considered. A high level annual forum on the International Poverty Alleviation Day addressing poverty reduction themes will be held to share the good practices, policy instruments and lessons in poverty reduction and MDGs progress and increases the global visibility of the IPRCC. This event will encourage wide partnerships with UN agencies, Chinese government and other interested stakeholders all over the world. Other regional key policy dialogue activities will be organized such as ASEAN-China and Africa– China high level workshops or exchange events. Research and Lessons Learned findings and recommendations will meet international standards, translated in many languages and widely shared.

Output 2.1: Establish formal partnerships and network with research institutions.

Output 2.2: A branding annual forum on poverty reduction and a high level regional policy dialogue event held each year.

Output 2.3: Chinese experiences and good practices in poverty reduction shared and promoted south-south learning and cooperation.

Activities and Outputs

Outcome 1

Steady progress has been made in implementing the planned activities under Outcome 1.

Output 1.1: IPRCC Capacity building needs assessed and recurrent internal training programme established.

A multi-channel talent introduction strategy has facilitated the working team of IPRCC to become more knowledge-based and more professional.

In 2015, internal and in-service training were conducted to upgrade IPRCC staff’s knowledge and skills.  To give a few concrete examples and figures: a delegation composed of 4 staff from 4 divisions (general affairs, finance, international exchanges, cooperation and training) of IPRCC were sent to ’South Africa to strengthen cooperation between China and Africa; through this activity, both the institutional capacity and the staff capability have been significantly improved.

Output 1.2: Knowledge & document management guidelines, systems and platforms further upgraded.

Progress has been achieved in research outcomes both in terms of quantity and quality in 2015. IPRCC has made tremendous efforts to ensure the research products are in line with the development trends of poverty reduction policies and practices, to have a real impact on policy-making.

Research completed and knowledge products released include 18 issues of International Poverty Reduction Briefing, 7 research contracted to carry out applied researches (Poverty Alleviation in Sudan and the Impact of China's investment; The competitive agricultural industries in rural development; Experiences and Implications of Poverty Reduction in Eastern China; Development Issues from the perspective of subjective well-being; Poverty Reduction Strategy towards 2030; Study on Poverty Reduction Cooperation for the maritime silk road in 21st century; Joint research on comparative study  on SEZs in Africa and China);

Furthermore, IPRCC has completed the International Poverty Reduction Briefing, Compilation of International and National Poverty Alleviation Cases, Newsletter for Overseas Chinese Enterprises.  To enable research products to reach a wider spectrum of audience, the upgrade and maintenance of the Knowledge-sharing Platform was also on-going with removal of the Server Room and upgrading of the video conference system.

Output 1.3: Training practices, schedules and delivery systems professionalized and optimized.

In early 2016, 10 staff will be sent to attend the Training abroad on Economic Inequality Reduction: Policy and Practice in Brazil (which is listed in 2015 AWP but has to be postponed to 2016 due to strict administrative regulations).

In addition, the international poverty reduction training is being increasingly institutionalized. IPRCC has started to evaluate impacts of 6 fixed provincial field visit sites for international training programmes, namely Shanxi, Jiangxi, Hubei, Guangxi. Gansu and Sichuan.

Output 1.4: Management, Monitoring & Advisory Services to IPRCC Upgraded and Strengthened

In 2015, IPRCC renewed contracts with 3 technical officers, 1 legal advisor and 2 UN Volunteers, and renewed contract with 1 post-doctoral fellow, which has brought fresh ideas and dramatically off set the Centre’s short handedness.

Outcome 2

This outcome is strongly supported by IPRCC’s partnership strategy and successful activities on experience sharing and South-South cooperation.

Output 2.1: Establish formal partnerships and network with research institutions.

IPRCC's partnerships with international organizations and traditional aid agencies have been strengthened through mutual visits, exchanges and participation in the other’s activities. For example, in 2015, IPRCC has sent delegations and individual staff to attend international conferences (e.g. poverty impact evaluation study tour to Colombia, study tour to Italy, attending IFAD regional conference in Asia, attending ASEAN+3 Rural Development and Poverty Reduction Conference in Asia) to exchange about development issues.

Output 2.2: A branding annual forum on poverty reduction and a high level regional policy dialogue event held each year.

In 2015, three high-level international events were successfully held. Especially "the International  Poverty Eradication Day Event" was held and raised public awareness on public involvement in poverty reduction.

The 9th China-ASEAN Forum on Social Development and Poverty Reduction was convened in Laos with a strong support from the Laos government.

The 6th Africa-China Poverty Reduction and Development Conference was held in South Africa with strong support from UNDP. The conference is themed as Towards Post-2015 Africa-China Sustainable Co-operation

on Poverty Reduction and Development which signifies China’s strong support to poverty reduction exchange and cooperation between China and African countries. Also this year the Conference has been included into the FOCAC framework as one sub-forum of the FOCAC Summit in South Africa.

These events have further promoted experience-sharing on international poverty reduction and development, international consensus building, and international cooperation.

Event 2.2.1: the Global Poverty Reduction and Development Forum

In 2015, to broaden the impact of Int'l Poverty Eradication Day and raise public awareness on public involvement in poverty reduction, IPRCC and UNDP and some other organizations jointly organized the Global Poverty Reduction and Development Forum (10.17 Forum). The theme was Common Development through Joint Shared Efforts on Poverty Eradication. The Forum brought together more than 350 participants, including government officials from China and other developing countries, renowned experts and scholars, entrepreneurs and representatives from civil society and international organizations.

Chinese President Xi Jinping attended the Plenary Session and delivered a keynote speech. Besides, In his video message, U.N. Secretary General Ban Ki-moon recognized the declaration made by China to ensure the entire poverty-stricken population in China may shake off poverty by 2020. As the special representative of the UN SG, UNDP Administrator Ms. Helen Clark attended the Forum. In her speech, she commended China for the major commitments to achieving the SDGs globally and also emphasized that China has the opportunity to mainstream the SDGs into its five-year plan for 2016-2020. She also indicated that China has had enormous success with poverty reduction, and its experience is of great interest globally.

The Forum has 7 parallel sessions in the afternoon, including Social Poverty Alleviation Forum, E-commerce Poverty Alleviation Forum, Forum on Poverty Alleviation through Industrial Development, Youth Poverty Alleviation Forum, Forum on Targeted Poverty Alleviation for the Disabled, Rural Development Forum and Forum on Financial Services for Poverty Alleviation and Development.

Event 2.2.2: the 9th ASEAN - China Forum on Social Development and Poverty Reduction

On 28-30 July 2015, the 9th ASEAN - China Forum on Social Development and Poverty Reduction opened in Vientiane, Lao PDR. The meeting was co-hosted by Minister of the State Council Leading Group Office of Poverty Alleviation and Development of China (LGOP) and ASEAN Secretariat and organized by International Poverty Reduction Center in China (IPRCC) and the National Committee for Rural Development and Poverty Eradication of Lao PDR (NRDPE). More than 120 delegates, including government officials, experts, scholars, media workers, and representatives of Chinese controlled enterprises,

NGOs and international organizations from China and ten ASEAN countries, participated in the meeting. Themed on “Financial Innovations for Poverty Reductions”, participants of the forum examined the new challenges for poverty reduction in the region, and discussed intensively the financial innovations for promoting more inclusiveness of growth in the region that is increasingly integrating. The topics fell into 4 categories: current institutional setup of financial policy and poverty Reduction in ASEAN and China; successful practices of micro-finance and inclusive finance supported by the government; roles of private sector, social enterprises and community development fund; how related land financial policy and internet financial innovations can work efficiently to reduce rural poverty.

Since 2007, nine sessions of “ASEAN - China Forum on Social Development and Poverty Reduction” have been held in China, Vietnam, Indonesia, Myanmar, etc. The forum has been included in the Plan of Action to Implement the Joint Declaration on China-ASEAN Strategic Partnership for Peace and Prosperity (2011-2015) and has become a platform for anti-poverty and development experience sharing between China and ASEAN countries.

Tianyun Hong, Vice Minister of the LGOP, Bounheuang Douangphachan, Chairman of the National Committee for Rural Development and Poverty Reduction, Lao PDR, Hap Omaly, Under Secretary-General of State, Ministry of Rural Development, Cambodia, Mdm. Alicia dela Rosa-Bala, Deputy Secretary-General, the ASEAN Secretariat addressed the opening ceremony. Ms. Kaarina Immonen, UN Resident Coordinator and UNDP Resident Representative gave a speech at the session one on “ASEAN & China: Financial Policy and Poverty Reduction”. A specialist from UN Capital Development Fund (UNCDF) also participated in the Forum and gave a presentation on ASEAN financial inclusion.

Event 2.2.3: the 5th Africa - China Poverty Reduction and Development Conference

On Dec. 9th, 2015, the Africa-China Poverty Reduction and Development Conference came to a close after two days of substantive discussions. Co-hosted by State Council Leading Group Office of Poverty Alleviation and Development, P.R. China and Department of Rural Development and Land Reform (DRDLR), South Africa, the conference explored the current state of development work in Africa and aimed to identify key areas for future endeavours. The conference was attended by around 200 participants, including government officials from African countries and China, diplomatic communities including South Africa, Nigeria, Djibouti and Senegal, as well as renowned experts and scholars and those from the private sector, civil society and international organizations.

LGOP Vice Minister Hong Tianyun expressed in his remarks that “at the National Conference on Poverty Alleviation and Development in late November 2015, the Chinese central government drew a comprehensive poverty alleviation plan for the next five years.

Mr. Gana Fofang, UN Resident Coordinator and UNDP Resident Representative of South Africa gave an opening remarks at the Conference and Ms. Agi Veres, Country Director of UNDP China moderated the session for discussion of China-Africa cooperation for achieving SDGs. In addition, the key findings of UNDP-IPRCC joint research “Comparative Study on SEZs in Africa and China” was presented by one of the key author at the Conference. In her closing remarks, Ms. Hannah Ryder, Head of Policy and Partnership of UNDP China, said that

This Conference lasted for a day and a half from 8th to 9th December. Participants had comprehensive discussion on issues including “China’s impacts on poverty reduction in Africa”, “Experience-sharing of China-Africa cooperation in poverty reduction”, “Prospects and key issues of China-Africa cooperation on poverty reduction” and “Exploring mechanisms and pathways for China-Africa cooperation on sustainable development”. On the afternoon of 9th, December, the conference participants visited villages neighbouring Pretoria for South Africa’s rural poverty reduction and development programs.

The Africa-China Poverty Reduction and Development Conference, the predecessor of this year’s sub-forum, has been successfully held for 5 consecutive years since 2010, covering issues like poverty reduction experience of China and Africa, poverty reduction and agricultural development, poverty reduction and infrastructure as well as poverty reduction and Special Economic Zones. After 5 years’ hard-work of all parties, the conference has become a core platform for poverty reduction exchanges between China and Africa.

After 15 years’ development since 2000, the Forum on China-Africa Cooperation has expanded its original focus on politics and economy to areas like science, education, culture, healthcare and social undertakings. The FOCAC has achieved fruitful results. China-Africa cooperation has also developed from practical interaction towards a new stage of improved quality, enhanced effectiveness and comprehensive advancement.

This year, the Africa-China Poverty Reduction and Development Conference was incorporated in the framework of FOCAC. All this has provided further and effective support to the wide-ranged and practical cooperation on poverty reduction between China and Africa and demonstrated that both parties attach great importance to this cooperation.

The FOCAC Sub-Forum Africa-China Poverty Reduction and Development Conference, an important step in implementing the Program for Strengthening Cooperation on China-Africa Poverty Reduction between the People’s Republic of China and the African Union, received staunch support from China, Africa as well as international organizations including the African Union and UNDP. The Conference continued to contribute to the exchanges and cooperation of poverty reduction and development between China and Africa.

Output 2.3: Chinese experiences and good practices in poverty reduction shared and South-South learning & cooperation promoted.

In 2015, IPRCC received 11 delegations from abroad and shared China’s poverty reduction experience with them. For example, a learning program for Bangladesh Mayors was designed by UNDP China and IPRCC to facilitate replication and innovation on existing model of public service provision to adapt to Bangladesh context; a ministerial-level delegation from Colombia.  In addition, IPRCC also sent delegations to Indonesia to attend a regional conference of IFAD.

Sustainability

Against empirical evidences, we can come to the conclusion that the prospects for sustainability are strong and valid. First and foremost, both UNDP and the Chinese Government have pledged to make efforts and ensure that IPRCC becomes a global hub of excellence and a primary vehicle for South-South cooperation in the area of poverty reduction.

Meanwhile, IPRCC has identified its long-term vision, mid-term trainings and research plans, and standards of operations for its core business. IPRCC applies these strategies and standards in capacity buildings as well as in other activities.

Externally, IPRCC has received increasing demands from developing countries to learn from China’s successes in combating poverty and achieving sustainable development. This suggests that IPRCC’s niche as a platform to share China’s development experiences has been acknowledged internationally. In relation to this, comprehensive national and global network of development partners has been gradually built and will contribute to regular communication on South-South Cooperation.

MDG Targets

This project concentrates on pro-poor policies, practices and ideas that are directly relevant to developing countries and transition economies in their pursuit of poverty specific MDGs by 2016 or earlier.

Partnership Effectiveness

Recognizing the significance of synergies among development partners and their direct impact in provoking changes in recipient countries, IPRCC has placed partnership building and consolidation high on its agenda. IPRCC sticks to the following criteria while identifying potential partners: potential synergies that are expected between IPRCC and its partner and experience and expertise that might be of help to IPRCC. Partners include UN agencies, governments, donor agencies, NGOs, etc. IPRCC has either signed joint programme agreements (including joint financial commitments on a ‘cost-sharing’ basis), memorandums of understanding or simply exchanges of letters with them.

In 2015, the partnership network of IPRCC was further strengthened, and collaboration with organizations and agencies both from the North and the South has continued. In addition, private sector companies such as China-Africa Agricultural Investment Co., Ltd and China-Africa Development Fund also joined in the network.

Cross-cutting Issues

A set of cross-cutting issues have been weaved into the high-level forums, researches,  training modules and  bilateral cooperation (co-)initiated or (co-)organized by IPRCC, such as gender equality, gender dimension in poverty and poverty reduction, sustainability of environment linking to poverty, youth employment and poverty, and sustainable poverty reduction.

3. Project Management and Oversight

During the reporting period, management and oversight of the project was satisfactory.

Implementation Status

The project implementation is going in a steady way as IPRCC has tried its best efforts to maintain smooth communication between the three parties.

However, due to lack of sufficient personnel and abundance in resources other than the UNDP project, in 2015 delivery rate is relatively low, around 45%. There is more room for improvement in the following aspects: on one hand, we should better plan activities such as research and capacity building so that they are not constrained by the central government’s prohibition against lavish spending; While on the other hand, as the project implementing agency, CICETE should better manage the project account, and ensure timely payment of project staff and activities.

As agreed by UNDP, IPRCC and CICETE, the project is extended to second quarter of 2016. In 2016, the project will come to a transitional period before the new-phase project plan is agreed.

Monitoring and Evaluation

Project monitoring has been conducted by UNDP and CICETE during the project cycle, in consultation with IPRCC, the State Council Leading Group of Poverty Alleviation and Development (LGOP) and the Ministry of Commerce (MOFCOM). Strong evidences suggest that project implementation has been timely, and the project is on the right track to meet the expected outcomes.

Human Resource Management

In 2015, human resource management of the project was effective. Besides regular staff, 2 UN volunteers, 3 technical supporting staffs and several interns joined IPRCC. 3 delegations composed of 10 individuals went to 3 countries to participate in international conferences and exchange missions; in addition, several staff were seconded to partner agencies and ministries, such as LGOP, MOFCOM and MOF, to provide assistance in setting up a comprehensive and multi-level capacity building platform for their staff.

Risk Management

Consensus has been reached and relevant parties are currently discussing necessary arrangements required to conduct the formulation of the new cooperation project with a concept note already at hand. In light of these considerations, insufficient TRAC funds from UNDP is considered as the most daunting obstacle, as a proper portion of TRAC funds is required as a pre-condition for IPRCC to apply for government cost-sharing for the new phase. To cope with this adverse situation, IPRCC and UNDP will have to mobilize funds from potential donors. Aside from this aspect, no other significant risks are foreseen between now and the end of the project period.

Inter-Agency Coordination and Delivering as One

In 2015, IPRCC has intensified internal coordination and communication between divisions, and engage relevant divisions in its dialogue and cooperation with donors. Still, a lot remains to be done, as different divisions have different mandates and they are always exposed to heavy workload and internal coordination sometimes is regarded as burdensome.

Communication and Advocacy

This has been placed at the core of IPRCC’s work and its advocacy work was further enhanced in 2015.

To give a few concrete examples: brochures on IPRCC’s work in both English and Chinese languages were compiled and disseminated; official website (www.iprcc.org.cn) is regularly updated with project documents and latest news of activities in both Chinese and English; new social media tools such as Sina weibo is in use to facilitate the exchange with the general public. As a result, IPRCC has increased its exposure on the TV, newspapers and radio. In accordance with the statistics, the major events (i.e., forum, conference, seminar and visits) has reached over 10,000 people in 2015,  and China’s success stories in poverty reduction, both theories and practices, have been effectively introduced and disseminated. However, lack of a market-based and audience-driven communication strategy and constraints from the nature of IPRCC and its supervisor LGOP have dragged the leg of IPRCC for timely and audience-oriented communication and publicity.

4. Financial Management

Budget depletion is on track although delivery rate in 2015 is not as high as expected. Furthermore, the Annual Tripartite Review Meeting held during the reporting period has not identified any significant financial issues requiring action.

IPRCC, UNDP and CICETE still need to intensify coordination, and ensure that project payments are done in a timely manner, as this has a direct impact on the delivery of project.

5. Management Recommendations

5.1 In accordance with the Project Document, IPRCC should become a sufficiently well-known and prestigious institution for its activities to be largely demand driven by donors and by developing country partners.  At the current stage, IPRCC is still viewed as an organization with strong Chinese characteristics, which means, there is still a long way to go before it indeed meets international standards and becomes professional and relatively independent. Therefore, UNDP and IPRCC need to join efforts and ensure that IPRCC is developing towards the right direction and make necessary arrangements to consolidate the mind set of the management of IPRCC (and LGOP), its core staff are properly trained and exposed to international cooperation, etc.

5.2 Consolidation of activities: Instead of investing staff time and budget in sporadic activities, IPRCC should re-focus and zoom down on key areas of concern. In addition, some established activities and events, in particular the annualized forums and conferences should be innovated and new social media are strongly advised to be utilized to increase its appeal among the general public. More joint research projects should be developed in future between IPRCC and UNDP. The theme of the research could be generated from the forum/seminar exchanges, which aims to provide policy recommendations to Chinese and participated countries.

5.3 Following the demand-driven approach: IPRCC is advised to be more proactive in regular communication with donors and partners, and take heed of specific needs from recipient countries while designing programmes for individual activities (in particular exchange seminars and conferences). By doing so, IPRCC is expected to move away from the supply-driven approach, and channel project resources to areas of need.

5.4 Last but not the least, in terms of project funds management, IPRCC is required to further coordinate with CICETE to ensure that project funds are spent in time and avoid delayed payment to the greatest extent.

6. Conclusion

Over the course of 2015, the IPRCC Project has progressed smoothly. The majority of expected outcomes have been achieved and good-quality activities have been conducted. Both the institutional capacity and the staff capability of the IPRCC have been significantly strengthened, which have rendered its effort in South-South cooperation more effective and professional. As a result, its reputation as an international poverty reduction hub is being further consolidated.

At the project implementation level, 7 outputs have been fulfilled, and activities such as research, cooperation, international exchange, training and information sharing have been carried out.  The project has been extended to the end of 2015 to fully utilise the fund and further professionalize and internationalize IPRCC in line with the outcomes e set in 2009.

At the policy level, all outputs and activities are consistent with China’snational policies on poverty reduction, and UNDP’s strategy in promoting SSC. This approach contributes to the sustainability of the project. Our efforts on advocacy and PR have also been intensified.

In terms of sustainability, the project has endeavoured to improve the capacity of development partners in other developing countries. Through adapting the lessons learned in China’s own poverty reduction courses into their own contexts, it will help other developing countries to address their pressing need in the course of poverty alleviation. Thus, sharing China’s development experience with a demand-driven approach, will contribute to both the sustainability of the overall SSC, but also that of the project itself.

7. Annexe/s

7.1 Summary report of the visit to South Africa

7.2 Summary report of the visit to Indonesia

# Text boxes

Annual Project Progress Report

Strengthening the Capacity of the International Poverty Reduction Centre in China

for South-South Cooperation

January, 2016