## Template
Work-plan for: 2021
Project ID and Project Name: 120605 Low-Pressure Metal Hydride Alloy-based Onboard Hydrogen Storage and Hydrogen Refueling for Commercialization of Fuel Cell Vehicles
UNDAF/CPD Outcome: Output 2.2: Reduction at (subnational level) in greenhouse gas (GHG) emissions. In-phase reduction in consuming of ozone-depleting substance (ODS). (linked to UNSDCF Output 4.2, Strategic Plan 2.1.1).
UNDP Strategic Plan output 2.1.1 Low emission and climate resilient objectives addressed in national, sub-national and sectoral development plans and policies to promote economic diversification and green growth
EXPECTED OUTPUTS/OUTCOMES INDICATORS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET
Output/outcome indicators and annual indicator targets/ benchmarks (if applicable) | List all activities to be undertaken (including evaluations and publications etc) | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | COA | Description | Amount (year) | Outcome 1
Outcome 1. ProDoc Development | [10 empty] | Fund | COA | Q1 2020 | Q2 2020 | Q3 2020 | Q4 2020
Output 1 | 1.1 Conduct an assessment on strategic capacity needs of the institutions in the changing environment | 25% | 25% | 25% | 25% | UNDP | 30000 | 71300 | national consultant | 10000 | 30000 | 71300 | 2500 | 2500 | 2500 | 2500
ProDoc development | 1.2 Take stock of existing and potential efforts as well as resources to assist strategic development of full size project | 25% | 25% | 25% | 25% | UNDP | 30000 | 71300 | national consultant | 15000 | 30000 | 71300 | 3750 | 3750 | 3750 | 3750
| Sub-Total for Output 1 | [8 empty] | 25000 |  |  | 6250 | 6250 | 6250 | 6250
Subtotal | [7 empty] | 71300 |  | 25000
Outcome 1 subtotal | [9 empty] | 25000
Outcome 2
Project Management | [10 empty] | Fund | COA | Q1 of 2020 | Q2 of 2020 | Q3 of 2020 | Q4 of 2020
Management & Evaluation | Project Management and evaluation |  | 25% | 50% | 25% | UNDP | GOVT | 71600 | Duty travel on demand | 2000 | GOVT | 71600 | 0 | 500 | 1000 | 500
|  |  | 25% | 50% | 25% |  | GOVT | 74500 | miscellaneous | 1000 | GOVT | 74500 | 0 | 250 | 500 | 250
General Management Support | GMS of UNDP, 8% cost sharing |  |  |  | 100% | UNDP | GOVT | 75100 | GMS | 2240 | GOVT | 75100 | 0 | 0 | 0 | 2240
Subtotal | [7 empty] | 71600 |  | 2000 |  |  | 0 | 750 | 1500 | 2990
[8 empty] | 74500 |  | 1000
[8 empty] | 75100 |  | 2000 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
Project Management Subtotal | [9 empty] | 5000
Total Amount | [7 empty] | COA |  | Total
[8 empty] | 71300 |  | 25000
[8 empty] | 71600 |  | 2000
[8 empty] | 74500 |  | 1000
[8 empty] | 75100 |  | 2000
Total | [9 empty] | 30000

## Examples
Work-plan for: please list the period which the work-plan covers
Project ID and Project Name: Please list project ID followed by the full project name according the project document or the short name listed in ATLAS
UNDAF/CPD Outcome: please list the CPD Outcome of the project which can be found in ATLAS
Applicable Output(s) from the UNDP Strategic Plan: please list the SP output of the project which can be found in Project List on Intranet
EXPECTED OUTPUTS/OUTCOMES INDICATORS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET
Output/outcome indicators and annual indicator targets/ benchmarks (if applicable) | List all activities to be undertaken (including evaluations and publications etc) | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | COA | Description | Amount 2017
Outcome 1: Voluntary agreements in three industries achieved | [10 empty] | Outcome 1
Indicators: No. of people voluntary agreements signed within the first two year of the project (2012 = 3 sector workshops held, 2013 = 12 enterprise have signed VA) | Activity 1.1: Nominate 12 enterprises from the Iron, steel and cement sectors. | [9 empty] | Fund | COA | Q1 | Q2 | Q3 | Q4
| Activity: Develop propaganda materials/pamphlets for Voluntary Agreements (VA) related to the iron, steel and cement sectors | 10% | 20% | 30% | 40% | ABC | GOVT | 72100 | Three sub-contracts (one for each sector) contracted to prepare materials (as per assignment TOR). Each contract is estimated at 30.000 US $ Payments (03/12; 10/12; 04/13) | 72000 | GOVT | 72100 | 7200 | 14400 | 21600 | 28800
| Activity Design and Print propaganda materials/pamphlets for Voluntary Agreements |  |  | 100% |  | ABC | GOVT | 71300 | A designer prepares and finalize uniform design for the three sector VA | 5000 | GOVT | 71300 | 0 | 0 | 5000 | 0
|  |  |  | 100% |  | UNDP | TRAC | 72100 | A sub-contractor contracted for printing of 3X500 copies of the three VA propaganda materials/pamphlets | 10000 | TRAC | 72100 | 0 | 0 | 10000 | 0
| Activity Hold workshops for enterprise representatives from the three sectors |  |  |  |  | ABC | GOVT | 72100 | A hotel is contracted to host three workshops (including meals rooms, conference hall etc.). Anticipated participation is 100 per workshop. |  | GOVT | 72100 | 0 | 0 | 0 | 0
[6 empty] | ABC | GOVT | 71600 | Travel for 150 participants for the workshops (100 local transportation at 10 US $ pp and 50 airfare at 150 US $ pp) |  | GOVT | 71600 | 0 | 0 | 0 | 0
[6 empty] | DEF | 3rd | 74500 | Miscellaneous expenses related to the workshop
| Activity Signing of VA by interested enterprises. | [7 empty] | PMO engages in correspondence with interested enterprises to ensure agreement signature (no cost)
Subtotal | [7 empty] | 72100 |  | 82000
[8 empty] | 71300 |  | 5000
71600
74500
Outcome 1 Subtotal | [9 empty] | 87000
Outcome 2: Institutional capacity of BVA and its staff in effective volunteer management and volunteer mobilization enhanced
Indicators: Users are actively utilizing the reconstructed IT platform. (2012 = IT platform tested and 100 MNB staff trained, 2013 = User survey shows 50% general satisfaction with IT platform) | Activity 2.1 Strengthening of online volunteer matching platform
| Activity Conduct problem analysis on current matching system | 50% | 50% |  |  | FGH | UNV | N/A | PMO analysis on currentl matching system and identifies inherit problems (no Cost) | 0
|  |  | 50% | 50% |  | FGH | UNV | 71200 | An Interantional consultant will review PMO analysis on currentl matching system and provide technical sound sugegstions to the PMO on a platform update (24 w/d x 500 US $ p/d) | 12000
| Activity Execute updates, test and launch updated platform |  |  | 50% | 50% | FGH | UNV | 72100 | Hired sub-contractor updates and test the applications of the platform and provides the fully functional updated platform to MNB (the subcontract is a combined contract with below - total cost 10 000 US $) Payments (07/12; 12/12) | 5000
| ActivityTrain MNB staff in IT platform maintenance |  |  |  |  | UNDP | TRAC | 72100 | The sub-contractor (please see above) also provides training in the platform usage to MNB (the subcontract is a combined contract with above - total cost 10 000 US $) Payments (03/13)
| Activity Organize outreach campaign targeting VIOs and prospective volunteers |  |  |  |  | WER | 3rd | 72100 | A design/printing company designs and prints 2000 copies of the outreach materials
[6 empty] | FGH | UNV | 72100 | 7 Local venues is hired to host the 7 PMO trainings on the voluntere matching and the use of the IT platform. For each venue cost for confrence roome and meals are covered (7 X 1000 US $)
[6 empty] | FGH | 3rd | 72100 | 2 Local venues is hired to host the 2 PMO trainings on the voluntere matching and the use of the IT platform. For each venue cost for confrence roome and meals are covered. (2 X 1000 US $)
| Activity Monitor platform rate of utilization and collect feedback from users |  |  |  |  | FGH | UNV | N/A | PMO monitor platform rate of utilization and collect feedback from users (No Cost)
Subtotal | [7 empty] | 72100 |  | 5000
[8 empty] | 71200 |  | 12000
Outcome 2 Subtotal | [9 empty] | 17000
Total | [7 empty] | Please list the budget code used in than above (i.e. 71100, 71200, 72100 etc) |  | Please list the total amount for each budget code per year
[8 empty] | 71200 |  | 12000
[8 empty] | 71300 |  | 5000
[8 empty] | 71600 |  | 0
[8 empty] | 72100 |  | 87000
[8 empty] | 74500 |  | 0
Total | [9 empty] | 104000