ANNUAL REPORT

Action for Cooperation and Trust

Report on Progress

1 October 2008 – 30th September   2009

Nicosia, 31 October 2009

Table of Contents

PREFACE	3

SECTION I – Situation Update	4

Political context in Q3 2009	4

General Context	4

Political climate in the GCC Q3 2009	6

Political climate in the TCC Q3 2009	6

Preliminary results from Trust Surveys (focus groups)	7

Annual Review Report	10

Recommendations from NGO audit 	13

SECTION II - Progress during the past year	14

SECTION III - Performance Indicator Framework 2008-2009	17

SECTION IV - Organizational Networking Matrix	20

List of organizations involved in ACT-funded projects during reporting period	20

Events organized under ACT-funded projects in the reporting period	28

Media coverage of ACT programmatic activities over the past year	35

SECTION V - PROJECT PROGRESS IN QUARTER 3 OF 2009	44

SECTION VI - FINANCIAL REPORT………………………………………………………………..51

# PREFACE

As the first year of Phase II of UNDP-ACT comes to a close, so does the first year of direct talks between the Leaders regarding possible reunification of the island. This report therefore provides an opportunity to review progress and outline ACT’s strategies to the changing political situation.

The period 2008-2009 has been a significant year for ACT. The transition of ACT to a second phase (2008-2011), has created new opportunities for the programme to position itself as a key player in supporting reconciliation between the island’s two main communities.

Significantly the ACT programme has taken the opportunity to re-orient its focus to better align its peacebuilding support to new realities. This started with the creation of a new vision for the second phase of ACT, involving main Cypriot partners, UNDP, USAID and other inputs from the wider UN family.

The vision laid out in 2008 emphasized civil society as agents of change, whereby the strategy for Phase II would be independent of larger political dynamics, though at the same time ready to take advantage of any political breakthrough that may occur.   With one third of Phase II already implemented, this Annual Report combines four objectives:

- To provide an overview of the political and media situation over the last quarter;

- To provide an overview of milestones and activities undertaken during the year;

- To report on annual targets for the last 12 months;

- To demonstrate progress and developments during the last quarter of the 2008-2009 programme cycle;

# SECTION I - Situation Update

## Political context in Q3 – July – September 2009

### General Context

This Quarter marked the first anniversary of the resumption of direct talks between the Leaders, since the full-fledged negotiations began on 3 September 2008.  At the time of writing, the two Leaders had moved from discussions on the Executive to discussions on the Property chapter.

Against this background, some of the Technical Committees continued to discuss the implementation of the confidence-building measures approved by the Leaders in 2009. The number of agreed measures has since risen to 23. Out of those measures, six have been implemented or are in the process of being implementation (opening of Limnitis crossing, ambulance crossings, creation of a cultural heritage advisory board, creation of health and veterinary advisory boards, implementation of an island-wide water awareness campaign, exchange of information on criminal matters). Four Technical Committees (Environment, Crime, Health and Cultural Heritage) have continued to meet.

The leaders continued to meet regularly and the message that the process is Cypriot-led has clearly resulted in them taking ownership of the process. Although the gaps have narrowed on a number of important issues, much work needs to be done to achieve full convergence. It is also clear that both sides still have to do a lot to explain to their communities the benefits of a solution so they can make informed decisions about the peace agreement.

As for the media environment, coverage of the peace talks is rather cynical, with little sense that a settlement will be reached in the near future. Unfortunately, the leaders continue to publically highlight their frustrations with the approach taken by the other side during the negotiations. This is often purposefully done so that they are not seen as making compromises which might result in negative criticism coming from parties in their own community. Furthermore, there have been direct attacks on the Special Advisor to the Secretary General (SASG) in Cyprus, Mr. Alexander Downer, in the Greek Cypriot press, following leaking of a large amount of documents from the Good Offices. Many mainstream media in the TCC are also reflecting the more skeptical approach (towards the negotiation process) of the new authorities.

However, coverage of UNDP-ACT activities and events, with a few minor exceptions, remains overwhelmingly positive in both communities. As an example, in Q3 2009, in the press island-wide, only 5% of coverage was negative. This is a net improvement when contrasted with press coverage from 2006 to 2008, which contained three times more negative coverage.

Positive and Negative coverage of ACT projects in the GC press – Q3 2009

Positive and Negative coverage in the TC press – Q3 2009

Positive and Negative coverage island-wide – Q3 2009

Positive and Negative coverage of ACT projects island-wide 2006-2008

### Political climate in the GCC Q3 2009

The conclusion of the first round of direct talks has given rise to different readings of the results achieved, but the overall feeling among Greek Cypriots was that very little progress was made on the major negotiation points of guarantees, property and power sharing. With the exception of the two main parties AKEL and DISY, all the other parties expressed disappointment at the “poor results”.

The decision of the two leaders to reopen Limnitis was seen initially as proof that tangible progress can be achieved at the talks. However, even this event was negatively perceive after Turkish Cypriots were allowed to visit Kokkina, without any checks by GC Police, but when Greek Cypriots tried to cross on September 2 there were long delays. The fact that TC authorities checked the identities of those that wanted to cross, resulted in people turning back and refusing to cross in the end. This created a big frustration in the GC side and gave ammunition to the rejectionist front and the majority of the mass media to undermine the talks. Christofias subsequently cancelled the first meeting of the second round of talks. Earlier, the government had decided to launch a campaign to explain the basic concepts of federation to the general public. This campaign, however, was not launched due to the bad climate created from the Limnitis incident.

The majority of the media cultivated a climate of pessimism about the chances of the talks succeeding. The attacks against the SASG included statements by certain politicians that that he should be replaced. The pessimism was exacerbated further due to the publication of press reports about the execution of GC prisoners during 1974.

### Political climate in the TCC Q3 2009

In the third quarter of 2009, the Turkish Cypriot media was primarily focused on the newly elected “government” and the new actions and policies being implemented. The third quarter also coincided with the 100th day of the newly elected “government” and it is by this time many Unions were starting to protest against the authorities. Among the reasons for demonstrations, were decisions against salary increments, lack of teachers in schools as well as the possible introduction of Quran courses.

In September there was a lot of media attention on Talat’s visit to New York and his meeting with the Secretary General. During his visit he emphasised that the international community should be more engaged in the negotiation process. The cancellation of the second round of the negations resulted in heavy criticism in the TC press against the Greek Cypriot Leadership and the tactics they were using. However, the fact that the negotiations started again the following week showed the commitment by the two leaders in spite of the ongoing criticism directed at them.

### Preliminary results from Trust Surveys (Focus Groups)

During the reporting period, the initial results from the focus groups which ACT undertakes to track the level of trust between the two communities were received. The final data and results from the quantitative results will be presented in the next quarterly report. Some of the initial findings from the qualitative data received from the focus groups are captured below:

Vision and Future

- At present, the focus of the Turkish Cypriot community is on many pressing internal problems, the erosion of Turkish Cypriot demographic identity, the displacement of Turkish Cypriot businesses by Turkish capital, and the increased nationalistic and religious pressure from Turkey. These conditions make it hard for Turkish Cypriots to have a clear vision for the future, but it increases their desire for self-rule in an internationally recognised state.

- Greek Cypriots appear to have a more focussed vision for the future of Cyprus, with central themes to what they desire being ‘peace’ and ‘financial prosperity’. Financial prosperity’ has more to do with personal needs rather than the two communities at large. The vision of ‘peace’ is linked to a solution of the Cyprus Problem that sees Turkey’s influence on the island diminish.

- The majority in both communities considers a form of bi-zonal, bi-communal federation as the only ideal and realistic solution. At the same time, the two communities generally agree that they can live in peace. Turkish Cypriots, however, are more likely to point to bi-zonality as a necessary condition for peaceful coexistence.

Contact

- Among everyday individuals of the Greek Cypriot community there appears to be an association between the level of contact and the age as well as the political ideologies. Among younger Greek Cypriots contact is more prominent among left wing individuals. The same pattern is observed among middle age individuals, but in this case the opportunities for incidental contact of right wing individuals with Turkish Cypriots increase. Among older individuals, differences in the level of contact given political ideology diminish.

- Most Turkish Cypriots have had personal contacts with Greek Cypriots, even though the conditions and the depth of contact vary significantly. Many contacts were explained as being incidental and superficial. Turkish Cypriots who have had more in depth contact with Greek Cypriots continue to frustrated with the perceived lack of commitment they feel are coming from Greek Cypriots to promote change.

- In the Greek Cypriot community, contact with members of the other community has had a permanent effect on the dissolution of myths as to how the people of the two communities differ on a personal level. For Greek Cypriots contact has been effective in dissolving myths that saw the other community as being ‘backwards’, ‘fanatic’ and ‘savage’ and in promoting the idea that ‘Turkish Cypriots are people just like us’.

- Greek Cypriots were displeased to see Turkish Cypriots gain the rights of citizens of the Republic of Cyprus, EU citizenship and access to public services paid for by Greek Cypriot citizens of the Republic, while they were still residing in Greek Cypriot properties in the north that they did not want to give up.

- Turkish Cypriots associated contact with a solution to the Cyprus Problem, EU membership and a solution of many problems on a social level. When contact failed to bring a solution (it was the Greek Cypriots who said ‘No’) and expectations for a better future were not met, relations between the two communities deteriorated. In parallel, Turkish Cypriots found the Greek Cypriots to be conservative, arrogant, and to show no true indication for trade relationships between the two communities (an important issue as the Turkish Cypriot community expected contact to bring much expected economic development). The influence of a nationalistic Church of Cyprus on the Greek Cypriot community also undermined possible positive effects of contact between the two communities.

Perceived Level of Trust

- The general consensus in both communities is that the level of trust between the Turkish Cypriots and Greek Cypriots continues to be low. A series of factors are presented as being responsible for current low trust levels:

- The ‘NO’ at the Anan Plan referendum has hurt relations between the two communities, and has decreased the level of trust on behalf of Turkish Cypriots towards Greek Cypriots.

- Greek Cypriots believe the Turkish Cypriot community’s policy is dictated by Turkey

- Turkish Cypriots believe the Greek Cypriot community’s policy is influenced by the Church of Cyprus

- The educational systems of both communities have fostered mistrust between the two communities.

- Improvement of the standard of living of the Turkish Cypriot community following the opening of the crossing points, and access  to public services in the areas under the control of the Government without the Turkish Cypriots reciprocating with pressure on their leadership for a compromising solution, has not been received well by Greek Cypriots

- The refusal of Greek Cypriots to trade with and buy goods from the Turkish Cypriot community is seen as being a conscious effort to keep the Turkish Cypriot community in economic isolation and hinder its economic development, and has not been received well by Turkish Cypriots.

- Greek Cypriots still see Turkish Cypriots as being inferior. Feelings of superiority that prevailed before 1974 are still in existence today. This is an observation made by members of both communities.

- The lack of personal contacts among younger members of the two communities that would help foster personal relationships and a better understanding between people of the two communities.

- The fact that many people still hold onto memories of atrocities and have not forgiven the other community for their loss.

- Extremist elements still exist in both communities and their presence (as well as the threat they pose to peace) is feared by members of the other community

- Separation of the two communities for almost three decades has caused a drift between them and new generations without the experience of living in peace are now growing up

- Among the Greek Cypriot community there is wide acknowledgement that the major event to have brought about an increase in trust within the near past is the opening of the crossing points. Besides new contacts on a personal level, the opening has given the chance to common platforms to emerge between the two communities and the fact that no major incidents have occurred serves as proof that the two communities can live together in peace. Contrary to Greek Cypriots who believe that nothing major has happened since the opening of the crossings, Turkish Cypriots recall incidents of vandalism of cars with Turkish Cypriot licence plates. Such incidents undermine the confidence that the two communities can live together in peace and hinder further communication and interaction. The two communities have a similar perception as to how the level of trust between the two communities has changed over time.

- It increased significantly following the opening of the crossings as increased contact and heightened expectations for a solution brought the two communities closer together.

- Trust drops dramatically following the rejection of the Anan plan by the Greek Cypriot community, a decision that many Turkish Cypriots interpreted as unwillingness to live with the Turkish Cypriot community. A trend of diminishing trust ensues for the following 4 years. The stalemate in the discussions and the presence of President Papadopoulos, in the leadership of the RoC, affected negatively the levels of trust. At the same time, Turkish Cypriots expectations for sanctions on the Greek Cypriot community for its ‘No’ to the Anan Plan and a strengthening of trade relationships between the two communities do not materialise. On the contrary, Turkish Cypriots are becoming increasingly convinced that Greek Cypriots do not want reconciliation and look down on them. Among the Greek Cypriot community this is a period where the initial feelings of ‘they are just like us’ are becoming increasingly overshadowed by feelings of ‘we pay for everything, they get citizenship and rights, and then they go back to the occupied areas and live in our houses that they do not want to give back’.

- In the Greek Cypriot community, the level of awareness of bi-communal groups or projects is higher among civil society members, policy makers, academics, and females involved in bi-communal activities. Even among the general public in the Greek Cypriot community, however, there is awareness of bi-communal initiatives. Awareness may not be universal (i.e. not all participants may be familiar with bi-communal activities) but in all sessions there are mentions of bi-communal activities. Among the general public, awareness revolves around initiatives and groups of a social and cultural type.

- In general, bi-communal efforts are positively seen as an attempt to build ties between the two communities and establish contact among their members as a means of fostering understanding and acceptance of each other, as well as eliminating negative stereotypes and perceptions.

- Overwhelmingly, members of both communities consider that continuing contact between the two communities is essential. In the Greek Cypriot community, this opinion is based on the understanding that in the event that a solution is reached, pre-existing contacts, relations and interactions with members of the other community will facilitate peaceful coexistence. In the Turkish Cypriot community, this opinion is based on the acknowledgement that no contact would only lead to further misconceptions and hinder a peaceful solution.

## Annual Review Report

Another milestone this year for ACT was the annual review that took place in July between USAID and UNDP. It provided an opportunity review annual progress of the first phase of ACT II (October 2008-June 2009) and strategize for the upcoming two years (July 2009-September 2011).

The objectives of the Annual Review were to:

- Review UNDP-ACT II Projects: Overview, Challenges & Opportunities and Financial Update

- Review the Operations and Financial aspect of UNDP-ACT II

- Review of UNDP-ACT Mid-Term Programme Outcome Evaluation Report

- Discuss Recommendations and Suggested Actions for the upcoming two years of UNDP-ACT II

The presentation delivered by UNDP-ACT staff included an overview of UNDP-ACT I accomplishments, the theoretical and practical foundations of ACT II, with a emphasis on the role of civil society in reconciliation process in Cyprus, as well as an analysis of the programme’s strengths, opportunities, weakness and threats found below:

| Strengths and Opportunities | Challenges and Threats |
| --- | --- |
| Experience, institutional knowledge and networks established | Volatile Political climate |
| Strategic link with the UN and diplomatic community | Public image and communications outreach |
| Improved relationship with authorities | Coordination between stakeholders, including donors and international community |
| Experience working with civil society in Cyprus | Collapse of the negotiations process or delayed solution |
| Staff capacity and experience | Limited direct relationships with the civil society sector as a result of new implementation arrangements |
| Capacity of NGO implementing partners |  |

UNDP-ACT and USAID staff also addressed the recommendations put forward in the mid-programme outcome report and developed suggested follow-up activities, as presented below:

| Recommendation | Suggested Action |
| --- | --- |
| Update Communications | Develop new communications and media strategy Update communications tools (website, etc) Regular partners meetings Common Message |
| Review Project Names | History project name changes Cyprus 2010 to Cyprus 2015 |
| Review Project Results Frameworks | All project RF’s have been revisited Ongoing process of revision and reflections |
| Establish an informal advisory group | The composition is to be agreed upon by the end of 2009 |
| Establish a Partners Forum | Bi-Annual Partners Meetings Initial linkages already established Communications linkages and sharing between partners Common message and communications |
| Adjust Management and Project Architecture | Revised management structure based on appropriate context |
| Establish a Civil Society Agenda on Reconciliation | ENGAGE take lead Partnership Meetings |
| Strengthen Leaders | Training Opportunities Build on each other’s strengths Resource mapping and sharing |
| Support ACT Team | Increase capacity training and opportunities for training for staff Flexibility in terms of working environment Retreats Facilitate active involvement of the Staff Association to Support the team |
| Establish and Share Good Practices | Increased input into knowledge networks |
| Reach Across the Aisle | Increased encouragement of partners to outreach Opportunities through the Good Offices and the Technical Committees Increased Communications Outreach |
| Explore Future Role | Increased dialogue with USAID about post-solution Strategic planning with UNDP |

The Annual Review was concluded with the following recommendations:

- In light of the extended experience for more than a decade with peacebuilding efforts through BDP and ACT, it should be explored how to increase knowledge sharing and development of lessons learned from past projects. It was also highlighted that the Peace and Development Advisor should be able to assist with this process.

- Communications strategy should be discussed and development in collaboration with the partners, to prepare for negative media coverage around peace efforts

- Approval mechanisms (should become more inclusiveContingency planning should be explored based on developments around the peace process

- ACT should continue its coordination and collaboration with organizations and groups funded by USAID and EU/EC funding sources.

- Changes in the political context and landscape should be continuously monitored and how it might influence the development of projects (including cultural heritage).

## NGO audit 2009

This year saw those NGO’s which received grants above $150 000 (NGO Project Cooperation Agreements) being externally audited for the period 2007-2008, which also provided a useful overview of best practices for managing civil society projects. All the local CSO partners justified their selection based on the Capacity Assessments, and received a clearance rating from Ernst & Young. However, there were some valuable suggestions which will be tracked and implemented under the existing projects. These trends and recommendations can be summarized as follows:

Finance and Accounting

Good practice should lead CSOs to have separate bank accounts for their project(s) funded by UNDP-ACT, and to keep up-to-date book-keeping systems covering all expenditure relating to these projects, which can be used as the basis for producing the final financial reports.

In addition, CSOs are not encouraged to issue cash payments. If such payments are unavoidable, they should establish a system for tracking such payments (i.e. an audit trail). In particular, for every cheque issued, an analysis should be made to detail expenditures covered by that cheque, or if payments are made through petty cash – a petty cash book with description of expenditures and an invoice or receipt should be maintained for each payment or groups of payments.

Human Resources

Working times to be charged should be properly recorded throughout the duration of the project by reliable means (e.g. time sheets or attendance records). A designated person should be responsible for certifying the accuracy and completeness of records. These records should be submitted as part of the final reports. Hiring processes for staff and consultants should be properly documented and should follow the standard process, including announcement for the position, evaluation of applicants, interviews and final selection.

Procurement

Existing procurement guidelines specified in the UNDP-ACT contracts should be followed.

Follow-up

In addition to informing all its partners of the above, UNDP-ACT has planned a training/workshop with the support of the audit company, to which all NGO partners will be invited and where the auditors will share with them good practices in the areas outlined above, including examples for procurement and HR processes, as well as simple tools for maintaining accounting records for those who will be interested. This workshop is planned for the 6th November.

# SECTION II - Progress during the past year

In 2008, the following results framework for Phase II was developed:

| Intended Focus Areas | Targets 2008-2011 | Milestones | Achievements |
| --- | --- | --- | --- |
| A. Civil society strengthened to effectively support and contribute to the peace process. | A. NGO legal reform advanced | 2008 – 2009: New draft law formulated and presented for discussion | The new draft NGO Legal Framework was formally launched after considerable consultations with various Departments and CSO groups. A working group has been established with Civil Society and the main findings from the project have been implemented in the draft NGO regulations. |
|  | Increased media coverage on the role of civil society in the peace process | 2008-2009: 20 news articles 2009-2010: 30 articles and broadcasts 2010 – 2011: 50 articles and broadcasts | A total of 186 positive media pieces were published/aired in the past year regarding ACT-sponsored reconciliation projects. A communications strategy and media strategy has also been developed for UNDP-ACT. |
|  | 9 cross-sectoral reconciliation opportunities launched involving at least two of the following: authorities, multi-stakeholder networks, youth organizations, CSOs and private sector. | 2008-2009: 2 Initiatives 2009-2010: 4 initiatives 2010-2011: 3 initiatives | In the past year, such activities launched have included: ENGAGE launch, 7 July: authorities and NGOs had a seminar on the role of civil society in the peace process Engage: the two implementing partners have consultations with authorities Youth Activism: on going collaboration of 12 organizations from both main communities, links also with teachers platforms, CMP team and other education related NGOs Multiperspectivity in Education: Collaborations with international organizations such as EUROCLIO and the Council of Europe |
| B. Opportunities for Cypriots to promote social and policy change on issues of common concern enhanced | Two pilot models for participatory decision-making developed and initiated. | 2008-2009: Partner consensus reached on participatory decision-making. 2009-2010: Two venues for pilot testing models identified with full ownership of local stakeholders. 2010 – 2011: Decision making process of two local authorities influenced by grass-roots participation. | A series of stakeholder consultations was held in early 2009 in view of launching the Participatory Development Initiative. The resulting views provided the raw material for the Request for Proposals now being advertised for implementation of this project. |
|  | Concrete policy reform agenda on history teaching developed and adopted by decision-makers | 2008-2009: Educational authorities encourage the use of teaching materials among teachers and schools through circulars and official notices. 2009-2010: pilot twinning arrangements created between GC and TC schools as a vehicle to road-test training materials 2010-2011: Inclusion of multi-perspective practices into work of Ministries and their in-service training as part of Curriculum development. | The textbooks developed by the Centre for Democracy and Reconciliation in South East Europe (CDRSEE) have been endorsed by educational authorities and have been disseminated to schools as supplementary teaching material |
|  | Two public sector bodies incorporate multicultural and diversity training as part of their core training scheme for new employees. | 2008-2009: Assessment report discussed by key stakeholders 2009- 2010: Training manual approved for use in selected public sector bodies 2010 – 2011: 20 Public servants trained in diversity methods. | Although an assessment mission and stakeholder consultations were organized in the Spring, the proposed “Diversity” initiative was not approved by the Programme Steering Committees. |
| Mechanisms to promote cooperation, common understanding and reconciliation fostered and demonstrated. | 6 cultural heritage monuments partially or fully restored | 2008-2009: Completed restorations - Peristerona House, Day Care centre, Prophet Elias 2009-2010: Restoration completed - Hammam 2010-201: Restorations completed – Armenian Church and Monastery, Preservation Circle | Three works were completed this year: the Peristerona House, the Day Care Centre at Paphos Gate, and the Prophet Elias Maronite Monastery. In addition, works began on the Armenian Church and Monastery and the Hammam is 50% complete. Finally, the works on Phase I of the Cultural Heritage Preservation Circle (Peace Park) were initiated. |
|  | Joint economic development plan discussed at the policy level | 2008-2009:TC and GC Chambers establish a framework to discuss the Economic plan 2009-2010: Evident public dialogue of the recommendations of the plan. 2010-2011: 50% of recommendations integrated into decision-making process. | The Interdependence project was launched in April 2009, and research has commenced on economic interdependence. Work on the bi-communal business directory has also begun, and the project has organized a series of high-profile advocacy events, including one involving the two Leaders, and one involving the former head of the EU Parliament. The Cyprus 2015 project has completed two interim reports on Sustainable Development based on a situation analysis and stakeholder interviews. The reports cover labour markets in the GCC and tourism, construction, commerce, industry, agriculture and banking in the TCC. |
|  | 6 key confidence building measures implemented with UNDP-ACT funding. | 2008-2009: 2 funded activities 2009-2010: 2 funded activities 2010-2011: 2 funded activities | Confidence-building measures implemented so far: Fiscal Federalism Conference, running bi-communal art exhibition at the Good Offices, Research on bi-communal opportunities for Recycling, Greek-Turkish forum meeting. In the pipeline are the water awareness island-wide campaign, support to the Cultural Heritage advisory board, and restoration of a facility for exchange of crime-related information. |

# SECTION III - Performance Indicator Framework 2008-2009

| Annual Targets for Common Spaces/Participatory Development | Final Achievement by 30 September 2009 |
| --- | --- |
| Stakeholder consensus reached on participatory decision-making | This was achieved during the consultancy mission in early 2009, which involved stakeholder consultations and a stakeholder workshop. |
| Annual Targets for Interdependence |  |
| At least 100 participants in public information events | Interdependence events totaled a cumulative total of 697 participants |
| At least 10 key stakeholders involved from each community | Aside from the Three Chambers, the project has enlisted the “Peace Economics” consortium to implement the research, which is composed of academics from both communities. In addition, cooperation with EDGE has been strengthened. |
| At least 6 seminars organized | Five events have been organized so far, with one additional event due October 30th |
| A conference will be organized to present the research results with the participation of at least 100 relevant stakeholders. | This has been postponed to the Spring of 2010 |
| Annual Targets for Cultural Heritage |  |
| 3 restoration projects completed | Prophet Elias, Day Care Centre and Peristerona House completed |
| Annual Targets for Support to Good Offices |  |
| 6 key confidence-building measures supported | Confidence-building measures implemented so far: Fiscal Federalism Conference, running bi-communal art exhibition at the Good Offices, Research on bi-communal opportunities for Recycling, Greek-Turkish forum meeting. In the pipeline are the water awareness island-wide campaign, support to the Cultural Heritage advisory board, and restoration of a facility for exchange of crime-related information. |
| Annual Targets for ENGAGE |  |
| Capacity of civil society enhanced to establish itself as a sustainable sector and a force for reconciliation in Cypriot society. | The project team is working to develop the network list and prepare the capacity assessment programme accordingly. Lists of consultant pools has also been created, with the possibility of including new consultants/ trainers to the pools,. Attemps to create a women’s network underway. Networks already approached: Development platforms,Youth Network, Criteria for the Small Funds Scheme are in the process of finalization and the call for applications is expected to be announced soon. |
| Public Awareness Campaign designed and delivered on the role of Civil Society | First media initiative and networking event was held on the 7th of July -“The role of civil society in supporting peace and reconciliation in Cyprus”. A very successful event, with high level participation and at least 100 NGO representatives as well as excellent media coverage. |
| Follow up study/assessment on the state of Cypriot Civil Society | 2 meetings of the advisory committees have taken place. Procurement process for the undertaking of the research has also been completed. |
| Monitoring and Evaluation programme developed. | The procurement exercise has been completed |
| Annual Targets for Youth |  |
| Opportunities for dialogue among youth increased | A number of events have already taken place: two youth camps with the participation of around 180 youth, youth exchanges with Bold Leaders and Northern Irish youth groups, |
| Public awareness on youth participation raised | Selection criteria for the youth parliament group have been set and youth have been selected. Two meetings have taken place so far. A bi-monthly magazine has been drafted, a communications stategy for the project has been developed. |
| Youth workers empowered. | Youth leaders have been identified and a number of trainings have taken place |
| Annual Targets for Multiperspectivity |  |
| Research and Evaluation reports produced | The new hired team has started developing the questionnaires to be used for the following research exercises on: Representations of history Mixed villages Benchmarking study on the educational system of Cyprus Funding from the EU has also been secured for the first two research exercises. The partner has announced the procurement exercise for research companies to undertake the data collection and conduct the focus group discussions |
| Archive and Library established | The team members are working on an Acquisition Policy for the Archive and Library which will be completed in October. |
| Teacher Training & Supplementary Materials produced | The partners are in the process of drafting a training framework for the MIDE project. To be completed by mid-October. The team is also organizing the launch of the Nicosia Is Calling booklets which will take place on October 10th. Additionally, a teacher training workshop with the Council of Europe and other partners is planned for November 6 & 7. |
| Policy Dialogue forums created | Preparations for the first policy dialogue workshop have started |
| Annual Targets for CCMC |  |
| CSO Consortium established and committed among the founding members. | Consortium established and Management Committee of 7 people elected who are meeting on a monthly basis. |
| Community Media Centre established and operational | Establishment of pre fabricated building at LPH is underway. Procurement for equipment, website and pool of consultants is in process. |
| Video and audio output produced and broadcast | 4 vodcasts, 1 podcast, 1 audio slide show, 1 blog, 2 radio spots and 1 video clip completed and disseminated. |
| Media skills training packages tailored for CSO’s developed and implemented. | Needs assessment of CSO’s completed and findings used as a basis to prepare a 6 month training and production plan which includes approximately 20 production and 15 training sessions. |
| Annual Targets for Cyprus 2015 |  |
| Capacity of local Cypriot team built to deliver the project | All staff provided with on the job training on participatory research |
| Research based reports and policy recommendations on two aspects of the Cyprus problem printed in a coherent monograph series | Interim reports on Daily Life and Sustainable development completed. The first public opinion poll commenced. |
| Public discourse campaign designed and implemented | Communications strategy developed. |

# SECTION IV - Organizational Networking Matrix

## List of organizations involved in ACT-funded projects during reporting period

| Number | Organization | Project | Role in Peacebuilding |
| --- | --- | --- | --- |
| 1 | Cyprus Chamber of Commerce and Industry | Interdependence | Economic interdependence between the two communities in Cyprus reinforced and nurtured as a vehicle to support reconciliation. |
| 2 | Turkish Cypriot Chamber of Commerce | Interdependence | Economic interdependence between the two communities in Cyprus reinforced and nurtured as a vehicle to support reconciliation. |
| 3 | Cyprus Turkish Chamber of Industry | Interdependence | Economic interdependence between the two communities in Cyprus reinforced and nurtured as a vehicle to support reconciliation. |
| 4 | The Management Centre | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process. |
| 5 | NGO Support Centre | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process. |
| 6 | DEX – ( partnership with a consortium of 20 CSOs pls see below) | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 7 | ADHD Support | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 8 | Soma Akriton | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 9 | The Management Centre | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 10 | NGO Support Centre | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 11 | Association of Historical Dialogue and Research | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 12 | AKOVA Women’s Association | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 13 | Biologists Association | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 14 | Cyprus Academic Forum | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 15 | Cyprus Film Archives | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 16 | Turkish Cypriot Diabetes Association | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 17 | Eastern Mediterranean Artists Association (EMAA) | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 18 | Environmental Society of Lefke | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 19 | European Network against Racism | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 20 | Future Worlds’ Centre (CNTI) | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 21 | International Children's Film Festival of Cyprus | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 22 | Cyprus EU Association (KAB) | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 23 | Action For Equality, Support, Antiracism (KISA) | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 24 | Olive Tree Music | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 25 | The Peace Centre | Cyprus Community Media Centre | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. |
| 26 | Cyprus Turkish Architects and Engineers Union (KTMMOB) | Cultural Heritage Preservation Circle | Expansion and/or establishment of inter-communal partnerships for sustainable development through cultural preservation (in relation with an inter-communal framework for participatory planning to be established) |
| 27 | Kontea Heritage Foundation | Cultural Heritage Preservation Circle | Expansion and/or establishment of inter-communal partnerships for sustainable development through cultural preservation (in relation with an inter-communal framework for participatory planning to be established) |
| 28 | Katokopia team | Katokopia | Expansion and/or establishment of inter-communal partnerships for sustainable development through cultural preservation (in relation with an inter-communal framework for participatory planning to be established) |
| 29 | Reconstruction and Resettlement Council | CH and Participatory Development | Expansion and/or establishment of inter-communal partnerships for sustainable development through cultural preservation (in relation with an inter-communal framework for participatory planning to be established) |
| 30 | Evkaf Administration | Restoration of Great Turkish Bath, and Armenian Church and Monastery | Expansion and/or establishment of inter-communal partnerships for sustainable development through cultural preservation |
| 31 | Association for the Welfare of People with Disabilities | Restoration of Day Care Center | Expansion and/or establishment of inter-communal partnerships for sustainable development through cultural preservation |
| 32 | Cultural Institute of Bishopric of Morphou | Restoration of Peristerona House | Expansion and/or establishment of inter-communal partnerships for sustainable development through cultural preservation |
| 33 | TC “Antiquities” | Armenian Church and Monastery | Expansion and/or establishment of inter-communal partnerships for sustainable development through cultural preservation |
| 34 | Armenian Prelacy | Armenian Church and Monastery | Expansion and/or establishment of inter-communal partnerships for sustainable development through cultural preservation |
| 35 | Department of Antiquities, GC | Armenian Church and Monastery | Expansion and/or establishment of inter-communal partnerships for sustainable development through cultural preservation |
| 36 | Soma Akriton | Youth Activism | Develop a common understanding on the role of youth in peace building which will be promoted island wide |
| 37 | North Cyprus Mediation Association | Youth Activism | Develop a common understanding on the role of youth in peace building which will be promoted island wide |
| 38 | Environmental Studies Centre (ESC) | Youth Activism | Develop a common understanding on the role of youth in peace building which will be promoted island wide |
| 39 | KAYAD Community Centre | Youth Activism | Develop a common understanding on the role of youth in peace building which will be promoted island wide |
| 40 | Doves Olympic Movement | Youth Activism | Develop a common understanding on the role of youth in peace building which will be promoted island wide |
| 41 | ADHD | Youth Activism | Develop a common understanding on the role of youth in peace building which will be promoted island wide |
| 42 | Frederick Research Centre | Youth Activism | Develop a common understanding on the role of youth in peace building which will be promoted island wide |
| 43 | Nicosia University Research Centre | Youth Activism | Develop a common understanding on the role of youth in peace building which will be promoted island wide |
| 44 | Foundation of Social and Political Studies | Youth Activism | Develop a common understanding on the role of youth in peace building which will be promoted island wide |
| 45 | HASDER | Youth Activism | Develop a common understanding on the role of youth in peace building which will be promoted island wide |
| 46 | Peace Players International | Youth Activism | Develop a common understanding on the role of youth in peace building which will be promoted island wide |
| 47 | European University Cyprus Research Center (EUC) | Youth Activism | Develop a common understanding on the role of youth in peace building which will be promoted island wide |
| 48 | KTOS | Multiperspectivity in Education and EUROCLIO | Build the capacity of educators to promote multiperspectivity in History Education to meet the needs of reconciliation and mutual understanding |
| 49 | KTOEOS | Multiperspectivity in Education and EUROCLIO | Build the capacity of educators to promote multiperspectivity in History Education to meet the needs of reconciliation and mutual understanding |
| 50 | POED | Multiperspectivity in Education and EUROCLIO | Build the capacity of educators to promote multiperspectivity in History Education to meet the needs of reconciliation and mutual understanding |
| 51 | OELMEK | Multiperspectivity in Education and EUROCLIO | Build the capacity of educators to promote multiperspectivity in History Education to meet the needs of reconciliation and mutual understanding |
| 52 | Association for Historical Dialogue and Research | Multiperspectivity in Education and EUROCLIO | Build the capacity of educators to promote multiperspectivity in History Education to meet the needs of reconciliation and mutual understanding |
| 53 | Council of Europe | Multiperspectivity in Education and EUROCLIO | Build the capacity of educators to promote multiperspectivity in History Education to meet the needs of reconciliation and mutual understanding |
| 54 | ETEK | CESF | Multi-disciplinary, multi-cultural environmental advocacy platform |
| 55 | KTMMOB | CESF | Multi-disciplinary, multi-cultural environmental advocacy platform |
| 56 | COAG | COAG organizational strengthening | Bi-communal organic farming advocacy group |
| 57 | MADAG | MADAG training farms | Bi-communal dairy farming advisory group |
| 58 | Unit of Environmental Studies | Pancyprian network of nature conservation organizations, Waterbirds project | Creation of online directories and databases of environmental efforts in both communities in view of creating an island-wide conservation network – also: island-wide scientific cooperation fo the monitoring of waterbirds. |
| 59 | Cyprus Game Fund | Waterbirds project, Biodiversity in the Buffer zone project | Island-wide wildlife monitoring scientific cooperation |
| 60 | Frederick University | Conservation of rare and endemic species in the buffer zone | Engage with local communities to empower them as custodians of a shared natural heritage through implementation of the plant micro-reserves concept |
| 61 | Institute of Earth, Ocean, Atmospheric and Environmental Sciences | Biodiversity in the buffer zone | Bi-communal scientific cooperation for conservation of shared natural heritage |
| 62 | AKTI | Recycling on Cycles, Network for a Sustainable Future | Projects aimed at using citizen participation as tools for an island-wide approach for sustainable development and integrated coastal zone management. Linked with CESF |
| 63 | Laona Foundation | Sustainable mining | Establishment of a bi-communal think tank for management of sites abandoned by the extractive industries |
| 64 | CING | Epidemiology of Cancer | Bi-communal partnership aimed at providing TC at-risk categories with screening and counseling in the GCC |
| 65 | Cyprus International Institute | Asthma and Allergies | Bi-communal scientific cooperation to help identify the causes of respiratory allergies in children |
| 66 | Cyprus Turkish Medical Association | Asthma and Allergies | Bi-communal scientific cooperation to help identify the causes of respiratory allergies in children |
| 67 | Intercultural Centre of Cyprus | Performing the Experience | Links created between the youth, parents and educators of Cyprus, Greek-Cypriots and Turkish-Cypriots, through theatre. Ties reinforced of the young people participating in the UNDP Youth Camps to be externalized and the participants’ experiences projected to the broad public. |
| 68 | Rooftop | Performing the Experience | Links created between the youth, parents and educators of Cyprus, Greek-Cypriots and Turkish-Cypriots, through theatre. Ties reinforced of the young people participating in the UNDP Youth Camps to be externalized and the participants’ experiences projected to the broad public. |
| 69 | American Academy (2 performances) | Performing the Experience | Links created between the youth, parents and educators of Cyprus, Greek-Cypriots and Turkish-Cypriots, through theatre. Ties reinforced of the young people participating in the UNDP Youth Camps to be externalized and the participants’ experiences projected to the broad public. |
| 70 | Paliometoho Lyceum | Performing the Experience | Links created between the youth, parents and educators of Cyprus, Greek-Cypriots and Turkish-Cypriots, through theatre. Ties reinforced of the young people participating in the UNDP Youth Camps to be externalized and the participants’ experiences projected to the broad public. |
| 71 | Ayia Fyla Lyceum | Performing the Experience | Links created between the youth, parents and educators of Cyprus, Greek-Cypriots and Turkish-Cypriots, through theatre. Ties reinforced of the young people participating in the UNDP Youth Camps to be externalized and the participants’ experiences projected to the broad public. |
| 72 | Polemidia Lyceum | Performing the Experience | Links created between the youth, parents and educators of Cyprus, Greek-Cypriots and Turkish-Cypriots, through theatre. Ties reinforced of the young people participating in the UNDP Youth Camps to be externalized and the participants’ experiences projected to the broad public. |
| 73 | Linopetra Lyceum | Performing the Experience | Links created between the youth, parents and educators of Cyprus, Greek-Cypriots and Turkish-Cypriots, through theatre. Ties reinforced of the young people participating in the UNDP Youth Camps to be externalized and the participants’ experiences projected to the broad public. |
| 74 | Dasoupolis Lyceum | Performing the Experience | Links created between the youth, parents and educators of Cyprus, Greek-Cypriots and Turkish-Cypriots, through theatre. Ties reinforced of the young people participating in the UNDP Youth Camps to be externalized and the participants’ experiences projected to the broad public. |
| 75 | Idalio Lyceum | Performing the Experience | Links created between the youth, parents and educators of Cyprus, Greek-Cypriots and Turkish-Cypriots, through theatre. Ties reinforced of the young people participating in the UNDP Youth Camps to be externalized and the participants’ experiences projected to the broad public. |
| 76 | Rizokarposso Gymnasium | Performing the Experience | Links created between the youth, parents and educators of Cyprus, Greek-Cypriots and Turkish-Cypriots, through theatre. Ties reinforced of the young people participating in the UNDP Youth Camps to be externalized and the participants’ experiences projected to the broad public. |
| 77 | Institute of Geopolitics | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process. |
| 78 | Sim TV | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process. |
| 79 | KISA - Action for Equality Support and Antiracism in Cyprus | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process. |
| 80 | Cyprus Turkish Diabetes Association | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process. |
| 81 | Turkish Cypriot Human Rights Foundation | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process. |
| 82 | Radio May | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process. |
| 83 | AKTI / Environmental Network | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process. |
| 84 | EU Association | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 85 | Kemal Saraçoğlu Vakfı | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 86 | Civil Society Support Team | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 87 | European Youth Forum | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 88 | INDEX - RESEARCH AND DIALOGUE | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 89 | Eastern Medditerranean University | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 90 | The Costas & Rita Severis Foundation | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 91 | PRIO Cyprus Centre | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 92 | The Association for Historical Dialogue and Research of Cyprus | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 93 | KTÜK | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 94 | KTÜK | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 95 | Feminist (FEMA) Workshop | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 96 | HAD | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 97 | CFPA | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 98 | Eastern Mediterranean Univeristy | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 99 | TC Human Rights Foundation | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 100 | Akova Women's Association | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 101 | UNDP | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 102 | CT Diabetes Association | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 103 | KAYAD | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 104 | CT Chamber of Commerce | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 105 | Radio May | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 106 | Cyprus Otonom Missing Persons | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 107 | Office of the President CSO Department | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 108 | Environmental Society of Lefke | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 109 | MEYAP | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 110 | KISA | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 111 | University of Cyprus | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 112 | Girl Guides | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 113 | Association of Historical Research and Dialogue | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 114 | Symfiniosis | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 115 | PEO | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 116 | Hands Across the Divide | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 117 | Pancyprian Volunteerism Coordinating Council | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 118 | Europa Donna | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 119 | University of Nicosia | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 120 | Prio | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 121 | European Youth Forum | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 122 | Cyprus Youth Council | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |
| 123 | Ministry of Interior | Engage | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process |

## Events organized under ACT-funded projects in the reporting period

| Number | Event | Objective | # Participants | # Female Participants | # Turkish Cypriot Participants | # Greek Cypriot Participants |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Final event for the project “Conservation of rare and endemic species in the buffer zone” | Event at Mammari village to empower local communities to become custodians of their shared natural resources, and to signal the creation of a network of plant-microreserves across the island | 330 | 150 | 15 | 315 |
| 2 | Final event for the project “Sustainable Mining” | Event co-organised by the Leventis foundation, aimed at publicly launching the report of the sustainable mining think-tank and ensuring the long-term viability of the group. Massive participation by relevant stakeholders, including the head of the EU representation in Cyprus. | 41 | 9 | 9 | 32 |
| 3 | Final event of the “asthma and allergies” project | Bi-communal seminar for the public and medical practitioners on the aetiology of respiratory illnesses. Significant participation by relevant stakeholders from both communities. | 50 | 22 | 7 | 33 |
| 4 | Workshop on bi-communal opportunities for recycling | Bi-communal workshop organized as part of the recycling feasibility study, and aimed at investigating scenarios for bi-communal cooperation on recycling issues | 35 | 13 | 5 | 24 |
| 5 | Common Spaces, Brainstorming workshop for design of the Common Spaces project | Stakeholder workshop aimed at identifying potential project partners and fine-tuning the outputs and activities planned under the project. Attendance by stakeholder representing a wide range of disciplines and sectors. | 31 | 10 | 12 | 15 |
| 6 | Diversity Project, Brainstorming workshop for design of the Diversity project | Stakeholder workshop aimed at identifying potential project partners and fine-tuning the outputs and activities planned under the project. Attendance by stakeholder representing a wide range of disciplines and sectors. | 15 | 7 | 4 | 11 |
| 7 | Conference on fiscal federalism | At the behest of the Economics Technical Committee, UNDP-ACT part-funded this awareness raising event about the costs and benefits of reconciliation, with renowned economists as keynote speakers. | 56 | 17 | 29 | 11 |
| 8 | Interdependence, Launch event | Announcement of the Interdependence project, including speeches by the two Leaders (Christophias and Talat). Attended by a large number of senior business leaders | 60 | 30 | 30 | 30 |
| 9 | Interdependence, Research launch event, 30 Jun 09 | Announcement of the Interdependence project research grants. Attended by a wide cross-section of the business sector from both communities. | 60 | 20 | 20 | 24 |
| 10 | CESF/NSF final event | Workshop to present and analyse the results of a bi-communal attitudes survey on integrate coastal management and opportunities for bi-communal cooperation on sustainable development issues. | 12 | 6 | 1 | 7 |
| 11 | Interdependence, CCCI Nicosia AGM | Members of the Nicosia business community were introduced to the Economic Interdependence project. | 350 | 60 | 0 | 350 |
| 12 | Interdependence, CCCI Limassol | Members of the Limassol business community were introduced to the Economic Interdependence project | 200 | 50 | 0 | 200 |
| 13 | CCMC, Consortium meeting | Member of the CCMC consortium decided on the management structure of the project in light of the project being approved | 7 | 3 | 4 | 2 |
| 14 | CCMC, Consortium meeting | Member of the CCMC consortium elected the Management Committee which consists of 7 CSO’s | 17 | 10 | 9 | 7 |
| 15 | CCMC, Management Committee Meeting | Members of the CCMC Management Committee finalized the TORs for staff, equipment and agreed on a draft Community Media charter for Cyprus | 7 | 3 | 4 | 2 |
| 16 | CCMC, Management Committee Meeting | Members of the CCMC Management Committee finalized Community Media charter for Cyprus | 8 | 4 | 4 | 2 |
| 17 | CCMC, Management Committee Meeting | Members of the CCMC Management Committee discussed the new premises, media needs survey results and finalized the new staff recruitment | 10 | 6 | 5 | 4 |
| 18 | Engage, The Role of Civil Society in Supporting Peace and Reconciliation – Workshop( closed) | The Engage project invited representatives from 22 CSOs to participate in a workshop session to discuss how civil society can support the peace process and concluded with a joint set of statements summarizing the workshop results. | 22 | 11 | 11 | 11 |
| 19 | Engage, The Role of Civil Society in Supporting Peace and Reconciliation – Conference (public) | The Engage project was launched to the media and public. George Iacovou and Mr. Özdil Nami provided opening remarks .Special Representative of the UN Secretary General in Cyprus Mr. Taye Brook Zerihoun, also, addressed the panel. Special guests Ambassador Mr. İlter Türkmen from Turkey and Professor Theodore Couloumbis from the University of Athens, Greece, shared their experiences and ideas about the broader factors impacting on the reconciliation process. Also Civil Society representatives presented the outcomes of the workshop that was held prior to the conference. | 134 | 34 | 40 | 74 |
| 20 | Engage, NGO-SC and MC Strategic training Workshop | The purpose of the meeting was to ensure that both centres and their stakeholders are informed about the project and contribute on its success. 17 people from the project team, centres board of directors and Overall Project Advisory Committee were present | 17 | 7 | 10 | 7 |
| 21 | Interdependence, Hans Pottering Event | Cypriot Chamber members from both communities met with the visiting former President of the European Parliament, Mr. Hans Pottering, to discuss Green Line Trade and other inter-communal issues. Mr. Pottering envisaged a key role for business leaders in the Peace Process. | 27 | 3 | 11 | 12 |
| 22 | MADAG training in TCC – Hygiene and Animal Health | EDGE took the lead in delivering training on dairy farming standards to Turkish Cypriot dairy farmers | 80 | 12 | 80 | 0 |
| 23 | MADAG training in TCC – artificial insemination and farm management | EDGE took the lead in delivering training on dairy farming standards to Turkish Cypriot dairy farmers | 40 | 6 | 40 | 0 |
| 24 | Rooftop Theatrical performance at the American Academy, 19 Nov 2008 | Present the theatrical performance and have a facilitated dialogue with youth afterwards | 32 | 15 | 2 | 30 |
| 25 | Rooftop Theatrical performance for Paliometocho Lyceum at Artos, 20 Nov 2008 | Present the theatrical performance and have a facilitated dialogue with youth afterwards | 42 | 25 | 2 | 40 |
| 26 | Rooftop Theatrical performance at Ayia Fyla Lyceum, Limassol, 21 Nov 2008 | Present the theatrical performance and have a facilitated dialogue with youth afterwards | 51 | 35 | 2 | 49 |
| 27 | Rooftop Theatrical performance at Polemidia Lyceum, Limassol, 27 Nov 2008 | Present the theatrical performance and have a facilitated dialogue with youth afterwards | 47 | 22 | 2 | 45 |
| 28 | Rooftop Theatrical performance for American Academy, 28 Nov 2008 | Present the theatrical performance and have a facilitated dialogue with youth afterwards | 32 | 15 | 2 | 30 |
| 29 | Rooftop Theatrical performance for Dasoupoli Lyceum, 2 Dec 2008 | Present the theatrical performance and have a facilitated dialogue with youth afterwards | 45 | 23 | 2 | 43 |
| 30 | Rooftop Theatrical performance for Rizokarposso Gymnasium, 3 Dec 2008 | Present the theatrical performance and have a facilitated dialogue with youth afterwards | 17 | 9 | 2 | 15 |
| 31 | Rooftop Theatrical performance for Idalio Lyceum at Artos, 5 Dec 2008 | Present the theatrical performance and have a facilitated dialogue with youth afterwards | 44 | 25 | 2 | 42 |
| 32 | EUROCLIO International Conference: Taking the perspective of the others: intercultural dialogue and teaching and learning history | Present multiperspective approaches to history teaching to Cypriot teachers based on experience with other teachers from the EU | 150 (80 from other countries) | 100 | 35 | 35 |
| 33 | Presentation of the CDRSEE Supplementary teaching material in Greek and Turkish language version, at Chateau Status, 9 Oct 2008 | Present the produced books to media, teachers and all those interested while advocating for their use by teachers | 50 | 31 | 28 | 22 |
| 34 | CDRSEE – Training of Trainers, 10-11 Oct 2008 | Train teacher trainers on how to use the newly developed CDRSEE history supplementary textbooks | 34 (four other) | 18 | 15 | 15 |
| 35 | CDRSEE, teachers training, 24 Jan 2009 | The already trained teachers to train their colleagues | 30 | 18 | 15 | 15 |
| 36 | CDRSEE, teachers training, 21 Feb 2009 | The already trained teachers to train their colleagues | 40 | 22 | 20 | 20 |
| 37 | Bi-communal art exhibition, 11 Sep 2009 | Meeting of the artists who have contributed works to the rotating art exhibition at the Good Offices with the two Leaders on the occasion of the start of Phase II of the reconciliation talks. Highly mediatised event. | 22 | 14 | 11 | 11 |
| 38 | Youth Activism, Cyprus Network for Youth Development, 11 Sep 2009 | Network meeting | 12 | 6 | 3 | 5 |
| 39 | Youth Activism, Preparatory Event by Mediation Association, 22 June 2009 | To introduce the new project | 14 | 7 | 13 |  |
| 40 | Youth Activism, Exchange Visits by Soma Akriton, 29 Jun - 6 Jul 2009 | A group of young Cypriots visited N.Ireland to study their bi-communal problem and see how the youth is dealing with this problem | 17 | 10 | 7 | 10 |
| 41 | Youth Activism, Exchange Visits by Soma Akriton, 12 - 25 Jul 2009 | A group from N.Ireland visited Cyprus in order to study the Cyprus problem and to work with the youth of Cyprus | 12 | 6 |  |  |
| 42 | Youth Activism, Exchange Visits by Soma Akriton, 17 Jul - 3 Aug 2009 | A group of young Cypriots travelled to USA and work together for 2 weeks | 6 | 3 | 3 | 3 |
| 43 | Youth Activism, 3-Day Peace Camp, 26 - 28 Jun 09 | To introduce the project and to have workshops on peace | 88 | 50 |  | 88 |
| 44 | Youth Activism, Training Workshops before the ‘Olympism for Peace’ Summer Camp, 29 Jun - 2 Jul 09 | Train the instructors and youth leaders on several topics that will be examined during the camp. | 27 | 16 | 12 | 14 |
| 45 | Youth Activism, Environment and Peace Summer Camp, 2 Jul - 8 Jul 09 | To bring together the youth from both communities, To increase activism amongst Cypriot Youth, encourage self development of participants, provide environmental education and skills for conflict resolution and peace building. In addition create lasting friendships between youth across Cyprus | 53 | 25 | 31 | 21 |
| 46 | Youth Activism, “Olympism for Peace” Summer Camp 2009, 21-27 Jul 2009 | Summer Camp-Peace-education, Conflict-Resolution, Action Plans for after-camp year-long activities that aim in supporting the peace-building efforts in Cyprus | 113 | 53 | 59 | 53 |
| 47 | Youth Activism, 1st After-Camp activity of ‘Olympism for Peace’ camp, 20 Aug 09 | -First after-camp meeting of the participants to finalize the final details and resolve logistical and other practical problems they have identified. They were given life-guard lessons. they had the opportunity to interact with each other and foster stronger relationships | 45 | 20 | 20 | 25 |
| 48 | Youth Activism, Youth Leader Training, 28 Aug - 4 Sep 09 | To provide foundation training in essential skills and concepts for activism | 18 | 9 | 9 | 9 |
| 49 | Youth Activism, Peacebuilding Workshop by Soma Akriton, 19 Sep 09 | To provide opportunities for dialogue among youth | 42 | 27 | 18 | 24 |
| 50 | Youth Activism, Peace building as human right by Mediation Association, 19 Sep 09 | To provide opportunities for dialogue among youth | 16 | 11 | 15 |  |
| 51 | Youth Activism, Preparatory event by Soma Akriton, 12 Sep 09, 23 Sep 09, 26 Sep 09 | To introduce the project to newcomers | 130 | 72 |  | 130 |
| 52 | Youth Activism, Earthdance festival: 4 on 4 Streetball Tournament, 26 Sep 09 | To bring together GC and TC children through the game of basketball. | 150 | 50 | 80 | 70 |
| 53 | Youth Activism, Music and dance event, 26 Sep 09 | To bring together G/C and T/C children and youth through music and dancing | 800 |  | 650 | 150 |
| 54 | Youth Activism, Youth Representative Committee, 26 Sep 09 | To create a youth core that will represent the network and the project. This was an introductory event to organize the committee | 29 | 20 | 11 | 18 |
| 55 | Youth Activism, Magazine Contribution (1st Issue), Jul-Sep 09 | To provide an outlet where youth can express themselves and talk about their experiences. Also, to promote the network and its goals, as well as the project | 25 | 13 | 4 | 19 |
| 56 | Engage, Consultation meeting for network inception of a women’s network | Women’s network consultation meeting, to explore the potential of forming a women’s network | 5 | 5 | 3 | 2 |
| 57 | Engage, CIVICUS Advisory Committee Meeting | CIVICUS AC Meeting for the TCC | 7 | 3 | 7 | 0 |
| 58 | Engage, CIVICUS Advisory Committee Meeting | CIVICUS AC Meeting for the TCC | 9 | 4 | 0 | 9 |
| 59 | Consultation meeting with the GTF | Meeting to explore the possibilities of organizing a joint event on International Peace Day | 9 | 3 | 3 | 4 |
| 60 | Multiperspectivity, Youth Camp Workshop, 25 Jul 09 | The aim of the workshops was to inform young people about the Home for Cooperation and other AHDR activities, including the Multiperspectivity Project, and to incorporate their ideas into future plans. | 98 | 43 | 44 | 54 |
| 61 | Multiperspectivity, Research Overview Meeting, 11 Sep 09 | A session was organized to present and discuss the research projects. The objectives, rationale and methodology was discussed with the group of researchers and the Multiperspectivity team members. | 15 | 11 | 4 | 11 |

## Media coverage of ACT programmatic activities over the past year

| Number | Date | Name of paper/radio program/TV station | Title of Story | Project Name or Description |
| --- | --- | --- | --- | --- |
| 1 | 05/10/2008 | Yeniduzen | The family is 84,9 percent responsible | Asthma and Allergies |
| 2 | 10/10/2008 | Alithia | 4 topics, 4 textbooks, 4 colours | CDRSEE |
| 3 | 10/10/2008 | Cyprus Weekly | Books take new look at history (launch in Nicosia follows presentations in Balkans) | CDRSEE |
| 4 | 10/10/2008 | Cyprus Mail | History books start the rewriting process (Hearing the other does not mean our own annihilation) | CDRSEE |
| 5 | 11/10/2008 | Politis | All the books are being revisited | CDRSEE |
| 6 | 13/10/2008 | Haravgi | We need a history that unites | CDRSEE |
| 7 | 22/10/2008 | CYBC | Growing prevalence of allergies in children | Asthma and Allergies |
| 8 | 03/11/2008 | Halkin Sesi | EU certificate process in organic farming course | COAG |
| 9 | 03/11/2008 | Halkin Sesi | Organic agriculture seminar organised | COAG |
| 10 | 03/11/2008 | Yeniduzen | Organic agriculture EU certification process course | COAG |
| 11 | 03/11/2008 | Kibrisli | (16) Organic agriculture EU certification process course | COAG |
| 12 | 03/11/2008 | Ortam | Works continues to develop organic production | COAG |
| 13 | 04/11/2008 | Cyprus Weekly | Bi communal meeting on the environment | COAG |
| 14 | 05/12/2008 | Politis | Reduce Reuse-recycle | Recycling on Cycles |
| 15 | 05/12/2008 | Halkin Sesi | The buffer zone has become a wildlife refuge | Biodiversity in the buffer zone |
| 16 | 05/12/2008 | Kibris | The construction boom and the stone pits are affecting the environment | Biodiversity |
| 17 | 05/12/2008 | Yeniduzen | The buffer zone has become a de-facto refuge for the wildlife | Biodiversity in the buffer zone |
| 18 | 05/12/2008 | Kibrisli | UNDP worried about the environmental damage | Biodiversity |
| 19 | 06/12/2008 | Politis | Environmental Awards | Recycling on Cycles |
| 20 | 12/01/2009 | CYBC | Asthma and quality of air in outdoor and indoor environments | Asthma and Allergies |
| 21 | 12/01/2009 | Phileleftheros | Recycling feasibility study | Good Offices Support - Recycling |
| 22 | 13/01/2009 | Phileleftheros | Recycling feasibility study | Good Offices Support - Recycling |
| 23 | 18/03/2009 | All major newspapers | Launch of Interdependence project | Interdependence |
| 24 | 18/03/2009 | All major newspapers | Launch of the Interdependence project | Interdependence |
| 25 | 18/03/2009 | All major newspapers | Launch of the Interdependence project | Interdependence |
| 26 | 18/03/2009 | All major newspapers | Launch of the Interdependence project | Interdependence |
| 27 | 18/03/2009 | All major newspapers | Launch of the Interdependence project | Interdependence |
| 28 | 18/03/2009 | All major newspapers | Launch of the Interdependence project | Interdependence |
| 29 | 18/03/2009 | All TV stations from both communities | Launch of the Interdependence project | Interdependence |
| 30 | 18/03/2009 | All TV stations from both communities | Launch of the Interdependence project | Interdependence |
| 31 | 18/03/2009 | All TV stations from both communities | Launch of the Interdependence project | Interdependence |
| 32 | 18/03/2009 | All TV stations from both communities | Launch of the Interdependence project | Interdependence |
| 33 | 18/03/2009 | All TV stations from both communities | Launch of the Interdependence project | Interdependence |
| 34 | 18/03/2009 | All TV stations from both communities | Launch of the Interdependence project | Interdependence |
| 35 | 06/04/2009 | Phileleftheros | EUROCLIO Conference | EUROCLIO |
| 36 | 06/04/2009 | BRT | "EUROCLIO holds its Annual Conference in Cyprus this year" | EUROCLIO |
| 37 | 06/04/2009 | UNFICYP website | UNFICYP Head Supports More Diverse Vision of History in Cyprus | EUROCLO |
| 38 | 07/04/2009 | Kibris | Euroclio Conference | EUROCLIO |
| 39 | 07/04/2009 | Alithia | Euroclio Conference | EUROCLIO |
| 40 | 07/04/2009 | Phileleftheros | EUROCLIO Conference | EUROCLIO |
| 41 | 11/04/2009 | Talk of the Island, Radio | Euroclio Conference, Interview by Chara Makriyianni and Joke Van Der Leew (Euroclio) | EUROCLIO |
| 42 | 28/04/2009 | Cyprus Mail | Biodiversity in the Buffer Zone | Biodiversity in the buffer zone |
| 43 | 03/05/2009 | Sunday Mail | Biodiversity in the buffer zone | Biodiversity in the buffer zone |
| 44 | 10/05/2009 | Phileleftheros | Global Compact Survey | Global compact survey |
| 45 | 24/05/2009 | Politis | Euroclio Conference | EUROCLIO |
| 46 | 26/05/2009 | Halkin Cesi | There are 300 quarries in the northern part of Cyprus | Sustainable Mining |
| 47 | 27/05/2009 | France 5 | Biodiversity in the Buffer Zone | Biodiversity in the buffer zone |
| 48 | 29/05/2009 | Cyprus Weekly | Healing nature's man-made wounds | Sustainable Mining |
| 49 | 31/05/2009 | Kibris | Turkish Cypriot and Greek Cypriot artists to exhibit their work | Good Offices Support - Art Exhibition |
| 50 | 31/05/2009 | Halikin Sesi | Greek Cypriot and Turkish Cypriot artists support the peace process | Good Offices Support - Art Exhibition |
| 51 | 31/05/2009 | Yeni Duzen | Greek Cypriot and Turkish Cypriot artists support the peace process | Good Offices Support - Art Exhibition |
| 52 | 31/05/2009 | Havadis | Art attack by the UN | Good Offices Support - Art Exhibition |
| 53 | 01/06/2009 | Politis | Art, an ally of Christophias and Talat | Good Offices Support - Art Exhibition |
| 54 | 01/06/2009 | Reuters | Coffee, tights keep Cyprus leaders company in talks | Good Offices Support - Art Exhibition |
| 55 | 06/06/2009 | The voice of Our Island –Radio Mayis | Peace Nature Summer Camp | Youth Activism |
| 56 | 09/06/2009 | ‘Bir Yaşam Biçim i’ - Radio Mayis | Peace Nature Summer Camp | Youth Activism |
| 57 | 11/06/2009 | Sigma | Asthma research findings | Asthma and Allergies |
| 58 | 11/06/2009 | Phileleftheros | Coverage of research findings of asthma project | Asthma and Allergies |
| 59 | 11/06/2009 | Politis | Coverage of research findings of asthma project | Asthma and Allergies |
| 60 | 11/06/2009 | Alithia | Coverage of research findings of asthma project | Asthma and Allergies |
| 61 | 11/06/2009 | Simerini | Coverage of research findings of asthma project | Asthma and Allergies |
| 62 | 12/06/2009 | Phileleftheros | Coverage of research findings of asthma project | Asthma and Allergies |
| 63 | 12/06/2009 | Politis | Coverage of research findings of asthma project | Asthma and Allergies |
| 64 | 12/06/2009 | Alithia | Coverage of research findings of asthma project | Asthma and Allergies |
| 65 | 12/06/2009 | Simerini | Coverage of research findings of asthma project | Asthma and Allergies |
| 66 | 15/06/2009 | Kibris | Prize for Biodiversity project | Biodiversity in the buffer zone |
| 67 | 16/06/2009 | ‘Biz/ Emeis’ - RIK 2 Television program | Peace Nature Summer Camp | Youth Activism |
| 68 | 17/06/2009 | BBC World Service | Biodiversity in the Buffer Zone | Biodiversity in the Buffer Zone |
| 69 | 20/06/2009 | RIK Radio3 | Peace Nature Summer Camp | Youth Activism |
| 70 | 23/06/2009 | Genc TV – Ak;am Saati | 2-8 July multicultural Summer Camp Final Announcement | Youth Activism |
| 71 | 24/06/2009 | KISS FM | Advertising of Peaceful Nature Summer Camp with hourly announcements | Youth Activism (for 6 days) |
| 72 | 25/06/2009 | BRT Radio | 2-8 July multicultural Summer Camp Awareness raising and Final Announcement | Youth Activism |
| 73 | 26/06/2009 | Politis | Paid advertisement for Peaceful Nature Summer Camp Awareness raising and final call for GC participants | Youth Activism |
| 74 | 26/06/2009 | Phileleftheros | Paid advertisement for Peaceful Nature Summer Camp Awareness raising and final call for GC participants | Youth Activism |
| 75 | 26/06/2009 | Radio Super Sport FM | Interview re 2-8 July Peaceful Nature Summer Camp Awareness raising and final call for GC participants | Youth Activism |
| 76 | 26/06/2009 | RIK 1 Eng Radio prog. (Rosie Charalambous) | Interview re 2-8 July Peaceful Nature Summer Camp Awareness raising and final call for GC participants | Youth Activism |
| 77 | 26/06/2009 | Radio Astra | Advertising of Peaceful Nature Summer Camp with hourly announcements | Youth Activism (for 6 days) |
| 78 | 30/06/2009 | Radio Energy | Interview re 2-8 July Peaceful Nature Summer Camp Awareness raising and final call for GC participants | Youth Activism |
| 79 | 30/06/2009 | GC and TC TV stations | Interdependence launch event | Interdependence |
| 80 | 30/06/2009 | SIM FM | Interdependence launch event | Interdependence |
| 81 | 01/07/2009 | Haravgi | Studies on economic interdependence announced by UNDP and CCCI | Interdependence |
| 82 | 01/07/2009 | Kibris | For a Common Future | Interdependence |
| 83 | 01/07/2009 | Yeni Duzen | Common Economic Interdependence Project Introduced | Interdependence |
| 84 | 01/07/2009 | Halkin Sesi | Project for Establishing Bi-Communal Partnerships | Interdependence |
| 85 | 01/07/2009 | Havadis | Showcase Project for the Business Community | Interdependence |
| 86 | 02/07/2009 | Phileleftheros | Studies on economic interdependence between GCs and TCs – funded by the United Nations | Interdependence |
| 87 | 02/07/2009 | Politis | Cooperation between CCCI and TCC on economic interdependence- Towards strengthening financial relations. | Interdependence |
| 88 | 02/07/2009 | Simerini | With UNDP Funding: Studies on economic interdependence between GC and TC | Interdependence |
| 89 | 02/07/2009 | Alithia | Multiple economic benefits from the reunification of Cyprus- A tender for studies on economic interdependence between GC and TCs” | Interdependence |
| 90 | 02/07/2009 | Phileleptheros | "The Businessmen” By George Frangos | Interdependence |
| 91 | 04/07/2009 | Cyprus Today | Article on the Interdependence project | Interdependence |
| 92 | 04/07/2009 | Phileleftheros P 4 | Discussion on the role of society in efforts to find a solution | Engage |
| 93 | 04/07/2009 | Alithia P 5 | Bicommunal Conference : The role of civil society in a solution | Engage |
| 94 | 04/07/2009 | Cyprus Mail P 5 | The role of Civil Society in Supporting Peace & Reconciliation | Engage |
| 95 | 05/07/2009 | Phileletheros P 49 | Former Turkish Foreign Minister in a conference in Nicosia | Engage |
| 96 | 05/07/2009 | Politis P 96 | The role of Civil Society in Supporting Peace & Reconciliation | Engage |
| 97 | 05/07/2009 | Cyprus Mail P 11 | The role of Civil Society in Supporting Peace & Reconciliation | Engage |
| 98 | 05/07/2009 | Havadis | KAYAD ile Güney Kıbrıs Çevre Çalışmaları Merkezi’nin iki toplumlu kampı | Youth Activism |
| 99 | 05/07/2009 | KIBRIS | KAYAD ile Güney Kıbrıs Çevre Çalışmaları Merkezinden ortak çalışma | Youth Activism |
| 100 | 05/07/2009 | Afrika | ‘Barışcıl Doğa Kampı’ Başladı | Youth Activism |
| 101 | 05/07/2009 | Yenıdüzen | KAYAD ile Güney Kıbrıs Çevre Çalışmaları Merkezi’nin ‘Barışcıl Doğa Kampı’ başladı… | Youth Activism |
| 102 | 05/07/2009 | BRT TV – Evening News | Peaceful Nature Summer camp, Images from the camp in workshops and press conference | Youth Activism |
| 103 | 05/07/2009 | Ada TV – Evening News | Peaceful Nature Summer camp, Images from the camp in workshops and press conference | Youth Activism |
| 104 | 05/07/2009 | Genc TV - Evening News | Peaceful Nature Summer camp, Images from the camp in workshops and press conference | Youth Activism |
| 105 | 05/07/2009 | Tempo TV- Evening News | Peaceful Nature Summer camp, Images from the camp in workshops and press conference | Youth Activism |
| 106 | 05/07/2009 | AS TV-Evening News | Peaceful Nature Summer camp, Images from the camp in workshops and press conference | Youth Activism |
| 107 | 05/07/2009 | Akdeniz TV – Evening News | Peaceful Nature Summer camp, Images from the camp in workshops and press conference | Youth Activism |
| 108 | 06/07/2009 | Volkan | Yabancı paraları ile gençlerimizin Türk Kimliğinin değiştirilerek Rumlara ortak ‘Kıbrıslı’ kimliği aşılama çabaları yeniden hızlandı | Youth Activism |
| 109 | 06/07/2009 | Phileleftheros P 13 | The role of Civil Society in Supporting Peace & Reconciliation” | Engage |
| 110 | 07/07/2009 | Afrika | Civil Society contributes to Peace | Engage |
| 111 | 07/07/2009 | Yenidüzen | Civil Society enhances steps to contribute to Peace | Engage |
| 112 | 07/07/2009 | CybC1 (news at 23.00) | Reading the press release and showed scenes from the 7th July event | Engage |
| 113 | 07/07/2009 | CnC Plus (news at 23.00 | Reading the press release and showed scenes from the 7th July event | Engage |
| 114 | 08/07/2009 | Cyprus Mail | Peace is much too important to be left to politicians | Engage |
| 115 | 08/07/2009 | Havadis | Civil Society has an important role to play in peace | Engage |
| 116 | 08/07/2009 | Yenidüzen | Nami: Civil Society efforts help us | Engage |
| 117 | 08/07/2009 | Alithia | The Role of the civil society is important in the achievement of a solution | Engage |
| 118 | 08/07/2009 | Phileleftheros | Role of the citizens | Engage |
| 119 | 08/07/2009 | Politis | Politicians are not in a hurry – The UN calls on the civil society to promote the benefits of a solution | Engage |
| 120 | 08/07/2009 | Kibris | Zerihoun: Everyone should contribute to a solution | Engage |
| 121 | 08/07/2009 | Sigma TV | Reading the press release and showed scenes from the event | Engage |
| 122 | 12/07/2009 | Phileleftheros | The TC should decide what they want – Ilker Turkment: All plans submitted for the Cyprus Issue are on the table | Engage |
| 123 | 16/07/2009 | Alithia P 10 | Unbearable responsibilities on the shoulders of the civil society” by Takis Konis | Engage |
| 124 | 17/07/2009 | Alithia Newspaper | Peaceful Nature in Cyprus | Youth Activism |
| 125 | 17/07/2009 | Cyprus Weekly | Women's show at UN | Good Offices Support - Art Exhibition |
| 126 | 17/07/2009 | Alithia P 18 | Peaceful nature in Cyprus | Youth Activism |
| 127 | 20/07/2009 | Yeniduzen | Article on the Interdependence project | Interdependence |
| 128 | 22/07/2009 | Politis Newspaper | “ Campaign in favour of diversity. Against Discrimination” | Youth Activism |
| 129 | 23/07/2009 | Local TV channels from Limassol “Extra TV” and “Capital TV | Coverage of the Camp, its Program and Objectives | Youth Activism |
| 130 | 29/07/2009 | Cyprus Mail P 30 | Peaceful Nature Summer Camp | Youth Activism |
| 131 | 04/08/2009 | Alithia | UNDP scenarios for the cooperation between the two communities | Good Offices - Recycling Feasibility Study |
| 132 | 05/08/2009 | Youtube | Historic Event in Cyprus 0ver 500 hits – The role of Civil Society in Peacebuilding | Engage/CCMC |
| 133 | 09/08/2009 | Politis Newspaper | “ Soma Akriton knows about co-habitation and peace and is teaching us - Youths are united and unite us” | Youth Activism |
| 134 | 10/08/2009 | Alithia Newspaper | “ Cypriot youths compare the problems of Cyprus and Northern Ireland – We want a common future, youths declare | Youth Activism |
| 135 | 11/08/2009 | France 5 TV (Report-Terre) | Report Terre | Interdependence |
| 136 | 16/08/2009 | France 5 TV (Report-Terre) | Report Terre | Interdependence |
| 137 | 29/08/2009 | Kibris | Pottering in the southern part of Cyprus | Interdependence |
| 138 | 29/08/2009 | Yeni-Duzen | Pottering in Cyprus | Interdependence |
| 139 | 30/08/2009 | Halkin Sesi | Pottering in Cyprus | Interdependence |
| 140 | 30/08/2009 | Havadis | Pottering coming to Cyprus | Interdependence |
| 141 | 30/08/2009 | Phileleftheros | Pottering visit | Interdependence |
| 142 | 31/08/2009 | Simerini | Pottering visit | Interdependence |
| 143 | 31/08/2009 | ANT-1 TV | Interdependence Pottering event | Interdependence |
| 144 | 01/09/2009 | Kibris | Do the Best You Can for Cyprus to be United States Mr. Pottering | Interdependence |
| 145 | 01/09/2009 | Halkin Sesi | Do the Best You can for Cyprus to be United States Mr. Pottering | Interdependence |
| 146 | 01/09/2009 | Havadis | You will have a Stronger Voice if Cyprus Unites | Interdependence |
| 147 | 01/09/2009 | Yeni Duzen | Do the Best you can for Unification says Mr. Pottering | Interdependence |
| 148 | 01/09/2009 | Simerini | Meeting with GC and TC businessmen | Interdependence |
| 149 | 02/09/2009 | Cyprus Mail | Pottering hopeful for reunification | Interdependence |
| 150 | 02/09/2009 | Alithia | Pottering - Businessmen have a role | Interdependence |
| 151 | 02/09/2009 | Haravgi | A reunited Cyprus will have a stronger voice | Interdependence |
| 152 | 02/09/2009 | Phileleptheros | Pottering said: "The fact that GC and TC businessmen meet, is a good sign for reunification" | Interdependence |
| 153 | 08/09/2009 | Havadis newspaper | “To have Cypriot youth voice heard” | Youth Activism |
| 154 | 09/09/2009 | Haravgi | Exhibition of GC and TC artists | Good Offices Support - Art Exhibition |
| 155 | 09/09/2009 | Phileleftheros | Talks with art work as background | Good Offices Support - Art Exhibition |
| 156 | 10/09/2009 | Kibris | They will add colours to the negotiations process - Bi-communal ‘Two/Four/two’ art exhibition to be opened today - covered by all TC papers | Good Offices Support - Art Exhibition |
| 157 | 10/09/2009 | Yeni-Duzen | They will add colours to the negotiations process - Bi-communal / ‘Two/Four/two’ art exhibition to be opened today - covered by all TC papers | Good Offices Support - Art Exhibition |
| 158 | 10/09/2009 | Halkin Sesi | They will add colours to the negotiations process - Bi-communal / ‘Two/Four/two’ art exhibition to be opened today - covered by all TC papers | Good Offices Support - Art Exhibition |
| 159 | 10/09/2009 | Havadis | They will add colours to the negotiations process - Bi-communal - ‘Two/Four/two’ art exhibition to be opened today - covered by all TC papers | Good Offices Support - Art Exhibition |
| 160 | 10/09/2009 | Kibrisli | They will add colours to the negotiations process - Bi-communal - ‘Two/Four/two’ art exhibition to be opened today - covered by all TC papers | Good Offices Support - Art Exhibition |
| 161 | 10/09/2009 | Afrika | They will add colours to the negotiations process - Bi-communal - ‘Two/Four/two’ art exhibition to be opened today - covered by all TC papers | Good Offices Support - Art Exhibition |
| 162 | 11/09/2009 | Kibris | Painted and exhibited for a solution | Good Offices Support - Art Exhibition |
| 163 | 11/09/2009 | Afrika | Art support for the negotiations | Good Offices Support - Art Exhibition |
| 164 | 11/09/2009 | Halkin Sesi | Art support for the negotiations | Good Offices Support - Art Exhibition |
| 165 | 11/09/2009 | Havadis | Artists set example for the Leaders | Good Offices Support - Art Exhibition |
| 166 | 11/09/2009 | Yeni-Duzen | To a Hopeful Start – Art Support for the Negotiations | Good Offices Support - Art Exhibition |
| 167 | 11/09/2009 | Kibrisli | Art support to the negotiations process | Good Offices Support - Art Exhibition |
| 168 | 11/09/2009 | Phileleftheros | Artists show the way | Good Offices Support - Art Exhibition |
| 169 | 11/09/2009 | Haravgi | An artistic challenge for peace-reunification | Good Offices Support - Art Exhibition |
| 170 | 11/09/2009 | Cyprus Mail | A sorry state of affairs | Good Offices Support - Art Exhibition |
| 171 | 11/09/2009 | Cyprus weekly | New Phase | Good Offices Support - Art Exhibition |
| 172 | 11/09/2009 | Politis | Hopes for the questions of government | Good Offices Support - Art Exhibition |
| 173 | 11/09/2009 | Mega | Main News - report on the exhibition | Good Offices Support - Art Exhibition |
| 174 | 11/09/2009 | Alithia | GC and TCs artists have overtaken the leaders | Good Offices Support - Art Exhibition |
| 175 | 11/09/2009 | BRT (TV) | Coverage of the visit by the two leaders of the bi-communal art exhibition at the good offices | Good Offices Support - Art Exhibition |
| 176 | 17/09/2009 | Yeni Duzen | These Children are Looking at You – Art Installation by Emin Cizenel at the Negotiations Room | Good Offices Support - Art Exhibition |
| 177 | 18/09/2009 | Alithia | Environmental GC and TC forum | CESF |
| 178 | 19/09/2009 | Politis Newspaper | Cyprus Participates in the Earthdance 2009 Festival | Youth Activism |
| 179 | 26/09/2009 | Havadis | “Earth dance excitement in Nicosia” | Youth Activism |
| 180 | 26/09/2009 | Afrika | “Earth dance activity at Selimiye square “ | Youth Activism |
| 181 | 26/09/2009 | Yeni Duzen | Earthdance | Youth Activism |
| 182 | 26/09/2009 | Kibris | Earthdance | Youth Activism |
| 183 | 27/09/2009 | Kibris | Dance for peace – Bi communal Dance and Music Festival was held at Selimiye square yesterday | Youth Activism |
| 184 | 27/09/2009 | Halikin Sesi | Dance for peace – Bi communal Dance and Music Festival was held at Selimiye square yesterday | Youth Activism |
| 185 | 28/09/2009 | Politis | At meeting Hall 1 – The children stare the two leaders in the eye | Good Offices Support - Art Exhibition |
| 186 | 07/05/2008 | Cyprus Mail | Return to a Past Glory | Armenian Church and Monastery |

# SECTION V - PROJECT PROGRESS IN QUARTER 3 OF 2009

| Project ID | Name of Activity | Relevant ACT Targets | Intended Project Results | Implementor | Start Date | End Date | Progress Q3 2009 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 47351 - SI Education | CDRSEE (History Teachers Training) | (Phase I): 15 Multicultural educational initiatives established | Understanding about multi-perspective history lessons enhanced among teachers. | CDRSEE | 15/04/2007 | 31/07/2009 | The supplementary history textbooks that have been developed have been endorsed by the authorities and have been disseminated to schools. The project has been completed in a timely manner. |
| 47351 - SI Education | Intercultural Dialogue and History | (Phase I): 15 Multicultural educational initiatives established | A core group of highly committed and motivated history educators and trainers in a network of professionals empowered and developed for sustainable future cooperation | EUROCLIO | 30/11/2007 | 15/05/2009 | The project came to a closure after the successful conference organized in Spring of 2009. The partner is in the process of printing the conference proceedings. |
| 47401 - SI Sustainable Dev | Waterbird Surveillance Programme | (Phase I): At least 3 ACT-supported bi-communal advisory groups achieve sustainability | Creation of an Island-wide waterbird surveillance programme with an online database and promoting awareness. | Unit of Environmental Studies | 08/05/2007 | 31/12/2008 | All project deliverables delivered, but project extended to September to issue a second publication on the waterbirds of Cyprus using savings incurred. |
| 47401 - SI Sustainable Dev | Rare and Endemic Species in the Buffer Zone | (Phase I): At least 3 ACT-supported bi-communal advisory groups achieve sustainability | The current situation assessed and awareness on biodiversity conservation and environmental values among GCC and TCC promoted. | Frederick University | 14/04/2007 | 30/04/2009 | Project completed, and will continue henceforth with EU LIFE+ funds. UNDP-ACT will provide an in-kind contribution (laboratory facilities). |
| 47401 - SI Sustainable Dev | Sustainable use of abandoned mines and quarries | (Phase I): At least 2 new intercommunal sustainable development CSO joint ventures established | 1. Set up and operate Think Tank under auspices of CESF 2. Establish premises of Think Tank 3. Cyprus-wide study of abandoned mines and quarries examining impacts and potential sustainable re-use 4. Site-specific study of the Apliki-Mavrovouni-Skouriotissa mines complex (that supplied the ore for the Xeros-Lefke Treatment area). 5. Publication of final report in English with summaries in Greek and Turkish. | Laona Foundation | 22/08/2007 | 31/03/2009 | Project completed. The Think Tank will continue with Leventis foundation funding, however it has voted on breaking away from the CESF and continuing a separate existence. Their headquarters will be at the facility in Limassol recently refurbished with support from this project. The report of the Think Tank has already attracted the attention of a range of stakeholders. |
| 47402 - Cultural Heritage | Armenian Church and Monastery | G. 6 cultural heritage monuments partially or fully restored | Armenian Church and Monastery Complex stabilized | Direct Implementation | 13/02/2006 | 30/09/2011 | Works contractor selected and mobilised to site in October. Filming of footage for a documentary film also initiated. Several meetings have been held to ensure the support of all the relevant stakeholders. |
| 47402 - Cultural Heritage | Restoration of Peristerona House | G. 6 cultural heritage monuments partially or fully restored | Restoration of House and conversion into a bi-communal cultural centre. | Cultural Institute of the Morphou Bishopric | 13/07/2006 | 30/01/2009 | Completed and inaugurated in Q3 2009 |
| 47402 - Cultural Heritage | Restoration of Turkish Bath | G. 6 cultural heritage monuments partially or fully restored | Grand Turkish Bath restored | EVKAF | 25/08/2006 | 30/06/2010 | Works 50% complete. Evkaf held various meetings with the KOBI Center in order to develop a business plan for the operation of the Grand Turkish Hamam. Despite many requests, the operation plan has not been submitted to UNDP-ACT for review. |
| 47402 - Cultural Heritage | Restoration of day-care centre at Paphos Gate | G. 6 cultural heritage monuments partially or fully restored | Restoration of the Day Care Centre at Favierou Street, Nicosia | Association for the Welfare of People with Mental Handicap. | 19/04/2007 | 30/06/2009 | Works completed. Inauguration planned for November. |
| 47402 - Cultural Heritage | Fencing at Prophet Elias Monastery | G. 6 cultural heritage monuments partially or fully restored | Prophet Elias Monastery fenced off, cleaned and basic repair to be carried out | Evkaf | 13/07/2006 | 30/06/2009 | Works completed |
| 47402 - Cultural Heritage | Kontea - Cultural Heritage Circle of Preservation | G. 6 cultural heritage monuments partially or fully restored | Restoration works of Church, Mosque, Peace Park, Lusignan Mansion etc. | Kontea Heritage Foundation and KTMMOB | 06/08/2007 | 30/09/2011 | October 2009 saw the launch of Phase I of the works: the Carob Peace Park, in an event bringing together over 200 participants, including old and new residents of the village. Filming of footage for a documentary film has also begun. |
| 61638 - TECH_COM | USAID Contribution to Technical Committees | I. At least 6 confidence-building measures implemented | Support the work of the Good Offices and implementation of Confidence-Building Measures put forward by the Technical Committees. | Direct Implementation | 03/06/2008 | 30/09/2011 | Further Art Exhibitions organised at the Good Offices. Recycling feasibility study completed. Implementation of the water awareness confidence-building measure proposed by the Environment Technical Committee is imminent. ACT has also received proposals from the Crime/Security Technical Committee on renovating a facility for crime information exchange in the buffer zone, as well as a proposal from the Cultural Heritage Technical Committee. |
| 63358 - ENGAGE | ENGAGE | B. Increased media coverage on the role of civil society in the peace process: 2008-2009: 20 news articles ; C. 9 cross-sectoral reconciliation opportunities launched involving at least two of the following: authorities, multi-stakeholder networks, youth organizations, CSOs and private sector: 2008-2009: 2 Initiatives | Capacity of Civil Society strengthened to provide a vehicle for citizens to play a role in the reconciliation process. | Management Centre & NGO Support Centre | 07/04/2009 | 31/07/2011 | On July 07 2009 , a workshop was facilitated among NGOs on “The role of civil society in supporting peace and reconciliation”. The workshop resulted in a number of recommendations that were then shared to a follow up event within a larger group and the presence of the two advisors to the leaders, namely Mr. Iacovou and Mr. Nami as well as the ex Foreign Minister of Turkey Mr Turkmen and Ambassador Kouloumbis from Greece. This event created a momentum amongst the public in realizing and discussing the importance of CSOs in the reconciliation process. A clear message was shared with all stating the aims and objectives of the project and the necessity of civil society’s contribution in the on-going peace process. More than 100 people from both communities participated. The event was captured by all main media. Additionally during this reporting period, the CIVICUS CSI Index was initiated. Two Advisory Committee meetings in both communities have been held, one in each community. Some delays have been observed in the implementation. There was also a turnover in the project team. The partners have been advised to deliver in a prompter manner. . On September 02, a brainstorming session was also organized with women’s groups and the potential strengthening of a women’s network. |
| 63359 - Youth Opinions | Youth Opinions | C. 9 cross-sectoral reconciliation opportunities launched involving at least two of the following: authorities, multi-stakeholder networks, youth organizations, CSOs and private sector: 2008-2009: 2 Initiatives | Common understanding on the role of youth in peace building created and promoted island wide. | Soma Akriton & North Cyprus Mediation Association | 21/05/2009 | 31/07/2011 | Two youth camps have taken place, gathering around 170 young people from both main communities of Cyprus. Possibilities of linking these young people with other ongoing activities in the project are underway such as the youth parliament. Some youth have also participated in the Bold Leaders camp in the USA and others participated in a youth exchange activity between Soma Akriton and Northern Irish youth. The Youth Parliament representatives met for the first time on September 26th. On that same day, the Earthdance Festival co-organized by Hasder and Peace Players took place in Phanenomeni School in the GCC where more 200 youth participated and Ayia Sophia square in the TCC where more than 2000 participated. Both events were very successful. During this quarter, youth leaders’ trainings also took place. All network members continue meeting on a monthly basis. Links with other partners such as the AHDR and the Engage partners are also taking place. |
| 63360 - Media Centre | Cyprus Community Media Centre | Targets 2009-2011: 30% increase in number of Consortium members, At least 12 Management Committee meetings and 12 CSO Consortium meetings,50% increase in the number CSOs using the facilities and services of CCMC,At least 25 events organised,At least 180 CCMC products distributed, At least 8 agreements signed with the mainstream media, At least a 300 people trained,50% rise in CSO’s receiving positive toned media coverage. | A more pluralistic, vibrant and diverse media landscape through an integrated and networked community media initiative led by Civil Society. | DEX | 28/04/2009 | 31/07/2011 | CCMC has made substantial progress with activities relating to the setting up of the Media Centre, including the recruitment of 2 Outreach Officers and a Technical Officer as well as the solicitation of equipment, premises, website construction and design and a pool of specialist media consultants. The project also undertook a survey to assess the media needs of CSOs across Cyprus. This has formed the basis for a more in-depth assessment and action plan for 27 CSO’s to be undertaken by the Outreach Officers over the next quarter.CCMC also produced a vodcast on “The role of Civil Society in Peace building”, in partnership with the ENGAGE project. This has had more than 500 views on Youtube and provides a valuable video documentation of a key reconciliation event in a mainstream online video based web portal. |
| 63361 - Cyprus 2010 | Cyprus 2015 | B. Increased media coverage on the role of civil society in the peace process | An enabling environment created which allows the promotion of open and diverse public discussion on the solution of the Cyprus problem | Interpeace | 28/04/2009 | 28/04/2009 | During this quarter 14 staff were recruited and trained;76 stakeholder interviews and meetings within the TC and GC community took place involving people from Track 1 to Track 3. This establishes a basis for issue and actor mapping which will guide the research ahead and it establishes a basis for further networking and partnerships. Based on the issue and actor mapping, draft Interim Reports will be made available by the first week of October. The first peace poll under the project also commenced in September. Results are expected by the end of October 2009. |
| 63362 - Common Spaces | Implementation of Common Spaces Project | D. Two pilot models for participatory decision-making developed and initiated. | Capacity-building for participatory development as well as implementation of pilot projects demonstrating the role of citizen participation in development and reconciliation. Creation of a participatory development network/platform. | To be determined | 24/06/2009 | 24/06/2009 | On 1st September 2009, the Request for Proposals for Implementation of the entire project was advertised internationally (deadline 26th October), urging international bidders to form consortia with GC and TC partners. Although approved in the GCC, TCC approval of the project is still pending. |
| 63363 - History | Multiperspectivity and Intercultural Dialogue in Education | E. Concrete policy reform agenda on history teaching developed and adopted by decision-makers: 2008-2009: Educational authorities encourage the use of teaching materials among teachers and schools through circulars and official notices. | Enhanced Multiperspectivity and Intercultural Dialogue around issues of Education | Association for Historical Dialogue and Research | 30/06/2009 | 31/07/2011 | During this reporting period , the AHDR has completed a very rigorous hiring process for all the project team which consists of 7 individuals most of which are on a part time basis. The team has gone through one week of orientation training and discussions. As a result, the team is in the process of preparing workplans to design their activities for the programs they exercise responsibility over. Additionally the team and its research experts have almost finalized the questionnaires to be used for the three research components and the procurement process for the hiring of services from a company to actually collect the data from both communities, based on the questionnaires developed by the AHDR, is almost complete. The Association had meeting with TC teachers’ unions to brief them about the project and similar meetings are planned for the GCC. An event for the launching of the project and the “Nicosia is calling” books is being organized for the beginning of October. |
| 63364 - Diversity | Diversity- Expert Support | F. Two public sector bodies incorporate multicultural and diversity training as part of their core training scheme for new employees. | Debate fostered among public service providers about social inclusion to prepare them for a post-settlement situation. | DEX | 09/02/2009 | 30/09/2011 | In September 2009, it was decided that since authorities in both communities were not prepared to approve this project at this stage, the project should be suspended until further notice. However, opportunities will be sought to mainstream Diversity concepts into all projects, and to retain some bridge with the UNDP Regional Human Development Report effort on social inclusion. |
| 63365 - Interdependence | Interdependence | H. Joint economic development plan discussed at the policy level | Economic interdependence between the two communities in Cyprus reinforced and nurtured as a vehicle to support reconciliation. | CCCI and TCCC | 17/03/2009 | 30/09/2011 | Several events took place to promote this project, including presentation of the project principles at the annual general meetings of local chambers, as well as an event involving the former president of the European Parliament, Mr. Hans Pottering, who encourage business leaders to play a key role in the peace process. Development of the business directory continued during this period, as did the receiving of bids for the research phase. The project has generated a significant amount of media coverage in this period. |

| SUMMARY (US$) FOR THE PERIOD OCTOBER 05 TO SEPTEMBER 09 |
| --- |
| Project number | Title | Status | Cumulative Budget 2005-2011 | Budget 2009 -2011 | Expenditures 2005 - 2008 | Disbursments Jan - 30 Sep 2009 | Cumulative Expenditures |
| 47350 | ON - Education | closed | $470,012 |  | $470,012 |  | $470,012 |
| 47397 | ON - Civil Society | closed | $1,006,465 | $40,496 | $965,969 | $40,496 | $1,006,465 |
| 47400 | ON - Environment | closed | $726,126 | $77,543 | $648,583 | $77,543 | $726,126 |
| Phase 1 - Organizational Netowrking | Closed | $2,202,603 | $118,039 | $2,084,564 | $118,039 | $2,202,603 |
| 47351 | SI - Education | closed | $4,508,798 | $125,360 | $4,383,438 | $125,360 | $4,508,798 |
| 47398 | SI - Civil Society | closed | $4,319,157 | $9,788 | $4,309,369 | $9,788 | $4,319,157 |
| Phase 1 - Thematic initiative projects | Closed | $8,827,955 | $135,148 | $8,692,806 | $135,148 | $8,827,954 |
| Phase 1 - Total of closed projects | Closed | $11,030,558 | $253,187 | $10,777,370 | $253,187 | $11,030,557 |
| 47401 | SI - Environment | open | $2,511,429 | $395,134 | $2,116,295 | $290,127 | $2,406,422 |
| Phase 1 - Thematic Initiatives | Open | $2,511,429 | $395,134 | $2,116,295 | $290,127 | $2,406,422 |
| 47402 | Cultural Heritage | open | $4,119,334 | $2,416,960 | $1,702,374 | $455,707 | $2,158,081 |
| Phase 1 & 2 - Cultural Resource Preservation | Open | $4,119,334 | $2,416,960 | $1,702,374 | $455,707 | $2,158,081 |
| 47409 | Monitoring and Evaluation | open | $667,421 | $303,601 | $363,820 | $25,498 | $389,318 |
| Phase 1 & 2 - Prog Impact Information System | Open | $667,421 | $303,601 | $363,820 | $25,498 | $389,318 |
| 47410 | Communications | open | $3,270,848 | $1,932,102 | $1,338,746 | $229,229 | $1,567,975 |
| Phase 1 & 2 - Information and Communications | Open | $3,270,848 | $1,932,102 | $1,338,746 | $229,229 | $1,567,975 |
| 47408 | Red Cross / HRM | open | $940,360 | $547,107 | $393,253 | $36,290 | $429,543 |
| Phase 1 & 2 - Humanitarian Assistance | Open | $940,360 | $547,107 | $393,253 | $36,290 | $429,543 |
| 47407 | Programme Management Unit | open | $9,600,898 | $4,717,008 | $4,883,890 | $997,146 | $5,881,036 |
| Phase 1 & 2 - Program Management Unit | Open | $9,600,898 | $4,717,008 | $4,883,890 | $997,146 | $5,881,036 |
| 47407 | Operating Costs | Open | $1,290,000 | $656,184 | $633,816 | $96,702 | $730,518 |
| Phase 1 & 2 - Operating Costs | Open | $1,290,000 | $656,184 | $633,816 | $96,702 | $730,518 |
| 61638 | Support to the Good Offices | Open | $1,008,492 | $757,399 | $251,093 | $151,231 | $402,324 |
| 63358 | Engage | Open | $1,268,054 | $1,268,054 |  | $225,202 | $225,202 |
| 63359 | Youth Opinions | Open | $1,353,982 | $1,353,982 |  | $390,198 | $390,198 |
| 63360 | Media Center | Open | $1,046,311 | $1,046,311 |  | $35,245 | $35,245 |
| 63361 | Cyprus 2015 | Open | $1,506,000 | $1,506,000 |  | $300,413 | $300,413 |
| 63362 | Common Spaces | Open | $1,280,000 | $1,280,000 |  | $24,472 | $24,472 |
| 63363 | Multiperspectivity | Open | $1,612,139 | $1,612,139 |  | $311,930 | $311,930 |
| 63364 | Diversity | Open | $102,274 | $102,274 |  | $28,177 | $28,177 |
| 63365 | Interdependence | Open | $1,680,000 | $1,680,000 |  | $168,316 | $168,316 |
| Phase 1 & 2 - Thenatice Intitiatives | Open | $10,857,252 | $10,606,159 | $251,093 | $1,635,184 | $1,886,277 |
| 58100 | Admin Fees |  | $2,711,900 | $887,068 | $1,274,832 | $550,000 | $1,824,832 |
| Administrative fees | Open | $2,711,900 | $887,068 | $1,274,832 | $550,000 | $1,824,832 |
|  | Totals |  | $47,000,000 | $22,714,510 | $23,735,490 | $4,569,070 | $28,304,560 |
| 58087 | UNDP Contribution | Open | $1,000,000 | $518,424 | $481,576 | $62,902 | $544,478 |
| UNDP Contribution | Open | $1,000,000 | $518,424 | $481,576 | $62,902 | $544,478 |
|  |  |  |  |  |  |  | $544,478 |
|  | Totals (including UNDP Contribution) |  | $48,000,000 | $23,232,934 | $24,217,066 | $4,631,972 | $28,849,037 |

| Project ID : 47350 - EDUCATION | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
| --- | --- | --- | --- | --- |
|  | Closed contracts |  | $470,012 | $470,012 |  | $470,012 |
|  |  |  | $470,012 | $470,012 |  | $470,012 |
| Project ID : 47397 - ON CIVIL SOCIETY | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Closed contracts |  | $1,006,465 | $965,969 | $40,496 | $1,006,465 |
|  |  |  | $1,006,465 | $965,969 | $40,496 | $1,006,465 |
| Project ID : 47400 - ON Sustainable Dev |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Closed contracts |  | $726,126 | $648,583 | $77,543 | $726,126 |
|  |  |  | $726,126 | $648,583 | $77,543 | $726,126 |
| Project ID : 47351 - SI Education |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Closed contracts |  | $4,508,798 | $4,383,438 | $125,360 | $4,508,798 |
|  |  |  | $4,508,798 | $4,383,438 | $125,360 | $4,508,798 |
| Project ID : 47398 - SI Civil Society |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Closed contracts |  | $4,319,157 | $4,309,369 | $9,788 | $4,319,157 |
|  |  |  | $4,319,157 | $4,309,369 | $9,788 | $4,319,157 |
| Project ID : 47401 - ENVIRONMENT | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Closed contracts |  | $848,668 | $815,034 | $33,634 | $848,668 |
|  | Contracted |  | $1,423,427 | $1,061,927 | $256,493 | $1,318,420 |
|  | Operational Support | $241,681 | $241,681 |  | $241,681 |
|  | Exchange Losses / (Gains) | -$2,347 | -$2,347 |  | -$2,347 |
|  |  |  | $2,511,429 | $2,116,295 | $290,127 | $2,406,422 |
| Project ID : 47402 - CULTURAL HERITAGE |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Closed contracts |  | $91,006 | $91,006 |  | $91,006 |
|  | Contracted |  | $3,929,074 | $1,527,036 | $440,785 | $1,967,821 |
|  | Operational Support | $99,783 | $84,861 | $14,922 | $99,783 |
|  | Exchange Losses / (Gains) | -$529 | -$529 |  | -$529 |
|  |  |  | $4,119,334 | $1,702,374 | $455,707 | $2,158,081 |
| Project ID : 47409 - MONITORING & EVALUATION |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Closed contracts |  | $363,820 | $363,820 |  | $363,820 |
|  | Contracted |  | $253,103 |  |  |  |
|  | Operational Support |  | $50,498 |  | $25,498 | $25,498 |
|  |  |  | $667,421 | $363,820 | $25,498 | $389,318 |
| Project ID : 47410 - COMMUNICATIONS |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Closed Contracts |  | $1,510,620 | $1,338,746 | $171,874 | $1,510,620 |
|  | Contracted |  | $1,667,177 |  | $57,355 | $57,355 |
|  | Operational Support | $93,051 |  |  |  |
|  |  |  | $3,270,848 | $1,338,746 | $229,229 | $1,567,975 |
| Project ID : 47408 - HUMANITARIAN ASSISTANCE |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Closed contracts | $393,253 | $393,253 |  | $393,253 |
|  | Contracted and budgeted | $547,107 |  | $36,290 | $36,290 |
|  | Exchange Losses / (Gains) |  |  |  |  |
|  |  |  | $940,360 | $393,253 | $36,290 | $429,543 |
| Project ID : 47407 - PROGRAM MANAGEMENT UNIT AND OPERATING COSTS | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Program Management Unit |  | $9,600,000 | $4,882,992 | $997,146 | $5,880,138 |
|  | Operating Costs |  | $1,290,000 | $633,816 | $96,702 | $730,518 |
|  | Exchange Losses / (Gains) | $898 | $898 |  | $898 |
|  |  |  | $10,890,898 | $5,517,706 | $1,093,848 | $6,611,554 |
| Project ID : 61638 - SUPPORT TO THE GOOD OFFICES |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Operational Support |  | $376,256 | $252,103 | $124,153 | $376,256 |
|  | Contracted |  | $633,246 |  | $27,078 | $27,078 |
|  | Exchange Losses / (Gains) | -$1,010 | -$1,010 |  | -$1,010 |
|  |  |  | $1,008,492 | $251,093 | $151,231 | $402,324 |
| Project ID : 63358 - ENGAGE |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Contracted |  | $1,233,039 |  | $220,187 | $220,187 |
|  | Operational Support |  | $35,015 |  | $5,015 | $5,015 |
|  |  |  | $1,268,054 |  | $225,202 | $225,202 |
| Project ID : 63359 - YOUTH OPINIONS |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Contracted |  | $1,302,525 |  | $383,875 | $383,875 |
|  | Opertational Support |  | $51,511 |  | $6,377 | $6,377 |
|  | Exchange Losses / (Gains) | $0 |  | -$54 | -$54 |
|  |  |  | $1,354,036 |  | $390,198 | $390,198 |
| Project ID : 63360 - MEDIA CENTRE |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Contracted |  | $329,425 |  | $19 | $19 |
|  | Operational support |  | $716,886 |  | $35,226 | $35,226 |
|  |  |  | $1,046,311.00 |  | $35,245.00 | $35,245.00 |
| Project ID : 63361 - CYPRUS 2015 |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Contracted |  | $1,500,000 |  | $300,000 | $300,000 |
|  | Operational Support |  | $6,000 |  | $413 | $413 |
|  |  |  | $1,506,000 | $0 | € 300,413 | € 300,413 |
| Project ID : 63362 - COMMON SPACES |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Contracted |  | $1,192,257 |  | $23,035 | $23,035 |
|  | Operational Support |  | $87,743 |  | $1,437 | $1,437 |
|  |  |  | $1,280,000 |  | $24,472 | $24,472 |
| Project ID : 63363 - HISTORY |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Contracted |  | $1,582,139 |  | $309,423 | $309,423 |
|  | Operational Support |  | $30,000 |  | $2,507 | $2,507 |
|  |  |  | $1,612,139 |  | $311,930 | $311,930 |
| Project ID : 63364 - DIVERSITY |  |  | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Contracted |  | $23,519 |  | $23,519 | $23,519 |
|  | Operational Support |  | $78,755 |  | $4,658 | $4,658 |
|  |  |  | $102,274 |  | $28,177 | $28,177 |
| Project ID : 63365 -Interdependence INTERDEPENDENCE | Budget (US$) | Exp 2005-2008 | Exp Jan- 30 Sep 09 | Total |
|  | Contracted |  | $1,670,000 |  | $163,244 | $163,244 |
|  | Operational Support |  | $10,000 |  | $5,072 | $5,072 |
|  |  |  | $1,680,000 | $0 | $168,316 | $168,316 |