UNDP Eritrea

2016 Annual Work Plan

| Project name | Amount |
| --- | --- |
| Support to Capacity Building of the Ministry of Finance | US $ 1,000,000.00 |
| Mr. Berhane Habtemariam Minister Ministry of Finance | Ms. Christine N. Umutoni Resident Representative UNDP Eritrea |
| Signature: | Signature: |
| Date: | Date: |

United Nations Development Programme

| Project Title | Support to Capacity Building of the Ministry of Finance |
| --- | --- |
| SPCF Outcome(s): | Selected government institutions have the capacity to effectively and efficiently provide services to all |
| Expected Output(s): | Effective Resource mobilization, coordination and management Regulatory instruments/framework and/ or tools reviewed or established for improved delivery The Government/UN Development System capacity for coordination resource mobilization and monitoring and reporting on the SPCF Strengthened |
| Implementing Partner: | Ministry of Finance |
| Responsible Parties: | Ministry of National Development, Ministry of Finance and UNDP |

| EXPECTED OUTPUTS And baseline, associated indicators and annual targets | PLANNED ACTIVITIES List activity results and associated actions | PLANNED BUDGET (USD) |
| --- | --- | --- |
|  |  | FUND | 2016 |
| Output 1 Effective Resource mobilization, coordination and management Baseline Insufficient staff skills, knowledge and tools for resource coordination, mobilization and management Inadequate and malfunctioning equipment and software Indicators Number of Reports, studies and tours conducted Functional Financial and Management Systems and platforms in place Hardware And software procured installed and functional in MoF | Staff equipped with knowledge and skills for resource mobilization, coordination, mobilization and management | UNDP | 50,000 |
|  | Capacity Need assessment | UNDP | 15,000 |
|  | Tax and non-tax revenue collection administration and management | UNDP | 25,000 |
|  | Study tours | UNDP | 45,000 |
|  | Establish public finance management systems and platform for managing development finance | UNDP | 50,000 |
|  | Undertake target research and consultative for a fro development of Eritrea’s position in international symposia | UNDP | 50,000 |
| Output 2. Regulatory instruments/framework and/ or tools reviewed or established for improved delivery Baseline: Weak regulatory instruments in MoF Indicators: Number of instruments reviewed/established and implemented Improved delivery of services | Review exiting regulatory frameworks/instruments and tools | UNDP | 50,000 |
|  | Conduct policy research, advocacy and /or reviews | UNDP | 45,000 |
|  | Develop new instruments’ where necessary | UNDP | 35,000 |
| Output 3 The Government/UN Development System capacity for coordination resource mobilization and monitoring and reporting on the SPCF Strengthened Baseline Insufficient staffing and capacity for coordination, communication/reporting resource mobilization and M& E for Government/UN development programming and results Indicators Improved quality of coordination, M & E and results reporting/communication Improved resources mobilization capacities | Conduct capacity needs assessment for coordination, resource mobilization, M & E and results reporting | UNDP | 30,000 |
|  | Preparation , Publication and dissemination of MDGR | UNDP | 30,000 |
|  | Facilitate local and international events on ODA and development coordination, and any other international discussion where Eritrea can learn but also share its experience in different fields. | UNDP | 50,000 |
|  | Develop international symposium programme | UNDP | 35,000 |
|  | Preparation of materials and publications for the international symposium and organize Study Tours | UNDP | 25,000 |
|  | Panel discussion on post 2015 development agenda at the international symposium | UNDP | 5,000 |
| Enhancing the institutional Capacity of the MoF Baseline: Limited and old office equipment at MoF Indicators: Office Equipment’s such as Computers, printers and photocopiers procured Solar Panels Target: Service delivery of MoF further enhanced with efficient modern office equipment’s. | Procurement of Equipment | UNDP | 360,000 |
| Project implementation | Direct Project Costing (DPC) | UNDP | 100,000 |
| TOTAL |  |  |  | 1,000,000. |

# Text boxes

Brief Description

It is envisaged that the SPCF will capitalize on the collective comparative strength of the UN System in responding to the priorities of the government. Government/UNRC/UNDP will continue to be strengthen to ensure coordination of the SPCF through the provision of technical and financial support to enhance their operational, coordination and development effectiveness role.

In this regard, this project will strengt5hyen the Ministry of Finance and the UN Development system to prompt and enhance in-country aid coordination duties and functions, mobilization of additional resources to support the SPCF and enhance communication.

Programme Period:    2013-2016

Atlas Award ID:           00058525

| Proejct Number 00088549 |
| --- |
|  |  | 00072724 |

Start date:		     	Jan 2016

End Date			Dec 2016

Management Arrangements:	 DIM            National  Execution

Management Arrangements:       National Execution

Total resources required    1,000,000

Total allocated resources:  1,000,000

Regular                                 1,000,000

Other:

  - Donor		_________

  - Donor		_________

  - Donor		_________

  - Government:   ______

Unfunded budget:  -

In-kind Contributions