## AWP
AWP for Private Sector Development Component of Enhanced Economic Growth Programme (Jan to June/July 2002 EFY /2010 )
UNDAF Outcome: By 2011, people's welfare and livelihoods improved through enhanced crooss-sectoral economic development in selected potential areas and products.
Expected CP Outputs and Indicators Including Annual Targets |  |  | Planned Activities | Time Frame |  |  |  | Responsible | Planned Budget and Description
|  |  |  | EFY 2002 |  |  |  | Party | Source of | Budget description | Amount
|  |  |  | GC 2010 |  |  |  |  | Fund |  | In USD
|  |  |  | Q1 | Q2 | Q3 | Q4
Enabling the leather sector’s market competitiveness
Output: Strengthened capacity thru acquisition of new knowledge to enhance and improve the leather industry |  |  | ■ Train engineering team and technician in the leather industry on machine maintenance of all model factories to provide effective service & technical support for the leather sector. |  | XX |  |  | LLPTI/MOTI | UNDP | Travel, national and international consultants, and miscellaneous expenses | 15000
Target: Enhanced capacity of LLPTI and the leather industry thru strengthened knowledge and training of some 157 persons with due consideration to gender. Indicator: Number of persons whose knowledge and capacity enhanced and improvement in work quality. |  |  | Train on managing leather sectoral process |  | XX |  |  | LLPTI/MOTI | UNDP | Consultants, and learning costs | 20000
|  |  | ■ Train in research on international market access including participation in trade fair and exhibitions |  | XX |  |  | LLPTI/MOTI |  | Consultants and learning costs | 20000
|  |  | ■ Training in management information system |  | XX |  |  | LLPTI/MOTI |  | Consultants, travel and learning costs | 10000
|  |  | ■ Training on quality control, testing and effluent treatment, fashion design and upgrading of defective leather |  | XX |  |  | LLPTI/MOTI |  | Learning costs | 20000
|  |  | ■ Procure office and ICT equipment for upgrading the ICT training centre in the LLPTI |  | XX |  |  |  |  | Procurement of goods | 90000
|  |  | Conduct national workshop on enhancing the leather industry and its market competitiveness. | [7 empty] | 20000
| Sub Total | [9 empty] | 195000
International Leather Fair
1.2 Output: Market access for Ethiopian leather and leather products promoted thru well organized All African Leather Fair.
Target: Potential buyers and sellers of leather and leather products from all over the world brought together |  |  | ■ Arrange ideal premises for the leather fair. | XX |  |  |  | ELIA/MOTI |  | Premises rental costs | 40077
Indicator: All African Leather Fair (AALF) successfully held with broad and increased international and domestic industries and consumers participation. |  |  | ■ Promote the leather fair thru publications, brochures, public media, etc. | XX |  |  |  | ELIA/MOTI |  | Procurement, sub-contracting | 59923
Sub- total | [10 empty] | 100000
Total for Leather | [10 empty] | 295000
Establishment of Regional Free Trade Area between Sana'a Cooperation Forum
Output: The impact on establishing FTA between Sana'a Cooperation countries assessed. |  | Output: Impact assessment conducted on feasibility of establishing Sana FTA. | ■ Carryout a study on Sana'a Cooperation Free Trade Area | XX | XX |  |  | MOTI | UNDP | Consultancy Costs | 36000
Target: Impact assessment report with recommendation for policy decision making. Indicator: Quality and endorsement of the assessment study. |  |  | ■ Conduct validation and awareness creation workshops based on the draft and ratified documents. | XX | XX |  |  | MOTI | UNDP | Miscellaneous expenses | 6000
Sub- total | [10 empty] | 42000
Public Private Dialogue Forum and Enhancing Capacity for PSD
Output: Enhanced public and private dialogue forum and capacity for private sector development |  |  | ■ Follow-up on the endorsement and singing off the MOU on the PPDF |  | XX |  |  | ECCSA/ MOTI | UNDP |  | 0
|  |  | ■ Training and strengthen knowledge on PPDF |  | XX | XX |  |  |  | Learning and travel costs | 25000
|  |  | ■ Organise PPDF forums |  |  | XX |  | ECCSA/ MOTI |  | Miscellaneous expenses | 6000
Target: Signed off MOU for PPDF and strengthen knowledge and capacity for private sector development |  |  | ■ Establish info centre for 6 regional chambers |  | XX | XX |  |  |  | Procurement, Miscellaneous costs | 35000
Indicator: ■Endorsement and signing off MOU/guideline and setup of operational PPDF office |  |  | ■ Train women entrepreneurs in product design and skill development |  | XX |  |  | ECCSA/MOTI | UNDP | Learning costs, travel costs | 13000
■ No of regional info centre established |  |  | ■ Develop women entrepreneurs' web-site |  | XX | XX |  | ECCSA/MOTI | UNDP | Workshop costs, learning costs | 2000
■ No. of women entrepreneurs trained and skills developed |  |  | ■ Establish women entrepreneurs' info and counseling centre |  | XX | XX |  | ECCSA/MOTI | UNDP | Sundries, miscellaneous | 8000
■ Quality of exporter guide produced and published |  |  | ■ Conduct feasibility study on establishment of chamber academy |  | XX | XX |  | ECCSSA/MOTI | UNDP | Consultancy Costs | 10000
|  |  | ■ Finalise and publish exporters guide |  | XX | XX |  | ECCSA/MOTI | UNDP | Consultancy , Procurement and miscellaneous costs | 65000
|  |  | ■ Procure office equipment ( computers, printers and photocopiers) | XX |  |  |  | ECCSA/MOTI | UNDP | Procurement | 8000
|  |  | ■ Promote chamber's and PSD activities in print and audio/video |  | XX | XX |  | ECCSA/MOTI | UNDP | Miscellaneous expenses | 8000
|  |  | ■ Prepare business directory |  | XX | XX |  | ECCSA/MOTI |  | Consultancy Costs | 20000
Sub Total | [10 empty] | 200000
Strengthened Commodity Exchange Authority
Output: Capacity of Ethiopia Commodity Exchange Authority enhanced |  |  | ■ Conduct public education to enhance the awareness of different actors and the public at large. | XX | XX |  |  | ECEA | UNDP | Learning costs | 200000
Target: ■Conducted 33 public education workshops at regional, zonal and wereda level for 5000 participants with due consideration to gender
■ Enhance the professional capacity of ECEA staff in areas of including operations of commodity exchange markets, risk management, regulatory techniques and process.
Indicators: ■ Number of workshops held and number of participants
■ Number of trained ECEA staffs
Sub-total | [10 empty] | 200000
|  | Grand Total | [8 empty] | 737000

## Cover page
WORK PLAN
EFY 2002/ 2010 January - June/July 2010
Country: Ethiopia
UNDAF Theme: Enhanced Economic Growth
Programme component: Private sector development
Expected UNDAF Outcome: By 2011, people's welfare and livelihoods improved through enhanced crooss-sectoral economic development in selected potential areas and products.
Programme outcome: Private sector development promoted as a motor of economic growth.
Total programme period: 2007 - 2011 Project ID (Atlas code): ____________ Duration: January - June/July 2010 | Estimated 6 months budget Government contribution: UNDP contribution: US 737,000
Brief Description This interim annual work plan (AWP) is intended to reflect the activities and budgets under the private sector development component of the Enhanced Economic Growth theme, for immediate release of fund and implementation. The main areas under this project include: a) enhancing capacity of the leather industry, b) assessing impact of establishing free trade area between countries of the Sana'a Co-operation Forum, c) strengthening the capacity for private business and public-private dialogue forum, and d) enhancing capacity of the Ethiopian Commodity Exchange Authority (ECEA). This interim AWP is an essential and immediate measure to avoid time gap in project implementation before having a fully prepared and signed off 24 months plan, for implementation as of July 2010 ( in accordance with the Ethiopian fiscal calendar).
Agreed by MOFED
Agreed by MOTI
Agreed by UNDP