Government of the Federated States of Micronesia

United Nations Development Programme

PROJECT DOCUMENT

| Project Title: | National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in the FSM |
| --- | --- |
| UNDAF Outcome(s): | UNDAF Outcome 1: Environmental management, climate change and disaster risk management |
| UNDP Strategic Plan Environment and Sustainable Development Primary Outcome: Strengthen national capacity to manage the environment in a sustainable manner while ensuring adequate protection of the poor. Mobilizing environmental financing. UNDP Strategic Plan Secondary Outcome: Mainstreaming environment and energy. |
| Regional UNDAF Outcome 1.1: By 2017 the most vulnerable communities across the PICTS are more resilient and select government agencies, civil society organizations and communities have enhanced capacity to apply integrated approaches to environmental management, climate change adaptation/ mitigation and disaster risk management |
| UNDAF Results Matrix Federated States of Micronesia 2013 – 2017 Outcome 1.1: Improved resilience and improved management of threats to the environment to minimize vulnerability and impacts of climate change [Project Objective]: To integrate FSM’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020. |
| Implementing Partner: FSM National Department of Resources and Development (FSMRD) |
| Responsible Partners: Department of Resources and Development (DRD) |

Brief Description This project is part of the second generation of Biodiversity Enabling Activities (BD EA) under the GEF. The FSM has been Party to the Convention on Biological Diversity (CBD) since June 1994. The project addresses the country’s need to continue to fulfill its obligations under the CBD, with particular focus on the Convention’s Article 6 and the CBD COP Decision X/2. Above all, the project is a significant contribution to the FSM’s efforts towards implementing the CBD Strategic Plan 2011-2020 at the national level. The project builds on the current status and achievements of the country with respect to biodiversity planning and reporting. It aims to integrate the FSM’s obligations under the CBD into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process. This process is expected to produce measurable targets for biodiversity conservation and sustainable use. It will equally ensure that the value of ecosystems’ goods and services, as well as the challenges and opportunities for ecosystem-based adaptation and resilience are taken into consideration in the process. The project will achieve its objective through the implementation of three components, whose activities are thoroughly described in the GEF approved proposal for BD EA. They are: (1) A participative stocktaking exercise on existing strategies takes place and national biodiversity targets are developed in response to the global Aichi Targets; (2) The NBSAP is revised/updated and it fully integrates new aspects of the CBD strategic plan, such as mainstreaming and anchoring the implementation of the plan into national development frameworks, valuing ecosystem services and promoting ecosystem-based adaptation and resilience; and (3) National frameworks for resource mobilization, Convention reporting and exchange mechanisms are strengthened.

| Programme Period: 2013-2017 Atlas Award ID: 00074643 Project ID: 00086941 PIMS : 5100 Start date: August 2013 End Date: August 2015 Management Arrangements: NIM PAC Meeting Date: 19 Aug 2013 |  | [A] + [B] Total resources required (total project funds) $524,724 [A] Total allocated resources (UNDP managed funds in the current Award) $ 220,000 Regular (UNDP TRAC) $ 0 GEF $ 220,000 [B] Other (partner managed resources): State Governments National Government In kind contributions of CSO $304,724 UNDP (parallel funding): |
| --- | --- | --- |

Agreed by (Government):

Date

Agreed by (Implementing Partner):

Date

Agreed by (UNDP):

Date

Contents

Overview of Approved Proposal	4

SECTION I: Elaboration of the Narrative	6

PART I: Situation Analysis	6

Stakeholder Analysis and Engagement	7

PART II: Strategy	8

Project Goal, Objective, Outcomes and Outputs/activities	8

Project Risks	8

PART III: Management Arrangements	9

PART IV: Monitoring and Evaluation Plan and Budget	13

Monitoring and reporting	13

Communications and visibility requirements	14

PART V: Legal Context	14

SECTION II: Project Results Framework and GEF Increment	16

PART I: Indicator Framework and Project Outputs	16

SECTION III: Total Budget and Workplan	19

SECTION IV: ADDITIONAL INFORMATION	21

PART I: Other agreements	21

Government Letter of Endorsement	21

PART II: Terms of References for key project staff	22

National Project Coordinator (Project Technical Coordinator)	22

Project Assistant(s)	25

Project Consultants	26

Project Annexes	29

Annex 1. Approved GEF proposal for BD EA (Headings Overview on page 4)	29

Annex 2 GEF CEO Approval Letter	60

Annex 3 Minutes of the Local Project Appraisal Committee (LPAC) Meeting	61

# Overview of Approved Proposal

Headings Overview

part i: project IDentifiers A. EA Framework B. Co-Financing For The Ea By Source And By Name C. Grant Resources Requested by Agency, Focal Area and Country D. EA Management Cost part ii: Enabling Activity JustiFication A. Enabling Activity Background and Context B. Enabling Activity Goals and Objectives C. Describe the EA and Institutional Framework for Project Implementation D. Describe, if possible, the expected cost-effectiveness of the project E. Describe the budgeted M&E Plan F. Explain the Deviations from typical Cost Ranges (where applicable): part iii: approval/endorsement by gef operational focal point(s) and GEF agency(ies) A. Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): B. Convention Participation C. GEF Agency(ies) Certification Annex A: consultants to be hired for the Enabling Activity Annex B: Chronogramme of activities Annex C. Annex C. UNDP Total Budget and Workplan [included in the PRODOC only.] Annex E. Technical Assistance Service Provision: TOR for launching a Request for Quotes

Acronyms and Abbreviations

| APR/PIR | Annual Project Review / Project Implementation Report |
| --- | --- |
| BD EA | Biodiversity Enabling Activities |
| CBD | Convention on Biological Diversity |
| CDR | Combined Delivery Report |
| CHM | Clearing House Mechanism |
| CO | Country Office (UNDP) |
| COP | Conference of the Parties |
| EEZ | Economic Exclusive Zone |
| FSM | Federated States of Micronesia |
| DRD | Department of Resources and Development |
| GEF | Global Environment Facility |
| LPAC | Local Project Appraisal Committee |
| M&E | Monitoring and Evaluation |
| NBSAP | National Biodiversity Strategy and Action Plan |
| NGO | Non-Governmental Organization |
| NIM | National Implementation Modality (UNDP’s) |
| NSC | National Steering Committee |
| NPD | National Project Director |
| POPP | Programme and Operations Policies and Procedures |
| PSC | Project Steering Committee |
| PM | Project Manager |
| PMU | Project Management Unit |
| PoWPA | CBD’s Programme of Work on Protected Areas |
| PRODOC | Project Document |
| QOR | Quarterly Operational Reports |
| RCU | Regional Coordination Unit |
| SBAA | Standard Basic Assistance Agreement |
| TEEB | The study of Economics and Biodiversity |
| TOR | Terms of Reference |
| TBW | Total Budget and Workplan |
| UNDAF | United Nations Development Assistance Framework |
| UNDP | United Nations Development Programme |

# SECTION I: Elaboration of the Narrative

## PART I: Situation Analysis

This Project Document (PRODOC) primarily lays out the mechanism to implement the GEF approved Enabling Activity project concept (see the project concept in Annex 1 and the GEF CEO Letter of Approval) in the Federated States of Micronesia (FSM). The project will support the FSM to meet its obligations as a party to the Convention on Biological Diversity (CBD), in particular the country’s biodiversity planning and Convention reporting processes, and its commitment to implement, the CBD’s Strategic Plan for the period 2011-2020. These processes and achievements are summarised in a matrix in Annex 1, under the heading ‘Enabling Activity Background and Context’.

On biodiversity conservation and sustainable use planning,  the FSM completed its first NBSAP in 2002 and it has  been updated through the Environment Sector Five Year (2009-2014) Plan but is still needs to consider the more recent Convention targets and guidelines. The CBD Strategic Plan, adopted at CoP-10 in 2010 in Nagoya, noted the need to update NBSAPs in its Target 17 as “By 2015, each Party has developed, adopted as a policy instrument, and has commenced implementing an effective, participatory and updated national biodiversity strategy and action plan.” The strategic plan also covers a range of issues that will need to be incorporated into the revised NBSAPs, including guidance to countries to: a) fully realise the value of biodiversity and ecosystem services, and incorporate these values into national and local development and poverty reduction strategies (Targets 1 and 2); b) increase the global terrestrial protected area estate from 12% to 17% and the marine estate from 6% to 10% (Target 11); c) restore and safeguard key ecosystem services, especially for water, health and livelihoods (Target 14); and d) strengthen ecosystem resilience to climate change and promote ecosystem-based approaches to climate change adaptation and mitigation (Target 15).

The achievements and shortcomings of previsous biodiversity planning processes in the FSM are described in the project concept (Annex 1), under heading ‘The Baseline Project: The Current NBSAP and the new CBD Strategic Plan’.

### Stakeholder Analysis and Engagement

There is an extensive body of guidance explaining how those responsible for biodiversity planning can approach the task of identifying stakeholders. In its guidance to Parties on the organization of NBSAPs and preparation of national reports, the COP has repeatedly stressed that, if the necessary transition from biodiversity planning to biodiversity implementation is to be made, then everyone with a stake in the outcome of the NBSAP needs to be engaged.

The stakeholder engagement process in the FSM will start with the CBD national focal points, the NBSAP responsible authority, the FSM Department of Resources and Development (FSMRD), and thereafter it will expand to include a much broader range of national actors, and especially the 4 State Governments of Chuuk, Kosrae,  Pohnpei, and Yap . The updating and implemention the NBSAP in the FSM will be a widely inclusive and participative process.

A national steering committee and one or more working groups will be proposed for accompanying the process of developing national targets, updating the NBSAP and preparing the national reports. As far as possible, the steering committee should include representatives of all sectors. Below is an overview of the potential role of different stakeholders and the rationale for their involvement in the project.

| Sector | Agency/department | Potential role in the project and rationale for involvement |
| --- | --- | --- |
| Agriculture, Marine Resources, Tourism, Energy, Trade and Investment | FSMR&D | Formally adopted NBSAP/BSAP Implements NBSAP/BSAP Committed to policy instruments - NEMS, BSAPs, SDP’s Environment Sector - & PoWPA State Agencies liaise with local governments Environment Protection Agency |
| Environment | Chuuk EPA |  |
| Environment | Kosrae Island Resource Management AgencyOffice of Environment and Emergency Management |  |
| Land Resources | Department of Land & Natural Resources |  |
| Agriculture, Marine Resources, Tourism, Trade and Investment | Department of Resources & Development |  |
| Education | College of Micronesia – FSM | National role in institutional and scientific capacity building CHM Administrator |
| NGO | Micronesia Conservation Trust | Long term funding mechanism to support biodiversity conservation & related sustainable development (NBSAP funding mechanism) |
| NGO | The Nature Conservancy, Micronesia Program | NBSAP technical supporter |
| NGO | Conservation Society of Pohnpei | Support implementation of Pohnpei BSAP on-the-ground activities and liaison to local communities |
| NGO | Kosrae Conservation & Safety Organization | Support implementation of Kosrae BSAP on-the-ground activities and liaison to local communities |
| NGO | Yap Community Action Program | Support implementation of Yap BSAP on-the-ground activities and liaison to local communities |
| NGO | Chuuk Conservation Society | Support implementation of Chuuk BSAP on-the-ground activities |
| NGO | Yap Institute of Natural Science | Support implementation of Yap BSAP on-the-ground activities and local research expert |

## PART II: Strategy

### Project Goal, Objective, Outcomes and Outputs/activities

The project’s goal is to enable the FSM to integrate its CBD obligations into national planning processes, in light of the CBD’s Strategic Plan 2011-2020.

The project objective is to To integrate FSM’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020.

In order to achieve the above objective, three ‘outcomes’ (corresponding to GEF components) are expected from the project:

- Outcome 1 – A participative stocktaking exercise on existing strategies undertaken and national biodiversity targets are developed in response to the global Aichi Targets

- Outcome 2 – The NBSAP is revised/updated and it fully integrates new aspects of the CBD strategic plan, such as mainstreaming and anchoring the implementation of the plan into national development frameworks, valuing ecosystem services and promoting ecosystem-based adaptation and resilience

- Outcome 3 – Strengthened national frameworks for NBSAP implementation, CDB reporting and exchange mechanisms

The Outcomes of the project, as well as the expected outputs and activities under those, are thoroughly described in the GEF proposal in Annex 1.

### Project Risks

Table 1. Project Risks Assessment and Mitigation Measures

| Identified Risks | Risk Assessment | Mitigation Measures |
| --- | --- | --- |
| Inability to reach consensus among the various stakeholders on an agreed strategy and action plan especially given that the plan will need to be relevant for all 4 States of the FSM | Moderate | Through an inception workshop, stakeholders will be informed of project objectives, linkages to stakeholders and potential collaboration. The project will work closely with existing biodiversity networks and groups established in all states as well as at national level. |
| Limited human capacity to implement the project | Moderate | Consultants will be recruited to provide necessary technical support whenever necessary. In addition, project will work closely with national and state stakeholders as well as seeking support services from UNDP. |
| Lack of willingness to share available biodiversity conservation outside environmental ministries and authorities | Low | An effective, user-friendly and easily updatable country-driven CHM site will be developed and linked up to the CBD’s global CHM networks and to other information and knowledge exchange network on biodiversity. It will be beneficial to all stakeholders and users that provide information. This will be updated on a weekly basis with news, feeds, photos, documents and other. |

## PART III: Management Arrangements

The institutional and management arrangements for this project are described in the GEF proposal in Annex 1 under the heading ‘Project Implementation Arrangement’.

The project will be implemented over a period of 30 months. UNDP is the GEF Agency for the project and accountable to the GEF for the use of funds. The project will be administered by UNDP using the national implementation modality (NIM) project, in line with the Standard Basic Assistance Agreement (SBAA, 2006) between the UNDP and the Government of FSM, and the United Nations Development Assistance Framework (UNDAF) Action Plan and FSM Country Matrix for 2013-2017. Under the NIM modality, the FSM National Department of Resources and Development (FSMRD) is the designated government institution responsible for the project towards the timely and verifiable attainment of project objectives and outcomes. The DRD will   manage implementation of all project activities. UNDP will provide country support services to the nationally implemented project.

The FSMRD will nominate a high level official (National Project Director) who will chair the Project Steering Committee (PSC) and will be responsible for providing government oversight and guidance to the project implementation. Project technical team will receive technical backstopping provided from the UNDP/GEF Regional Technical Advisor responsible for the project and the UNDP Environment Focal Point at the Regional Office.

In working closely with its stakeholders, FSMRD will be responsible for providing project oversight and  assurance services for project implementation including (i) recruitment of project staff and contracting of consultants and service providers; (ii) overseeing financial expenditures against project budgets approved by Project Board; and (iii) ensuring that all activities including procurement and financial services are carried out in strict compliance with Government and/or UNDP/GEF procedures. A FSMRD staff member will be assigned with the responsibility for the day-to-day management and control over project finance.  A UNDP staff member will be assigned with the responsibility of project assurance activities and will be the point of contact between the project and UNDP.

A National Project Steering Committee (PSC) which will  will be convened by FSMRD, and will serve as the project’s coordination and technical advisory body. The PSC will include representation of all the key project stakeholders. It will meet according the necessity, but not less than once in 6 months, to review project progress and advice on technical matters concerning the project.

The  PSC will also provide technical advice.  The PSC may meet more frequently to discuss issues of technical nature and make recommendations which would be fowarded to the Project Board for final decision making.

The Project Steering Committee may be an existing or previously formed NBSAP Steering Committee. This committee may comprise of  smaller  thematic working groups. The thematic area groups may meet  quarterly or on an adhoc basisi when need arises . The steering committee however meets at least twice per year to review and monitor the performance of the project. The PSC will include NBSAP stakeholder group, thematic area working group and some key people involved in planning and implementing NBSAP activities. This may include other key government Ministries and departments.

Until the PSC has met and has deliberated, the following are the proposed TOR for the Committee:

Provide policy and strategic oversight and support to the implementation of the project, in particular to the process of updating the NBSAP, supporting the development of the country’s CHM and provide strategic support to the development of the CBD national reports with with full government endorsement. Advise and ensure stakeholder involvement on matters of biodiversity sectoral and development mainstreaming, biodiversity valuation and on the nexus biodiversity-climate change, and other emerging issues. The PSC is responsible for ensuring that the project remains on course to deliver products of the required quality to meet the outcomes defined in the project document Review project progress and approve project’s annual workplans and major project deliverables, as well as other project planning and implementation instruments. Provide inputs to the projects’ APR/PIR. Support project evaluations, if applicable Deliberate on the TOR and membership for other committees and working groups that are expected contribute to the implementation of project activities and the achievement of its outcomes. Any other relevant task as applicable.

Besides the roles and responsibilities of different stakeholders outlined in this PRODOC and in the approved proposal in Annex 1, the following project diagram represents the expected key relationships governing the project.

The Project Board  will consist of  the FSM Department of Resources and Development, Office of Statistics, Budget and Economic Management, Overseas Development Assistance and Compact Management, Department of Finance and Administration and UNDP. It is responsible for overall direction and management of project. The board is ultimately responsible for the proejct supported by the national steering committee. It is responsible for making management decisions for a project in particular when guidance is required by the Project Manager.  The Project Board plays a critical role in project monitoring and evaluations by quality assuring these processes and products, and using evaluations for performance improvement, accountability and learning.  It ensures that required resources are committed and arbitrates on any conflicts within the project or negotiates a solution to any problems with external bodies. In addition, it approves the appointment and responsibilities of the Project Manager and any delegation of its Project Assurance responsibilities.  Based on the approved Annual WorkPlan, the Project Board can also consider and approve the quarterly plans (if applicable) and also approve any essential deviations from the original plans. The Project Board is expected to meet aleast once annually in in delierbations will consider recommendations put forward by the Project Steering Committee.  In the event that board members are not able to meet physically, other alternatives could be considered such as teleconfernces, skype  as well as email discussions.

In order to ensure UNDP’s ultimate accountability for the project results, Project Board decisions will be made in accordance to standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.  In case consensus cannot be reached within the Board, the final decision shall rest with the UNDP.

Project Coordinator : The Project Coordinator  has the authority to run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Board. The Project Coordinator  prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost. The Project Coordinator will report to the Secretary for FSMRD.

Audit: The project audit will be conducted according to UNDP Financial Regulations and Rules and applicable Audit policies.

In order to accord proper acknowledgement to GEF for providing funding, a GEF logo should appear on all relevant GEF project publications, including among others, project hardware and vehicles purchased with GEF funds. Any citation on publications regarding projects funded by GEF should also accord proper acknowledgment to GEF. The UNDP logo should be more prominent  and separated from the GEF logo if possible, as UN visibility is important for security purposes.

In order to ensure UNDP’s ultimate accountability for the project results, Project Board decisions will be made in accordance to standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.  In case consensus cannot be reached within the Board, the final decision shall rest with the Project Technical Coordinator.

Potential members of the Project Board are reviewed and recommended for approval during the PAC meeting.  Representatives of other stakeholders can be included in the Board as appropriate. The Board contains four distinct roles, including:

- An Executive: individual representing the project ownership to chair the group. The Department of Resources and Development will nominate a high level official who will serve as the National Project Director (NPD), who will chair the meeting.

- Senior Supplier: representing the interests of the parties concerned which provide funding for specific cost sharing projects and/or technical expertise to the project. UNDP and GEF’s primary function within the Board is to provide guidance regarding the technical feasibility of the project.

- Senior Beneficiary: the Department of Finance and Administration and the Office of Statistics, Budget and Economic Management, Overseas Development Assistance and Compact Management representing the interests of those who will ultimately benefit from the project. The Senior Beneficiaries’ primary function within the Board is to ensure the realization of project results from the perspective of project beneficiaries.

- The Project Assurance role supports the Project Board Executive by carrying out objective and independent project oversight and monitoring functions.  The Project Manager and Project Assurance roles should never be held by the same individual for the same project. UNDP FIJI MCO staff member, supported by UNDP/GEF RCU, will hold the Project Assurance role.

Project Manager: The Project Manager (PM) has the authority to run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Board. The Project Manager’s prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost.

Project Support: The Project Support role provides project administration, management and technical support to the Project Manager as required by the needs of the individual project or Project Manager.

Audit: Audit will be conducted according to UNDP Financial Regulations and Rules and applicable Audit policies.

## PART IV: Monitoring and Evaluation Plan and Budget

### Monitoring and reporting

At the initial stage of the project, the project Monitoring and Evaluation system, composed of following components will be developed:

- Monitoring plan, with defined benchmarks, indicators and targets, based on results and resources framework to be developed by the PM/coordinator in consultation with relevant UNDP programme staff;

- Risk, issues and quality logs to be created by the PM and relevant program officer;

- Quarterly project planning (with detailed activities and budget) and reporting to be conducted by the PMU;

- Quarterly project reporting and monitoring, conducted by the PMU and the Project Board (also to include risk and issues monitoring and development of lessons learned reports);

- Annual project planning (with general activities and budget) and reporting to be conducted by the PMU;

- Annual project review to be conducted by the Executive Board on the basis of monitoring reports and products prepared by the project (also to include proposal for eventual changes to the project strategy or even project revision)

All main reports will be complied by the PMU and endorsed by the Project Board. Regular financial reports will be submitted to UNDP according to the UNDP financial rules and regulations. The M&E System should include standardized formats (aligned with UNDP procedures and formats) for the following documents:

- quarterly action plan

- quarterly progress report, including financial report

- quarterly monitoring report, including risk monitoring report

- quarterly lessons learned report

- annual action plan

- annual report, including financial report

- the simplified Biodiversity Enabling Activities Annual Project Review / Project Implementation Report (APR/PIR)

- PMU monthly workplans and progress reports

- task reports

- final report, including lessons learned

### Communications and visibility requirements

Full compliance is required with UNDP’s Branding Guidelines.  These can be accessed at http://intra.undp.org/coa/branding.shtml, and specific guidelines on UNDP logo use can be accessed at: http://intra.undp.org/branding/useOfLogo.html. Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects needs to be used.  For the avoidance of any doubt, when logo use is required, the UNDP logo needs to be used alongside the GEF logo.   The GEF logo can be accessed at: www.thegef.org/gef/GEF_logo. The UNDP logo can be accessed at http://intra.undp.org/coa/branding.shtml.

Full compliance is also required with the GEF’s Communication and Visibility Guidelines (the “GEF Guidelines”). The GEF Guidelines can be accessed at: www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf.  Amongst other things, the GEF Guidelines describe when and how the GEF logo needs to be used in project publications, vehicles, supplies and other project equipment.  The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.

Where other agencies and project partners have provided support through co-financing, their branding policies and requirements should be similarly applied.

## PART V: Legal Context

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA and all CPAP provisions apply to this document.

Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

# SECTION II: Project Results Framework and GEF Increment

## PART I: Indicator Framework and Project Outputs

| Objective/ Outcome | Indicator | Baseline | End of Project target | Source of Information | Risks and assumptions |
| --- | --- | --- | --- | --- | --- |
| Objective – To integrate The FSM’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, aligning the results of the process to the global guidance contained in the CBD’s Strategic Plan for 2011-2020. | The inclusion of measurable biodiversity conservation and sustainable use targets into the following sectoral planning frameworks: Agriculture Tourism, Trade, Travel and Transport Fisheries Energy | No targets available in order to measure the loss of biodiversity and ecosystem functionality in the agriculture, plantation forestry, fishery and mining and gas sectors | Target to be set during the stocktaking exercise | Approved NBSAP Annual budgets and work plans Approved | Risks: Poor buy-in by line ministries and agencies to mainstream biodiversity conservation limits agreement on targets. Assumptions: All relevant stakeholders will agree to proposed targets. Effective cooperation from relevant agencies and departments. |
|  | The inclusion of measurable biodiversity conservation and sustainable use targets into the following development frameworks: Development Planning & Finance Water quality, security, planning Poverty alleviation Gender Climate change mainstreaming Land use planning and management, including spatial planning and infrastructural development | No targets to measure the integration of biodiversity and sustainable development | Target to be set during the stocktaking exercise | Approved NBSAP Annual budgets and work plans Approved |  |
| Outcome 1 – A participative stocktaking exercise on existing strategies undertaken and national biodiversity targets are developed in response to the global Aichi Targets | 1.1 Review and stocktaking of products and results from previous biodiversity planning processes at the sub-national level with national facilitation and assistance are carried out in participative manner. 1.2 In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to FSM’s reality. 1.3 The achievement of national targets, developed in line with the global Aichi Targets, is monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means. 1.4 In an iterative manner, FSM taps into useful information on, and participates into, regional and global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership, Global Biodiversity Information Facility and the World Conservation Monitoring Centre, the Global Environment Outlook portal, the Micronesia Challenge Measures among other relevant ones). |
|  | Effective establishment of a multi-sectoral/multi-stakeholder working group | No working group is established | By end 2013, a multi-sectoral/multi-stakeholder working group is established and it completes the stock-taking exercise. | Project reports CBD National Reports CBD Strategic Plan for 2011-2020 |  |
|  | Development of a national targets in response to the global Aichi Targets | No national targets have been developed | By end 2013, national targets in response to the global Aichi Targets are developed. | Project reports CBD National Reports Official gazette (e.g. on PA establishment) |  |
| Outcome 2 – The NBSAP is revised/updated and it fully integrates new aspects of the CBD strategic plan, such as mainstreaming and anchoring the implementation of the plan into national development frameworks, valuing ecosystem services and promoting ecosystem-based adaptation and resilience | 2.1 A National Biodiversity Strategy and its four subset (State) Action Plans (NBSAPs) for FSM anchored into national development frameworks, is updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: mainstreaming; the valuing of ecosystem goods and services; and the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. 2.2 The updated and fully endorsed NBSAPs for FSM are submitted to the CBD preferably within the deadline set by the COP, incorporating recommendations of the following strategic studies: Integrating the challenges to Protected Areas in the 21st Century into the NBSAP and the national implementation of the CBD’s Programme of Work on Protected Areas (PoWPA) The Economics of Ecosystems and Biodiversity (TEEB) developed for assessing and capturing value in ecosystems’ goods and services in FSM |
|  | Status of NBSAP vis-à-vis the guidance in the CBD Strategic Plan (2011-2020) | NBSAP is out of date and does not consider newer guidance | By early 2015, the The FSM’s NBSAP is fully updated, it is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP | CBD Website. | Government recognises need and prepared to adopt a realistic plan. All relevant stakeholders will agree to proposed Plan and Action Plan. |
| Outcome 3 – Strengthened national frameworks for NBSAP implementation, CDB reporting and exchange mechanisms | 3.1 National frameworks for NBSAP implementation is in place and includes: (i) institutional leadership for implementation is established andstrategic partnerships forged (nationally, regionally and internationally); (ii) a costed and prioritized Action Plan is appended to the National Biodiversity Strategy; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) a strategy for resource mobilization for the implementation of the NBSAP is produced and includes a baseline assessment of existing biodiversity finance. 3.2. Immediate CBD reporting obligations are met by FSM in a timely manner, in particular the Fifth National Report to the CBD by 31 March 2014. |
|  | Status of the national clearinghouse mechanisms (CHM) | CHM is not kept up to date and is not linked up to the CBD’s global CHM networks and to other information and knowledge exchange network. | By 2015, the national CHM is complete the kept up-to-date and has been improved | CBD Website CHM national site(s) |  |
|  | Status of the capacity, technology and financial frameworks for implementing the revised NBSAP | No framework exists | By 2015, a complete plan for implementing the NBSAP, including capacity, technology and finance needs assessment, has been produced and underpins NBSAP implementation | Project APR/PIR |  |

A detailed activity list and a chronogram of activities per output will be finalised upon project inception.

SECTION III: Total Budget and Workplan

| GEF Component (Outcome) /Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | ERP / ATLAS Budget Code | Atlas Budget Description | TOTAL Amount (USD) | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Comp 1. Stocktaking and national target setting | DRD | 62000 | GEF-10003 | 71200 | International Consultants | 5,000 | 5,000 | 0 | 0 | a |
|  | DRD | 62000 | GEF-10003 | 71300 | Local Consultants | 8,000 | 8,000 | 0 | 0 | b |
|  | DRD | 62000 | GEF-10003 | 71600 | Travel | 7,000 | 7,000 | 0 | 0 | c |
|  | DRD | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 8,000 | 8,000 | 0 | 0 | d |
|  | DRD | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 5,000 | 5,000 | 0 | 0 | e |
|  | DRD | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 3,000 | 3,000 | 0 | 0 | f |
|  | DRD | 62000 | GEF-10003 | 72800 | Information Technology Equipmt | 2,110 | 2,110 | 0 | 0 | g |
|  | DRD | 62000 | GEF-10003 | 74500 | Miscellaneous Expenses | 500 | 500 | 0 | 0 | l |
| TOTAL ACTIVITY 1 (Comp 1) - GEF | 38,610 | 38,610 | 0 | 0 |  |
| Comp 2. NBSAP update | DRD | 62000 | GEF-10003 | 71200 | International Consultants | 13,000 | 0 | 13,000 | 0 | a |
|  | DRD | 62000 | GEF-10003 | 71300 | Local Consultants | 18,000 | 0 | 18,000 | 0 | b |
|  | DRD | 62000 | GEF-10003 | 71600 | Travel | 10,000 | 0 | 10,000 | 0 | c |
|  | DRD | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 17,100 | 0 | 17,100 | 0 | d |
|  | DRD | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 14,000 | 0 | 14,000 | 0 | e |
|  | DRD | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 9,000 | 0 | 9,000 | 0 | f |
|  | DRD | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 12,500 | 0 | 12,500 | 0 | h |
|  | DRD | 62000 | GEF-10003 | 74200 | Audio Visual&Print Prod Costs | 3,700 | 0 | 3,700 | 0 | i |
|  | DRD | 62000 | GEF-10003 | 74500 | Miscellaneous Expenses | 1,000 | 0 | 1,000 | 0 | l |
| TOTAL ACTIVITY 2 (Comp 2) - GEF | 98,300 | 0 | 98,300 | 0 |  |
| Comp 3. National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms | DRD | 62000 | GEF-10003 | 71200 | International Consultants | 7,000 | 0 | 0 | 7,000 | a |
|  | DRD | 62000 | GEF-10003 | 71300 | Local Consultants | 13,000 | 0 | 0 | 13,000 | b |
|  | DRD | 62000 | GEF-10003 | 71600 | Travel | 8,090 | 0 | 0 | 8,090 | c |
|  | DRD | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 10,000 | 0 | 0 | 10,000 | d |
|  | DRD | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 6,000 | 0 | 0 | 6,000 | e |
|  | DRD | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 6,000 | 0 | 0 | 6,000 | f |
|  | DRD | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 12,500 | 0 | 0 | 12,500 | h |
|  | DRD | 62000 | GEF-10003 | 74500 | Miscellaneous Expenses | 650 | 0 | 0 | 650 | l |
| TOTAL ACTIVITY 3 (Comp 3) - GEF | 63,240 | 0 | 0 | 63,240 |  |
| 4. Project Mgt | DRD | 62000 | GEF-10003 | 71300 | Local consultant | 5,850 | 975 | 3,900 | 975 | j |
|  | DRD | 62000 | GEF-10003 | 71300 | Local consultant | 10,500 | 1,750 | 7,000 | 1,750 | k |
|  | DRD | 62000 | GEF-10003 | 74500 | Miscellaneous Expenses | 1,500 | 100 | 1,300 | 100 | l |
|  | DRD | 62000 | GEF-10003 | 74100 | Professional Services | 2,000 | 0 | 1,000 | 1,000 | m |
| TOTAL ACTIVITY 4 (Project Management) - GEF | 19,850 | 2,825 | 13,200 | 3,825 |  |
| GRAND TOTAL (in cash) | 220,000 | 41,435 | 111,500 | 67,065 |  |

| Budget Notes |
| --- |
| a | Int. NBSAP Consultant fee (lump-sum $25K / or approx. 10 weeks) - budget spread among the three components |
| b | National Expert Biodiversity Management and Consultation Processes (lump sum $39K / or approx. 60 weeks) - budget spread among the three components |
| c | Travel for Int. NBSAP Consultant; Environmental economics, finance and biodiversity service provision; Capacity needs assessment for BD management service provision, and Local Travel. |
| d | Groups of Experts: (1) National Target Setting and NBSAP Update Working Group; and (2) Economic and Development Sectors. Lump sum $35.1K - budget spread among the three components |
| e | Environmental economics, finance and biodiversity mainstreaming service provision (lump sum $25K) – budget spread among the three components |
| f | Consultations and meetings in connection with the biodiversity planning stock-taking and target setting exercises; NBSAP update exercise; NBSAP implementation plans and 5NR. |
| g | Two laptops for local consultants. |
| h | Capacity needs assessment for BD management service provision (lump-sum $25K) - divided equally among components 2 and 3 |
| i | Printing of 1000 copies of the NBSAP and related reports. May involve basic editorial work. |
| j | National Expert: Biodiversity Management and Consultation Processes (managerial tasks corresponding to 9 out of 65 weeks @ $650/week) |
| k | Project Assistant(s) part-time, one per state, amounting in total to $10,500 to be financed by GEF for the duration of the project (approx 70 weeks @$150/week). |
| l | Costs of communication, including telephone costs and internet service provision (in connection with project management). Stationary and other supplies (in connection with project activities). |

# SECTION IV: ADDITIONAL INFORMATION

## PART I: Other agreements

### Government Letter of Endorsement

PART II: Terms of References for key project staff

TOR Background (standard for all posts)

The GEF approved funding for Biodiversity Enabling Activities in the FSM. UNDP is the GEF implementing agency for the project, whose title is “National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in the FSM” The project aims to integrate the FSM’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative “biodiversity planning” and strategizing process, including revising the country’s NBSAP to reflect effectively the emerging issues identified in the CBD Strategic Plan for 2011-2020. This will be achieved through three inter-related outcomes: Outcome 1) A participative stocktaking exercise on existing strategies undertaken and national biodiversity targets are developed in response to the global Aichi Targets Outcome 2 ) The NBSAP is revised/updated and it fully integrates new aspects of the CBD strategic plan, such as mainstreaming and anchoring the implementation of the plan into national development frameworks, valuing ecosystem services and promoting ecosystem-based adaptation and resilience Outcome 3) Strengthened national frameworks for NBSAP implementation, CDB reporting and exchange mechanisms UNDP, in close collaboration with the national implementing agency, the Department of Environmental Affairs, would like to engage a qualified candidate for the above mentioned post for rendering services to the project. The contract will be drawn by the Department of Environmental Affairs for a period of [complete as applicable]. The contract will be performance-based. Terms and conditions of service linked to type of proposed contract will apply for the specific position.

### National Project Coordinator (Project Technical Coordinator)

| Location: | Pohnpei |
| --- | --- |
| Application Deadline: | 30 days after publication |
| Category | Environment and Energy |
| Type of Contract: | Consultancy Contract |
| Languages Required: | Written English; |
| Starting Date (date when the selected candidate is expected to start): | TBD |
| Duration of Initial Contract: | 1 year |
| Expected Duration of Assignment: | Up to 2.5 years. |

Duties and Responsibilities

Managerial tasks Objective: To undertake the general administrative requirements of the project, including those related to project management and funding. The key tasks are: Ensure that project Objective, Outcomes, Outputs and Activities are executed in a timely and appropriate manner. Develop annual work plans and budgets, and submit these to the Steering Committee and to the UNDP Country Office for approval. Develop TORs for consultants for technical assistance services, and other types of service provision works, as well as specifications for materials as required by the project, in consultation with the National Project Director. Facilitate, guide and monitor the work of consultants, and approve/clear their deliverables in association with the Project Committee. Organize and assist in project related activities, where required. These may include planning for meetings, local and national workshops, consultations, trips, and other project related activities. Establish and maintain linkages with national and projects, programmes, initiatives, international organizations and persons which/who can be of assistance to the objectives of the project. Provide timely reporting of project status as required by the Project Committee and the UNDP. Maintain records of Project Committee meetings, decisions, actions etc. Coordinate with other initiatives and programs whose outcomes and outputs are relevant to this project’s objectives. Any other duties assigned by the Project Committee that have direct relevance to the project. Technical tasks Objective: To lead the overall process of the stocktaking, stakeholder consultation, national target setting and the development of the NBSAP and be responsible for the timely drafting and finalization of the NBSAP. The key tasks are: Play a leading and resource person role vis-a-vis the National Target Setting and NBSAP Update Working Group and in a number of national sub-national consultation processes for all relevant activities under the Enabling Activity project. Develop planning methodologies and processes for the sub-national technical meetings and consultations. Review base documents for the inputs to the sub-national technical meetings and consultations. Work on the preparation of base documents for technical meetings. Together with support from technical staff review the consolidated results of the five regional consultations Review the NBSAP update. Develop methodologies for the national validation of the national targets and draft NBSAP. Carry out consultations with provincial authorities and organize sub-national technical meetings and consultations and National Technical meetings. Collect and consolidate information arising from the technical meetings. Provide inputs for evaluation of institutional capabilities. Work with local experts and government authorities to collect available information on biodiversity. Provide inputs to the development of the NBSAP implementation plans. Contribution to the following deliverables: Brief Action-Oriented National Biodiversity Framework for The FSM, reviewing biodiversity planning processes in The FSM and including requirements for implementation of the new NBSAP Biodiversity Targets for The FSM: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 Second National Biodiversity Strategy and Action Plan for The FSM Sub-product 1: Implementation Priorities for the NPAES Sub-product 2: Assessing and capturing value in ecosystems’ goods and services in The FSM – analysis of primary research needs Sub-product 3: Ecosystem-based adaptation Study: Options and costs of nature-based solutions to climate change in The FSM Sub-product 4: Analysis of biodiversity impacts and opportunities in key economic sectors – focus on agriculture, fisheries, plantation forestry Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP, including a resource mobilization strategy Fully functional CHM Gateway for The FSM, based on best international practice on the matter

Competencies

Writes clearly and convincingly. Focuses on achieving results Sets priorities, produces quality outputs, meets deadlines and manages time efficiently Shares knowledge and is willing to provide support to others who request advice or help Works toward creative solutions by analyzing problems carefully and logically Demonstrates sufficient technical knowledge to perform effectively in own specialty Leads and supports team decisions Maintains strong relationships with partners and clients Facilitates meetings effectively and efficiently and to resolve conflicts as they arise

Required Skills and Experience

Core skills: Ability to communicate effectively orally and in writing in order to communicate complex, technical information to technical and general audiences Skills in negotiating effectively in sensitive situations Skills in achieving results through persuading, influencing and working with others Skills in facilitating meetings effectively and efficiently and to resolve conflicts as they arise Required experience: Advanced degree in environmental or natural sciences (e.g. MSc), economics, social sciences, management, with professional exposure to biodiversity management issues; At least 5 years of professional experience, of which at least three are at international level Proven track record of drafting relevant materials in with biodiversity as a topic (publications, reports and related documentation). Proven ability to collect, verify and analyze information, and to finish and present work with a high degree of accuracy, timeliness and technical quality. Knowledge and understanding of the relevant UN Convention, Previous experience in the development of NBSAPs. Strong skills in monitoring and evaluation, and experience in implementing environmental projects; Previous experience with GEF projects is an added plus; Ability to effectively coordinate a large, multidisciplinary team of experts and consultants; Be an effective negotiator with excellent oral and presentation skills; Excellent writing skills in English; A good working knowledge of the other FSM official languages is an added plus.

### Project Assistant(s)

| Location: | Chuuk, Kosrae, Pohnpei and Yap |
| --- | --- |
| Application Deadline: | [30 days after publication] |
| Category | Environment and Energy |
| Type of Contract: | Part-time Individual Contract |
| Languages Required: | Written English; good oral command of [second language, if applicable] is a plus |
| Starting Date (date when the selected candidate is expected to start): | [date] |
| Duration of Initial Contract: | 1 year |
| Expected Duration of Assignment: | Up to 2.5 years. |

Duties and Responsibilities

The Administrative Assistant(s), working under the direct supervision of the Project Coordinator (PC), will be responsible for all the administrative, secretarial and office logistical matters of the CBD project. The Administrative Assistant will be responsible for the project’s record keeping systems, meetings and travel arrangements, stationary requirements, and general office functions and systems management. The Administrative Assistant will work closely with the Project Manager, the project Accountant and Specialists. The project assistant will work closely with the project coordinator to: Conduct the secretarial activities of the project including correspondences, filing and drafting minutes of meetings. Responsible for arranging the travel, contracts, and accommodation logistics for project-related meetings. Assist in the organization and daily operation of the Project Unit. Ensure communications, office equipment and computer systems are kept fully operational.

Competencies

Writes clearly and convincingly. Focuses on achieving results Sets priorities, produces quality outputs, meets deadlines and manages time efficiently Shares knowledge and is willing to provide support to others who request advice or help Works toward creative solutions by analyzing problems carefully and logically.

Required Skills and Experience

Required experience: Working experience in office management or secretarial responsibilities. Working knowledge of common communications and computer operating systems; Previous experience in a management team of conservation funded projects or similar regional/multi-country projects in small island developing countries would be an advantage; Excellent working knowledge of English; Proven ability to work as part of an interdisciplinary and/or multi-cultural team; Background and /or experience in environmental or natural sciences economics, social sciences, management, with professional exposure to biodiversity management issues; Knowledge and understanding of the relevant UN Convention, Previous experience in the development of NBSAPs. Strong skills in monitoring and evaluation, and experience in implementing environmental projects; Previous experience with GEF projects is an added plus; Ability to effectively coordinate a large, multidisciplinary team of experts and consultants; Excellent writing skills in English; A good working knowledge of other The FSM official languages is an added plus.

### Project Consultants

| Consultant | Number of weeks | Deliverables |
| --- | --- | --- |
| Lead International Consultant | 10 weeks 25,000 US$ | Contribution to the following deliverables: Brief Review of the Biodiversity Planning Process in FSM Updated National Biodiversity Strategy and Action Plan for the FSM, it is in line with the guidance in the CBD Strategic Plan (2011-2020) and ready for stakeholder consultation and to pass procedure for Government’s endorsement before it could be submitted to the CBD Sub-product 1: Assessing and capturing value in ecosystem’s goods and services in FSM Sub-product 2: Exploring and costing options for Ecosystem-based adaptation to Climate Change in FSM |
| Contracted group of experts in economic and development sectors | 10 weeks 17,500 US$ | Contribution to the following deliverables: Brief Review of the Biodiversity Planning Process in FSM Second National Biodiversity Strategy and Action Plan for FSM Sub-product 1: Assessing and capturing value in ecosystem’s goods and services in FSM Sub-product 2: Exploring and costing options for Ecosystem-based adaptation to Climate Change in FSM |
| Contracted group of experts working as part of the National Target Setting and NBSAP Update Working Group | 10 weeks 17,600 US$ | Contribution to the following deliverables: Brief Review of the Biodiversity Planning Process in FSM Biodiversity Targets for FSM: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 Second National Biodiversity Strategy and Action Plan for FSM Sub-product 1: Assessing and capturing value in ecosystem’s goods and services in FSM Sub-product 2: Exploring and costing options for Ecosystem-based adaptation to Climate Change in FSM Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP |
| Expert on Environmental economics, finance and biodiversity mainstreaming | 10 weeks 25,000 US$ | Identify and assess the full range of values of key ecosystem services within FSM, based on existing local, national, regional and global studies on the value of ecosystems and biodiversity, including: the valuation of protected areas, any other national ecosystem services studies that have been conducted (e.g. water, carbon), and existing global and regional maps and overlays of key ecosystem services. Identify the implications of these services for different stakeholder groups within the country, including those who benefit from, and pay for, the maintenance of these ecosystem services, and those that degrade ecosystems through unsustainable use. Estimate and demonstrate the value of key ecosystem services (using methods appropriate to each service), including the value of the ecosystem service in contributing to climate resilience, adaptation and mitigation; reducing poverty, and sustaining livelihoods. Where appropriate, assist in identifying potential means of capturing the value of targeted ecosystem services including through policies such as payments for ecosystem services and other positive incentives. Identify priority Biodiversity investment needs and opportunities based on the NBSAP. Analyse internal sources of finance for action in the NBSAP including i) the national budget cycle and the allocation to public administrations (ministries), ii) the budget of local governments, iii) national funds to support local development, and iv) fiscal and economic instruments. Analyse external sources of finance for actions in the NBSAP including i) bilateral sources, ii) multilateral sources, iii) regional development banks, iv) international foundations and non-governmental organisations (NGOs) Analyse innovative sources of finance for actions in the NBSAP, especially fiscal measures related to: i) tourism and infrastructure development (to encourage the mainstreaming of biodiversity into their operations, ii) bank loans for investment projects. NBSAP Integrated Financing Action Plan summarising concrete activities required to mobilise BD finance for the 10-year period of the implementation of the NBSAP. |
| Expert Capacity Needs Assessment for Biodiversity Management | 10 weeks 25,000 US$ | Assess extent of role clarity and the level of implementation and enforcement of the CBD and its CoP guidance across all primary and secondary stakeholders in central government. Determine the level of willingness to take responsibility and provide leadership in ensuring relevant CBD obligations and activities are fulfilled. Assess whether the identified primary and secondary duty bearers have the necessary human resources to meet the specific obligations. Assess the pattern and efficacy of participation at regional technical committees and COP meetings. Based on international best practice, recommend the most suitable institutional and/or accountability structure for the effective implementation and coordination of the CBD. Identify and prioritise the capacity development needs required to effectively implement CBD obligations at all levels within central government. Generate recommendations for capacity enhancement at all levels. Generate recommendations to enable rationalisation of capacity and efficient resource allocation during implementation Develop a comprehensive Capacity Development Programme and Training Action Plan for effective implementation and coordination of CBD at the municipal and central government levels. |

# Project Annexes

## Annex 1. Approved GEF proposal for BD EA (Headings Overview on page 4)

REQUEST FOR BIODIVERSITY enabling activity

Proposal for Funding Under the GEF Trust Fund

part i:  project IDentifiers

| EA Title: | National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in the Federated States of Micronesia |
| --- | --- |
| Country(ies): | Federated States of Micronesia | GEF Project ID: | TBD |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | 5100 |
| Other Executing Partner(s): | UNDP in collaboration with the Department of Resources and Development | Submission Date: | 6 May 2013 |
| GEF Focal Area (s): | Biodiversity | Project Duration (Months) | 30 |
| Check if applicable: | NCSA NAPA | Agency Fee ($): | 20,900 |

- EA framework

EA Objective: To integrate FSM’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020.

| EA Component | Type | Expected Outcomes | Expected Outputs | Grant Amount ($) | Confirmed Co-financing ($) |
| --- | --- | --- | --- | --- | --- |
| 1) Stocktaking and national target setting | TA | By mid-2013, national targets in response to the global Aichi Targets are developed. | 1.1 Review and stocktaking of products and results from previous biodiversity planning processes at the sub-national level with national facilitation and assistance are carried out in participative manner. 1.2 In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to FSM’s reality. 1.3 The achievement of national targets, developed in line with the global Aichi Targets, is monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means. 1.4 In an iterative manner, FSM taps into useful information on, and participates into, regional and global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership, Global Biodiversity Information Facility and the World Conservation Monitoring Centre, the Global Environment Outlook portal, the Micronesia Challenge Measures among other relevant ones). | 38,610 | 60,000 |
| 2) NBSAP update | TA | By 2014, FSM’s NBSAP is fully updated, is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP | 2.1 A National Biodiversity Strategy and its four subset (State) Action Plans (NBSAPs) for FSM anchored into national development frameworks, is updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. 2.2 The updated and fully endorsed NBSAPs for FSM are submitted to the CBD preferably within the deadline set by the COP, incorporating recommendations of the following strategic studies: Integrating the challenges to Protected Areas in the 21st Century into the NBSAP and the national implementation of the CBD’s Programme of Work on Protected Areas (PoWPA) The Economics of Ecosystems and Biodiversity (TEEB) developed for assessing and capturing value in ecosystems’ goods and services in FSM | 98,300 | 150,000 |
| 3) National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms |  | By 2014, complete plan for implementing the NBSAP, including capacity, technology and finance needs assessment By 31 March 2014, the Fifth National Report is submitted to the CBD | 3.1 National frameworks for NBSAP implementation is in place and includes: (i) institutional leadership for implementation is established and strategic partnerships forged (nationally, regionally and internationally); (ii) a costed and prioritized Action Plan is appended to the National Biodiversity Strategy; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) a strategy for resource mobilization for the implementation of the NBSAP is produced and includes a baseline assessment of existing biodiversity finance. 3.2. Immediate CBD reporting obligations are met by FSM in a timely manner, in particular the Fifth National Report to the CBD by 31 March 2014. | 63,240 | 60,000 |
| Subtotal | 200,150 | 270,000 |
| EA Management Cost | 19,850 | 34,724 |
| Total EA Cost | 220,000 | 304,724 |

a   List the $ by EA components.

- Co-financing for the EA by source and by name

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| National Government | State Governments of the Federated States of Micronesia: Chuuk, Kosrae, Pohnpei and Yap State Governments* | In-kind | 233,102 |
| National Government | Department of Resources and Development, Division of Resource Management and Development | In-kind | 41,622 |
| CSO | Kosrae Conservation and Safety Organization | In-kind | 30,000 |
| Total Co-financing | $304,724 |

* Sub-national, but not local.

- Grant  Resources Requested by Agency, Focal Area and Country

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | EA Amount (a) | Agency Fee (b) | Total (c)=(a)+(b) |
| --- | --- | --- | --- | --- | --- | --- |
| UNDP | GEF TF | Biodiversity Focal Area Set-Aside | Federated States of Micronesia | 220,000 | 20,900 | 240,900 |
| Total Grant Resources |  |  |  |

- EA Management Cost

| Cost Items | [GEF only] Total Estimated Person Weeks/Months | Grant Amount ($) | Co-financing ($) | EA Total ($) |
| --- | --- | --- | --- | --- |
| Local consultants* | 79 | 16,350 | 7,451 | 23,801 |
| International consultants* | 0 | 0 | 0 | 0 |
| Office facilities, equipment, vehicles and communications* |  | 0 | 0 | 0 |
| Travel |  | 0 | 0 | 0 |
| Others**: Miscellaneous expenses and project audit |  | 1,500 | 273 | 1,773 |
| Professional services |  | 2,000 | 27,000 | 29,000 |
| Total |  | 19,850 | 34,724 | 54,574 |

*   Details to be provided in Annex A.     ** Other items to be clearly specified.

Additional information for Table D, if applicable:

If costs for office facilities, equipment, vehicles and communications, travels are requesting for GEF financing, please provide justification here:

n/a

part ii:  Enabling Activity JustiFication

A. Enabling Activity Background and Context (Provide brief information about projects implemented since a country became party to the convention and results achieved):

Background: The FSM is the largest and most diverse part of the greater Micronesian region and is comprised of four States, which are, in geographic sequence from west to east, Yap, Chuuk, Pohnpei and Kosrae. The total landmass of the FSM is 438 square miles (702 km2), with a declared Exclusive Economic Zone (EEZ) covering over 1 million square miles (1.6 million km2). The FSM is comprised of 607 islands with land elevation ranging from sea level to the highest elevation of about 2,500 feet (760 m). The FSM’s natural heritage has supported, maintained and improved both the social and economic wellbeing of its people and cultures since the arrival of the first inhabitants. The importance of the nation’s biodiversity cannot be understated and is present in every facet of a Micronesian's way of life including the provision of various natural resources for food, shelter, medicinal and traditional purposes. In the past, utilization of these resources was allowed under strict traditional and community management and is believed to have provided a balance with nature that allowed the biodiversity to be utilized in a sustainable manner. The biodiversity and natural heritage of the FSM is both globally significant and the foundation for the country’s long term economic self-sufficiency. The islands of FSM contain over 1,000 plant species, at least 200 that are found nowhere else on Earth. Its reefs, which provide coastal protection and the source of livelihood for a majority of Micronesians, are home to nearly 1,000 species of fish and more than 350 species of hard coral. FSM also has particularly high species endemism, especially among the terrestrial biota. The high endemism within the nation is a direct result of the isolation of the islands to one another and to other landmasses in the greater Micronesian region. The conservation and preservation of endemic species is of particular importance to the nation. The conservation and sustainable management of all biodiversity of the nation is vital to the ongoing social, economic and cultural development of the FSM. Economic Development Challenges and threats to biodiversity: With a population of 107,000 people, the monetary economy of FSM is small and is largely dependent on aid provided through the Compact of Free Association with the United States of America (NEMS, 1993). The majority of activities are government services, wholesale and retail, and subsistence farming and fishing. The government services dominate the economy at 42%. The commercial tuna fishery (international and domestic) is the nation’s second highest revenue earner with annual revenues between US$13–20 million dollars (FSM Government Report, 1999). Tourism is an important component of the economy, with over fifty thousand tourists entering the country annually, contributing revenue earnings to the economy of the country (SPREP, 1993). Real GDP per capita is US$2,030. The same challenges that existed in 2001 when the first NBSAP was developed are in many respects still valid today, including the need to: • Integrate environmental considerations in economic development; • Improve environmental awareness and education; • Improve the management and protection of natural resources; and • Improve waste management and pollution control. The FSM clearly still has a relatively rich biodiversity inheritance, including ethnobiological traditions. Nevertheless, this fragile biological inheritance is seriously threatened due to both natural and anthropogenic events. Significant declines in the biodiversity of the FSM are clearly evident. Conversion and Degradation of Habitat and Ecosystems: Primary causes include inappropriate farming practices (e.g. extensive burning & wildfires); agricultural degradation, soil degradation, deforestation; inappropriate and indiscriminate use of fertilizers and pesticides; degradation of freshwater resources, watersheds and catchments ecosystems; degradation and deforestation of coastal and mangrove forests from inappropriate and greatly increased marine and coastal development; ship groundings; increasing urbanization and development; and increased and poorly planned infrastructure development (e.g. roads). Over Exploitation and Unsustainable Harvesting Methods and Practices: Primary causes include: destruction of coral reefs and associated ecological communities (e.g. coral extraction, reef anchors); and over exploitation of marine organisms (e.g. reef fish, sea cucumbers, giant clams). Unregulated Exportation and Utilization for Social Functions: Primary causes include: overexploitation and inappropriate development of coastal & marine ecosystems (including mangrove forests); over exploitation of forest resources; destructive and unsustainable fishing methods – e.g. dynamite, chlorine, fish poisoning plant (Derris elliptica) and small mesh gillnets; marine sand mining, dredging operations, causeway and sea wall construction; over exploitation of fish aggregation spawning sites; illegal bio-prospecting of genetic resources; loss of traditional ethnobiological knowledge; and illegal offshore and inshore fishing. Waste Management: Primary causes include: terrestrial and aquatic pollution (e.g. oil spills, coastal waste dumpsites); solid waste collection and disposal; hazardous waste usage and disposal; sewage collection, treatment and disposal; disposal of heavy equipment (e.g. cars); Invasive Organisms and Pests: These include the introduction of pests and diseases as well as direct negative impacts on native species and terrestrial and aquatic habitats by alien invasive species (e.g. Mikania micrantha, toad (Bufo marinus), rats and feral animals (e.g. pigs, wild cats). Impacts from Climate Change: Primary impacts include increased frequency and intensity of typhoons, sea level rise and coral bleaching and acidification. All of these impacts threaten biodiversity in the FSM. It is essential to take climate change and resilience into account in the new NBSAP of the FSM. Administration: The national constitution of the FSM is the basis for all legal authority and decision making for the nation. The legislation and institutional framework of the Federated States of Micronesia includes, both National and individual State constitutions with each of the four States functioning as semi-autonomous governments. This structure makes it a prerogative of each State to enact their own legislation in line with their powers as mentioned in the FSM Constitution to address all issues relating to the conservation of biodiversity. Therefore, the responsibility for the implementation and monitoring programs of the NBSAP is to be undertaken by the individual States, not the National government. Each State will develop a State BSAP consistent with the NBSAP. The responsibility for environmental issues is shared between the FSM National Government and the individual FSM State governments. The States take the lead role in ensuring that development is avoided in vulnerable areas and ensuring that critical natural systems are protected. Each State has made efforts to control development and manage natural resources through the creation of land use plans, coastal zone plans, legislation and regulations. The National Government provides guidance and technical assistance to the States when needed and requested on matters related to planning, economic development, natural resources, fisheries, and the environment. Protected area system: FSM’s has a total country area of 1.6 million km² in its Exclusive Economic Zone, and a land area of 702 km². Of this, 14% of the terrestrial area is protected, and 7 % of territorial waters are protected, with Chuuk State having 2% marine and 18% protection, Kosrae having 7% and 8% protection, Pohnpei having 29% and 20% protection, and Yap having 10% marine protection. Given the complexity challenges faced by the country, resilience has been introduced at various aspects of public administration and policy development, depending on the state or community. For example, Pohnpei has several MPAs, established by state law in 1999 and 2001. In 2005, the Conservation Society of Pohnpei led a Rapid Ecological Assessment to assess the existing MPAs and identify potential new sites, based on habitat types and threat status. In 2011, two major conservation bills were signed into law in Pohnpei. The first bill amended the Pohnpei State Sanctuary and Wildlife Act adding four protected sites to become part of the Pohnpei protected areas network. The sites are Nan Wap reef, Senpehn mangrove reserve, Enipein mangrove reserve, and Pakin island reefs, and collectively the four sites amounts to over 1500 hectares of reefs and mangroves to the Pohnpei network. This law significantly increases the biodiversity conservation coverage in Pohnpei. Principles of resilience are being incorporated into guidance for developing state protected areas networks and work toward achieving the goals of the Micronesia Challenge (MC), an ambitious initiative by the jurisdictions of Micronesia to effectively conserve at least 30% of their nearshore marine resources and 20% of their terrestrial resources by 2020. The states are also working toward a standardized monitoring program, to measure some key regional indicators, to assess broad trends in the country, and track progress toward achieving the goals of the MC. Also as part of the MC, a communications campaign is being developed by a communications working group, which will incorporate the principles of resilience. FSM has recently concluded an ecological gap assessment for the protected area system. Examples of key protection priorities for Yap and Pohnpei are shown below, with areas most important to protect shown in dark blue: Gap Assessment Map Primary barriers to the effective implementation of the CBD in FSM include: Population growth: Rapidly increasing populations especially in urban centers are leading to more consumptive lifestyles putting pressure on natural resource and exploitation/extraction; Scientific knowledge: Insufficient scientific baseline biological information on the status of biodiversity limits management scheme with respect to monitoring and adaptive management; Legislative gaps: Insufficient biodiversity legislation hinders enforcement and compliance. Human resources: Insufficient skilled/trained human resources impede the sustainability of natural resource management Awareness: Insufficient awareness leads to disconnected linkages and distortion of the balance between environment, economics and sustainable development Funding: Insufficient and unsustainable funding does not sustain the management of conservation activities Other related biodiversity planning processes: In addition to the CBD reporting processes and the conclusions from previous capacity needs assessments, the preparation of FSM’s new NBSAP will build on prior and ongoing biodiversity planning processes, including: A national-level and state-level ecological gap assessment for the country, conducted as part of the Early Action Grant project for FSM, supported by GEF and implemented by UNDP; The Micronesian Challenge, a regional conservation collaboration that aims to achieve 20% of terrestrial and 30% of marine protection by 2020; A regional Pacific-wide project on adaptation to climate change (GEF project identification 3101) – a project to implement long-term adaptation measures to increase the resilience of a number of key development sectors in the Pacific islands to the impacts of climate change. The key development sectors included in this project are water resources management; food production and food security; and coastal zone and associated infrastructure (roads and breakwater). A regional Pacific-wide project on international waters (GEF project 2131) aimed at providing support for discussions and negotiations between Pacific SIDS, other coastal states including Indonesia and the Philippines and fishing states, on a new regional arrangement for the conservation, management and sustainable development of transboundary stocks of highly migratory species. National Reporting to CBD Reports Date of Submission to CBD Secretariat Current Status* Comments National Biodiversity Strategy and Action Plan 02 May 2002 Submitted Currently outdated, as does not address Aichi Targets fully. Revision of NBSAP Not submitted Not yet started Funding being applied for under this project 1st National Report 15 May 2001 Submitted 2nd National Report 21 March 2002 Submitted 3rd National Report Not submitted 4th National Report 22 June 2010 Submitted Although completed, the report does not fully consider the Aichi Targets and new CBD guidance. These will be included in the 5th National Report under this project. Capacity Needs Assessments carried out YES NO Start Date: Jan 2005 End Date: Dec 2010 Please list all of the CBD Program of Work and cross-cutting themes that were addressed in the Biodiversity Enabling Activities Capacity Needs Assessments: Dates Cross-cutting capacity needs assessments for the implementation of the Rio Conventions. Nov 2007 Under the Fourth National Report to the CBD: Agrobiodiversity Biodiversity for Development Invasive Alien Species Protected Areas Sustainable Use of Biodiversity Marine and Coastal Biodiversity Oct 2010 3) Clearing House Mechanism (CHM) established? YES NO CHM link(s): www.comfsm.fm/bchm/index.htm Is the CHM website maintained up to date? YES NO How many people currently operate and maintain the national CHM? 1 How many people visited the national CHM website in the past 12 months? Unknown

B. Enabling Activity Goals and Objectives (The proposal should briefly justify the need for the project.)

The Baseline Project: The Current NBSAP and the new CBD Strategic Plan The new CBD Strategic Plan, adopted at CoP-10 in 2010 in Nagoya, clearly addresses the need for updating NBSAPs, stating in Target 17 that “By 2015, each Party has developed, adopted as a policy instrument, and has commenced implementing an effective, participatory and updated national biodiversity strategy and action plan.” The strategic plan also covers a range of issues that will need to be incorporated into the revised NBSAPs, including guidance to countries to: a) fully realize the value of biodiversity and ecosystem services, and incorporate these values into national and local development and poverty reduction strategies (Targets 1 and 2); b) increase the global terrestrial protected area estate from 12% to 17% and the marine estate from 6% to 10% (Target 11); c) restore and safeguard key ecosystem services, especially for water, health and livelihoods (Target 14); and d) strengthen ecosystem resilience to climate change and promote ecosystem-based approaches to climate change adaptation and mitigation (Target 15). The most recent NBSAP for FSM was completed in 2001. This version of the NBSAP does not include the following elements of the CBD Strategic Plan’s Aichi Targets: A plan for integrating the value of biodiversity into national and local development and poverty reduction strategies and planning processes and are being incorporated into national accounting, as appropriate, and reporting systems (Target 2) – although the previous NBSAP did address linkages between biodiversity and humans, its focus was on humans population growth as a primary threat to biodiversity, and did not include specific strategies for poverty alleviation and linkages with human wellbeing, including the identification of critical ecosystem services; A plan for creating incentives and removing harmful subsidies (Target 3) – although there is a section on mainstreaming legislation, it does not address incentives and subsidies. A plan for fully implementing the Programme of Work on Protected Areas, including increased protection and landscape/seascape connectivity (Target 11) – FSM has recently developed a draft action plan for the Programme of Work on Protected Areas, but still needs to assess specifically how the new proposed protected areas can address many of the Aichi Targets, including avoiding extinctions, safeguarding critical ecosystems, and strengthening climate resilience (in particular reef resilience); A plan for restoring and safeguarding ecosystems that provide essential services, including services related to water, and contribute to health, livelihoods and well-being (Target 14) – the previous NBSAP did not identify areas of critical ecosystem services, nor did it address specific strategies for safeguarding these ecosystem services; A plan for strengthening ecosystem resilience and the contribution of biodiversity to carbon stocks, including the restoration of at least 15 per cent of degraded ecosystems (Target 16) – this is particularly important in FSM, and will be a key feature of the revised NBSAP; A plan for the mobilization of financial resources for effectively implementing the Strategic Plan for Biodiversity 2011-2020 from all sources (Target 20) – This was a major decision at CoP-11, and FSM will be identifying and mobilizing required resources to implement its revised NBSAP. Proposed Response and Rationale: The new generation of BD EA. This project seeks to fully incorporate the above issues into the NBSAP. This ‘next generation’ NBSAP will create a national road map for achieving the Aichi Targets, and for changing the trajectory of development in FSM. Special emphasis will be placed on mainstreaming biodiversity into development plans, incorporating protected area networks and sustainable production systems into ecosystem-based climate adaptation and resilience plans, and creating sustainable finance for biodiversity conservation through the full valuation of key ecosystem services. Alignment with Focal Area Outcome(s): BD5 Objective: Integrate CBD Obligations into National Planning Processes through Enabling Activities (herein serving as the ‘Project Development Goal’) Focal Area Outcome 5.1: Development and sectoral planning frameworks at country level integrate measurable biodiversity conservation and sustainable use targets. The Project Objective is: To integrate FSM’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020. This will be achieved through the following Outcomes (corresponding to components described in detail below): Outcome 1 – A participative stocktaking exercise on biodiversity planning takes place and national biodiversity targets are developed in response to the global Aichi Targets Outcome 2 – The NBSAP is revised/updated and it fully integrates new aspects of the CBD strategic plan, such as mainstreaming and anchoring the implementation of the plan into national development frameworks, valuing ecosystem services and promoting ecosystem-based adaptation and resilience Outcome 3 – National frameworks for resource mobilization, NBSAP implementation, Convention reporting and exchange mechanisms are strengthened How the project plans to build national capacity Enabling Activities are considered foundation activities within the framework of the GEF. The ultimate goal of Biodiversity Enabling Activities is to build national capacity across the board for biodiversity management. The effective achievement of global biodiversity benefits depends on the development of national capacity for managing biodiversity. The approach to building of national capacity in this proposal will include: (1) driving a participatory and consultative process for preparing all of key products under the project; and (2) bringing professional expertise into the process, e.g. by planning a few highly strategic output-based consultancies, where one of the key aims is to build national capacity to carry out activities related to biodiversity planning. The project will focus on strengthening national capacity in FSM in the following manner: Individual Much of the work under this project will be carried out through working groups. This is an ideal forum for imparting knowledge among different individuals involved in biodiversity planning and in environmental matters in FSM. This approach ensures that national and international consultants, technical experts and advisors, stakeholders and government staff collaborate in a shared learning process. Organizational UNDP’s approach to Biodiversity Enabling activities in GEF5 goes beyond the mere production of national reports and strategies to the CBD and the development of a website for the CHM. Rather, it is concerned about developing a permanent framework for reporting to the CBD and monitoring on biodiversity management. This implies institutionalizing the capacity for eventually achieving this with as little external assistance as possible. Given the ambitious targets of the CBD Strategic Plan for 2011-2020, it is recognized that actions to engage external assistance and retain national are in the meanwhile needed. This will be availed through the project. In particular, the following activities are specially targeted at building organizational capacity: Taking stock of the NBSAP and identifying barriers to its implementation Setting targets and priorities Developing implementation plans for the revised NBSAP Assessing and strengthening capacity needs Developing a permanent framework for reporting to the CBD Systemic The approach that UNDP has developed for Biodiversity Enabling Activities in GEF5 is transformational with respect to systemic capacity elements (i.e. policy, economic, regulatory, and accountability frameworks within which organizations and individuals operate). The aim is to ensure that the objectives, targets and guidance from the CBD Strategic Plan for 2011-2020 become fully anchored into national development frameworks and that the system is capable of effectively and in those cases where relevant and possible real-time collecting, analyzing and feeding back the relevant information into the policy making. The method will utilize systemic and societal capabilities and harness those for policy making and monitoring and evaluation that will combine traditional with innovative mechanisms of data collection. The knowledge developed through these activities will become part of FSM’s new NBSAP and will have a greater chance of influencing and even becoming policy. In particular, the following activities are specially targeted at building systemic capacity: Assessing and integrating ecosystem services through economic valuation Mainstreaming biodiversity into development policies, plans and practices, into sectoral plans and strategies, and into national accounting frameworks Incorporating climate change issues into the NBSAP, including the incorporation of challenges and opportunities linked to ecosystem-based adaptation and mitigation and ecosystem resilience. Integrating the NBSAP implementation plan with the CBD Programme of Work on Protected Areas implementation plan Securing sustainable finance for NBSAP implementation Monitoring and reporting on the status of biodiversity under climate change scenarios

C. Describe the Enabling Activity and Institutional Framework for Project Implementation (discuss the work intended to be undertaken and the output expected from each activity as outlined in Table A ).

Detailed Description of Activities per Project Component / Outcome The description that follows has been organized in five modules (I -V), following the GEF’s guidance, but which for the sake of simplicity were grouped within the three already mentioned Components / Outcomes. The following are modules: Component Outline of modules for NBSAP Revision and Related Activities Indicative percentage of total GEF funding in the proposal (mgt costs excl.) 1 I. Preparation 7% II. Setting national targets, principles, & main priorities of the strategy 12% 2 III. Strategy and action plan development 49% 3 IV. Development of Implementation plans and related activities 20% V. Institutional, monitoring, reporting and exchange 12% Component 1. Stocktaking and national target setting Key Outputs expected under this component includes the following: Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in participative manner. In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to FSM reality. The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means. In an iterative manner, FSM taps into useful information on, and participates into, global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership, Global Biodiversity Information Facility and the World Conservation Monitoring Centre, the Global Environment Outlook portal, among other relevant ones). Key Outcomes: By early 20123, a multi-sectoral/multi-stakeholder working group is established and it completes the stock-taking exercise. It is very likely that the existing multi-sectoral advisory group that already exists in FSM will be tasked with this job By mid-2013, national targets in response to the global Aichi Targets are developed. Key Products or publications resulting from activities: Brief Review of the Biodiversity Planning Process in FSM Biodiversity Targets for FSM: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 Key Activities (I-II): The existing multi-advisory group, and a stakeholder group of key sectors will play a pivotal role in preparatory and target-setting activities under Component 1. They will be assisted by the national coordinator and consultants, who will carry out the various products. The process of setting targets will be participatory and will include the views of a broad audience, e.g. through a national workshop. Key activities of this component include: Preparing for the NBSAP revision Taking stock of the NBSAP and identifying barriers to its implementation: This activity will focus on rapidly but accurately taking stock of existing plans, policies and practices, and of the root causes of biodiversity loss. Within country-specific contexts, the aim is not only to identify key threats, but to understand the drivers behind these threats, as well as the key aspects of the policy environment that are barriers and challenges to effective conservation/sustainable use. Based on existing studies and analyses, the emphasis of this activity will be on identifying key gaps in the existing NBSAP, understanding the primary drivers and root causes, and identifying the means of overcoming existing barriers and challenges. Stakeholder consultation and participation: This activity will focus on ensuring a robust consultative process that engages representatives from key sectors, administrative leaders, and traditionally under-represented groups. The aim is to develop and sustain a participatory process in order to increase the likelihood of successful implementation of the NBSAP. This is especially important relative to the goals of mainstreaming biodiversity into national development plans, and promoting resilient landscapes that include production sectors. For this specific task the project will closely collaborate with the currently on-going Micronesian Challenge and the GEF funded, UNDP implemented Early Action Project on Protected Areas in FSM, which has already identified many primary stakeholders in the biodiversity area and established mechanisms for exchanging information. Setting targets Setting targets and priorities: This activity focuses on setting specific, measurable, achievable and time-bound targets for the NBSAPs based on the global Aichi Targets, including targets on restoration of ecosystems, protected area coverage, overall biodiversity loss, and other aspects of the Strategic Plan. This activity, which is linked to priority setting among different aspects within the NBSAP, will be initiated (if not completed) by CoP-11. Component 2. NBSAP Update Key Outputs expected under this component includes the following: The National Biodiversity Strategy and Action Plan (NBSAP) for FSM, anchored into national development frameworks, is updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. The updated and fully endorsed NBSAPs for FSM is submitted to the CBD preferably within the deadline set by the COP, incorporating recommendations of the following strategic studies: Local-level assessment of the value of critical ecosystems within FSM, and opportunities for capturing that value; and Exploring and costing options for developing ecosystem-based adaptation strategies and for strengthening resilience of climate change in FSM Revised and updated protected areas action plan Key Outcome: By early 2014, FSM’s NBSAP is fully updated, it is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP Key Products or Publications resulting from activities Second National Biodiversity Strategy and Action Plan for FSM Sub-product 1: Assessing and capturing value in ecosystem’s goods and services in FSM Sub-product 2: Exploring and costing options for ecosystem-based adaptation to climate change and strengthening resilience to climate impacts in FSM Sub-product 3: The revised and updated protected area action plans includes strategies for addressing related Aichi Targets, such as avoiding extinctions, increasing representativeness, improving marine connectivity; designing protected areas for climate resilience; and safeguarding critical ecosystems, most importantly key fisheries habitat (e.g., mangrove, coral reef, reef grass beds, important aggregation spawning sites, etc.) Key Activity (III) Developing the NBSAP This step will seek to achieve the following: (i) Developing the strategy and actions to implement the agreed targets though national consultations; (ii) Application of the NBSAP to sub-national entities through sub-national and local consultations; and (iii) Sectoral integration including mainstreaming into development, poverty reduction and climate change plans through sectoral consultations. While the project will focus on updating all aspects of NBSAPs, it will place particular emphasis on those aspects that are both highlighted in the 2011-2020 CBD Strategic Plan, and that are typically absent from its existing NBSAP. These include the following: Assessing and integrating ecosystem services through economic valuation: The study on the Economics of Ecosystems and Biodiversity (TEEB) has drawn attention to the global economic benefits of biodiversity and ecosystem services and to the growing costs of biodiversity loss and degradation. However, FSM has not yet linked the value of biodiversity and ecosystem services to its own national development goals, including poverty alleviation, employment and sustainable livelihoods. The only effort to develop a rough estimate of the lower limit of the total economic value (TEV) of the protected area system was done through a GEF-funded project “Strengthening PA system in FSM”. This economic valuation was done for the PAS in order to support the case for sustained public investment in protected area establishment and management. Based on the previous study, but by looking at other elements of ecosystem valuation not typically captured in the mentioned study, FSM will be able to demonstrate the benefits and values of ecosystems and biodiversity at a national level, and better link ecosystems and priority sectors in national development plans, in order to guide allocation of resources. The aim is to strengthen the point that biodiversity not only underpins human well-being, but that biodiversity and associated ecosystem services can make a significant contribution to poverty reduction and economic development. By engaging national specialists and providing support from global specialists, hard economic data will be collected and processed at the country level to demonstrate the costs and benefits of investing in biodiversity management. Capacity to carry out the assessments and make important links to priority economic sectors will be simultaneously built within the country. The availability of essential data and the analysis will allow FSM to “make the case” for biodiversity and will facilitate the process of mainstreaming biodiversity into sectoral planning through concrete biodiversity valuation examples. Specific steps in this process include: Identify and assess the full range of values of key ecosystem services within the country, based on existing local, national, regional and global studies on the value of ecosystems and biodiversity, including: the national TEEB valuation results, the valuation of protected areas, any other national ecosystem services studies that have been conducted (e.g. water, carbon), and existing global and regional maps and overlays of key ecosystem services Identify the implications of these services for different stakeholder groups within the country, including those who benefit from, and pay for, the maintenance of these ecosystem services, and those that degrade ecosystems through unsustainable use. Estimate and demonstrate the value of key ecosystem services (using methods appropriate to each service), including the value of the ecosystem service in contributing to climate resilience, adaptation and mitigation; reducing poverty, and sustaining livelihoods. Where appropriate, this activity will also identify potential means of capturing the value of targeted ecosystem services including through policies such as payments for ecosystem services and other positive incentives. Mainstreaming biodiversity into development policies, plans and practices and into sectoral plans and strategies: Mainstreaming has been defined as the internalization of biodiversity conservation goals into economic and development sectors, policies and programs, such that they become an integral part of their functioning of these sectors. This aspect is deeply linked to several of the Aichi Targets (3, 4, 14, 16 and 20 to mention a few). As part of this process, the project will focus on the following sectors and development topics: Agriculture Tourism, Trade, Travel and Transport Energy Fisheries Development Planning & Finance Water quality, security, planning Poverty alleviation Gender Climate change mainstreaming Land use planning and management, including spatial planning and infrastructural development Specific steps in this process will include: Forming partnerships between relevant stakeholders interested in biodiversity conservation issues and in development issues Explicitly identifying key stakeholders’ interests, and desired outcomes Embedding and institutionalizing these strategies in the institutions, policies, agreements, programs and mechanisms of each sector Incorporating climate change issues into NBSAPs: The previous NBSAP did not adequately address aspects of climate change. This activity will involve incorporating aspects of climate change into NBSAPs, including, for example: identifying, protecting and appropriately managing areas important for carbon sequestration; updating, where needed, the country’s ecological gap assessment to include predicted future distribution of biodiversity under climate change scenarios; assessing the impact of climate change on the functioning of ecosystem services, such as water, soil formation, refugia to threatened species, recreation, among others; identifying areas important for improving nature’s ability to adapt to climate change, such as altitudinal gradients and conservation corridors identifying areas of particular importance for restoration in order to improve climate resilience, adaptation and mitigation. Component 3. National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms Key outputs expected under this component includes the following: 3.1 National frameworks for NBSAP implementation is in place and includes: (i) institutional leadership for implementation is established and strategic partnerships forged (nationally and internationally); (ii) a costed and prioritized Action Plan is appended to the NBS; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) a strategy for resource mobilization for the implementation of the NBSAP is produced and includes a baseline assessment of existing biodiversity finance. 3.2 Immediate CBD reporting obligations are met by FSM in a timely manner, in particular the Fifth National Report to the CBD by 31 March 2014. Key Outcomes: - By 2014, complete plan for implementing the NBSAP, including capacity, technology and finance needs assessment - Fifth National Report to the CBD Key Products or publications: Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP and fully address the Aichi Targets Fifth National Report for the CBD Key Activities (IV – V) Developing implementation plans This activity will focus on developing an overall plan for implementing the NBSAP. The National Expert Biodiversity Management and Consultation Processes, the Group of experts in economic and development sectors will play a pivotal role in the development of implementation plans for the NBSAP under Component 3. They will be assisted by the international service providers on environmental economics, finance and biodiversity mainstreaming and on capacity needs assessment for biodiversity management. Collectively, these consultants, service providers and the working group will be responsible for preparing the required products according to their TOR (see Annex A, D and E) and for involving a wide range of stakeholders in the process. The development implementation plan will include the following elements: Developing an overall implementation plan: The primary output of this activity is an overall implementation plan that delineates major steps, responsible parties, costs for main activities, expected outcomes and a timeline. Integrating the NBSAP implementation plan with the CBD Programme of Work on Protected Areas implementation plan: FSM is working towards the strengthening of its protected area system through gap analysis, capacity building for a more effective management and by dealing with the challenges of sustainably financing of the system. These are all aspects linked to the implementation of the PoWPA, to which FSM committed to adhering to. We will place particular emphasis on those aspects of Target 11 from the CBD Strategic Plan, including our plans for expanding protected areas, improving management effectiveness, sustainably financing protected areas, improving connectivity, and integrating protected areas into the wider landscape and seascape. Securing sustainable finance for NBSAP implementation: Article 20 of the Convention mentions the need for Parties “to provide, in accordance with its capabilities, financial support and incentives in respect of those national activities which are intended to achieve the objectives of this Convention.” In the past few years, there has been a wide proliferation of innovative biodiversity finance mechanisms, such as payments for ecosystem services, conservation trust funds, biodiversity offsets and bio-carbon funding, among many others. FSM is still in the early stages of exploring these mechanisms. This activity will therefore focus on the following: Identifying the existing financial gap for implementing the NBSAP Identifying potential sources of revenue for filling these gaps Assessing the feasibility for these revenue sources Developing a detailed plan for operationalizing these revenue sources Assessing and strengthening capacity needs: One of the primary areas of enabling activities is the assessment of capacity needs. The decisions at CoP-10 place new and ambitious demands on countries, including requirements to protect and sustainably manage their lands and water, to develop comprehensive plans that integrate climate change into their land use, development and sectoral plans and strategies, and to develop appropriate biodiversity and climate policies, laws and incentives. This activity will ensure that FSM develops a road map for strengthening these specific capacities. Building on existing capacity needs assessment, and using existing guidance, FSM will identify the following gaps, along with capacity-building strategies to fill those gaps: Insufficiency mandate and attributions and functions of authorities responsible for biodiversity management to execute their programme of work in full; Inadequate level of expert knowledge in sphere of biodiversity management; Limited funding for direct implementation of NBSAP Lack of clarity on possible economic benefits derived from the sustainable use of biodiversity General lack of financial, human and information resources needed for an ecosystem approach Reduced capacity for research of the biodiversity components and monitoring Reduced management and financial capacities for development and maintenance of the protected areas system Underdeveloped financial incentive measures Lack of experience for biodiversity rehabilitation Institutionalizing, monitoring and reporting Monitoring and reporting on the status of biodiversity under climate change scenarios: Monitoring and reporting on the status of biodiversity is a key aspect of several Programmes of Work within the CBD. To date, efforts to monitor and report on the status of biodiversity have been sporadic and have typically not taken into full account the status and trends of biodiversity, the status of effective conservation, the contribution of ecosystem services (such as water and carbon), and the likely impacts of climate change on biodiversity and ecosystem services. Through this project, FSM will ensure that future monitoring and reporting on the status of biodiversity and ecosystem services is comprehensive, and fully incorporates climate change issues. Developing a permanent framework for reporting to the CBD: Parties to the CBD committed to submitting a fifth national report by 2014. In this project, FSM will submit a 5th National Report that fully covers the NBSAPs, key changes in the status and trends in biodiversity status, threats and conservation. Collaboration and synergies with related initiatives UNDP has a large and active GEF biodiversity portfolio in FSM and in the surrounding region. The project manager, the host initiations and the UNDP Multi-country Office will ensures that this proposed project and the other projects benefit from technical synergies. These synergies will be created primarily with the following projects: Implementation of Global and Regional Oceanic Fisheries Conventions and Related Instruments in the Pacific Small Island Developing States (GEF #4746): The aim of this recently approved project is to support Pacific SIDS in meeting their obligations to implement and effectively enforce global, regional and sub-regional arrangements for the conservation and management of transboundary oceanic fisheries thereby increasing sustainable benefits derived from these fisheries. This will be particularly important when addressing Aichi Targets 6 and 7. Pacific Islands Oceanic Fisheries Management Project (GEF #2131): The aim of this recently completed project was to support Pacific SIDs’ efforts to reform, realign, restructure and strengthen their national fisheries laws, policies, institutions and programmes. Pacific Adaptation to Climate Change Project (GEF #3101): The aim of this project, which is under implementation, is to implement long-term adaptation measures to increase the resilience of a number of key development sectors in the Pacific islands to the impacts of climate change. This will be particularly important when addressing Target 15. The Micronesia Challenge: Sustainable Finance Systems for Island Protected Area Management - under the GEF Pacific Alliance for Sustainability (GEF # 3626): The aim of this project is to develop a national incentive program for mainstreaming sustainable land management planning and practices in order to combat land degradation, conserve biodiversity of global importance and protect vital carbon assets. This will be particularly important when addressing Targets 2 and 3. Implementing Sustainable Integrated Water Resource and Wastewater Management in the Pacific Island Countries - under the GEF Pacific Alliance for Sustainability (GEF # 2586): The aim of this project is to implement sustainable integrated water resource and wastewater management in the Pacific Island Countries - under the GEF Pacific Alliance for Sustainability. The planned Ridge to Reef project for FSM (GEF5) will support protected areas management, expansion as well as effective biodiversity conservation outside protected areas. The NBSAP project will build strong synergies with this planned project development. For all above-mentioned projects, the key idea is for them to assist the NBSAP process by providing data and sharing studies carried out in connection with the implementation of this project. Project officers and consultants for the above-mentioned projects will be invited to key events under the BD EA project, so that synergies and collaboration can effectively take place. A National Target Setting and NBSAP Update Working Group will be established that ensembles relevant stakeholders and technical experts on BD issues and all the related projects in FSM will be represented on this group. Regular meetings will be held between the different projects to leverage synergies and ensure efficiency in implementing the projects. The studies conducted and information gathered under the other projects will be integrated into project implementation and into the strategic documents developed under this project. In particular, the Report on the State of Biodiversity and the two currently being developed documents, the Protected Area Gap Assessment and the National Financial Plan for the PA System will provide valuable information in the development of the NBSAP. Appropriate lessons from the region in dealing with biodiversity issues and related subjects will also be of importance and integrated into the implementation of the project and highlighted through the facilitation of the meetings. The list herein is covers the initiatives which are immediately relevant for the BD EA project. This does not exclude other possible synergies with a number of different initiatives lead by partners, either governmental, non-governmental, research centres, interest groups, private sector etc. Project consistency with national strategies and plans or reports and assessments relevant for the CBD, as well as other cross-cutting assessments and priority setting exercises At a national level, the key strategies, policies and plans that are relevant for FSM’s Enabling Activity Proposal: FSM’s Strategic Development Plan (2004 – 2023) FSM’s Energy Policy (2010) FSM’s Agriculture Policy (2012-2016) FSM’s Coconut Industry Reform – Biofuel Strategy (2013 – 2018) FSM’s Forestry State-wide Assessment and Resource Strategy Micronesia Challenge Measures Pacific Islands Managed and Protected Areas Community Strategic Plan This project is a follow-on to the existing NBSAP, and it is consistent with it. It will be guided by priorities in the above-mentioned strategies, policies and plans. The project builds on previous biodiversity planning and CBD reporting processes. It also builds on the conclusions from previous capacity assessments, taking these one step further. Project implementation arrangement: The project will be implemented over a period of 30 months. UNDP is the GEF Agency for the project and accountable to the GEF for the use of funds. The project will be administered by UNDP using the national implementation modality (NIM) project, in line with the Standard Basic Assistance Agreement (SBAA, 2006) between the UNDP and the Government of FSM, and the United Nations Development Assistance Framework (UNDAF) Action Plan and FSM Country Matrix for 2013-2017. Under the NIM modality, the FSM National Department of Resources and Development (FSMRD) is the designated government institution responsible for the project towards the timely and verifiable attainment of project objectives and outcomes. The DRD will manage implementation of all project activities. The DRD will nominate a high level official (National Project Director) who will chair the Project Steering Committee (PSC) and will be responsible for providing government oversight and guidance to the project implementation. Project technical team will receive technical backstopping provided from the UNDP/GEF Regional Technical Advisor responsible for the project and the UNDP Environment Focal Point at the Regional Office. In working closely stakeholders the Department of Resources and Development, will be responsible for providing project oversight and assurance services for project implementation including (i) recruitment of project staff and contracting of consultants and service providers; (ii) overseeing financial expenditures against project budgets approved by Project Board; and (iii) ensuring that all activities including procurement and financial services are carried out in strict compliance with Government and/or UNDP/GEF procedures. A FSMRD staff member will be assigned with the responsibility for the day-to-day management and control over project finance. A UNDP staff member will be assigned with the responsibility of project assurance activities and will be the point of contact between the project and UNDP. A National Project Steering Committee (PSC) which will be convened by DRD, and will serve as the project’s coordination and technical advisory body. The PSC will include representation of all the key project stakeholders. It will meet according the necessity, but not less than once in 6 months, to review project progress and advice on technical matters concerning the project. The Project Steering Committee (PSC) will also provide technical advice. The PSC may meet more frequently to discuss issues of technical nature and make recommendations which would be forwarded to the Project Board for final decision making. The following will be the composition of the PSC for the project: The Project Steering Committee may be an existing or previously formed NBSAP Steering Committee. This committee may comprise of smaller thematic working groups. The thematic area groups may meet quarterly or on an ad hoc basic when need arises . The steering committee however meets at least twice per year to review and monitor the performance of the project. The PSC will include NBSAP stakeholder group, thematic area working group and some key people involved in planning and implementing NBSAP activities. This may include other key government Ministries and departments. Until the PSC has met and has deliberated, the following are the proposed TOR for the Committee (the TOR may be amended by the committee): Provide policy and strategic oversight and support to the implementation of the project, in particular to the process of updating the NBSAP, developing the country’s CHM and of completing and submitting national reports to the CBD with full government endorsement. Advise and ensure stakeholder involvement on matters of biodiversity sectoral and development mainstreaming, biodiversity valuation and on the nexus biodiversity-climate change. Review and provide advice on technical components of the Annual Work Plans. Provide inputs to the projects’ APR/PIR. Support project evaluations, if applicable Deliberate on the TOR and membership for other committees and working groups that are expected contribute to the implementation of project activities and the achievement of its outcomes. Discuss and make recommendations on any matter involving an alteration in the mandate, terms of reference, membership, or structure of the PSC. Any other relevant task as applicable. The day-to-day administration of the project will be carried out by a Project Implementation Unit (PIU), comprising of a Project Coordinator and a Project Assistant(s), who will be located within National and/or sub-national executing offices. The project staff will be recruited using standard Government recruitment procedures. The Project Coordinator will manage the administrative implementation of all project activities and will ensure that all reporting is submitted according to pre-agreed deadlines. The Project Coordinator will also be technically supported by contracted national and international consultants and service providers. Comparative advantage of UNDP in FSM with respect to this project: The Government of the Federated States of Micronesia has requested UNDP assistance in designing and implementing this project, due to UNDP’s track record in Asia and the Pacific. UNDP has an established national representation in the FSM UN Joint Presence Office, Kolonia, Pohnpei with well-developed working relationships with the key stakeholders of the project. It counts on a country development manager exclusively dedicated to FSM’s affairs. This officer is supported by other programme, operations and Senior Management staff at UNDP Fiji Multi-country Coordinating Office’s. Moreover, the project will benefit from the presence of a UNDP/GEF Regional Technical Advisor dedicated to Biodiversity in Regional Service Centre Bangkok. UNDP also has extensive experience in integrated policy development, human resources development, institutional strengthening, and non-governmental and community participation. Project’s alignment with UNDP’s programme for FSM: The project is in line with the UNDP Sub Regional Program Document for Pacific Island Countries 2013 – 2017, the endorsed United Nations Development Assistance Framework (UNDAF) 2013 – 2017 and the endorsed UNDAF Action Plan and Country Results Matrix of Pacific the Federated States of Micronesia. In particular, the project contributes to UNDAF Outcome 1 “By 2017 the most vulnerable communities across the PICTs are more resilient and select government agencies, civil society and communities have enhanced capacity to apply integrated approaches to environmental management, climate change adaptation, mitigations and disaster risk reduction”. Stakeholder involvement in the implementation of the project: The stakeholder involvement element is embedded in the description of several activities within this proposal which will have a consultative and participatory character. A full stakeholder involvement plan will be developed in connection with the preparation of the UNDP Project Document that will operationalize this proposal at the level of UNDP, allowing FSM to access the funding. This plan will depart from the following indicative and non-exhaustive list: National level Chuuk State Pohnpei State Kosrae State Yap State Council and committees The President’s Environmental Management and Sustainable Development Council. “NBSAP PANEL” or current equivalent TBD Resource Management Committee Resource Management Committee Environmental Stewardship Committee Terrestrial biodiversity Department of Resources and Development, Division of Resource Management and Development, Agriculture Program Department of Agriculture Department of Land and Natural Resources, Division of Forestry Office of Economic Affairs, Division of Agriculture Kosrae Island Resource Management Authority, Division of Forestry Department of Resources and Economic Affairs Department of Resources and Development, Division of Agriculture and Forestry Marine biodiversity Department of Resources and Development, Division of Resource Management and Development, Marine Resources Program Department of Marine Resources Department of Public Safety, Division of Fish and Wildlife Office of Fisheries and Aquaculture Kosrae Island Resource Management Authority, Division of Marine Conservation Department of Resources and Development, Marine Resources Management Division Environmental quality Department of Health, Education and Social Affairs Environmental Protection Agency Environmental Protection Agency - Kosrae Island Resource Management Authority Environmental Protection Agency Non-governmental organizations Micronesia Conservation Trust- College of Micronesia – FSM The Nature Conservancy Chuuk Conservation Society - Conservation Society of Pohnpei Kosrae Conservation and Safety Organization Yela Environment Landowners Association Yap Community Action Program Yap Institute of Natural Sciences Bi/Multi-lateral Partners (in-country) AusAid, JICA, Japan Embassy’s Grassroots Program, PRC Embassy Assistance, USDA NRCS Office, USDA-Rural Development, Secretariat of the Pacific Community North Rep Office, International Organization for Migration/USAID, UN Joint Presence Office The participation of NGOs and CSOs stakeholders in the implementation of this project will be ensured in every stage of it. NGOs and CSOs in FSM are active in the environment arena. They play an important advocacy role with respect to biodiversity. Many of them count on extensive networks of stakeholders and have produced research data that can help enrich the products that this project will be concerned with. These advantages will be explored in full during project implementation. Members of local communities have large influence over the long-term conservation of biodiversity. Therefore, their full involvement and participation in the revision of the NBSAP are very important to ensure common agreement and support to the NBSAP. This is also paramount to the success of the implementation of the NBSAP and in the overall objective - the conservation of biodiversity. In order to ensure the full involvement of local communities at a national level, community representatives (community leaders and NGOs) will be included in the National Target Setting and NBSAP Update Working Group. This is to ensure that community perspectives and knowledge are integrated into the national targets and the updated NBSAP, in particular on issues of protection of biological diversity in priority areas, forms of sustainable uses of biological diversity/natural resources, threats and factors threatening biodiversity. Further, the participation of local communities at a local level will be secured through UNDP-coordinated projects in the field and cooperation with environmental NGOs. The projects and NGOs are working with the municipalities and local communities and NBSAP topics will be included in their agendas when they organize working groups and public consultations. The participation of indigenous and traditional groups in the project will be ensured through locally based CSOs. The project coordination will ensure that the voice of indigenous and traditional groups will be duly heard and taken into consideration in the preparation of the new NBSAP. Specific COP guidance on the matter, linked to implementation of the Convention’s Article 8(j), will be followed. Gender marking FSM enjoys a relatively high degree of gender parity. The country complies with the UN treaties, such as the Convention on the Elimination of all forms of Discrimination Against Women (CEDAW) and Millennium Development Goals (MDGs), and the national and state constitutions have articles stipulating that all the people have equal rights. Women and men share a high adult literacy rate. In response to the relatively low percentage of women in public service and leadership positions, the government of FSM has started to sensitize gender mainstreaming approaches in trainings to both public and private sectors. Consultation under this project will make a particular emphasis on including women from the beginning of the project, with an emphasis on women’s NGOs (similar to the process of involving women’s NGOs during the 44th session of the UN’s CEDAW in July 2009). The project coordination will ensure that gender consideration become an integral part of the updated NBSAP. COP guidance will be followed. More specifically two are worth mentioning: (i) COP Decision 1X/24 on the approval and endorsement of the CBD Gender plan of Action; and (ii) COP Decision X/19, which amongst other matters invited Parties to consider gender as a core cross-cutting issue in the implementation of biodiversity-related activities. During the project inception the mandatory UNDP gender marker will be applied. This requires that each project in UNDP's ATLAS system be rated for gender relevance. This will for example include a brief analysis of how the project plans to achieve its environmental objective by addressing the differences in the roles and needs of women and men. Furthermore, gender marking implies the production of the following data by the project's year 2 and by its end: Total number of full-time project staff that are women Total number of full-time project staff that are men Total number of Project Board members that are women Total number of project Board members that are men The number jobs created by the project that are held by women The number jobs created by the project that are held by men

D. Describe, if possible, the expected cost-effectiveness of the project:

The proposed GEF project will ensure that a national strategy and action plan guide all stakeholders and partners in the conservation of these precious resources. This is one way of making optimal use of biodiversity planning resources. The project combines GEF funding with government and non-government co-financing in order to achieve the project objectives without duplication to ensure the application of resources in the most critical areas. The government contribution to the project include the staff time of a Project Director and of support staff at the DRD, a number of project activities, organization of and participation in Project Board meetings, plus other work related to reporting, work plan approvals, signing off on CDR reports, RDPs, and reviewing APRs/PIRs. In addition, information and data will be collected and provided by the DRD and other state agencies regularly throughout the project. The cost-effectiveness of the proposed activities will further be ensured by combining government-internal, other national and international expertise in implementing similar projects. GEF funding of consultation costs will be kept to a minimum, as government can finance much of it from existing resources. The same applies to the national contribution to EA working groups. The Government of FSM wishes the work on the new NBSAP to be transformational from a biodiversity planning point of view. This requires expertise that is not found in the country. Hence, the GEF’s financing of specialized consultants and knowledge / capacity building within the framework of this project is essential to its success, to the extent that it finances the costs of going beyond what government would be able to do without foreign assistance. The GEF funding to the project will focus in overcoming this specific barrier. UNDP is well positioned to assist FSM in sourcing the necessary expertise for this EA project in a cost-effective manner. Other options have been considered, e.g. sub-contracting NGO(s) to assist in NBSAP update as an entire ‘package’ of services to be rendered. High costs in fees from service providers would make such option less cost effective, coupled with the risk of biasing the NBSAP, which is supposed to reflect broad societal views on the national strategy for biodiversity. The project adopts the least-cost means of achieving the project’s objectives and follows the activity norms and cost benchmarks defined by GEF guidelines. It will be built upon the strong foundation of the previously developed NBSAP, Capacity Assessments and National Reports.

E. describe the budgeted M&E Plan:

Type of M&E activity Responsible Parties Budget US$ Excluding project team staff time Time frame Inception Meeting Project Coordinator UNDP MCO UNDP GEF $5,000 Within first two months of project start up Inception Report Project Team UNDP MCO None Immediately following IW Measurement of Means of Verification for Project Purpose Indicators, Project Progress and Performance (measured on an annual basis) Oversight by Project Manager Project team To be finalized during the inception phase and determined as part of the Annual Work Plan's preparation. Annually prior to ARR/PIR and to the definition of annual work plans Simplified Biodiversity Enabling Activities Annual Project Review / Project Implementation Report (APR/PIR) Project Team UNDP-MCO UNDP-GEF None Annually Quarterly progress reports, including narrative and FACE Financial Reports Project team/National Project Director None Quarterly, within 15 days of end of each quarter CDRs – production/distribution CDRs – review and endorsement UNDP_MCO Project Manager/National Project Director None Quarterly Lessons Learned Log Project Manager UNDP CO Programme Staff None Quarterly as part of the QPR Terminal Report Project team/National Project Director UNDP-MCO Printing costs only, if any. At least one month before the end of the project Lessons learned Project team UNDP-GEF Regional Coordinating Unit (suggested formats for documenting best practices, etc.) To be determined as part of the Annual Work Plan's preparation. Yearly Audit UNDP-CO Project team $2,000 for 3 years To be included in the CO audit plan. Yearly TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses US$ 7, 000

F. Explain the Deviations from typical Cost Ranges (where applicable):

-- n/a--

part iii:  approval/endorsement by gef operational focal point(s) and GEF AGENCY (ies)

A.   Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s):

| Name | Position | Ministry | Date (Month, day, year) |
| --- | --- | --- | --- |
| Andrew Yatilman | GEF Operational Focal Point | Office of Environment and Emergency Management | April 24, 2013 |

B. Convention Participation*

| Convention | Date of Ratification/ Accession (mm/dd/yy) | National Focal Point |
| --- | --- | --- |
| CBD | 06/20/1994 | H.E.Mr. Marion Henry, Secretary, Department of Resources and Development |

*To be filled for NCSA proposals only

B.  GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the standards of the GEF Project Review Criteria for Biodiversity Enabling Activity approval.

| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | E-mail Address |
| --- | --- | --- | --- | --- | --- |
| Adrian Dinu, Officer-in-Charge and Deputy Executive Coordinator, UNDP - GEF |  | May 6, 2013 | Sameer Karki, Regional Technical Advisor, EBD | +662-3049100 Ext.2729 | sameer.karki@undp.org |

Annex A. consultants to be hired for the Enabling Activity

| Position Titles | $ / Person Week to be covered by GEF | Estimated Person Weeks to be covered by GEF | Tasks to be Performed |
| --- | --- | --- | --- |
| For EA Management |
| Local |  |  |  |
| National/Local Experts: Biodiversity Management and Consultation Processes (managerial tasks corresponding to 9 out of 65 weeks) | 650 | 9 | Objective: To undertake the general administrative requirements of the project, including those related to the management of the project and its funding. Key tasks are: Ensure that project Objective, Outcomes, Outputs and Activities are implemented in a timely and appropriate manner. Develop detailed Annual Work Plans and Budgets (including activity descriptions and a chronogram), and submit these to the Project Board and to the UNDP Country Office for approval). Develop TORs for Consultants for technical services, consultants, experts, and specifications of materials as required by the project, in consultation with the National Project Director/UNDP. Facilitate, guide and monitor the work of consultants, and approve their deliverables in association with the Project Steering Committee or other applicable instance. Organize and assist in project related activities, where required. These may include planning for meetings, local and national workshops, consultations, field visits, and other project related activities. Establish and maintain linkages with national and international organizations and persons which/who can be of assistance to the objectives of the Project. Provide timely reporting of project status as required by the Project Steering Committee, Project Board and UNDP. Maintain records of Project Steering Committee meetings, decisions, actions etc. Coordinate with other initiatives and programs whose outcomes and outputs are relevant to this project’s objectives. Any other duties assigned by the Project Committee that have direct relevance to the project. Selection criteria: should have a Bachelor’s degree in management, administration, environmental management or related field with a minimum of 5 years management experience at a senior level, or an advanced degree with 3 years management experience. Knowledge and understanding of the relevant UN Convention, environmental issues in FSM, good leadership, coordination, communication, and facilitation skills are essential. |
| Project Assistant(s) part-time, one per state, amounting in total to $12,000 to be financed by GEF for the duration of the project. | 150 | 70 | Objective: The Project Assistant shall be responsible for day-to-day administrative and financial support for project activities and procurements of goods and services for the project including effective accounting of the project funds and financial reporting in line with government and UNDP requirements and procedures. The Project Assistant will ensure high quality and accuracy of work. Administrative/Financial Support for project: Preparation of the project budgetary revisions/annual work plans (at least once a year). Preparation of quarterly advance requests in conjunction with quarterly progress reports and reporting in accordance with UNDP procedures. Preparation of payment requests (under 2500 USD). Preparation of travel requests for Project staff and Implementing Partner, in accordance with Government, rules and procedures. Logistical support for travel (tickets and hotel reservations). Assistance to the Project Coordinator in maintaining regular contacts with Implementing Partner, UNDP, project partners and other organizations through direct contacts, collection of information and proposals, recording of incoming and outgoing correspondence, drafting letters and organization of meetings. Assistance to the Project Coordinator in project monitoring activities by revising the existing materials, correspondence, reports, project activities, project inputs, budgets and financial expenditures in accordance with UNDP requirements; preparation and archiving the above correspondence and materials. Organization and logistical support of the workshops, task meetings, delegations, field visits etc. Preparation of hand outs for workshops, briefings and meetings. Equipment inventory, preparation of reports on equipment condition. Maintaining the records pertaining to the issuance of project equipment to PIU experts; monitoring of such equipment. Collection and distribution of incoming mail, dispatching outgoing mail; locating files etc. Recording of the data related to the office car use. Unofficial translation and acting as a translator where necessary. Procurement: Preparation of Procurement plan in accordance with Government and UNDP requirements and Annual Work Plan of the project. Preparation of the documentation on procurement of goods/works/services in Government/ UNDP format and control the observance of contractual terms and conditions. Preparation of the documentation on procurement of goods/works/services in Government/UNDP format. Preparation (in consultation with the project experts) of the rationale on the selected suppliers of goods/services for review by the relevant UNDP units and government and/or UNDP Procurement Committee. Carrying on negotiations with the suppliers of goods/works/services. Ensuring tender selection of the suppliers of goods/works/services in accordance with government and / or UNDP requirements and procedures. Collection and ranking the information on potential goods/services providers. Filing the catalogue on contracts and agreements. Selection criteria: should have a Secondary education, preferably higher education in the field of Accounting, Finance or Administration. The relevant work experience shall exceed 3 years including at least one year’s work experience in administrative/financial/procurement functions in an international company/project. Fluency in English. |
| For Technical Assistance |
| Local |  |  |  |
| National Expert: Biodiversity Management and Consultation Processes (managerial tasks corresponding to 9 out of 65 weeks) | 650 | 60 | Play a leading and resource person role vis-a-vis the National Target Setting and NBSAP Update Working Group and in a number of national sub-national consultation processes for all relevant activities under the Enabling Activity project. Develop planning methodologies and processes for the sub-national technical meetings and consultations. Review base documents for the inputs to the sub-national technical meetings and consultations. Work on the preparation of base documents for technical meetings. Together with support from technical staff review the consolidated results of the five regional consultations Review the NBSAP update. Develop methodologies for the national validation of the national targets and draft NBSAP. Carry out consultations with provincial authorities and organize sub-national technical meetings and consultations and National Technical meetings. Collect and consolidate information arising from the technical meetings. Provide inputs for evaluation of institutional capabilities. Work with local experts and government authorities to collect available information on biodiversity. Provide inputs to the development of the NBSAP implementation plans. Contribution to the following deliverables: Brief Review of the Biodiversity Planning Process in FSM Biodiversity Targets for FSM: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 Second National Biodiversity Strategy and Action Plan for FSM Sub-product 1: Assessing and capturing value in ecosystem’s goods and services in FSM Sub-product 2: Exploring and costing options for Ecosystem-based adaptation to Climate Change in FSM Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP Qualifications and experience: Should have an advanced degree (MSc) in environmental or natural sciences, economics, social sciences, management, preferably with professional exposure to biodiversity conservation issues. Proven track record of drafting relevant materials in the biodiversity/ecosystem based adaptation areas (publications, reports and related documentation). Proven ability to collect, verify and analyze information, and to finish and present work with a high degree of accuracy and technical quality. Ability to communicate effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences. Knowledge and understanding of the relevant UN Convention, Previous experience in the development of NBSAPs. |
| International |  |  |  |
| Lead Int. Consultant | 2,500 | 10 | Objective: To take stock of the success of the existing NBSAP and develop national targets in line with the global Aichi Targets. The key tasks are: Take stock of existing plans, policies and practices in FSM that result in biodiversity conservation or loss. Identify the root causes of biodiversity loss in FSM by first identifying the threat and then the drivers behind the threats. Identify the key barriers and challenges in the policy environment to effective biodiversity conservation/sustainable use. Based on existing studies and analyses, identify key gaps in the existing NBSAP. Identify the means to overcome existing barriers and challenges. Develop a stakeholder consultation and participation plan that will ensure that the NBSAP development process is participatory, increasing the likelihood of successful implementation of the NBSAP. Contribution to the following deliverables: Brief Review of the Biodiversity Planning Process in FSM Second National Biodiversity Strategy and Action Plan for FSM Sub-product 1: Assessing and capturing value in ecosystem’s goods and services in FSM Sub-product 2: Exploring and costing options for Ecosystem-based adaptation to Climate Change in FSM Selection criteria: should have an advanced university degree in environmental management or related field with a minimum of 5 years management experience at a senior level. Knowledge and understanding of the relevant UN Convention, the existing NBSAP and environmental issues in FSM essential. |

Annex B. Chronogramme of activities

| Comp | Modules | Guiding activities under each module | 2013 | 2014 | 2015 |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | COP 12 | Q1 | Q2 | Q3 | Q4 |
| 1 | I. Preparation | 1. Rapid stocktaking and review of relevant plans, policies and reports |  |  | X | X | X | X | X |  |  |  |  |  |
|  |  | 2. Identification of new stakeholders; consultations and awareness |  |  | X | X | X | X | X | X |  |  |  |  |
|  |  | 3. Rapid assessment of the causes and consequences of biodiversity loss highlighting the value of biodiversity and ecosystem services and their contribution to human well-being |  |  |  | X | X | X | X | X |  |  |  |  |
|  | II Setting national targets, principles, & main priorities of the strategy | 4. Setting national targets, principles, & main priorities of the strategy though national consultations |  |  |  |  |  | X | X | X | X |  |  |  |
| 2 | III. Strategy and action plan development | 5. Developing the strategy and actions to implement the agreed targets though national consultations |  |  |  |  |  | X | X | X | X | X |  |  |
|  |  | 6. Application of the NBSAP to sub-national entities through sub-national and local consultations |  |  |  |  |  | X | X | X | X | X |  |  |
|  |  | 7. Sectoral integration including mainstreaming into development, poverty reduction and climate change plans through sectoral consultations |  |  |  |  |  | X | X | X | X | X | X | X |
| 3 | IV. Development of Implementation plans and related activities | 8. Development of a plan for capacity development for NBSAP implementation. |  |  |  |  |  |  |  | X | X | X | X | X |
|  |  | 9. Technology needs assessment |  |  |  |  |  |  |  |  | X | X | X |  |
|  |  | 10. Development of a communication and outreach strategy for the NBSAP. |  |  |  |  |  |  | X | X | X | X | X |  |
|  |  | 11. Development of a plan for resource mobilization for NBSAP implementation |  |  |  |  |  |  |  |  |  | X | X | X |
|  | V. Institutional, monitoring, reporting and exchange | 12. Establishment/ strengthening of national coordination structures |  |  |  | X | X | X | X | X | X |  |  |  |
|  |  | 13. CHM development. |  |  |  |  |  |  |  |  | X | X | X | X |
|  |  | 14. Development of indicators and monitoring approach |  |  |  |  |  |  |  | X | X | X | X | X |
|  |  | 15. Fifth national reports |  |  |  |  |  | X | X | X | X | X |  |  |

Annex C. UNDP Total Budget and Workplan

-PLEASE REFER TO TBWP IN PRODOC-

Annex D. TOR for Working Groups supported by the project

GEF financing: $35,100 lump-sum (refer to Annex C. TBW, budget note “d”)

Government co-financing: approx. $274,724  (includes people’s time, meeting costs, some travel and other sundries)

Non-government co-financing: approx. $30,000 (includes people’s time, equipment and other sundries)

D-1)

Group of Experts in Economic and Development Sectors

To assist National Expert Biodiversity Management and Consultation Processes and NBSAP Lead Consultant in taking stock of the success of the existing NBSAP, developing national targets in line with the global Aichi Targets and updating FSM NBSAP. The experts will cover the main sectors and areas linked to biodiversity conservation

- Agriculture

- Forestry

- Tourism

- Trade

- Travel and Transport

- Fishery

- Land-use management

- including spatial and infrastructural development planning

- Food security

- Gender

- Climate change mainstreaming

- Population & urban planning)

Contribution to the following Outputs:

2.1 A National Biodiversity Strategy and Action Plan (NBSAP) for FSM anchored into national development frameworks, is updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as:

(i) mainstreaming;

(ii) the valuing of ecosystem goods and services; and

(iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience.

2.2	The updated and fully endorsed NBSAPs for FSM are submitted to the CBD preferably within the deadline set by the COP, incorporating recommendations of the following strategic studies:

- Integrating the challenges to Protected Areas in the 21st Century into the NBSAP and the national implementation of the CBD’s Programme of Work on Protected Areas (PoWPA)

- The Economics of Ecosystems and Biodiversity (TEEB) developed for assessing  and capturing value in ecosystems’ goods and services in FSM

The group will be formed by 4-5 specialists in key domains. The key tasks of the group related to all described areas and sectors are:

- Stocking of existing plans, policies and practices in FSM that result in biodiversity conservation or loss.

- Identify the root causes of biodiversity loss in FSM by first identifying the threat and then the drivers behind the threats.

- Identify the key barriers and challenges in the policy environment to effective biodiversity conservation/sustainable use.

- Based on existing studies and analyses, identify key gaps in the existing NBSAP in each sector or area.

- Identify the means to overcome existing barriers and challenges.

- Submit all required information by team leaders for finalizing the NBSAP activities.

The group of experts will work extensively with all consultants responsible for specific products.

Contribution to the following deliverables:

- Brief Review of the Biodiversity Planning Process in FSM

- Second National Biodiversity Strategy and Action Plan for FSM

- Sub-product 1: Assessing and capturing value in ecosystem’s goods and services in FSM

- Sub-product 2: Exploring and costing options for Ecosystem-based adaptation to Climate Change in FSM

D-2)

National Target Setting and NBSAP Update Working Group

The National Target Setting and NBSAP Update Working Group will be an essential vehicle for ensuring that the Enabling Activity project is successful in building national capacity for biodiversity planning. group will congregate representatives from key stakeholder institutions and national specialists. It will and provide support to the project activities from beginning to end. More specifically, the Working Group (or several sub-working groups under it) will ensure the process of wide stakeholder engagement and provide technical and policy inputs to the NBSAP review process, including by providing data and information to and by commenting the key products emanating from the Enabling Activity.

Contribution to the following Outputs:

1.1 Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in participative manner.

1.2 In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to FSM reality.

1.3 The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means.

1.4 In an iterative manner, FSM taps into useful information on, and participates into, global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership, Global Biodiversity Information Facility and the World Conservation Monitoring Centre, the Global Environment Outlook portal, among other relevant ones).

2.1 A National  Biodiversity Strategy and Action Plan (NBSAP) for FSM anchored into national development frameworks, is updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as:

(i) mainstreaming;

(ii) the valuing of ecosystem goods and services; and

(iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience.

2.2	The updated and fully endorsed NBSAPs for FSM are submitted to the CBD preferably within the deadline set by the COP, incorporating recommendations of the following strategic studies:

- Integrating the challenges to Protected Areas in the 21st Century into the NBSAP and the national implementation of the CBD’s Programme of Work on Protected Areas (PoWPA)

- The Economics of Ecosystems and Biodiversity (TEEB) developed for assessing  and capturing value in ecosystems’ goods and services in FSM

3.1 National frameworks for NBSAP implementation is in place and includes: (i) institutional leadership for implementation is established and strategic partnerships forged (nationally and internationally); (ii) a costed and prioritized Action Plan is appended to the NBS; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) a strategy for resource mobilization for the implementation of the NBSAP is produced and includes a baseline assessment of existing biodiversity finance.

Iterative and collective contributions to the following deliverables:

- Brief Review of the Biodiversity Planning Process in FSM

- Biodiversity Targets for FSM: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020

- Second National Biodiversity Strategy and Action Plan for FSM

- Sub-product 1: Assessing and capturing value in ecosystem’s goods and services in FSM

- Sub-product 2: Exploring and costing options for Ecosystem-based adaptation to Climate Change in FSM

- Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP

Annex E. Technical Assistance Service Provision: TOR for launching a Request for Quotes

| Block of Services (A) Environmental economics, finance and biodiversity mainstreaming | Budget note “e” | Available budget $25K |
| --- | --- | --- |
| Block of Services (B) Capacity needs assessment for biodiversity management | Budget note “h” | Available budget $25K |

The complete Requests for proposal prepared by UNDP normally have the following structure:

i.	Instructions to Offerors

ii.	General Conditions of Contract

iii.	Terms of Reference (TOR)

iv.	Proposal Submission Form

v.	Price Schedule

In this annex, only the TOR are described. The remainder of the chapters of the Requests for proposal will be completed before launching the tenders and after due validation by UNDP.

The complete TOR for Requests for proposal will include the following headings (Sections):

(1) Summary and Background

(2) Objective of the Consultancy

(3) Scope of Work

(4) Expected Results

(5) Duty station

(6) Requirements to the documents

(7) Responsibility

(8) Qualification requirements

(9) Available information

(10) Selection Process

TOR for the RFP

Technical Support Services for National Biodiversity Target-setting and the development of the NBSAP and related products in FSM

(1) Summary and Background

The FSM is in the process of implementing a GEF biodiversity planning project whose objective is to integrate the country’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020.

The following key outcomes are sought as part of the project:

1) A participative stocktaking exercise on biodiversity planning takes place and national biodiversity targets are developed in response to the global Aichi Targets

2) FSM’s National Biodiversity Strategy and Action Plan (NBSAP) is revised/updated and it fully integrates new aspects of the CBD strategic plan, such as mainstreaming and anchoring the implementation of the plan into national development frameworks, valuing ecosystem services and promoting ecosystem-based adaptation and resilience

3) National frameworks for resource mobilization, Convention reporting and exchange mechanisms, including the Clearing House Mechanism (CHM) of the CBD, are established and strengthened

The ultimate goal of the project is to build national capacity within the topic of biodiversity planning. This implies procuring knowledge and capacity building services that are usually not available in the country, due to the specificity of the topics at hand and the technical requirements.

Hence, an international Request for RFP s being launched in view of having services rendered by a group of specialised consultants within the following areas of expertise:

- Environmental economics, finance and biodiversity mainstreaming

- Capacity needs assessment for biodiversity management

Services may combine national and international expertise and quotes for qualified companies should be presented as a package of services, including honoraries, travel expenses and admin costs.

[ - More on ‘Background’ can be added when composing the final documentation for the Request for RFP ]

(2) Objective

Provide knowledge and capacity building services to the government of FSM, as well as to other key stakeholder involved in the implementation of the Biodiversity Enabling Activities Project, with the following specific sub-objectives:

- The Environmental Economist & Finance Specialist will be carrying out the tasks under two sub-activities: i) Assessing and integrating ecosystem services through economic valuation (under Component 2), and ii) the mobilisation of financing for the implementation of the Action Plan of the NBSAP and in raising awareness among key stakeholders on the NBSAP (under Component 3).

- To objectively reveal FSM’s capacity to effectively implement the obligations deriving from the ratification and accession of the UN Convention on Biological Diversity.

(4) Scope of Work

Block of Services (A) Environmental economics, finance and biodiversity mainstreaming

- Identify and assess the full range of values of key ecosystem services within FSM, based on existing local, national, regional and global studies on the value of ecosystems and biodiversity, including: the valuation of protected areas, any other national ecosystem services studies that have been conducted (e.g. water, carbon), and existing global and regional maps and overlays of key ecosystem services.

- Identify the implications of these services for different stakeholder groups within the country, including those who benefit from, and pay for, the maintenance of these ecosystem services, and those that degrade ecosystems through unsustainable use.

- Estimate and demonstrate the value of key ecosystem services (using methods appropriate to each service), including the value of the ecosystem service in contributing to climate resilience, adaptation and mitigation; reducing poverty, and sustaining livelihoods.

- Where appropriate, assist in identifying potential means of capturing the value of targeted ecosystem services including through policies such as payments for ecosystem services and other positive incentives.

- Identify priority Biodiversity investment needs and opportunities based on the NBSAP.

- Analyse internal sources of finance for action in the NBSAP including i) the national budget cycle and the allocation to public administrations (ministries), ii) the budget of local governments, iii) national funds to support local development, and iv) fiscal and economic instruments.

- Analyse external sources of finance for actions in the NBSAP including i) bilateral sources, ii) multilateral sources, iii) regional development banks, iv) international foundations and non-governmental organisations (NGOs)

- Analyse innovative sources of finance for actions in the NBSAP, especially fiscal measures related to: i) tourism and infrastructure development (to encourage the mainstreaming of biodiversity into their operations, ii) bank loans for investment projects. NBSAP Integrated Financing Action Plan summarising concrete activities required to mobilise BD finance for the 10-year period of the implementation of the NBSAP.

Block of Services (B) Capacity needs assessment for biodiversity management

- Assess extent of role clarity and the level of implementation and enforcement of the CBD and its CoP guidance across all primary and secondary stakeholders in central government.

- Determine the level of willingness to take responsibility and provide leadership in ensuring relevant CBD obligations and activities are fulfilled.

- Assess whether the identified primary and secondary duty bearers have the necessary human resources to meet the specific obligations.

- Assess the pattern and efficacy of participation at regional technical committees and COP meetings.

- Based on international best practice, recommend the most suitable institutional and/or accountability structure for the effective implementation and coordination of the CBD.

- Identify and prioritise the capacity development needs required to effectively implement CBD obligations at all levels within central government.

- Generate recommendations for capacity enhancement at all levels.

- Generate recommendations to enable rationalisation of capacity and efficient resource allocation during implementation

- Develop a comprehensive Capacity Development Programme and Training Action Plan for effective implementation and coordination of CBD at the municipal and central government levels.

The above services, including blocks A and B, comprise a minimum of 20 persons-week in total. This is but indicative. Each bidder will need to indicate the number of days of service the company can offer based on the scope of the consultancy.

Service providers will work together with the team of national and international consultants for the project in FSM, in particular the National Expert Biodiversity Management and Consultation Processes, the Project Manager and the Project Assistant, who will play a leading role vis-a-vis project activities, in collaboration with in collaboration with the UNDP Programme Officer, the Project Director and the International NBSAP Lead Consultant.

(4) Expected Results

[The National Expert Biodiversity Management and Consultation Processes in collaboration with the UNDP Programme Officer, the Project Director, the Project Manager and the Project Assistant will elaborate more and finalise the expected results when composing the Request for Quotes’ documentation]

Contribution to the following deliverables:

- Brief Review of the Biodiversity Planning Process in FSM

- Second National Biodiversity Strategy and Action Plan for FSM

- Sub-product 1: Assessing and capturing value in ecosystem’s goods and services in FSM

- Sub-product 2: Exploring and costing options for Ecosystem-based adaptation to Climate Change in FSM.

- Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP

– Number of minimum mission days and schedule of payment to be completed when composing the final documentation for the Request for Quotes –

(5) Duty station:

- FSM, for the mission part*

- Home based, for the completion of certain reports

*Note: all travel expenses should be included into the breakdown of contract total amount by submission of financial proposal.

(6) Requirements to the documents

- Draft and final documents should be submitted in English in MS Word (2007 or later). Used font: Arial, size: 12;

- Presentational documents should be prepared in Power Point.

– May be complemented when composing the final documentation for the Request for RFP–

(7) Responsibility

- Agrees the above results with UNDP (in consultation with the Project Manager), under the guidance from the International NBSAP Lead Consultant;

- Ensures timely and quality execution of the Terms of Reference;

- Ensures unconditional implementation of requirements of the contract

(8) Qualification requirements

- As minimum 5 years of work experience (preferably more, given the complexity of the services in question) in the relevant field for the two blocks of services (or combines the required expertise in the presentation of individual consultants’ profiles): (a) environmental or natural science; (b) economics, with focus on environmental finance; (c) national biodiversity valuation studies, payment for ecosystem services, sectoral mainstreaming of biodiversity; (d) policy development, national accounting practices and methods; (e) human resource management or public administration.

- Valid certificates and licenses for consulting services in the field of biodiversity and or development.

- Available qualified personnel with university degrees in the required fields.

- Outline of proposed approaches for the two blocks of services

- List of rendered consulting services for the past 3 years.

- Ability to submit the 2 reference letters confirming the successfully rendered services for the last 2 years.

- Ability to write hold the trainings in English is a requirement.

(9) Available information:

Complete Project Document for the UNDP/GEF PIMS 4870 “National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in FSM”

– Relevant hyperlink to the project document to be added when composing the final documentation for the Request for RFP  –

(10)  Selection Process

The selection of the company will follow an open competitive process in line with UNDP procurement standards. The successful company would be required to enter into a standard UNDP Institutional Contract. The contract will be awarded according to the cumulative analysis scheme: proposal with the overall highest score after adding the score of the technical proposal and the financial proposal, the winning service provider will be chosen.

## Annex 2 GEF CEO Approval Letter

## Annex 3 Minutes of the Local Project Appraisal Committee (LPAC) Meeting

# Footnotes

Biodiversity Enabling Activities use an abridged PIR/APR format for reporting.

www.bipindicators.net

www.gbif.org

www.unep-wcmc.org

geodata.rrcap.unep.org

www.bipindicators.net

www.gbif.org

www.unep-wcmc.org

geodata.rrcap.unep.org

This is the cost associated with the unit executing the project on the ground and could be financed out of trust fund or co-financing sources.

Contact Gordon Segal, Director, Office of Information Technology <gsegal@comfsm.fm> for more details. Although the CHM is currently up-to-date, it will need to be updated as part of the NBSAP revision process.

The actual submission of the NBSAP to the CBD Secretariat is the responsibility of the government of the FSM, not UNDP.

Petersen, C and B. Huntley. 2005. Mainstreaming Biodiversity in Productive Landscapes. Working Paper 20. Washington DC: GEF.

See e.g. www.cbd.int/traditional.

http://www.jica.go.jp/english/our_work/thematic_issues/gender/background/pdf/e09mic.pdf Country Gender Profile: Micronesia. 2009. JICA.

“Gender Mainstreaming: The Role of Civil Society. Results of Monitoring the National Gender Mechanism” report by the Public Union for Gender Equality and Women’s Initiatives, Baku, August 2010, paper copy

See e.g. www.cbd.int/doc/nbsap/nbsapcbw-pac-02/nbsap-nadi-scbd-gender.pdf and www.cbd.int/doc/publications/cbd-ts-49-en.pdf.

www.bipindicators.net

www.gbif.org

www.unep-wcmc.org

geodata.rrcap.unep.org

# Text boxes

Project Manager

Project Board

Senior Beneficiary:

Department of Finance and Administration/ SBOC

Executive: Department of Resources and Development

Senior Supplier:

UNDP

National Steering Committee

Project Implementation Unit

Project Organization Structure

NBSAP Thematic Group

NBSAP Thematic Group