United Nations Development Programme

Country: Georgia

PROJECT DOCUMENT

Project Title: Ensuring Sufficiency and Predictability of Revenues for the Georgia’s Protected Areas System

UNDAF Outcome(s): Progress towards environment sustainability demonstrated

Expected CP Outcome(s): National and local capacities enhanced and best practices adopted for sustainable environmental and natural resources management

Expected CP Output (s):   Protected areas system expanded and strengthened

Executing Entity/Implementing Partner:  Agency for Protected Areas, Ministry of Environmental     Protection and Natural Resources

Implementing Entity/Responsible Party: Caucasus Protected Areas Trust Fund

TABLE OF CONTENTS

List of Acronyms	3

I.	Situation Analysis	4

1.1 Background	4

1.2 Pressures on Protected Areas	4

1.3 Baseline	5

1.4 Desired Scenario and Key Barriers to Achieve it	7

II.	Strategy	11

2.1 Objectives, Outcomes and Outputs	11

2.2 Sustainability, Replicability, Cost-effectiveness	16

2.3 Alignment with National Pririties and Expected Global Envrionmental Benefits	18

2.4 Indicate Risks and Assumptions	19

III.	Project Results Framework:	22

Total Budget and Workplan	24

IV.	Management Arrangements	27

4.1 Overall Responsibilities	27

4.2 Communications	28

4.3 Financial and Other Procedures	28

4.4 Project Organization	29

V.	Monitoring Framework and Evaluation	30

5.1 Monitoring and Evaluation Framework	30

5.2 Learning and knowledge sharing	31

5.3 Audit clause	31

VI.	Legal Context	32

VII.	Annexes	33

Annex1. Capacity Assessment for CPAF	33

Annex 2. Sinking Fund and Project Management Agreement	39

Annex 3:  UNDP Strategic Plan:  Key Focal Areas + Key result areas + Provisional Corporate Outcomes	42

# List of acronyms

APA	Agency for Protected Areas

AWP	Annual Work Plan

BRC	Bratislava Regional Center for Europe and CIS

CBD	Convention on Biological Diversity

CEPF	Critical Ecosystem Partnership Fund

CPAF	Caucasus Protected Areas Fund

CPAP	Country Programme Action Plan

CPD	Country Programme Document

Est.	Estimated

EUR	Euro (European currency)

GDP	Gross Domestic Product

GEF	Global Environment Facility

GIS	Geographic Information System

GoG	Government of Armenia

HDI	Human Development Index

IBA	Important Bird Area

IMF	International Monetary Fund

IUCN	International Union for the Conservation of Nature

KfW	Kreditanstalt fur Wiederaufbau

METT	Management Effectiveness Tracking Tool

MDG	Millennium Development Goals

MOE	Ministry of Environmental Protection and Natural Resources

NGO	Non-Governmental Organization

PA	Protected Area

PAS	Protected Areas System

PEB 	Project Executive Board

PIR	Project Implementation Review

PM	Project Manager

RCU	Regional Coordination Unit

SP	Strategic Programme

SPNA	Strictly Protected Natural Area

TJS	Transboundary Joint Secretariat

UNCCD	United Nations Convention to Combat Desertification

UNDAF	United Nations Development Assistance Framework

UNDP	United Nations Development Programme

UNDP-CO	United Nations Development Programme Country Office

UNEP	United Nations Environment Programme

UNFCC	United Nations Framework Convention on Climate Change

USAID	United States Agency for International Development

US$	Unites States Dollar

WB	World Bank

WWF	World Wide Fund for Nature

# Situation analysis

## 1.1 Background

Georgia covers an area of 69,500 sq. km. and is located in the Caucasus region which forms the isthmus between the Black and Caspian Seas. Georgia is in the west of the region on the southern slopes of the Greater Caucasus Mountain Range, and borders the Russian Federation in the north, Armenia and Turkey to the south, Azerbaijan to the East and the Black Sea to the west. Together with Armenia and Azerbaijan, Georgia is at the core of the Caucasus Ecoregion, which has very high plant and animal diversity and endemism. It is classified by WWF as one of the “Global 200 Ecoregions,” by Conservation International as one of only 25 biodiversity “hotspots” worldwide and as one of the World’s 221 Endemic Bird Areas. Located at a biological crossroads, species from Central and Northern Europe, Central Asia and the Middle East and North Africa mingle with endemics. Over 6,500 species of vascular plants are found in the Caucasus. At least a quarter of the plants are found nowhere else–the highest level of endemism in the Temperate Zone of the Northern Hemisphere. One-third of the endemic plants in the Caucasus are thought to have originated in the Greater Caucasus Range. Seventeen endemic plant genera thrive in the region, nine of which are associated with high mountain communities. Plant associations from the Tertiary period have been preserved in the Colchic and Hyrcanic refugia–centers of plant endemism. There are several reasons for the high level of diversity: the country is at the junction of two major bio-geographic zones– the Eastern Anatolian montane steppe and the Caucasus mixed forests, the latter itself located at the convergence of three bio-geographic provinces (Central/Northern Europe, Central Asia, and the Middle East/North Africa). Georgia holds the major part of the region’s biodiversity with almost all Caucasus ecosystems and habitats represented and a high number of globally threatened species. On its own it has a richness of species and level of endemism that make it an important biodiversity reservoir.

Georgia became independent from the Soviet Union in 1991, and has since undergone a dramatic economic transition. Declines in socio-economic conditions have in turn resulted in substantial over-use of biological resources, and declines in the effectiveness of environmental protection, ultimately threatening refuges of biodiversity through: (i) habitat degradation and fragmentation caused by illegal logging timber trade, overgrazing and water pollution; (ii) poaching and illegal wildlife trade; (iii) overfishing; and (iv) infrastructure development. The cumulative impact of these threats has been a reduction in the ecological functioning of many natural areas including their capacity to provide key ecosystem services, the increased fragmentation of the remaining natural areas, the continuing loss of threatened habitats and associated species and the loss of the economic benefits accruing from biodiversity.

## 1.2 Pressures on Protected Areas

Four primary threats to biodiversity have been identified within and around protected areas in Georgia: (1) Habitat loss: throughout Georgia, habitat loss caused by grazing, unsustainable logging and pollution threatens biodiversity; (2) Overexploitation of natural resources: there is de facto open access to most natural resources except within the boundaries of a few better-managed protected areas, as well as poaching and illegal wildlife trade; (3) Overfishing: Georgia’s marine ecosystems are being threatened by unregulated fishing. (4) Infrastructure development: plans to develop infrastructure rarely take environmental measures into account. The impact of these threats includes the accelerated loss of vulnerable habitats and associated species, the reduction of ecological functionality and the growing insecurity of ecosystem services. Opportunities for communities to realize the potential social and economic benefits accruing from biodiversity are lost.

## 1.3 Baseline

The Government of Georgia adopted the law on Protected Areas System in 1996, putting the PA network under a firm legal footing. Georgia now has a system of protected areas covering about 482,842 ha of land or 7% of the country’s territory. The system is composed of 39 protected areas (PAs) of the different management categories presented in the table below. The PA network has grown to include 21 nature reserves, four national parks, three national monuments, eleven managed reserves and one protected landscape. Until 2008, all protected areas were managed by the Department of Protected Areas (DPA). The DPA was replaced in January 2008 by the newly created parastatal, the Agency for Protected Areas (APA), under the oversight of the Ministry of Environment. The APA has begun the process of developing its own internal management policies and systems. The 39 PAs are divided into 19 administrative divisions for management purposes (grouping, for example, adjacent Nature reserves and National Parks, as well as certain larger PAs with smaller non-contiguous but nearby Pas. Protected areas represent the cornerstone of Georgia’s biodiversity conservation strategy, as reflected in the government’s commitment to achieve a 20.2% coverage (1,417, 522 ha) by 2010 by establishing new protected areas and enlarging some of the existing ones. For this purpose, Georgia has developed a very comprehensive programme on protected areas and strong partnerships with numerous international organizations, such as the World Bank, the EU, BMZ/KfW/GTZ, Governments of US and Norway, IUCN, WWF, Conservation International, etc.

Table 1: Georgian protected areas (NBSAP 2005)

| # | Type | Area (ha) | Established |
| --- | --- | --- | --- |
|  | Nature reserves – IUCN Category I – managed for strict protection |
| 1. | Lagodekhi | 22,358 | 1912 |
| 2. | Tusheti | 10,694 | 1980 |
| 3 | Babaneuri | 770 | 1960 |
| 4. | Batsara | 3,042 | 1935 |
| 5. | Vashlovani | 8,480 | 1935 |
| 6. | Algeti | 6,400 | 1965 |
| 7. | Liakhvi | 6,388 | 1977 |
| 8. | Saguramo | 5,241 | 1946 |
| 9. | Mariamjvari | 1,040 | 1935 |
| 10. | Kazbegi | 8,707 | 1976 |
| 11. | Ajameti | 4,848 | 1935 |
| 12. | Sataplia | 300 | 1935 |
| 13. | Borjomi | 17,948 | 1935 |
| 14. | Bichbinta | 1,461 | 1935 |
| 15. | Miusera | 2,300 | 1934 |
| 16. | Ritsa | 17,200 | 1930 |
| 17. | Pskhu | 27,333 | 1978 |
| 18. | Gumista | 13,400 | 1976 |
| 19. | Skurcha | 85 | 1971 |
| 20. | Kintrishi | 13,893 | 1959 |
| 21. | Kobuleti | 331.25 | 1999 |
| National parks – IUCN category II – managed for conservation and recreation |
| 1. | Borjomi-Kharagauli NP | 57,964.44 | 1995 |
| 2. | Kolkheti NP | 44,313 | 1999 |
| 3. | Tusheti NP | 83,453 | 2003 |
| 4. | Vashlovani MP | 25,114 | 2003 |
| Natural monuments – IUCN category III – managed for conservation of natural features |
| 1. | Alazani natural monument | 138 | 2003 |
| 2. | Takhi-Tefa | 0,5 | 2003 |
| 3. | Artsivis Kheoba |  | 2003 |
| Managed reserves - IUCN category IV – preservation through active management |
| 1. | Gardabani | 3,315 | 1957 |
| 2. | Korugi | 2,068 | 1958 |
| 3. | Iori | 1,336 | 1965 |
| 4. | Chachuna | 5,200 | 1965 |
| 5. | Katsoburi | 295 | 1964 |
| 6. | Ktsia-Tabatskuri | - | 1995 |
| 7. | Nedzvi | - | 1995 |
| 8. | Tetrobi | - | 1995 |
| 9. | Kobuleti | 438.75 | 1999 |
| 10. | Ilto | 5,273 | 2003 |
| 11. | Lagodekhi | 1,998 | 2003 |
| Protected landscapes – IUCN category V –managed for ecosystem restoration and conservation |
| 1. | The Tusheti Protected landscape | 27,903 | 2003 |

With regard to the enabling legal and institutional environment for PA financing, in the recent years the Government has created a number of legal and institutional prerequisites for increasing the financial sustainability of the PA system, which serve as a positive baseline for the project. Thus, there is a National Biodiversity Conservation Strategy and Action Plan adopted in 2005 containing 10-year strategic goals and objectives for Georgia in the area of biodiversity protection and costed actions to achieve those goals and objectives. The Protected Area Law dates from 1997, but various recent changes have significantly modernized the way in which Protected Areas are administered. Under the law, the Ministry of Environmental Protection and Natural Resources (MOEPNR) exercises overall control of protected areas, realizes state policy in the field and coordinates the activities of various bodies involved in the process. A 2008 MOENPR order created the Agency of Protected Areas (APA), a state body with separate legal character under the MOENPR. Day to day management of protected areas is conducted by the APA. Under separate MOENPR orders from 2008, PAs conduct their activities on the basis of by-laws, and standard form by-laws were adopted. PAs do not have separate legal existence, they represent structural divisions of the APA; however, they may have separate property as well as their own bank accounts. PAs conduct management activities locally on specific protected areas and implement instructions of the APA. Directors of PAs, who are appointed and dismissed by the head of the APA, submit each year an action plan for the coming year and report on the implementation of a current action plan. The allocation of responsibilities as between the MOENPR and the PAs leaves the PAs some measure of autonomy; the budget for the funding of the whole PA system is approved on an annual basis by the Government; and there are standards for collection of fees by PAs. Nevertheless, legal gaps remain, and the following summarizes some of the more important remaining gaps: (i) the economic and financial elements of the law do not fully reflect existing budgetary regulations; (ii) standardized national PA business planning guidelines do not exist with some exceptions (iii) levels of public financing and donor assistance are not sufficient for management effectiveness of PAs and innovative and sustainable models for revenue generation, including PPPs were not supported; (iv) there are inconsistencies and conflicts among PA and other laws; and (v) failure to define clear codes of management with adequate specificity and the existence of contradictions even in some of the general guidelines given – e.g. some strict nature reserves allowed tourism and some not.

# These issues in Georgia’s PA legislation are, however, being addressed by the UNDP/GEF 3957 project on PA Financing entitled “Catalyzing Financial Sustainability of Georgia’s Protected Area System” ( hereafter the “Sister Project”). The project will include detailed legal review and revision of the legal-regulatory framework for PA management in order to allow for: a) revenue generation opportunities allowed for each type of PA; b) retention of raised income by PAs and permission for its reinvestment into site management; c) resource user fees at PAs and procedures for their collection and retention by sites; d) delegation (in full or in part) of PA management to private companies, NGOs, local community groups thus “legally” recognizing public-private-partnership” models for PAs; e) tourism and natural resource use based concessions at PAs; f) linking the PA law with the Law on State Budget, thus ensuring better accuracy and predictability of central budget allocations to PAs; and (g) setting of standard formats for PA business plans for IUCN Category I and II, with guidance for site managers. The sister project will also create a PA Network Sustainable Financing Plan (NSFP), the implementation of which will also be facilitated by these changes in legislation. Finally, the sister project also contains a demonstration component with a pilot project in Tusheti Protected Areas designed to increase revenue from tourism and sustainable management of PA resources.

## 1.4 Desired Scenario and Key Barriers

# Analysis of the current status-quo and barriers with regard to the financial sustainability of the PA system in Georgia covered three “classic” pillars of financial sustainability: (1) enabling legislative and institutional environment, (2) sufficiency and predictability of revenue sources (i.e. the supply of funding), and (3) capacities and cost-effectiveness of site management (i.e. the efficiency of use of available funding by PAs).

On-going UNDP/GEF project on PAS financial sustainability considered as a sister project to the present project will fully address the first pillar of financial sustainability through improving legal-regulatory and policy and planning frameworks for PAS sustainable financial management and partially, the third pillar through developing institutional and individual level capacities for PAS sustainable financial management as well as through testing various innovative revenue generation models and tools at site level. However, pillars 2 and 3, discussed at length below, continue to represent barriers to achieving a financial sustainability of the PA system in the country. The Financial Scorecard created for the sister project (see Annex I: CEO Endorsement Proposal) estimated the annual needs of Georgia’s PA system at $8.6 million to achieve optimal financing and at $5.7 million to achieve a basic financing level. With current revenues available to it of $2.9 million, the current financing ratio is 51% in relation to basic needs and 34% in relation to optimal needs. The sister project aims to provide the tools to enable the system access an additional $1.1 million and to raise those ratios to 70% and 47%, respectively. For purposes of this project, a “Financial Scorecard 2013 Projection” has been added to supplement the Financial Scorecard (Annex I: CEO Endorsement Proposal). The projection includes the effect of the sister project, an assumed increase in government funding of PAs of 35% compared with 2008 levels and the planned contribution from this project. In the desired scenario contemplated by this project, these new revenue sources combine so that the basic operating and investment needs of the PA system in Georgia will be more than 100% covered, and coverage of the optimal needs will be increased to 70% in 5-7 years, ensuring long-term integrity of the habitats and species protected by the priority PAs.

Barrier 1. The sufficiency and predictability of revenue sources remains the key barrier to financial sustainability. There have been a number of studies in the recent years that have engaged the Government, as well as NGOs (e.g. WWF) and donors (e.g. the KfW), and which have taken stock of issues and opportunities for diversifying revenue sources for PAs in Georgia. The conclusion of the majority of the studies was that under the business-as-usual scenario in the foreseeable future there will remain two main revenue sources – annual Government allocations and project-based donor funding; alternative sources of revenue (such as payment for ecosystem services, etc.), while perhaps accessable over the long-term, are uncertain in amount and will take significant time to develop. As discussed above, government allocations are inadequate and project-based donor funding has been unstable and difficult to predict, adding on average only $100,000-$200,000 of available resources annually. Accordingly, an alternative source of revenues was required for the foreseeable future to close the funding gap.

The Caucasus Protected Areas Fund (CPAF) was “launched” at a conference in Berlin attended by the Ministers of Environment from the three South Caucasus countries, and was formally established in 2007 following receipt of sponsoring commitments from its initial donors. The CPAF’s “Framework Agreement” with Georgia establishing the government’s commitment was signed in December 2008, and financing under its pilot project in Georgia is expected to begin in April 2010. The CPAF’s current permanent endowment capital amounts to €8.5 million (approximately $12 million) on which only the investment income can be spent. Recognizing that not all potential donors would want (or be able) to contribute to its endowment, the CPAF’s structure was designed to accommodate sinking and other types of project funds, but these have not yet been created or funded.

The CPAF’s mission is to supplement the funding for operating costs of priority PAs in Georgia, Armenia and Azerbaijan. As long as the relevant government maintains or increases its funding of operational costs on an inflation adjusted basis, the CPAF can up to match the government’s funding of such costs, thereby effectively doubling the current budget, as long as doing so is justified by a budget presented by the government as part of its project proposal. For new protected areas, the CPAF can fund up to 50% of total operating costs. These funds will be granted on a PA by PA basis to support at least a basic level of an individual PA’s costs – i.e. the basic running costs and the critical capital and scientific research costs, ranger programmes and monitoring. The funds enable PAs to pay adequate salaries, to maintain basic physical infrastructure, or to carry out essential management and operational functions.

As mentioned above, the sister project aims to increase the financing capacity available to the Georgian PA system to 70% of basic needs and 47% of optimal needs as measured by the Financial Scorecard. The government has significantly increased its funding of PAs in recent years, but government budgets can only be expected to cover a portion of the remaining gap. For purposes of the Financial Scorecard 2013 Projection in Annex G, it has been assumeed that budget funding will increase by 35% and add just over $ 1million in new funding to the system. After such increase, the remaining financing GAP in absolute terms will be $650,000 to cover basic needs and almost $3.5 million to cover optimal needs. The problem, accordingly, is that the CPAF’s current endowment is insufficient for it to cover even Georgia’s basic projected funding gap. And for the CPAF to cover even half ($1.75 million) of the financing gap for optimal needs through its endowment element alone (at a 4% real return on its investment), its capitalization would need to be in the range of $45 million, just for Georgia. If the current endowment fund is not increased in the next few years, and not supported in the meantime with sinking funds, there is a high risk that the CPAF impact on covering Georgia’s PA funding gaps will be limited.

Barrier 2. The second system-wide barrier to increasing financial sustainability of the country’s PA system is the level of business skills and cost-effectiveness of site management. Studies have indicated that the problem is not only about making more funds available, but also about eliminating the sometimes highly ineffective budget planning on the side of park managers and ministries. The exercise to compile the UNDP Financial Sustainability Scorecard proved that site-level business planning has been only sporadically piloted without any lasting country-wide effect. In the majority of PAs, managers are unaware of what cost-effectiveness means and what cost-effective approaches to PA management are, biodiversity needs/objectives are not juxtaposed with costs when site managers prepare request for funding from the state, and there is no analysis of return on investment when capital investment proposals are being made to government or donors. Protected area managers must have the business acumen necessary to identify creative funding mechanisms and efficiently allocate income. Providing funding alone for the PAs will not solve the problem—financial sustainability can only be achieved with intensive capacity building on management effectiveness with particular focus at the site level.

There are numerous aspects to the business planning/cost effectiveness problem. One may be a question of the number as much as the qualification of the staff. It will need to be determined whether, with training, existing (or fewer) personnel can perform additional duties, or whether new managers need to be added. Further, the limited knowledge and experience of stakeholders at the Ministry level to promote sound business planning at the PA level is a barrier to protected area expansion and improvement. In addition, the establishment and management of protected areas in community lands will be more warmly received if there is a perception that such designation is accompanied by improved revenue generation possibilities, and proper management of protected areas will require the ability to work with community members to encourage change in their current livelihood practices to be more supportive of biodiversity conservation. Accordingly, protected area managers will need the business acumen necessary to implicate their communities into the PA management planning process. Particularly those PA managers tasked with managing potentially more complex landscapes such as Sanctuaries will need to be able to identify creative funding mechanisms and efficiently allocate income. Because these skills are currently missing from the protected area toolbox, financial sustainability remains out of reach.

If properly managed, tourism could begin to contribute meaningfully to the financial sustainability of the PA system while providing valuable social and economic benefits and contributing to the overall interest and support for biodiversity conservation. However, the limited capacity of protected area managers (not to mention communities, tourism professionals and others) to embark on conservation oriented tourism continues to be a barrier. There is no national corpus of knowledge capable of leading the way towards designing and managing tourism operations that become an asset rather than a liability to PA management and community development. Tangible examples, guidelines and other templates showing stakeholders how to establish and sustainably manage sustainable tourism, particularly with community participation, are nearly non-existent. Until this barrier is removed, tourism will continue to be a biodiversity threat rather than benefit. An ineluctable first step is the creation of the necessary capacity in the PA managers to manage tourism, along with the basic infrastructure in the PAs to support it. Hotels, restaurants, guides and other tourism services can only develop if there is something to visit and an ability to receive tourists. In this sense, developing PA manager capacity and PA infrastructure for tourism are demand drivers—without them, tourists will not want to visit the sites and the eco-tourism component of financial sustainability will continue to be missing.

Many professionals identify “poaching” as a major threat to biodiversity in Georgia. Outside of State Reserves, the enforcement of conservation law is very erratic. Several factors, including poverty and lack of funding to support enforcement efforts (the latter of which will be addressed by Component 1), contribute to this problem. An additional important contributing factor is the limited capacity of protected area managers to mobilize community support. Park managers have almost no experience with and/or access to creative examples of anti-poaching measures that focus upon integrating communities and building community support for biodiversity conservation. Often communities and even conservation professionals do not fully understand conservation legislation. Community-based management models where non-consumptive tourism, limited sport hunting, alternative income generation, poacher recruitment, and/or collection and marketing of non-timber forest products serve as incentives for careful community stewardship and participation are not known. A direct correlation generally exists between a high level of community support for protected areas and savings in protected area management costs. In other words, the more communities understand and support biodiversity conservation efforts, the less time and money is required for law enforcement. Accordingly, in a financially challenged country such as Georgia, building capacity to design and implement anti-poaching tools that are creative and premised upon positive incentives to alleviate illegal activity can be a direct contributor to financial sustainability by reducing long-term PA management costs.

# Strategy

## 2.1 Objectives, Outcomes and Outputs

The project’s overall objective is to secure long-term financial sustainability of the Georgian PA system. The objective will be achieved through two components: (1) ensuring sufficiency and predictability of revenue sources for the PA system and (2) raising cost-effectiveness and capacities of PAs.

The main part of the project is in essence the co-financing, through the establishment of a sinking-fund for Georgia, of the emerging CPAF. Georgia is a developing country where PA management is viewed as a fundamental government function, the basic PA legislation is in place, but funds are scarce. It has been shown in the barriers analysis above that addressing the funding gaps in the foreseable future will require small (in absolute terms) but constant support to operational costs of protected areas. As mentioned above, the government and the CPAF are not ruling out other sources of revenue (on the contrary), but view the need as urgent and seek a mechanism likely to have a near term impact. The philosophy underpinning the CPAF is that, in circumstances such as these, the best way to support the PA system and the bio-diversity it supports is to strengthen the government’s hand in its park protection and management functions. The Ministry of Environmental Protection and Natural Resources in Georgia is supportive of the CPAF’s philosophy that its matching funds principle will encourage the government to continue its funding for existing PAs, and, together with the CPAF, to fund new PAs. As mentioned above, the key GEF prerequisites for the establishment of the fund have been found satisfactory in Georgia, and it is critical to support it through a sinking account in the next years before it is fully capitalized with endowment or other long-term funding. The small technical assistance part is key to ensure that the funds provided to the PAs through the CPAF and government contributions are used efficiently by increasing the cost-effectiveness of PA management at the site level.

GEF Project Outcome/Activity 1: Securing Long-term financial sustainability of the majority of the PA system in Georgia

The project has been designed to achieve a desired scenario in which the basic operating and investment needs of the PA system in Georgia will be more than 100% covered, and coverage of the optimal needs will be increased to 70% in 5-7 years. The financing provided by the project assures that the existing gaps to those objectives are reduced by more than 25% by year four. The remaining reductions result from the fundraising component of the project which should begin to add further resources at latest by year five.

GEF Project Output/Sub-activity 1.1: APA/PAs Sinking fund structure set and operation started based on studies previously prepared by the CPAF feasibility study. The sinking fund is a method for addressing the first barrier (inadequacy and unpredictability of revenue streams for PAs). The Feasibility Study for the Fund confirmed that the key GEF prerequisites for it were in place in Georgia, which are based on the 1999 GEF Evaluation Report on Conservation Trust Funds:

- the biodiversity conservation issue to be addressed requires a long term commitment—at least 10 to 15 years;

- there is active government support for creating a mixed, public-private sector mechanism that will function beyond direct government control;

- there is a critical mass of people from diverse sectors of society who can work together despite different approaches to biodiversity conservation and sustainable development;

- there is a basic fabric of legal and financial practices and supporting institutions in which people have confidence.

The CPAF and the APA are entering into a Sinking Fund and Project Management Agreement in the form attached as Annex H to the CEO endorsement proposal. Under the Sinking Fund and Project Management Agreement, the APA appoints the CPAF as project responsible party under this project. As project responsible party, one of the CPAF’s tasks is to operate a sinking fund with an initial deposit of $825,500, representing the grant portion (covering Component 1) of the GEF Trust Fund Grant (the “GEF Sinking Fund Grant”). Under the Sinking Fund and Project Management Agreement, the APA requests UNDP to transfer the sinking fund monies to the CPAF’s sinking fund account upon CPAF’s request when all the conditions to the disbursement of the GEF Sinking Fund Grant are satisfied. Once in the sinking fund, funds deposited will be invested by the CPAF in accordance with its investment policies prior to disbursement. Funds deposited in the sinking fund account, together with all investment earnings thereon, must be fully amortized (spent) by December 31, 2016 (seven years after the year in which the contribution occurs (assumed to be 2010)).

In summary, the sinking fund will operate as follows:

- Sinking Fund Project and Expenditures: The sinking fund (less any investment, advisory and management costs) is to be used exclusively for re-granting to support the budgets of PAs in accordance with the CPAF’s Articles and by-laws, as amended from time to time, and subject to the additional condition that such funds can only be spent to support Georgia. The CPAF will, during the period beginning in 2010 and ending on December 31, 2016, use its best effort so that (i) annual expenditures from the Fund to support the operating costs of PAs under Grant Agreements with the APA and MOEPNR in Georgia equal at least 1/7th of the total Fund by 2013 (the “Minimum Spending Goal”), and (ii) the Fund is used in its entirety by December 31, 2016. If the Minimum Spending Goal is not achieved by 2013, the Project Executive Board will consult urgently on the reasons for the prevailing level of spending and the measures that can be taken to increase it.

- Return of Funds:

  - If any part of the sinking fund remains unspent at December 31, 2016,

    - As to the pro rata portion of the Fund provided by GEF through UNDP, CPAF shall reimburse UNDP and UNDP shall reimburse GEF unless otherwise instructed by GEF.

    - As to the pro rata portion of the Fund provided by other donors, the CPAF shall make payment as directed by such donor and, failing such instruction by December 31, 2017, as it shall determine.

  - If at any time the CPAF makes a payment from the sinking fund for expenditures that are not consistent with the provisions of this Agreement, upon notice from UNDP or any other donor, the CPAF will refund to such donor an amount equal to the amount so used or the portion thereof as shall be specified by the donor.

  - The CPAF shall, upon notice from UNDP or any other donor of a Sinking Fund Grant, promptly refund to such donor its pro rata share of the remaining balance of the sinking fund that is not committed to cover expenditures under existing obligations including existing re-grant agreements, if various events (such as dissolution of the CPAF) occur that would materially and adversely affect the implementation of the project.

Under this project output, the sinking fund will be initially capitalized with co-financing of $825,500 of UNDP/GEF funds dedicated to this output, which will be deposited by the CPAF for investment with the CPAF’s custodian bank in Germany, which follows standards adopted for third-party independent non-governmental conservation trust funds.

GEF Project Output/Sub-activity 1.2: Sinking fund capitalized in full and rounds of proposals advertized to PAs (with focus on IUCN Cat.I and II). Rounds of applications will be announced. Applications from PAs and the Ministry of Environmental Protection and Natural Resources (MOEPNR) or the Agency for Protected Areas (APA) will be collected, reviewed and funding will be channelled to recipients to cover the regular PA annual running costs, biodiversity research and monitoring, establishment and support of tourism, catering, interpretation and other income-generating facilities, as well as for preparation of management plans. This process will occur in accordance with the arrangements agreed in the Framework Agreement between the CPAF and the MOEPNR and APA. The PEB will be timely advised of proposed projects and the views of the Senior Supplier will be given due consideration.

On top of the GEF/UNDP funding of $825,500, funding totalling at least $1,384,500 will be available either directly from the CPAF’s existing funds or from other donors with which the CPAF is in current discussions. In addition, the Bank of Georgia has agreed to donate $225,000 over a three year period to support the CPAF’s pilot project in Borjomi Kharagauli National Park. Together with the GEF commitment, the new funding for Georgia’s PAs (excluding government funding) will thus amount to $2,435,000. These $2,435,000 are referred to below as the “CPAF Sourced Funding”.

The CPAF’s current plan is to use the CPAF Sourced Funding by offering to add one new Georgian PA per year to the CPAF’s stable of partner PAs over the 4-year period 2010-2013. The CPAF expects to use the CPAF Sourced Funding per PA to supplement the government provided funding by approximately $110,000 annually per PA supported. Accordingly, the current overall plan is that $110,000 of the CPAF Sourced Funding will be used to support one PA in 2010, $220,000 will be used to support two PAs in 2011, $330,000 will be used to support three PAs in 2012, and $440,000 will be used to support four PAs in each of the four years from 2013-2016. On that plan, the CPAF will have “used” $2,420,000, or virtually the entire amount of the available new funds, by 2016 as planned.

The government will match the CPAF Sourced Funding, providing at least an addtional $2,435,000 in PA funding, so that at least $4.87 million in total will be spent in Georgia’s PAs over the next seven years. By year four, total government and CPAF spending in the CPAF’s projects should amount to at least $880,000 annually, and should result in at least basic investment and operating funding for more than a quarter of the highest priority areas of the Georgian PA system, ensuring coverage of the necessary annual running costs, as well as biodiversity research and monitoring, support of tourism, catering, nature interpretation and income generating activities.

Overall, output 1.2 will, for the years 2013-2016, thus reduce the annual funding gap identified by the Financial Scorecard by $440,000. With the current financing ratio in relation to basic needs is increased from 47% to 70% by the sister project, and from 70% to 88% by the assumed increase in government spending contemplated by the Financial Scorecard 2013 Projection, it would be further increased to 96% by output 1.2. The comparable figures in relation to optimal needs show a rise from a starting point at 34% to 64% taking account of the additional projected revenues including output 1.2. See Annex G.

GEF Project Output/Sub-activity 1.3: Negotiations completed for full capitalization of the CPAF (both the endowment fund and – if still required – replenishment of the sinking part). This output will support continued aggressive fund-raising for the CPAF’s ongoing funding requirements. Beyond 2013, the CPAF’s mission is to expand its funding from the initial four projects to cover as many as possible of the highest priority protected areas in Georgia. It is expected that this will be accomplished by a combination of additions to the CPAF endowment, new sinking funds and new project funding. Through its fundraising, it is planned that by 2017 the CPAF’s annual financing PA capacity will be increased from the planned $440,000 for the years 2013-2016 to at least $950,000. At latest from 2017 onward, the minimum $950,000 permanent reduction in the annual funding gap effected by output 1.3 would erase the funding gap for basic needs and increase the financing ratio to at least 70% of optimal needs, achieving the desired project outcome. See Annex G.

GEF Project Outcome/Activity 2: Raising cost-effectiveness and capacities of protected areas at the site level

For certain aspects of Component 2 below, KfW has agreed with the CPAF that, as an in kind contribution to the project, its regional vehicle, the Transboundary Joint Secretariat for the Southern Caucasus (“TJS”), either directly or by organizing the participation of other experts, will spearhead the implementation of these actions in at least the period 2010-2012. Thereafter, if the support of the TJS were no longer to be available, the CPAF would assure the role of TJS in the relevant action from its own resources. Additionally, the UNDP/GEF sister project “Catalyzing Financial Sustainability of Georgia’s Protected Area System” (MSP project - ID 3957) has a sizable component for developing business planning capacities within the APA and outside through trainings, business planning guidelines and sample business plans.

GEF Project Output/Sub-activity 2.1: CPAF implements project audits through external auditors and puts in place “PA management support group” to assist PAs to increase cost-effectiveness of PA management. The CPAF, as project responsible party, will organize regular financial and technical audits of the projects it sponsors. It is expected that financial audits will be conducted annually and technical audits at regular intervals. Potential auditors include major accounting firms represented in Georgia NGOs active in the environmental/protected area scene.

The results of these audits will feed into the second element of this component, which will involve establishing a PA management support group. The precise workings of the management support group will be established in connection with the implementation workshop, but the concept is already clear. The TJS will coordinate a group that, relying on best international guidance on PA business-planning, develops guidance for PAs on staffing ratios, assessment of financial returns on investment, cost-accounting and reporting adapted to Georgia’s context. This will give site managers the tools needed to run protected areas at international standards, budget funds appropriately and effectively and handle project audits. Other members of the group will be the CPAF ED and a representative of the APA.

Once it has developed this guidance, the management support group would make the guidance available, through the trainings contemplated by Output 2.3 but also on an ongoing basis online, to all recipients of assistance from CPAF and other PAs. It is expected that the management support group would meet not less than three times a year and that TJS would be available on a real time, as needed basis to consult with PA managers on specific management questions related to the guidance.

Furthermore, the management support group will support the continued efforts of the CPAF and PA management to ensure that PAs are run cost-effectively throughout the life of the project. This means that after the initial capacity strengthening trainings discussed in output 2.3, the other members of the Management Support Group will be available to consult with the CPAF to evaluate PA reporting and the results of project audits. This will help the CPAF determine whether these practices remain daily routines of site managers, so that it can take corrective action if necessary. This will guarantee the sustainability of the capacity building and its replicability in all of the protected areas in Georgia.

GEF Project Output/Sub-activity 2.2: Application forms for funding from CPAF and proposal review protocols designed to request confirmation of how cost-effectiveness considerations have been incorporated in the request. Measures under this output will generate the forms for project proposals, proposal review protocols, annual project reporting and the like for the CPAF that will be designed in such a way that applicants will need to show that the requested funding will be (and is being) spent in a cost-effective way, thus linking “theory” to “practice.” With these procedures in place, the monitoring of PA business practices and cost-effective management will be made easier, and site-level managers will have to demonstrate the progress they have made in business planning through their grant proposal applications and reporting. It will serve as a guarantee of outcomes from the work of the PA management support group and related trainings.

GEF Project Output/Sub-activity 2.3: Capacities of site managers strengthened through series of trainings delivered on cost-effective PA management. The goal of this output is to boost overall capacities of the site managers, creating better business and PA management on a whole and increasing the cost-effectiveness of PA management in the Georgian PA system. The trainings will be the initial catalyst to international business standards, with the ongoing audits, CPAF reporting and management support group and CPAF intervention maintaining this level of business skills at the site level.

The details of the training programs to be implemented will be discussed and agreed at the IW. TJS has agreed to play the coordination role. This means that it will either develop the training and curriculum itself, or organize others to do so through the best adapted of the various technical assistance donors who could be called upon for assistance (e.g., Germany’s GTZ, USAID, the EU’s twinning program, and the like).

The trainings would focus on two to three key managers at the various sites, but will also seek to include appropriate personnel at the Ministry or APA. Subjects to be covered will include those implicated by output 2.1 such as effective budgeting, return on investment analysis, cost accounting, reporting, project audits and planning. In addition, other relevant subjects such as management and leadership skills, tourism development, anti-poaching techniques and training and bio-diversity monitoring programs will be considered. Through this work the business and management planning barriers will be addressed.

GEF Project Output/Sub-activity 2.4: An electronic system in place, at the CPAF, to track changes in the cost-effectiveness of sites it funds, based on the METT score and – where appropriate – on the Financial Sustainability Scorecard. TJS will coordinate the design and implementation of an electronic system to track dynamics in the cost-effectiveness of site management. The system will capture regular reporting on management effectiveness received by the CPAF as part of its grant processes. The reporting will be linked to processes of decision making within the CPAF (including, e.g., determinations as to whether grants should be made or renewed), and will also be available to the government offices in charge of allocating government resources across protected areas in Georgia. This is one more way the CPAF will ensure the sustainable capacity strengthening of Georgia’s protected areas. The electronic system will allow for any appropriate action to be taken should cost-effectiveness levels drop, enabling the CPAF either directly or through the management support group to engage the PA to reinstate good business practices and effective management. The system will be linked to the Government reporting on protected areas to facilitate its use for decision-making not only about CPAF funds, but also government funding allocations across all PAs.

The combined effect of the additional revenues made available through the outocme 1 of the project, including a fully successful capitalization of the CPAF financing mechanism, with the efficiency and cost effectiveness gains of the outcome 2 of the project, will result in improvements to the Financial Scorecard and should lead to further reductions in the funding gap. Full capitalization of the CPAF will create a financially sustainable vehicle for the continued support of the chronically underfunded protected areas in Georgia and the rest of the South Caucasus. Overall, the project will secure the long term financial sustainability of Georgia’s PA system, thus securing globally important habitats, reducing illegal logging and poaching and other direct threats at key protected areas. This will contribute importantly to sustainable development and monitoring of biodiversity within the PA system and the economic well-being of PA employees.

## 2.2 Sustainability, Replicability, Cost-effectiveness

Sustainability

Environmental sustainability: The project will help ensure the proper financing and effective management of Georgia’s protected areas system, thus substantially increasing environmental sustainability per se. Increased funding for PA operations, including patrol vehicles and equipment, and strengthened salaries and capacities of rangers and park personnel, will enable better control of threats such as poaching and illegal logging. These threats will also be mitigated as increased tourism revenues improve community “buy-in” to the PAs. Increased funding for, and training in implementing, dedicated research and monitoring programmes will allow development and implementation of concrete, on-the-ground measures for globally threatened mammals and birds. Priority habitats include those harbouring threatened or endangered Caucasian leopards, Bezoar goats, Cinereous vultures and other threatened, vulnerable or endangered species, as well as Georgia-specific endemics found within its PA estate.

Financial sustainability: The long-term financial sustainability of the Georgian PA system will be based on four pillars:

- continued government funding;

- a dedicated trust fund to supplement that funding;

- diversified additional funding sources based on tourism; and

- improved efficiency and productivity in park management.

CPAF was founded as a long-term trust fund for protected areas of the South Caucasus; accordingly, its existence, and the funding support provided for the CPAF by Component 1 of this project directly address the second pillar. The CPAF’s own grant-making activity, but also ongoing financial support for eco-tourism development and other measures in the PAs funded by the CPAF, will address the third pillar. Component 2 of this project, which will embed efficiency and cost effectiveness considerations into the CPAF’s routine work with PAs, directly addresses the fourth pillar. While ultimately, only the government can be responsible for ensuring that the first pillar, the CPAF’s very structure requires the government’s to provide at least 50% of the PA operating costs and to at least maintain their current contributions on an inflation adjusted basis in order to attract CPAF funds; accordingly, the CPAF operates as a kind of financial incentive for the governments, both to continue funding for current PAs, and, by offering the possibility of up to 50% of the necessary funding for new PAs, to expand the PA system. GEF support for the sinking fund not only adds to the CPAF’s financing capacity in real terms, but also enables it to attract the co-financing necessary to fully implement the medium-term goals of this project. Success breeds success, and successful implementation of the other components of this project will lay the necessary groundwork for the aggressive fundraising measures that will lead to the final capitalization of the trust fund. With GEF support, the long-term financial sustainability of at least 482,000 ha of protected areas bearing globally threatened species and habitats within the WWF 200 Caucasus Global Ecoregion will thus be secured.

Social sustainability: The direct and indirect contributions of the project to social sustainability will be considerable. A variety of different stakeholders--from the PAs themselves, to the ministry officials involved in supervising their operations, to NGOs and independent audit firms involved in technical/operational and financial audits of their operations—will be implicated in the successful management of PA’s supported by the CPAF. The CPAF’s procedures also mandate that management plans—adopted with the participation of the rural communities surrounding the PAs--will be put into place for each PA supported by it, thus ensuring the involvement of local communities as well. The project will also help Georgia to achieve Millenium Development Goal 1 (“Eradicate extreme poverty and hunger”) by generating local employment and regional development (including development of a tourism industry) in remote and impoverished sections of the country where incomes are commonly less than $3/day but where most of the highest biodiversity PAs are located.

Institutional sustainability: With the PA Management Support Group that the CPAF will put in place, PAs will be guided in business planning and raising cost-effectiveness of site management and generally provided with the tools to manage themselves on a long-term, sustainable and transparent basis. This capacity building component of the project will thus help achieve institutional sustainability at the PA level. The sound and transparent PA budgeting, planning and operational and financial reporting that will result from the project will also benefit institutional sustainability at the MOEPNR and APA level, as will the planned participation of selected MOEPNR or APA personnel directly involved in the supervision of PAs in the trainings and in the PA Management Support Group. The improved dialogue between the PAs and the MOEPNR and APA will enable better communication within the government of the achievements and benefits of the PA system.

Replicability

The potential for replication of this project is substantial. First, replicability within Georgia is built into the project itself. The sinking fund portion of the project will finance the first four to five Protected Areas under the CPAF model over the first several years of the project, with each grant to a PA building on the knowledge and experience gained from the previous project. Then, with resources from the deepening of the CPAF’s funding sources contemplated by the fundraising component of the project in hand, the model will be extended to all of the highest value PAs system-wide.

In addition, there is significant scope for replicability outside of Georgia. A similar project is being implemented in Armenia, and the CPAF’s mandate extends to Azerbaijan as well. If the projects in Georgia and Armenia succeed, Azerbaijan will be more likely to follow suit. Furthermore, PAs in the other Caucasus countries (portions of Russia, Turkey and Iran are in the Caucasus) are theoretically potential recipients of CPAF funding if geo-political circumstances someday permit. Finally, as a rare regional trust fund, the CPAF model, if successful, will be studied in other regions.

Cost-effectiveness

The Financial Scorecard (Annex I: CEO endorsement proposal) and the CPAF’s initial experience with developing a pilot project make clear that the current financial management of PAs is not cost-effective and funding levels are not enough to meet conservation priorities. Against this backdrop of inadequate funding, PA expenditures are skewed towards meeting recurrent costs, especially staffing, and even those costs appear to be underfunded. Investment needs that are critical over the long-term receive even fewer funds. The project’s focus on (i) plugging a portion of the funding gap short-term, (ii) bringing cost- and management- efficiencies to bear as well as enhancing tourism and exploring alternative revenue generation mechanisms medium-term, and (iii) achieving an appropriate long-term capital structure for the CPAF longer-term, is the most effective way to achieve a close-to-perpetual financial sustainability of the PA system in Georgia.

Alternatives to supporting a viable CPAF financial support mechanism include: increased national government financing; developing increased tourism and NRM revenues; developing a PES revenue stream for the PAs; and relying on bilateral, multi-lateral and private donor support. The Feasibility Study that led to the CPAF’s establishment, and the discussions that led to the proposal for GEF support for the CPAF, concluded that:

- Given its other pressing development needs, it would not be reasonable to expect the GoA to cover the PA financing gap for many years—at a minimum the 10-15 year minimum GEF time horizon for establishing a conservation trust fund.

- While eco-tourism and related NRM, and the possible implementation of PES mechanisms in Georgia are and should be a focus of PA development over the coming years, it will take many years to develop them as a significant contributor to the overall financial gap, particularly given the current state of tourist infrastructure in Georgia.

- Relying on uncoordinated donor support as in the past had not been effective in addressing the systemic need, in part because of the focus of most donors on visible projects such as the establishment of new PAs and the erection of new infrastructure rather than the nitty-gritty, day-to-day needs of the PAs.

So it is not realistic to expect additional government financial resources, tourism, NRM and PES to have a medium-term impact on the scale required. And the project will clearly produce more cost-effective financial management of PAs as compared to the business-as-usual practice of PAs being funded largely from piece-meal, uncoordinated donor grants, even if they were capable of being increased in amount and re-focussed on PA operating costs. As to any alternative (i.e. non-market based) way to invest resources, e.g. an investment wholly through technical assistance, these would inevitably suffer from higher uncertainty in terms of biodiversity impact generation given the lack of sustainability at the PA site level.

But with the proper financial sustainability in place, the technical assistance component of the project represents a very cost-effective conservation approach. Done properly, the long-term management direction of the entire PA system can be improved for decades as a result of a relatively small capital investment in technical assistance and associated capacity building. Ideally, this investment results in both institutions being given the fundamental management tools required to actively engage in conservation and development initiatives leading to even greater conservation returns.

Investment in protected area management represents a pro-active expenditure that usually pays significant down-stream dividends. The immediate strengthening of a protected area mosaic will create a more secure future for a great number of species and landscapes currently vulnerable to the threats identified during project. This timely and pro-active investment will alleviate the need for later and much more costly conservation expenditures such as habitat restoration and species re-introduction, which generally entail greater economic conflicts and costs.

Project activities were designed to work with proposed and on-going conservation initiatives. The project is designed to achieve the proposed outcomes while only incurring essential incremental expenses. To accomplish this, the project will build upon the existing baseline activities and national and local capacities, as well as available infrastructure, and will target increased co-financing commitments during project design and implementation. The project will seek to contribute to the existing government efforts to expand and strengthen the national protected area system, and will increase the capacity of PAs and the MNP to meet biodiversity conservation priorities in compliance with international standards. Technical assistance, both national and international, is designed to be strategic and efficient. This means that properly selected individuals can provide support for several project outputs, alleviating the need to recruit, transport, and otherwise support a large team of experts to support project implementation.

## 2.3 Alignment with National Pririties and Expected Global Envrionmental Benefits

The project is aligned with the Government’s policy for biodiversity conservation, as stated in the National Biodiversity Conservation Strategy and Action Plan and relevant PA legislation. The Government of Georgia has set up a comprehensive program for protected areas implemented in partnership with a series of international organizations. The proposed project is an integral part of this overall program and all key members of the program have been consulted in developing this project. The CPAF will support exclusively protected areas that possess globally significant biodiversity and have been proposed for funding by the Ministry of Environment Protection and Natural Resources of Georgia, and this project to secure the long-term financial sustainability of Georgia’s PA system through the Caucasus Protected Areas Fund is strongly supported by the Ministry.

The project is also consistent with the spatial priorities and PA targets identified in the Millennium Development Goals: Nationalization and Progress – Millennium Development Goals Report (2004), MDG Progress Report (2005), the Eco-regional Conservation Plan for the Caucasus 2nd edition (2006) and the Georgian Basic Data and Directions (BDD), the government medim-term expenditure framework for the period of 2006-2010.

By promoting the conservation of Georgia’s PA system, the project will be helping to protect part of WWF’s “Global 200” and Conservation International’s “Caucasus Hotspot” at an area of almost 500,000 hectares. The project will remove pressures on a number of endangered species, including Bezoar goat (Capra Aegagrus), Eurasian lynx (Lynx lynx), Caucasian leopard (Panthera pardus sicaucasica), Lesser Kestrel (Falco naumanni), Imperial Eagle (Aquila heliaca), Greater Spotted Eagle (Aquila clanga), and countless endemic flora. Example habitat types to be included are low-mountain dry steppe, low and middle mountain steppe, high-mountain subalpine and high-mountain alpine. The project also addressed the three major gaps in the countries commitments under the CBD PoWPA, namely Goal 3.4 (to ensure financial sustainability of the PA systems).

2.4 Indicate Risks and Assumptions

| Risk/Assumption | Rating | Mitigation measures |
| --- | --- | --- |
| Strategic: Slow uptake of measures to increase cost-effectiveness by site managers and business planning is not recognized as a necessary element in PA management. | Medium | The strategy of the project on this risk is to make it explicit to site managers that obtaining funding from CPAF depends on them ensuring cost-effectiveness of funds use (work on this is integrated in Component II). Faced with failure to reform at a particular site, the CPAF will not hesitate to impose discipline by ceasing funding at that site and moving funds to another more receptive site; competition among sites should assist in mitigating this risk. |
| Governance: Poor governance, perhaps best characterized by the inability to put an end to poaching of Red List species inside of protected areas by machine gunning from helicopters hired by rich Georgians, will prevent the project from realizing its goals. | Low | Governance was a major problem until 2003 when the new government was formed. Progress since then has been so impressive that the stakeholders developing the project have judged that the project does not require a separate component to deal with governance problems. Environmental economic evaluation to be used in improved awareness raising, new public private partnerships, new incentives and improved PA financing will all serve to mitigate remaining governance problems. |
| Political: Insufficient support for key decisions on behalf of the most important government institutions | Low | Key government officials consulted during project preparation and government co-funding commitment ensured. The project will be implemented by the Ministry of Environmental Protection and Natural Resources through APA. It will play an executive role in the Project Executing Board. It will coordinate project activities through the National Project Director appointed from its staff. In addition, targeted PR campaigns targeting high officials will be conducted and the mechanisms for information sharing with them will be established. |
| Financial: The international financial crisis coupled with moderate inflation may require reconsideration of the project budget and fundraising approaches. | Medium | The international financial crisis may impact this project in three obvious ways. First, the project may experience large and unforeseen fluctuations in both currency levels and commodity prices. The US dollar is now stronger in comparison to the Euro and other currencies, and commodity prices levelling. However, the spikes seen during the summer of 2008 may return. The buying power of protected areas budgets are somewhat affected upon both of these factors, and the CPAF’s grant-making capacity will be affected by the value of the currencies in which it’s assets are invested. Second, a repeat of the substantial declines in the value of investments experienced in late 2008 and early 2009 could affect the ability of the CPAF to fund at the levels contemplated. The project designers are well aware of these issues. Expectations and budgets can and must be elastic in a multi-year project, and will be adjusted in light of these factors as circumstances warrant. The CPAF is being advised by experienced financial advisors, its executive director is experienced in financial matters, and it has managed to increase the value of its endowment despite the recent turmoil. In addition, the project has been designed to ensure relevance for the CPAF for an initial seven year period—long enough so that it should have the ability to continue through to the next economic cycle even in the event of a prolonged downturn. |
| Climate change: Climate aridation is already evidenced in Georgia resulting in altitudinal shifts of forests. The semi-desert and steppe vegetation belts have expanded and the alpine vegetation belt has reduced. It is expected that the desert and semi-desert zone area will expand by 33%, a new desert zone will form, and semi-desert will move over the bottom border of the forest in the south-eastern part. | Low | One of the aspects that will be considered by the CPAF in reviewing progress at the PAs will be measured for adaptation to climate change, aimed at increasing the resilience and adaptability of the ecosystems, as in some PAs. The CPAF will encourage site managers to ensure active participation of local communities in the identification and implementation of adaptation measures where such will be appropriate. |
| Environmental: Biodiversity threats grow beyond the background levels and thus demand still higher funding levels from them CPAF than currently planned. | Medium | CPAF and the Ministry of Environment will be regularly monitoring the risk levels at the site level. The project will maintain regular communications with the current fund co-financiers (i.e. KfW) to sensitize them to the need of ensuring that the CPAF capital is sufficient to deal with possible aggravations of biodiversity risks. Further the project’s Component I includes support to continued fund-raising, seeking project and sinking funds in addition to endowment funding, from as large a universe of potential donors as possible. . |

# Project Results Framework:

| This project will contribute to achieving the following Country Programme Outcome:: National & local capacity for sustainable environmental and natural resources management enhanced |
| --- |
| Country Programme Outcome Indicators: Enhanced planning and implementation capacities of the government and civil society (yes/no); No. of sustainable environmental and natural resource management practices adopted, their geographic scope and size of population affected |
| Primary applicable Key Environment and Sustainable Development Key Result Area: Catalyzing environmental finance |
| Applicable GEF Strategic Objective and Program: SO: Catalyze Sustainability of Protected Area Systems; SP: Sustainable finance of protected area systems at the national level |
| Applicable GEF Expected Outcomes: Biodiversity conserved and sustainably used in protected area systems; Strategic Programme: PA systems secure increased revenue and diversification of revenue streams to meet total expenditures required to meet management objectives; Reduction in financing gap to meet PA management objectives |
| Applicable GEF Outcome Indicators: Total revenue and diversification in revenue streams |
|  | Indicator | Baseline | Targets End of Project | Source of verification | Risks and Assumptions |
| Project Objective To secure long-term financial sustainability of the Georgian PA system | Area of sustainably financed PAs | 0 | >100,000 ha cat. I-II by 2013 >400,000 ha cat. I-IV by 2016 | CPAF project grants and technical audits | Renewed regional political stability MOEPNR/APA leadership remains committed to the project objectives |
|  | Improved funding ratio of optimal needs of PAs measured by financial sustainability score card | 47% | 70% | Financial Scorecard |  |
|  | Critical ecosystems of protected areas providing habitats for endemic and endangered species are conserved | Ecosystems are deteriorating | Habitats in 4-5 Cat1-II PAs are conserved by 2013 | Monitoring and reporting of park rangers |  |
| Outcome 1 Ensuring sufficiency and predictability of revenue sources for the PA system | Reduce annual funding gap by $440,000 by 2013 | 70% of basic funding 47% of optimal funding | 96% of basic funding 64% of optimal funding | Financial Scorecard; End-of year PA financial reports | MOEPNR sets an effective coordination mechanism for development of PAs’ management and financial plans and take a lead on preparation of grant applications |
|  | US$ value of capitalization of sinking fund. | 0 | $2,435,000 | CPAF reporting |  |
|  | Number of PAs financed from CPAF | CPAF is currently not financing any PAs | Four to five PAs financed by 2013 | CPAF reporting and mid-term and final evaluation reports |  |
|  | Increase in tools for PA system revenue generation | 30% | 55% | Financial Scorecard rating |  |
|  | Long-term annual funding capacity of CPAF available for Georgia based on its endowment, sinking fund and other regular annual commitments. | $100,000 | $950,000 | CPAF audit and financial statements; agreements with CPAF donors. |  |
| Outcome 2 Raising cost-effectiveness and capacities of PAs | Increase in cost-effectiveness of at least 10 PAs measured by financial score card (part II, component II); | 8% | 33% | Financial Scorecard rating |  |
|  | Adoption of site-specific business plans at 10 PAs providing transparency on the optimum level of management costs | 0 | 10 business plans adopted | CPAF funding applications; annual PA reporting and technical audits include assessment of cost-effectiveness; benchmarking of appropriate staff & salary levels, equipment and infrastructure |  |
|  | Number of site managers trained in cost-effective management | 0 | At least three in a minimum of 10 targeted PAs | PA Management Support Group; Technical audits; project reviews |  |
|  | Existence of electronic system to track changes in management effectiveness based on the METT score and – where appropriate – on the Financial Sustainability Scorecard. | No such system exists | Development and implementation of such a system | Review of CPAF reporting; project reviews |  |

# Total budget and workplan

| Award ID: |  | Project ID(s): |  |
| --- | --- | --- | --- |
| Award Title: | Country Name Project Title: PIMS 4285 BD MSP: Ensuring sufficiency and predictability of revenues for the Georgia’s protected areas system |
| Business Unit: |  |
| Project Title: | Country Name Project Title: PIMS 4285 BD MSP: Ensuring sufficiency and predictability of revenues for the Georgia’s protected areas system |
| PIMS no. | 4285 |
| Implementing Partner (Executing Agency) | Agency for Protected Areas, Ministry of Environmental Protection and Natural Resources |
| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Amount Year 5 (USD) | Amount Year 6 (USD) | Amount Year 7 (USD) | Total (USD) | Notes |
| Outcome 1. Ensuring sufficiency and predictability of revenue sources for the PA system | GoG | 62000 | GEF | 71200 | International Consultant | 0 | 0 | 0 | 9,900 | 0 | 0 | 12,600 | 22,500 | 1,2 |
|  |  |  |  | 72600 | Grants | 825,500 | 0 | 0 | 0 | 0 | 0 | 0 | 825,500 | 3 |
|  |  |  |  | Total Outcome 1 | 825,500 | 0 | 0 | 9,900 | 0 | 0 | 12,600 | 848,000 |  |
| Outcome 2. Raising cost-effectiveness and capacities of PAs | GoG | 62000 | GEF | 72100 | Contractual Services Company | 0 | 3,500 | 7,000 | 9,250 | 11,500 | 11,500 | 10,250 | 53,000 | 4 |
|  |  |  |  | Total Outcome 2 | 0 | 3,500 | 7,000 | 9,250 | 11,500 | 11,500 | 10,250 | 53,000 |  |
| PROJECT MANAGEMENT | GoG | 62000 | GEF | 71400 | Contractual Services Individuals | 12,000 | 12,000 | 12,000 | 12,000 | 12,000 | 12,000 | 12,000 | 84,000 | 5 |
|  |  |  |  | 74100 | Professional services | 0 | 2,500 | 2,500 | 2,500 | 2,500 | 2,500 | 2,500 | 15,000 | 6 |
|  |  |  |  | Total Project Management | 12,000 | 14,500 | 14,500 | 14,500 | 14,500 | 14,500 | 14,500 | 99,000 |  |
| PROJECT TOTALS | 837,500 | 18,000 | 21,500 | 33,650 | 26,000 | 26,000 | 37,350 | 1,000,000 | 7 |

Budget notes:

- Pro rata costs are based on a 50/50 allocation between GEF and cash co-financing commitments other than from the government and CPAF, except that (i) for project management, the allocation is 36% for GEF and 64% for the cash co-financing commitments other than from the government and CPAF so that the GEF contribution to PM does not exceed 10% of its commitment, and (ii) for PA funding (the “grants” item), the amounts are based on the funds remaining after funding of the other portions of the project.

- Pro rata costs of contractual appointment of evaluation experts for mid-term and final evaluation. : $20,000 is planned for the mid-term review, to be performed by an international consultant, and $25,000 is planned for the final review, also by an independent international consultant.

- GEF pro rata share of the funding going directly to the protected areas. The funds flow into the CPAF sinking fund in year 1 and are spent in the discretion of the CPAF Board, with the input from the Project Executive Board (PEB). The CPAF’s working assumption is that it will, from the combination of the sinking fund and the earnings on its endowment, co-finance with the government: one PA for 7 years beginning in 2010; a second PA for 6 years beginning in 2011; a third PA for 5 years beginning in 2012; and a fourth PA for four years beginning in 2013. The total number of PA budget years financed would thus be 22. See footnote 7 below. The total co-financing provided by GEF, TJS, the Bank of Georgia and the CPAF is $2,435,000, of which GEF’s share is $825,500 (33.6%). This sum divided over 22 PA budget years equals an assumed average CPAF contribution to the PA budgets of about $110,000 per year, of which GEF would be financing about $37,500. The government will, at a minimum, be required to match the CPAF contribution, so that a minimum of $4,870,000 flows to the target PAs over the period.

- The amounts here represent GEF’s pro rata share of 10 technical audits over the seven-year period (at the end of the first year and the second year and every third thereafter) at $2,500 per audit plus 18 annual financial audits of the protected areas over the seven-year period (one in 2011; two in 2012, three in 2013, and four each in 2014- 2016 at $4,500 per audit. See footnote 8 below.

- GEF’s pro rata share of the salaries of the CPAF employees who will effect project management, calculated as follows: Executive Director’s salary + social charges = $150,000/year or $2900/week. Assistant’s salary + social charges = $44,000/year, $858/week. Project management is calculated as 10 weeks of the Executive Director’s time and 5 weeks of the assistant’s time, or around $33,000 per year ($233,000 over seven years).

- Costs associated with a yearly project audit: $7,000 per year for six years.

- Summary of Funds*

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | GEF | 837,500 | 18,000 | 21,500 | 33,650 | 26,000 | 26,000 | 37,350 | 1,000,000 |
|  | Ministry of Environment | 110,600 | 221,200 | 331,800 | 442,850 | 442,850 | 442,850 | 442,850 | 2,435,000 |
|  | Caucasus Protected Areas Fund, including Bank of Georgia contribution to BKNP | 91,100 | 182,200 | 273,300 | 364,600 | 364,600 | 364,600 | 364,600 | 2,005,000 |
|  | TOTAL | 1,039,200 | 421,400 | 626,600 | 841,100 | 833,450 | 833,450 | 844,800 | 5,440,000 |

* All co-financing (cash and in-kind) that is not passing through UNDP.

- The following table shows the anticipated funding of PAs from the project and the frequency of the financial and technical audits associated with such funding:

| Year | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | Total 2010-2016 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PA 1 |  |  |  |  |  |  |  |  |
| Financing | √ | √ | √ | √ | √ | √ | √ | 7 |
| Financial Audit |  | √ | √ | √ | √ | √ | √ | 6 |
| Technical Audit* |  | √ | √ |  |  | √ |  | 3 |
| PA 2 |  |  |  |  |  |  |  |  |
| Financing |  | √ | √ | √ | √ | √ | √ | 6 |
| Financial Audit |  |  | √ | √ | √ | √ | √ | 5 |
| Technical Audit* |  |  | √ | √ |  |  | √ | 3 |
| PA 3 |  |  |  |  |  |  |  |  |
| Financing |  |  | √ | √ | √ | √ | √ | 5 |
| Financial Audit |  |  |  | √ | √ | √ | √ | 4 |
| Technical Audit* |  |  |  | √ | √ |  |  | 2 |
| PA 4 |  |  |  |  |  |  |  |  |
| Financing |  |  |  | √ | √ | √ | √ | 4 |
| Financial Audit |  |  |  |  | √ | √ | √ | 3 |
| Technical Audit* |  |  |  |  | √ | √ |  | 2 |
| Total PA Budget Years Financed | 1 | 2 | 3 | 4 | 4 | 4 | 4 | 22 |
| Total Financial Audits |  | 1 | 2 | 3 | 4 | 4 | 4 | 18 |
| Total Technical Audits |  | 1 | 2 | 2 | 2 | 2 | 1 | 10 |

*Technical audits are planned during second and third year of a 3-year grant cycle and, assuming renewal of the grant on the basis of the audit in year 3, every third year thereafter as a basis for determining whether to continue the grant.

# Management Arrangements

## 4.1 Overall Responsibilities

The project will be executed by the APA (Project Executive), with the support of the CPAF (PM), which will play a project responsible party role (filled in capacity assessment tool for CPAF is attached to this document as an annex 1I). The Project Executive, with the support of the PM, will be responsible for the achievement of the overall project objectives, activities and outputs. The PM will be responsible for implementation of the project, in particular operationalizing the Sinking Fund and implementing project outcomes 1 and 2. The PM currently operates with a four-member Board of Directors and is run by its Executive Director, who is currently supported by an Assistant. The Executive Director and his assistant are currently based in Paris, consistent with their overall fundraising mission. A project management team (“project team”) will be created and will be composed initially of the Executive Director of the CPAF and the Georgia representative of the Transboundary Joint Secretariat for the Southern Caucasus (together, the “project team”). During the first 3 years of the project (2010-2012), the PM will be supported on the ground in Georgia by the local country representative of the TJS. TJS support is being provided as an in kind contribution to the project from KfW. TJS support will include leadership of the Management Support group referred to in Output 2.1 above and support on other aspects of Component 2. During 2012, the CPAF will consider whether it wishes to continue the relationship with TJS and KfW will consider whether it is willing to consider extending the TJS’s mandate for the CPAF. As an alternative, the CPAF will also consider the advisability of adding local staff to the project. These discussions will be shared with the Project Executive Board.

The Project Executive Board (PEB) will direct the project and will be an ultimate decision-maker for it. It will ensure that the project remains on course to deliver the desired outcomes of the required quality. The PEB will make management decisions for the project when guidance is required by the Project Executive or the PM or when project tolerances have been exceeded. More specifically, the PEB will set up tolerance levels for project stages in terms of duration and disbursement of financial resources. The PEB will review and clear Annual Work Plans (AWPs), which will include budget revisions and annual progress achieved by the project through Annual Project Reviews based on the approved AWPs. The AWP will be sent to the RCU in Bratislava for clearance by the Regional Technical Advisor on Biodiversity. It will review and approve project stage (annual) plans and will authorize any major deviation from these agreed stage plans. The PEB is the authority that signs off on the completion of each stage plan as well as authorizes the start of the next stage plan. It will ensure that required resources are committed, will arbitrate any conflicts within the project or negotiate a solution to any problems between the project and external bodies. The PEB will meet on a bi-annual basis (more often if required). Prior to the bi-annual meetings, the PM will duly submit the progress report on the previous period and the plan for the next one. The PEB will evaluate submitted documents and be in charge of approving plans and budgets.

The responsibilities of the PEB will be divided into the Executive, Senior User/Beneficiary (“Senior User”) and Senior Supplier components.

The Executive component is ultimately responsible for the project, supported by the Senior User and Senior Supplier components. The Executive component’s roles are to ensure that the project is focused throughout its life cycle on achieving its outputs and that the project has a cost-conscious approach, balancing the demands of the user (or beneficiary) and supplier. For the project purposes, the APA through the National Project Director (mid/high level official) will assume the Executive Role in the Board, and will be supported in that role by the PM – CPAF representative.

The Senior User is responsible for specification of the needs of all those who will be primarily using or benefiting from the project outputs, for user liaison with the project team and for monitoring that the solution will meet those needs. The Senior User role commits user resources and monitors project outputs against agreed requirements. One of the directors of the PAs supported by the project, Representative of the International Relations and/or Bio-diversity Service of the Ministry of Environment will represent the Senior User/Beneficiary in the PEB.

The Senior Supplier represents the interests of those committing resources either financial or human to the project. The Senior Supplier is accountable for the quality of the outputs delivered by the supplier(s). The Senior Supplier role must have the authority to commit or acquire supplier resources required. Thus, major project donors including UNDP senior management (Deputy Resident Representative or Assistant Representative), CPAF Chief executing officer/representative of Board of Directors will represent the senior supplier role and may be extended by other major project co-financier donors.

Project Assurance – this is one of the key roles in the project management structure. The Project Assurance will act as an independent and objective quality monitoring agent, avoiding the potential “self-serving bias”. In addition, the project assurance will verify the products’ or outputs’ quality. UNDP Energy and Environment Team Leader and Regional Technical Advisor for Biodiversity at RCU will play the Project Assurance role.

## 4.2 Communications

The Project Executive, PM and the project team will communicate with a variety of audiences and be in charge of keeping the stakeholders informed of the progress overall and on the most important project events. The Project Executive will be responsible for building and sustaining the MOEPNR’s commitment to the project, and, with the support of the PM, the involvement of project stakeholders. To do this, the Project Executive and PM, supported by the Senior User, will develop a communications strategy and will maintain a high level of transparency and openness throughout the project implementation. CPAF promotional materials will be developed bearing the logos of all project partners. The same standard will also apply for all other written materials and publications and will also apply to all public events.

## 4.3 Financial and Other Procedures

The financial arrangements and procedures for the project are governed by the UNDP rules and regulations for National Implementation Modality (NIM) that allow for government rules and procedures to be used for implementation of project components and activities, including setting up and operations of the Sinking Fund. General rules for operations of the Caucasus Protected Areas Trust Fund are set up in the framework agreement between the Government of Georgia and the CPAF and, for the purpose of this project the rules and procedures for the Sinking Fund operations, to be a part of the Trust Fund – in the Sinking Fund and Project Management Agreement between the APA and CPAF, attached as Annex 2 hereto. Financial transactions will be conducted through direct payment requests made by APA to UNDP to transfer funds to the CPAF, the project responsible party. All the procurements and financial transactions to be made by the APA within the framework of each sub-grant provided by the CPAF through the Sinking Fund facility are governed by national rules and regulations.

## 4.4 Project Organization

# Monitoring and Evaluation Framework

## 5.1 Monitoring and Evaluation Framework

Project monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures by the project team and the UNDP Country Office (UNDP-CO) with a support of UNDP/GEF Regional Coordination Unit (RCU) in Bratislava. The Logical Framework Matrix provides impact and outcome indicators for project implementation along with their corresponding means of verification. The Financial sustainability score card will be used to monitor progress in PAs, financial sustainability and management effectiveness. The Baseline Financial Sustainability Scorecard is attached to the CEO endorsement proposal.

The M&E plan and reporting requirements include: inception workshop and inception report, regular interim and annual project reviews by a project executive board, project implementation reviews, short quarterly operational reports for GEF submission and detailed quarterly progress reports in UNDP format, including financial reports, both mid-term and final evaluations, project terminal report. The principal components of the M&E Plan and the indicative cost estimates related to M&E activities are outlined below. The project's M&E Plan will be presented and finalized at the project's inception workshop following a collective fine-tuning of indicators, means of verification and the full definition of project staff M&E responsibilities. Full details of the M&E plan are found in the Request for CEO Endorsement.

Table: Project Monitoring and Evaluation Plan and Budget

| Type of M&E activity | Responsible Parties | Budget US$ | Time frame |
| --- | --- | --- | --- |
| Inception Workshop | Project team | 5,000 | Within first three months of project start up |
| Inception Report | PM & Project Executive, UNDP CO | None | Immediately following IW |
| Conduct METT | Project team MOEPNR/APA staff UNDP CO | None | Mid-term and end |
| APR/PIR | PM & Project Executive UNDP CO RCU | None | Annually (August-September) |
| Quarterly progress reports | PM & Project Executive UNDP CO | None | Quarterly |
| Annual progress reports | PM & Project Executive UNDP CO | None | End of calendar year |
| Project Executive Board Meetings | Project Executive PM TJS WWF | 5,000 | Following Project IW and subsequently at least once annually in addition to the APR |
| Annual Project Reviews | PM & Project Executive PEB | None | Annually |
| Technical reports | Project team | None | To be determined by Project team |
| Mid-term Evaluation | UNDP- CO UNDP-GEF Regional Coordinating Unit External Consultants (i.e. evaluation team) | 20,000 | At the mid-point of project implementation. |
| Final Evaluation | UNDP-CO UNDP-GEF RCU External Consultants + national consultants | 25,000 | At the end of project implementation |
| Terminal Report with lessons learned | Project team & Project Executive UNDP-CO | 3,000 | At least one month before project end |
| Visits to field sites (UNDP staff travel costs to be charged to IA fees) | PM UNDP CO MOEPNR | 5,000 | Semi-Annually |
| Audit | UNDP-CO Project team | 8,000 | Annual |
| TOTAL COST |  | US$ 71,000 |  |

## 5.2 Learning and knowledge sharing

Results from the project will be disseminated within and beyond the project intervention zone through a number of existing information sharing networks and forums. In addition, the project will participate, as relevant and appropriate, in UNDP/GEF sponsored networks, organized for Senior Personnel working on projects that share common characteristics. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects. Identification and analysis of lessons learned is an on-going process, and the need to communicate such lessons as one of the project's central contributions is a requirement to be delivered not less frequently than once every 12 months.

## 5.3 Audit clause

The project will be subject to independent annual audits that will be conducted in accordance with UNDP financial rules and procedures.

# Legal Context

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA [or other appropriate governing agreement] and all CPAP provisions apply to this document.

Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

# annexes

## Annex1. Capacity Assessment for CPAF

| CSO Capacity Assessment Tool; CSO Title: The Caucasus Protected Areas Fund (CPAF) |
| --- |
| PART I. ASSESSING CSO COMMITMENT TO THE UNDP PRINCIPLES OF PARTICIPATORY HUMAN DEVELOPMENT AND DEMOCRATIC GOVERNANCE |
| 1.1 Legal status and history | Degree of legal articulation and biographical indications |
| INDICATOR | AREAS FOR ASSESSMENT | Ye/No or Comments | APPLICABLE DOCUMENTS/TOOLS |
| 1.1.1 Legal status | Is the CSO legally established? Does the CSO comply with all legal requirements of its legal identity and registration? | Yes, It is a private-law foundation with full legal capacity. | See: CPAF Charter, Paragraph 1.2. See at www.caucasus-naturefund.org |
| 1.1.2 History | Date of creation and length in existence; Reasons and circumstances for the creation of the CSO Has the CSO evolved in terms of scope and operational activity? | The CPAF was created on the 26th of June, 2007, following a feasibility study. It is operating substantially as originally conceived. | See: Background Report; also see: Management Reviews and most recent Annual audited financial Reports [2007, 2008] at www.caucasus-naturefund.org |
| 1.2 Mandate, policies and governance | Compatibility between the goals of the CSO with those of UNDP and a sound governance structure |
| INDICATOR | AREAS FOR ASSESSMENT |  | APPLICABLE DOCUMENTS/TOOLS |
| 1.2.1 CSO mandate and policies | Does the CSO share UNDP principles of human development? Does the CSO share similar service lines to UNDP? Is it clear on its role? | Yes | See: Mission Statement on website |
| 1.2.2 Governance | Who makes up the governing body and what is it charged with? How does the independent governing body exert proper oversight? Does the CSO have a clear and communicated organizational structure? | The CPAF is governed by its board of directors. It exerts oversight through regular meetings and has a clear and communicated organizational structure. | See: paragraphs 6, 7, 8 and 9 on the Board of Directors; By-Laws, paragraphs 3, 4, 6 and 7; CPAF’s Operations Manual. |
| 1.3 Constituency and external support | Ability to build collaborative relationships and a reputable standing with other sectors |
| INDICATOR | AREAS FOR ASSESSMENT |  | APPLICABLE DOCUMENTS/TOOLS |
| 1.3.1 Constituency | Does the CSO have a clear constituency? Is the organization membership based? Is there a long-term community development vision? Does the CSO have regular and participatory links to its constituency? Are constituents informed and supportive about the CSO and its activities? | The CPAF's constituency is made up of the protected areas (Pas) in the eco-region and the Environmental Ministries. The organization is not membership based, there is a long-term community development vision and constituents are informed and supportive. | See: Framework Agreements at CPAF web-site |
| 1.3.2 CSO local and global linkages | Does the CSO belong to other CSO organizations and/or CSO networks in its own sector? Does the CSO have strong links within the CSO community and to other social institutions? | Yes, the CPAF belongs to the Bundesverband Deutscher Stiftungen and it has strong links within the CSO community and to other social institutions. The ED is a member of CFA and there is regular contact with REDLAC. | See: "the CPAF wb-site |
| 1.3.3 Other partnerships , networks and external relations | Does the CSO have partnerships with government / UN agencies / private sector / foundations / others? Are these partnerships a source of funding? | The CPAF's partnerships with the governments of the South Caucasus countries are legalized in the framework agreements. Other organizations, including KfW, BMZ, CI and CEPF are sources of funding for the foundation | See: Grant Agreement at CPAF web-site |

| 2.1 Technical capacity | Ability to implement a project |
| --- | --- |
| INDICATOR | AREAS FOR ASSESSMENT | Yes/No, Comment | APPLICABLE DOCUMENTS/TOOLS |
| 2.1.1 Specialization | Does the CSO have the technical skills required? Does the CSO collect baseline information about its constituency? Does the CSO have the knowledge needed? Does the CSO keep informed about the latest techniques/ competencies/policies/trends in its area of expertise? Does the CSO have the skills and competencies that complement those of UNDP? | Yes, the CPAF's staff members have adequate technical skills and knowledge that enable the organization to collect baseline information about its constituency, be informed about the latest techniques/ competencies/policies/trends in biodiversity conservation and sustainable use. The CPAF's main technical skills are in finance and budgeting, and it leverages off of the knowledge of its partner organizations for scientific and other expertise. | See: CPAF's feasibility study Also, see: Grant Application and Financial Scorecard |
| 2.1.2 Implementation | Does the CSO have access to relevant information/resources and experience? Does the CSO have useful contacts and networks? Does the CSO know how to get baseline data, develop indicators? Does it apply effective approaches to reach its targets (i.e participatory methods) | Yes, the CPAF has all the relevant information/resources and experience including useful contacts and networks; it has experience in obtaining baseline data, developing indicators and applying effective approaches to reach its targets; Applicable documents demonstrate all the above-mentioned |  |
| 2.1.3 Human resources | Does the CSO staff possess adequate expertise and experience? Does the CSO use local capacities (financial/human/other resources)? Does the CSO have a strong presence in the field? What is the CSO's capacity to coordinate between the field and the office? | Yes, the CPAF uses local experts for technical advice, audits and the like. It expects to engage a local employee in 2011. | See: CPAF's website, section "our team." |
| 2.2 Managerial capacity | Ability to plan, monitor and co-ordinate activities |
| INDICATOR | AREAS FOR ASSESSMENT |  | APPLICABLE DOCUMENTS/TOOLS |
| 2.2.1 Planning, monitoring & evaluation | Does the CSO produce clear, internally consistent proposals and intervention frameworks? Does the development of a programme include a regular review of the programme? Does the CSO hold annual programme or project review meetings? Is strategic planning translated into operational activities? Are there measurable objectives in the operational plan? | Yes, the CPAF produces clear, internally consistent proposals | See: Strategic Plan and Fundraising overview |
| 2.2.2 Reporting and performance track record | Does the CSO report on its work to its donors, to its constituency, to CSOs involved in the same kind of work, to the local council, involved government ministries, etc.? Does the CSO monitor progress against indicators and evaluate its programme/project achievement? Does the CSO include the viewpoint of the beneficiaries in the design and review of its programming? | Yes, The CPAF reports to its donors, constituency and monitors progress. | See CPAF’s web-site |
| 2.3 Administrative capacity | Ability to provide adequate logistical support and infrastructure |
| INDICATOR | AREAS FOR ASSESSMENT |  | APPLICABLE DOCUMENTS/TOOLS |
| 2.3.1 Facilities and equipment | Does the CSO possess logistical infrastructure and equipment? Can the CSO manage and maintain equipment? | Yes | See: audited financial reports from 2007 and 2008 at CPAF’s web-site |
| 2.3.2 Procurement | Does the CSO have the ability to procure goods, services and works on a transparent and competitive basis? | Yes | See: 2007 and 2008 audited financial reports at CPAF’s web-site |
| 2.4 Financial capacity | Ability to ensure appropriate management of funds |
| INDICATOR | AREAS FOR ASSESSMENT |  | APPLICABLE DOCUMENTS/TOOLS |
| 2.4.1 Financial management & funding resources | Is there a regular budget cycle? Does the CSO produce programme and project budgets? What is the maximum amount of money the CSO has managed? Does the CSO ensure physical security of advances, cash and records? Does the CSO disburse funds in a timely and effective manner? Does the CSO have procedures on authority, responsiblity, monitoring and accountability of handling funds? Does the CSO have a record of financial stability and reliability? | Yes, the CPAF has a regular budget cycle and it produces programme and project budgets; maximum amount of that CPAF managed equaled USD 10,000,000 in 2008. It also ensures physical security of advances, cash and records. |  |
| 2.4.2 Accounting system | Does the CSO keep good, accurate and informative accounts? Does the CSO have the ability to ensure proper financial recording and reporting? | Yes |  |

## Annex 2. Sinking Fund and Project Management Agreement

This Agreement is between the Agency of Protected Areas of the Ministry of Environment Protection and Natural Resources of Georgia (the “APA”) and the Caucasus Protected Areas Fund (“CPAF”).

Whereas:

UNDP is acting as a GEF implementing agency and the APA as an executing agency under a grant by Global Environment Facility (“GEF”) to the Government of Georgia for the benefit of the CPAF (the “GEF Trust Fund Grant”). The GEF Trust Fund Grant is GEF Agency Project, PIMS: 4285, for Georgia, for the Project entitled: Ensuring sufficiency and predictability of revenues for the Georgia’s protected areas system, hereafter “the Project.”

The Caucasus Protected Areas Fund (CPAF), Ministry of Environment Protection and Natural Resources and the APA have entered into a Framework Agreement, attached as Schedule 1 to this Sinking Fund and Project Management Agreement, governing the basis on which the CPAF grants funds to the APA to finance “Covered Costs” of Priority Protected Areas (“PPAs”).

For the benefit of the Project the APA hereby appoints CPAF as a responsible party to act in accordance with this Agreement.

APA recognizes that the GEF Trust Fund Grant was made on the condition that the CPAF would act as project responsible party thereunder, and that the action of the CPAF under this Agreement supports the National Biodiversity Conservation Strategy and Action Plan.

Now, therefore, the parties hereby agree as follows:

- Sinking Fund. CPAF shall operate a sinking fund with $825,500, representing the grant portion (covering Component 1 of the Project) of the GEF Trust Fund Grant (the “GEF Sinking Fund Grant”). The GEF Sinking Fund Grant shall be subject to these Sinking Fund Rules.

  - Transfer and Deposit. The GEF Sinking Fund Grant shall be transferred directly by UNDP to the CPAF for administration and use by the CPAF in accordance with this Agreement. The APA hereby requests UNDP to make such direct payment upon CPAF’s request when all the conditions to the disbursement of the GEF Sinking Fund Grant are satisfied. The GEF Sinking Fund Grant shall be deposited by the CPAF for investment with the CPAF’s custodian bank, Deutsche Bank AG in Frankfurt, Germany, or its successor as the CPAF’s custodian bank. The CPAF shall establish in its financial accounts a separate account or accounts called the Georgia 2017 Sinking Fund Account (“SFA 1”) that will record the GEF Sinking Fund Grant and other contributions to SFA1 (collectively, the “Sinking Fund Grants”), earnings, gains and losses on the contributions to SFA1, as well as expenditures from SFA1. The proceeds of the Sinking Fund Grants shall be invested in accordance with CPAF’s investment policy pending expenditure for project purposes as described below. Funds from time to time in the SFA1 Account (the Sinking Fund Grants and earnings thereon) are herein referred to as SFA1 Funds.

  - Sinking Fund Project and Expenditures. The SFA1 Funds (less any investment advisory and management costs) shall be used exclusively for re-granting by the CPAF to support the budgets of PAs in accordance with (i) the CPAF’s Articles and by-laws, as amended from time to time, and subject to the additional condition that such funds can only be spent to support Georgia, and (ii) the Framework Agreement, as amended from time to time. The CPAF shall, during the period beginning in 2010 and ending on December 31, 2016, use its best effort so that (i) annual expenditures from SFA1 Funds to support the operating costs of PAs under Grant Agreements with the MOEPNR in Georgia equal at least 1/7th of the total of all Sinking Fund Grant contributions by 2013 (the “Minimum Spending Goal”), and (ii) all SFA1 Funds are used in their entirety by December 31, 2016. If the Minimum Spending Goal is not achieved by 2013, the Project Executive Board will consult urgently on the reasons for the prevailing level of spending and the measures that can be taken to increase it.

  - Return of Funds.

1.3.1. If any SFA1 Funds remain unspent at December 31, 2016,

- As to the pro rata portion of the SFA1 Funds representing the GEF Sinking Fund Grant, CPAF shall reimburse such funds to UNDP and UNDP shall reimburse such funds to GEF unless otherwise instructed by GEF.

- As to the pro rata portion of the SFA1 Funds representing the Sinking Fund Grants of other donors, the CPAF shall make payment of the remaining SFA1 Funds as directed by such donor and, failing such instruction by December 31, 2017, as it shall determine.

1.3.2 If at any time the CPAF makes a payment from SFA1 Funds for expenditures that are not consistent with the provisions of this Agreement, the CPAF shall, upon notice from UNDP or any other donor of a Sinking Fund Grant, promptly refund to such donor (in the case of UNDP for deposit into the GEF Trust Fund Grant Account) an amount equal to the amount so used or the portion thereof as shall be specified by the donor.

1.3.3 The CPAF shall, upon notice from UNDP or any other donor of a Sinking Fund Grant, promptly refund to such donor its pro rata share of the remaining balance of the SFA1 Funds that are not committed to cover expenditures under existing obligations including existing re-grant agreements, if any of the following events shall occur:

(a) the CPAF’s charter, By-laws, Operations Manual or Investment Policy has been amended, suspended, abrogated, repealed or waived in a manner which, in the opinion of the donor, would materially and adversely affect the implementation of the Project or the attainment of its objectives; or

(b) CPAF has been dissolved or its operations have been suspended.

- The project —M&E, Components 2 and 3: Implementation and Project Management.

As project responsible party, CPAF will contract for the M&E reports contemplated under Component 1 of the by the GEF Trust Fund Grant. In addition, CPAF will mandate project audits and oversee the Management Support Group and other elements of Component 2 of the GEF Trust Fund Grant. In consideration for its services as project responsible party, CPAF will be entitled to all payments in respect of project management as contemplated by the project documents.

The APA shall from time to time, sign and authorize direct payment requests to UNDP of GEF Trust Fund Grant funds to permit the CPAF to timely cover the relevant costs and receive the project management payments.

- Project Reporting. The CPAF shall make the reports for which it is responsible and support the APA in making the reports for which it is responsible, as contemplated in the project documents.

- No GEF Trust Fund Grant Funds shall be used for any purpose other than those contemplated by this Agreement.

In Witness Whereof, the parties have hereunto signed their names.

Agency of Protected Areas

________________________

Caucasus Protected Areas Fund

________________________

## Annex 3:  UNDP Strategic Plan:  Key Focal Areas + Key result areas + Provisional Corporate Outcomes

| Key Focal Area | Key result area | Provisional Corporate Outcomes |
| --- | --- | --- |
| Poverty Reduction and MDG achievement | Promoting inclusive growth, gender equality and MDG achievement | MDG-based national development strategies promote growth and employment, and reduce economic, gender and social inequalities |
|  |  | Enhanced national and local capacities to plan, monitor, report and evaluate the MDGs and related national development priorities, including within resource frameworks. |
|  |  | Policies, institutions and mechanisms that facilitate the empowerment of women and girls strengthened and implemented. |
|  |  | Macroeconomic policies, debt-sustainability frameworks, and public financing strategies promote inclusive growth and are consistent with achieving the MDGs. |
|  |  | Strengthened capacities of local governments and other stakeholders to foster participatory local development for the MDGs. |
|  |  | Policies, strategies and partnerships established to promote public-private sector collaboration and private-sector and market development that benefits the poor and ensures that low-income households and small enterprises have access to a broad range of financial and legal services. |
|  | Fostering inclusive globalization | 1. Enhanced capacities of developing countries to compete internationally and to negotiate interpret and implement agreements on trade, intellectual property, and investments in a manner which prioritizes poverty and inequality reduction and human development. |
|  |  | 2. Strengthened national capacities to negotiate and manage development finance, including aid and debt, consistent with the achievement of the MDGs and other internationally agreed development goals. |
|  | Mitigating the impact of AIDS on human development | 1. AIDS response integrated into poverty reduction strategies, MDG-based national development plans, and macroeconomic processes. |
|  |  | 2. Strengthened national capacity for inclusive governance and coordination of AIDS responses, and increased participation of civil society entities and people living with HIV in the design, implementation and evaluation of AIDS programmes. |
|  |  | 3. Policies and programmes implemented through multi-stakeholder approaches to protect the human rights of people affected by AIDS. Mitigate gender-related vulnerability, and address the impact of AIDS on women and girls. |
|  |  | 4. Accelerated implementation of AIDS funds and programmes financed through multilateral funding initiatives, including the Global Fund to fight AIDS, Tuberculosis, and Malaria. |
| Democratic governance | Fostering inclusive participation | 1. Civic engagement, through civil society organizations, voluntary associations, trade unions, political parties, and private sector organization, enables all people to influence public policy processes. |
|  |  | 2. Electoral laws, processes and institutions strengthen inclusive participation and professional electoral administration. |
|  |  | 3. Communication channels support government accountability and transparency through e-governance, independent journalism, and access to information policies. |
|  | Strengthening responsive governing institutions | 1. National, regional and local levels of governance expand their capacities to manage the equitable delivery of public services and support conflict reduction. |
|  |  | 2. Legislatures, regional elected bodies, and local assemblies have strengthened institutional capacity, enabling them to represent their constituents more effectively. |
|  |  | 3. Effective, responsive, accessible and fair justice systems promote the rule of law, including both formal and informal processes, with due consideration on the rights of the poor, women and vulnerable groups. |
|  | Support national partners to implement democratic governance practices grounded in human rights, gender equality and anti-corruption | 1. Strengthened national, regional and local level capacity to mainstream human rights in government policies and institutions. |
|  |  | 2. Strengthened national, regional and local level capacity to mainstream gender equality and women’s empowerment in government policies and institutions. |
|  |  | 3. Strengthened national, regional, and local-level capacity to implement anti-corruption initiatives. |
| Crisis Prevention | Enhancing conflict and disaster risk management capabilities | 1. Solutions generated for natural disaster risk management and conflict prevention through common analysis and inclusive dialogue among government, relevant civil society actors and other partners (i.e. UN, other international organizations, bilateral partners). |
|  |  | 2. Disaster – strengthened national capacities, including the participation of women to prevent, reduce, mitigate and cope with the impact of the systemic shocks form natural hazards. |
|  |  | 3. Conflict – strengthened national capacities, including the participation of women, to prevent, reduce, mitigate and cope with the impact of violent conflict. |
|  |  | 4. Other |
|  | Strengthening post-crisis governance | 1. Early post-crisis resumption of local governance functions to facilitate recovery. |
|  |  | 2. Disaster – post disaster governance capacity strengthened, including measures to ensure the reduction of future vulnerabilities. |
|  |  | 3. Conflict – post-conflict governance capacity strengthened, including measures to work towards prevention of resumption of conflict. |
|  |  | 4. Other |
|  | Restoring the foundations for development at local level | 1. Gender equality and women’s empowerment enhanced in post-disaster and post-conflict situations. |
|  |  | 2. Conflict – post-crisis community security and social cohesion restored. |
|  |  | 3. Post-crisis socio-economic infrastructure restored, economy revived and employment generated; crisis affected groups returned and reintegrated. |
|  |  | 4. other |
| Environment and sustainable development | Mainstreaming environment and energy | 1. Strengthened national capacities to mainstream environment and energy concerns into national development plans and implementation systems. |
|  |  | 2. Other |
|  | Catalyzing environmental finance | 1. Countries develop and use market mechanisms to support environmental management. |
|  |  | 2. other |
|  | Promote climate change adaptation | 1. Strengthened capacity of developing countries to mainstream climate change adaptation policies into national development plans. |
|  |  | 2. Other |
|  | Expanding access to environmental and energy services for the poor. | 1. Strengthened capacity of local institutions to mange the environment and expand environment and energy services, especially to the poor. |
|  |  | 2. Other |

SIGNATURE PAGE

Country: Georgia

UNDAF Outcome: Progress towards environment sustainability demonstrated

CP Outcome:  National and local capacities enhanced and best practices adopted for sustainable environmental and natural resources management

CP Outputs: Protected areas system expanded and strengthened

Executing Entity/Implementing Partner: Agency for Protected Areas, Ministry of Environmental Protection and Natural Resources

Implementing entity/Responsible Partner: Caucasus Protected Areas Trust Fund

Agreed by (Government): Ministry of Environmental Protection and Natural Resources

George Khachidze, Minister

NAME						SIGNATURE				Date/Month/Year

Agreed by (Executing Entity/Implementing Partner): Agency for Protected Areas

Giorgi Shonvadze, Head

NAME						SIGNATURE				Date/Month/Year

Agreed by (Responsible Party):  Caucasus Protected Areas Trust Fun d

David Morrison, Executive Director

NAME						SIGNATURE				Date/Month/Year

Agreed by (UNDP):

Jamie Mcgoldrick, Resident Representative:

NAME						SIGNATURE				Date/Month/Year

# Footnotes

Financing plan scenarios were prepared for Kolkheti National Park with World Bank/GEF assistance;

2005 Feasibilty Study which led to the creation of the CPAF pointed to cases of Belize, Papua New Guinea and Namibia where Trust Funds failed, among other reasons for “long delays in obtaining funding from donors” which entailed prohibitively high overhead costs assosiated with maintaining expensive consultants and administrative structure without any actual grant-making or lending, constant “restructuring of the trust fund design, changing legal documents” and ultimate loss of trust form Governments and failure. The Feasibilty Study concluded that perhaps the most viable way for the CPAF to avoid the problems of the three countries mentioned above would be to establish a additional medium-term sinking fund facility that allows the CPAF to effectively "jump-start" its operations and prove its viability; and then to confirm funding over the next 5-7 years.

The full study provides the details. It is available on request and not extensively quoted here for lack of space.

Deterioration is halted; habitats are conserved

Of which $825,500 from GEF and $1,609,500 from co-financing  (a portion of the $1,609,500 is in the form of project funding or annual grants).

CAPF funding is being channeled to recipients to cover the regular PA annual running costs, biodiversity research and monitoring, establishment and support of tourism, catering, interpretation and other income-generating facilities, as well as for preparation of management plans.

Information on the CPAF, including its statute, operational procedures, financial status are available at

http://www.caucasus-naturefund.org/about-contact.html

Excluding project team and UNDP staff time and UNDP staff travel expenses

# Text boxes

Programme Period:	      2006-2010; 2010-2014

Programme component:	 Energy & Environment               for Sustainable Development

Atlas Award ID:	                        tbd

Project ID:                                         tbd

PIMS #                                               4285

Start date:                                        2010

End Date:                                         2016

Management Arrangement:   NIM

PAC Meeting Date:                      tbd

Total budget:    	US$ 5,440,000

Allocated resources:

- Government

- Regular

- GEF	US$ 1,000,000

In-kind contributions:

- Government	US$ 2,435,000

- TJS, KfW	US$ 144,000

- CPAF	US$ 1, 636,000

- Bank of Georgia	US$ 225,000

TJS led Management Support Group provides guidance to PAs

APA and PAs develop and implement PA financing projects with input from project team

Project Organizational Structure

Project Support: TJS

Project Assurance: - UNDP Georgia Energy & Environment Team Leader; Biodiversity Technical Advisor, BRC

lRegional Technical Advisor for Biodiversity at the UNDP Bratislava Regional Center UNDP Program Associate

Senior Beneficiary: Targeted Park managers, MoE representative(s)

Executive: National Project Director (APA mid/high level representative)

Senior Supplier: UNDP senior management, Project co-financier donors

Project Executive Board

Project Manager:

CPAF

Brief Description

The overall objective of the project is to secure long-term financial sustainability of the Georgia’s PA system. This will be achieved through two components: (1) ensuring sufficiency and predictability of revenue sources for the PA system and (2) raising cost-effectiveness and capacities of PAs. The project has been designed to achieve a desired scenario in which the basic operating and investment needs of the PA system in Georgia will be more than 100% covered, and coverage of the optimal needs will be increased to 70% in 5-7 years, ensuring long-term integrity of the habitats and species protected by the priority PAs.

The project will address such barriers to financial sustainability of Georgia’s PAS as the insufficiency and unpredictability of revenue sources and, the poor business planning capacities and cost ineffectiveness of site management.  Concrete activities will include: i) establishment and capitalization of the APA/PAs Sinking Fund under the Caucasus Protected Areas Trust Fund (CPAF) to be channelled to the Agency for Protected Areas to cover regular PA annual running costs, biodiversity research and monitoring, tourism, catering, interpretation and other income-generating facilities, as well as preparation of management plans;  ii) aggressive fund-raising for CPAF for its full capitalization iii) technical and financial audits of CPAF-funded projects and setting-up of manageent support team; iv) development of application forms for funding from CPAF and proposal review protocols, incorporating cost-effectiveness criteria; v) strengthening capacities of site managers for cost-effective site management and vi) setting-up and running of an electronic system to track dynamics in the cost-effectiveness of site management.

The project’s durations is 7 years (2010-2016) and the budget – US$ 5,440,000. Of these, US$ 1,000,000 is a GEF cash contribution and the rest – in-kind or parallel contributions from the Government of Georgia, CPAF and various donors. The project will be executed by the APA, who will entrust the Sinking Fund operations and project managemen responsibilities to the CPAF with a management support from CPAF and KfW funded  by Transbounday Joint Secretariat (TJS).

Total budget:    	US$ 5,440,000

Allocated resources:

- Government

- Regular

- GEF	US$ 1,000,000

In-kind contributions:

- Government	US$ 2,435,000

- TJS, KfW	US$ 144,000

- CPAF	US$ 1, 636,000

- Bank of Georgia	US$ 225,000

Programme Period:	      2006-2010; 2010-2014

Programme component:	 Energy & Environment               for Sustainable Development

Atlas Award ID:	                        tbd

Project ID:                                         tbd

PIMS #                                                4285

Start date:                                         2010

End Date:                                         2016

Management Arrangement:    NIM

PAC Meeting Date:                       tbd