# UNDP Project Document

UNDP-GEF Medium-Size Project (MSP)

Government of Ghana

United Nations Development Programme

Global Environment Facility

GEFSEC Project ID: 3162

Establishing an Effective and Sustainable Structure for Implementing

Multilateral Agreements

# TABLE OF CONTENTS

Section									                                               Page

TABLE OF CONTENTS	2

SECTION I: ELABORATION OF THE NARRATIVE	4

PART I: Situation Analysis	4

PART II: Strategy	4

PART III : Management Arrangements	5

PART IV: Monitoring and Evaluation Plan and Budget	6

SECTION II:  STRATEGIC RESULTS FRAMEWORK, SRF AND GEF INCREMENT	10

SECTION III: TOTAL BUDGET AND WORKPLAN	11

SECTION IV:  ADDITIONAL INFORMATION	14

PART 1: Approved MSP PIF	14

Other agreements	15

PART II: Organigram of Project	18

PART III: Terms of References for key project staff and main sub-contracts	18

ACRONYMS

APR/PIR	Annual Project Review/Project Implementation Review

CTA	Chief Technical Advisor

DA	District Assembly

EPA	Environmental Protection Agency

FP	(Convention) Focal Points

GECCA                    	Ghana Environmental Conventions Coordinating Authority

GOG	Government of Ghana

MDA	Ministries, Departments and Agencies

MDG	Millennium Development Goals

MEn	Ministry of Energy

MEA	Multilateral Environmental Agreements

MLGRDE	Ministry of Local Government, Rural Development and Environment

MFEP	Ministry of Finance and Economic Planning

MFA	Ministry of Food and Agriculture

MLFM	Ministry of Lands, Forestry and Mines

NCSA	National Capacity Self-Assessment

GECCA	Ghana Environmental Conventions Coordinating Authority

NDPC	National Development and Planning Commission

NPC	National Project Coordinator

NPD	National Project Director

OFP	GEF Operational Focal Point

PMO	Project Management Office

PSC	Project Select Committee

PSCC	Project Steering and Coordination Committee

RCU	UNDP-GEF Regional Coordination Unit

UNCCD	United Nations Convention on Combating Desertification

UNDAF	United Nations Development Assistance Framework

UNFCCC	United Nations Framework Convention on Climate Change

SECTION I: ELABORATION OF THE NARRATIVE

## PART I: Situation Analysis

The degradation of Ghana’s renewable natural assets is equal to 5.5 percent of its annual GDP i.e. US$475 million. Threats to biodiversity, increasing risk to climate change vulnerability and adaptability and land degradation are the major consequences. As part of efforts toward addressing these environmental challenge, Ghana has ratified the three Rio Conventions and taken active steps to meet its obligations. Ghanaian stakeholders recently undertook a comprehensive, participatory assessment of the capacities needed to implement the Rio Conventions – the National Capacity Self-Assessment (NCSA). This Assessment was the first time that the stakeholders for all three Conventions had worked together. Through this process, they recognized that they have common functions and tasks, have shared resources, and face common challenges and constraints. A priority recommendation of the assessment was to strengthen coordination in order to more effectively and jointly address the challenges facing them. The proposed project is to improve coordination structures and mechanisms, so that stakeholders in Ghana are addressing the shared needs facing the implementation of the three Rio Conventions in an effective manner. The proposed project objective is to improve the institutional structures and mechanisms for implementing the Rio Conventions in Ghana, so that they generate global environmental benefits and contribute to poverty alleviation.

## PART II: Strategy

The proposed project strategy is to remove the barriers to coordination described in the previous section. Accordingly, the government will be able to firmly take responsibility for coordinating actions and implementing the Conventions. Three key strategic pillars are set drive implementation of this project. The first pillar of the strategy is to bring the existing institutional structures for the three Conventions into one structure. Under the leadership of MLGRDE, all ongoing initiatives with governmental involvement and related to the Conventions will be brought into a single structure. For example, existing internationally supported projects that target the implementation of the UNCBD and UNCCD have agreed to be brought into this structure. This structure will consist of a single Ghana Environmental Conventions Coordinating Authority (GECCA) and a Secretariat to service the GECCA. The GECCA and Secretariat will be backed up by a national Law and budget allocation. The GECCA and its Secretariat will become the entry point for all international, national and local bodies. The GECCA and Secretariat will be designed in order to respond flexibly to the political and technical requirements under each Convention, whilst maintaining a coherent structure and synergies across the Conventions. The second pillar of the strategy is to ‘capacity-building by doing’ for the structure and the third pillar of the project strategy recognizes that, ultimately, the most important Convention stakeholders are at the local level.

## PART III : Management Arrangements

The project will use the implementation and executing arrangements that were successfully used for the NCSA project. However, once the GECCA becomes operational, it will take over the functions of project guidance, steering and management. At the highest level, the project will be overseen by a Project Steering and Coordination Committee (PSCC). Initially, the PSCC will consist of the GEF OFP, the three Convention FPs, UNDP-GEF, key MDAs and representative NGOs. The participation of private sector representatives in this will be considered. The PSCC will serve as a sounding board and validation assembly for project results, and will promote project activities and findings. Once the GECCA is fully functioning, it will take over the functions of the PSCC. The GECCA will also perform these functions for other internationally supported environmental projects. Under the PSCC, a Project Select Committee (PSC) will be established and be responsible for regular supervision. The PSC will consist of the GEF OFP, the three Convention FPs and UNDP-GEF. Initial tasks of the PSC include: Approving progress reports and workplans; Approving major project outputs, such as the compliance strategies, tools or policy recommendations; Ensuring coordination with related projects; and, Ensuring that the national contributions to the project are forthcoming.

On behalf of the government of Ghana (GOG), the MLGRDE will be responsible for the implementation of the Project. The MLGRDE will appoint a high level official to be the National Project Director (NPD). As with the NCSA, the MLGRDE will establish a Project Management Office (PMO) to manage the project on a daily basis. As with the NCSA, the PMO will be managed by the National Project Coordinator (NPC) and technical support will be provided by a Chief Technical Advisor (CTA). The CTA will also be responsible for assuring the technical quality of all project activities and inputs. The PMO will also benefit from the services of a Financial and Administrative Assistant, financed by the project. Initial tasks of the PMO include: Preparing workplans and Terms of reference; Overseeing the recruitment of experts and the mobilization of inputs; Preparing quarterly progress reports; Preparing payment requests; Organising meetings of the PSCC, PSC, GECCA, etc; and, Organising workshops and travel to districts. Once the GECCA has been established, its Secretariat will also be created, and the Secretariat will take on all the functions of the PMO. PMO staff will then become Secretariat staff. The project will hire a series of national experts to provide services to key actions in the project, such as drafting the Law, developing the Secretariat Business Plan, facilitating workshops, training on key issues etc. As appropriate, the project will also sub-contract services to local institutes, NGOs or universities.

The GECCA will be chaired by the MLGRDE, and its members will be formed by the concerned MDA, NGOs and others that are currently members of the UNCBD, UNFCCC and UNCCD Committees/Commissions. The level of participation should be equivalent to MDA Director or higher. Meetings will initially be held quarterly. A secretariat to service the GECCA and perform key tasks under the Conventions in a coordinated manner will be established. The secretariat will be housed in the MLGRDE and will report to the GECCA. It will be well staffed and resourced. The first year operations will be mostly financed by GEF, and henceforth it will be primarily financed by Government. It will be accessible, transparent and accountable. The first step will be to develop, in a detailed manner, the business plan for the Secretariat. This business plan will establish its structure, staffing, activities, targets, financing and monitoring. It is likely that the Secretariat will, by the end of the project, be performing the following tasks and functions: Housing the Focal Points for GEF and the three Rio Conventions; Taking the lead in mainstreaming Rio Conventions into sectoral activities and practices; Overseeing data collection, data storing, data dissemination and data clearing. "In order to accord proper acknowledgement to GEF for providing funding, a GEF should appear on all relevant GEF project publications, including among others, project hardware and vehicles purchased with GEF funds. Any citation on publications regarding projects funded by GEF should also accord proper acknowledgment to GEF. The UNDP logo should be more prominent -- and separated from the GEF logo if possible, as UN visibility is important for security purposes.”

## PART IV: Monitoring and Evaluation Plan and Budget

Project progress will be monitored according to UNDP-GEF rules and regulations by using annual reviews against a set of implementation milestones. Monitoring will be ongoing, involving data collection and assessment of the project’s field implementation and will involve key project staff meeting periodically to review operations and field implementation and assess whether new priorities require a shift in the project’s implementation. The PSCC/GECCA will meet at least once a year to assess the project’s progress against planned outputs and to give strategic direction to the implementation of the project.  The PMO/Secretariat will hold monthly meetings with UNDP to monitor progress and troubleshoot. Quarterly Progress Reports reflecting all aspects of project implementation will be prepared by the project and shared with the PSCC/GECCA members for review. The UNDP CO will share short updates on the progress of the project with the GEF Regional Coordination Unit (RCU) on a quarterly basis. Also, the project will rely on the Global Support Programme for Capacity Development for technical assistance.

Annual Project Reports/Project Implementation Reviews (APR/PIRs) will be prepared by the project and submitted to the PSCC/GECCA for approval. The APRs, prepared in UNDP-GEF format, shall assess the performance of the project and the status of achievement of project outputs and their contribution to the relevant UNDP Outcomes. The project will be subject to at least one external financial audit in accordance with established UNDP-GEF regulations, and to one independent evaluation. At a general level, the PMO/Secretariat, under the NPC, will be responsible for collecting data on the indicators and reporting on progress. For monitoring, the data collection by the PMO/Secretariat will be supplemented by information resulting out of: An annual survey to determine the percentage of government officers that hold the view that ‘implementing the Rio Conventions conflicts with poverty alleviation’. This survey is to be undertaken by a sub-contracted organisation specialising in surveys and surveying techniques; Annual surveys in each of the pilot districts to determine the ‘awareness and understanding of District Assembly members of Rio’. This survey is to be undertaken by a sub-contracted organisation specialising in surveys and surveying techniques, and; Monitoring of the implementation of the Secretariat Business Plan. This will be done by a staff member of the Secretariat, reporting directly to the GECCA.

In line with UNDP and GEF procedures, the project will be audited annually, and will be subject to at least one independent, external evaluation. The monitoring framework and indicators will provide the project management with regular information on the project status. In addition, regular feedback will come from the PSC/GECCA and from the project’s ongoing outreach activities. At the project outset, an inception workshop will be organized. At this workshop, the first year workplan and budget will be finalized. The ToR of all inputs for the first year will also be finalized. This will include finalizing the monitoring and evaluation framework. A range of governmental, non-governmental national, local and international agencies have a role to play in this project. Details are provided in the following table.

| Category of Stakeholder | Name of stakeholder | Possible Role in Project |
| --- | --- | --- |
| National |
| Convention Focal Points | Ministry of Local Government, Rural Development and Environments (and Environmental Protection Agency) | Technical support to activities Beneficiary of institutional and individual capacity development Co-financing and hosting the Secretariat Advocacy and lobbying for the project outputs Providing training Disseminating results |
| Ministries, Department and Agencies (MDA) | Ministry of Food and Agriculture (MFA) | Beneficiary of institutional and individual capacity development Participation in the GECCA and Secretariat Disseminating results |
| Ministries, Department and Agencies | Ministry of Lands, Forestry and Mines (MLFM) | Beneficiary of institutional and individual capacity development Participation in the GECCA and Secretariat Disseminating results |
| Ministries, Department and Agencies | Ministry of Energy (ME) | Beneficiary of institutional and individual capacity development Participation in the GECCA and Secretariat Disseminating results |
| Ministries, Department and Agencies | Ministry of Finance and Economic Planning (MFEP) | Supporting coordination and integration into national development processes Participation in the GECCA and Secretariat |
| Ministries, Department and Agencies | Ministry of Local Government and Rural Development (MLG) | Beneficiary of institutional and individual capacity development Participation in the GECCA and Secretariat Disseminating results |
| Ministries, Department and Agencies | National Development and Planning Commission (NDPC) | Supporting coordination and integration into national development processes Beneficiary of institutional and individual capacity development Participation in the GECCA and Secretariat Disseminating results |
| Ministries, Department and Agencies | Ministries responsible for industry, transport, energy and foreign affairs, etc. | Participation in the GECCA and Secretariat Disseminating results |
| Academia | Universities and Research institutes, for example the University of Ghana (Geography Department), and the University of Cape Coast (Faculty of Agriculture). | Technical support to activities Beneficiary of institutional and individual capacity development Possible sub-contractors, trainers etc Advocacy and lobbying for the project outputs |
| NGOs – The NGO sector in Ghana is strong and there are many national NGOs, many of which are active in environmental issues. | For example, ‘Friends of River Bodies’, ‘Environmental Protection Association’, ‘Environmental Applications and Technology Centre’, and Earth Services | Beneficiary of institutional and individual capacity development Possible sub-contractors, trainers etc |
| Private Sector | Large scale enterprises (e.g. mining, energy, forestry), chamber of commerce | Participation in project coordination mechanisms |
| Local |
| Civil society, local community and local people | There are many in each district. In the five districts, to be selected | Beneficiary of institutional and individual capacity development |
| Traditional chieftains | In the five districts, to be selected | Beneficiary of institutional and individual capacity development Facilitate project implementation at district level and mainstreaming of Rio into district plans. |
| District Assemblies (DA) | In the five districts, to be selected | Beneficiary of institutional and individual capacity development Facilitate project implementation at district level and mainstreaming of Rio into district plans |
| District Environmental Management Committee |  | Beneficiary of institutional and individual capacity development. |
| International |
| Development partner | CIDA - Plays role as co-chair of ENRM Sector Group and Chef de File in NAP | Help ensure coordination amongst internationally supported projects. Support to GECCA and Secretariat Advocacy and lobbying for the project outputs |
| Development partner | Many | Support to implementing the Conventions and to GECCA and Secretariat Advocacy and lobbying for the project outputs Disseminating results |

PART V: Legal Context

This Project Document shall be the instrument referred to as such in Article I of the Standard Basic Assistance Agreement between the Government of Ghana and the United Nations Development Programme, signed by the parties on April 24, 2006. The host country implementing agency shall, for the purpose of the Standard Basic Assistance Agreement, refer to the government co-operating agency described in that Agreement.

The UNDP Resident Representative in Dakar, Senegal is authorized to effect in writing the following types of revision to this Project Document, provided that he/she has verified the agreement thereto by the UNDP-GEF Unit and is assured that the other signatories to the Project Document have no objection to the proposed changes:

- Revision of, or addition to, any of the annexes to the Project Document;

- Revisions which do not involve significant changes in the immediate objectives, outputs or activities of the project, but are caused by the rearrangement of the inputs already agreed to or by cost increases due to inflation;

- Mandatory annual revisions which re-phase the delivery of agreed project inputs or increased expert or other costs due to inflation or take into account agency expenditure flexibility; and

- Inclusion of additional annexes and attachments only as set out here in this Project Document

# SECTION II:  STRATEGIC RESULTS FRAMEWORK, SRF AND GEF INCREMENT

In order to reach the Project Objective, and implement the Project Strategy, there are three Project Outcomes. These are:

- The national level structure and mechanisms for coordinating activities within and across the Rio Conventions are functioning.

- National stakeholders responsible for the Rio Conventions are coordinating to perform the following key tasks: mainstreaming; knowledge management; reporting to Conventions; financial investment and mobilization; and increasing participation of stakeholders in Convention implementation.

- Stakeholders in five diverse and representative Districts are piloting the coordination of implementation of the Conventions at the District level.

- Monitoring, Learning, Adaptive feedback & Evaluation

A summary of SRF and GEF increment is below:

GEFSEC Project ID: 3162

IA/ExA Project ID: 3710

Country: Republic of Ghana

Project Title: Establischning and Effective and Sustainable Structure for Implementing Multilateral Environement Agreements

GEF  IA/ExA: UNDP

Other project executing agency(ies): Ministry of Local Government, Rural Development and Environment

Duration: 3 years

GEF Focal Area:

GEF Strategic objectives: CB-2 (Cross-cutting capacity Building)

GEF Operational Program: Capacity Building

IA/ExA Fee: US$45,000

Contribution to Key Indicators Identified in the Focal Area Strategies: The project contributues to the GEF's strategic priority to enhance capacity for global environmenet management by leveraging financial and technical resources to adress country needs for cpacity to better manage glaobal environement issues.

Table 1:  Logical Framework and Objectively Verifiable Impact Indicators

| Project Strategy | Objectively verifiable indicators |
| --- | --- |
| Goal | The overall project goal is to generate global environmental benefits through the effective coordination of activities related to the Rio Conventions at the national and local levels. |
|  | Indicator | Baseline | Target | Sources of verification | Risks and Assumptions |
| Objective of the project To improve the institutional structures and mechanisms for implementing the Rio Conventions in Ghana, so that they generate global environmental benefits and contribute to poverty alleviation. | The percentage of government officers that holds the view that implementing the Rio conventions conflict with poverty alleviation reduced. | Will be established through a survey at the project outset | Suitable target will be determined and agreed upon with government and UNDP-GEF after the survey. | Survey reports | International development partners other than GEF are contributing to the financing of the GECCA |
| Outcome 1: The national level structure and mechanisms for coordinating activities within and across the Rio Conventions are functioning. | The GECCA law is passed by parliament of Ghana within 12 months. | Non-existing GECCA law | GECCA law is passed | GECCA Act and LIs | Irregularity of donor and government financial support No law is passed Non-collaboration of government on GECCA institutional support Availability of experts |
|  | The GECCA secretariat is fully staffed and resourced within 24months. | Non-existing GECCA secretariat | GECCA secretariat operational in 24 months | Reports of GECCA secretariat |  |
|  | The number and duration of visits to the secretariat website | Non availability of secretariat website | To be set after project start-up | Frequency of visits to secretariat website |  |
| Outcome 2: National Agencies responsible for the Rio Conventions are coordinating to perform the following key tasks: Mainstreaming, Knowledge management, Reporting to Conventions, Financial investment and mobilization, Increasing participation of stakeholders in Conventions Implementation. | The number of Memoranda of Understanding (MoU) between the GECCA and other MDA by the end of the project. | Non-existing MoUs between the GECCA and other MDA | 6 MoUs by the end of the project | 6 MoU documentations | Irregularity of donor and government financial support. Non-collaboration of other MDAs |
|  | The number of position papers for Conventions prepared within 24 months | No publication on position papers on conventions | 10 per year | 10 publication on position papers on Convention |  |

| Outcome 3: Stakeholders in five diverse and representative Districts are piloting the coordination of implementation of the Conventions at the District level. | Significant reduction in the amount of land converted to unsustainable uses in the five districts | Will be determined through s survey. | To be set after the survey | Hectares of land maintained for sustainable use | Irregularity of donor and government financial support. Non-collaboration of stakeholder institutions Availability of experts |
| --- | --- | --- | --- | --- | --- |
|  | DA allocates 1.5% of its budget to environment, with due attention to Rio issues |  | 1.5% of DA budget set aside for environment (Rio issues) | Reliable funding for environment (Rio issues) activities |  |
|  | Awareness and understanding of DA members of Rio issues in the pilot districts | Will be established through s survey. | Understanding of number of DA members on Rio issues | Survey reports |  |

[NOTE : Costs associated with adaptive management and project processes that cannot easily be prorated across the other components could be charged to an Outcome entitled “Learning, evaluation, and adaptive management increased”. This might include salaries of a project coordinator, or administrative assistant that is not specifically related to any particular outcome, or spans all of the outcomes.  Sundries, travel, Steering Committee Meetings, Evaluation events, etc. might be charged here.  Note that any travel or other costs which can be related to a specific outcome activity – such as a seminar, mission, sub-contracts, consultants, etc. should be charged to that outcome.

# SECTION III: TOTAL BUDGET AND WORKPLAN

| Award ID: | tbd. |
| --- | --- |
| Award Title: | PIMS 3710 Ghana_MFA CB2: Coordination Authority for Conventions |
| Business Unit: | GHA10 |
| Project Title: | PIMS 3710 Ghana_MFA CB2: Establishing an effective and Sustainable Structure for Implementing Multilaral Environmental Agreements |
| Implementing Partner (Executing Agency) | Ministry of Local Government, Rural Development and Environment |
| GEF Outcome/Atlas Activity | Responsible Party/ | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Total (USD) |
|  | Implementing Agent |  |  |  |  |  |  |  |  |
| OUTCOME 1: The National level structure and mechanisms for coordinating activities within and across the Rio Conventions are functioning | MLGRDE | 62000 | GEF | 71300 | Local Consultants | 32,300 | 32,000 | 32000 | 96,300 |
|  |  |  |  | 72100 | Contractual services | 9,430 | 0 | 0 | 9,430 |
|  |  |  |  | 72215 | Tran Equip | 50,000 | 0 | 0 | 50,000 |
|  |  |  |  | 72205 | Office Machinery | 15,000 | 5000 | 0 | 20,000 |
|  |  |  |  |  | sub-total GEF | 106,730 | 37,000 | 32,000 | 175,730 |
|  |  | 4000 | UNDP | 71600 | Travel |  |  |  |  |
|  |  |  |  | 71300 | Local Consultants |  |  |  |  |
|  |  |  |  | 72100 | Contractual services |  |  |  |  |
|  |  |  |  |  | Etc |  |  |  |  |
|  |  |  |  |  | sub-total UNDP |  |  |  |  |
|  |  |  |  |  | Total Outcome 1 | 106,730 | 37,000 | 32,000 | 175,730 |
| OUTCOME 2: National Agencies responsible for the Rio Conventions are coordinating to perform the following key tasks: Mainstreaming, Knowledge management, Reporting to Conventions, Financial investment and mobilization, Increasing participation of stakeholders in Conventions implementation | MLGRDE | 62000 | GEF | 71300 | Local Consultants | 17,105 | 10,000 | 9,105 | 36,210 |
|  |  |  |  | 72100 | Contractual services | 18,000 | 15,000 | 10,000 | 43,000 |
|  |  |  |  | 71600 | Travel | 15,000 | 15,000 | 5,000 | 35,000 |
|  |  |  |  | 72500 | Supplies | 10,000 | 7,500 | 7,500 | 25,000 |
|  |  |  |  |  | sub-total GEF | 60,105 | 47,500 | 31,605 | 139,210 |
|  |  | 4000 | UNDP | 71600 | Travel |  |  |  |  |
|  |  |  |  | 71300 | Local Consultants |  |  |  |  |
|  |  |  |  | 72100 | Contractual services |  |  |  |  |
|  |  |  |  |  | Etc |  |  |  |  |
|  |  |  |  |  | sub-total UNDP |  |  |  |  |
|  |  |  |  |  | Total Outcome 2 | 60,105 | 47,500 | 31,605 | 139,210 |
| OUTCOME 3: Stakeholders in five diverse and representative Districts are piloting the coordination of implementation of the Conventions at the District ct level | MLGRDE | 62000 | GEF | 71300 | Local Consultants | 10,000 | 0 | 0 | 10,000 |
|  |  |  |  | 72100 | Contractual services | 30,500 | 10,000 | 7,500 | 48,000 |
|  |  |  |  | 71600 | Travel | 10,000 | 7,000 | 7,000 | 24,000 |
|  |  |  |  | 72500 | Supplies | 2,000 | 500 | 500 | 3,000 |
|  |  |  |  |  | sub-total GEF | 52,500 | 17,500 | 15,000 | 85,000 |
|  |  | 4000 | UNDP | 71600 | Travel |  |  |  |  |
|  |  |  |  | 71300 | Local Consultants |  |  |  |  |
|  |  |  |  | 72100 | Contractual services |  |  |  |  |
|  |  |  |  |  | Etc |  |  |  |  |
|  |  |  |  |  | sub-total UNDP |  |  |  |  |
|  |  |  |  |  | Total Outcome 3 | 52,500 | 17,500 | 15,000 | 85,000 |
| OUTCOME 4: Monitoring, Learning, Adaptive feedback & Evaluation | MLGRDE | 62000 | GEF | 71300 | Local Consultants | 2,500 | 2,810 | 5,000 | 10,310 |
|  |  |  |  | 71600 | Travel | 1,000 | 1,000 | 1,000 | 3,000 |
|  |  |  |  |  | sub-total GEF | 3,500 | 3,810 | 6,000 | 13,310 |
|  |  | 4000 | UNDP | 71600 | Travel |  |  |  |  |
|  |  |  |  | 71300 | Local Consultants |  |  |  |  |
|  |  |  |  | 72100 | Contractual services |  |  |  |  |
|  |  |  |  |  | Etc |  |  |  |  |
|  |  |  |  |  | sub-total UNDP |  |  |  |  |
|  |  |  |  |  | Total Outcome 4 | 3,500 | 3,810 | 6,000 | 13,310 |
| Project Management Unit | MLGRDE | 62000 | GEF | 71300 | Local Consultants | 26,000 | 0 | 0 | 26,000 |
|  |  |  |  | 72100 | Contractual services | 7,000 | 2,500 | 3,500 | 13,000 |
|  |  |  |  | 72400 | Communication | 7,000 | 3,000 | 2,750 | 12,750 |
|  |  |  |  | 72500 | Offices supplies | 5,000 | 2,500 | 2,500 | 10,000 |
|  |  |  |  |  | sub-total GEF | 45,000 | 8,000 | 8,750 | 61,750 |
|  |  | 4000 | UNDP | 71600 | Travel |  |  |  |  |
|  |  |  |  | 71300 | Local Consultants |  |  |  |  |
|  |  |  |  | 72100 | Contractual services |  |  |  |  |
|  |  |  |  | 72200 | Equipment |  |  |  |  |
|  |  |  |  | 72500 | Offices supplies |  |  |  |  |
|  |  |  |  |  | Etc |  |  |  |  |
|  |  |  |  |  | sub-total UNDP |  |  |  |  |
|  |  |  |  |  | Total Management | 45,000 | 8,000 | 8,750 | 61,750 |
| Project Total | 267,835 | 113,810 | 93,355 | 475,000 |

# SECTION IV:  ADDITIONAL INFORMATION

## PART 1: Approved MSP PIF

- A

GEFSEC Project ID: 3162

IA/ExA Project ID: 3710

Country: Republic of Ghana

Project Title: Establischning and Effective and Sustainable Structure for Implementing Multilateral Environement Agreements

GEF  IA/ExA: UNDP

Other project executing agency(ies): Ministry of Local Government, Rural Development and Environment

Duration: 3 years

GEF Focal Area:

GEF Strategic objectives: CB-2 (Cross-cutting capacity Building)

GEF Operational Program: Capacity Building

IA/ExA Fee: US$45,000

Contribution to Key Indicators Identified in the Focal Area Strategies: The project contributues to the GEF's strategic priority to enhance capacity for global environmenet management by leveraging financial and technical resources to adress country needs for cpacity to better manage glaobal environement issues.

| Financing Plan ($) |
| --- |
|  | PPG | Project* |
| GEF Total | 25,000 | 475,000 |
| Co-financing | (provide details in Section b: Co-financing) |
| GEF IA/ExA | 0 | 144,000 |
| Government | 0 | 140,300 |
| Others | 0 | 0 |
| Co-financing Total | 0 | 284,300 |
| Total | 25,000 | 759,300 |
| Financing for Associated Activities If Any: |

* If project is multi-focal, indicate agreed split between focal area allocations

| fOR jOINT PARTNERSHIP** |
| --- |
| GEF Project/Component ($) |
|  | (Share) | (Fee) |
|  | (Share) | (Fee) |
|  | (Share) | (Fee) |
| Milestones | Dates |
| Pif Approval | (actual) |
| PPG Approval | 11 January 2006 |
| MSP Effectiveness | October 2007 |
| MSP Start | August 2007 |
| MSP Closing | October 2010 |
| TE/PC Report* | September 2010 |

*** Projects that are jointly implemented by more                                                                                                                 than one IA or ExA

*Terminal Evaluation/Project Completion Report

| Approved on behalf of the UNDP. This proposal has been prepared in accordance with GEF policies and procedures and meets the standards of the Review Criteria for GEF Medium-sized Projects. |
| --- |
| Yannick Glemarec Deputy Executive Coordinator UNDP-GEF | Project Contact Person: Tom Twining-Ward UNDP-GEF Capacity Development Technical Specialist Tel. and email: + 1 212-906-6591, tom.twining-ward@undp.org |

## Other agreements

GEF OFP Endorsement Letter

Government co-financing letter

UNDP co-financing letter

## PART II: Organigram of Project

## PART III: Terms of References for key project staff and main sub-contracts

On behalf of the government of Ghana (GOG), the MLGRDE will be responsible for the implementation of the Project. The MLGRDE will appoint a high level official to be the National Project Director (NPD). As with the NCSA, the MLGRDE will establish a Project Management Office (PMO) to manage the project on a daily basis. As with the NCSA, the PMO will be managed by the National Project Coordinator (NPC) and technical support will be provided by a Chief Technical Advisor (CTA). The CTA will also be responsible for assuring the technical quality of all project activities and inputs. The PMO will also benefit from the services of a Financial and Administrative Assistant, financed by the project. Initial tasks of the PMO include:

- Preparing workplans and Terms of reference;

- Overseeing the recruitment of experts and the mobilization of inputs;

- Preparing quarterly progress reports;

- Preparing payment requests;

- Organising meetings of the PSCC, PSC, GECCA, etc; and,

- Organising workshops and travel to districts.

SIGNATURE PAGE

Country: ___________________

UNDAF Outcome(s)/Indicator(s):				_____________________________________

(Link to UNDAF outcome., If no UNDAF, leave blank)

Expected Outcome(s)/Indicator (s):				_____________________________________

(CP outcomes  linked t the SRF/MYFF goal and service line) 	_____________________________________

Expected Output(s)/Indicator(s):					_____________________________________

(CP outcomes  linked t the SRF/MYFF goal and service line)	_____________________________________

Implementing partner:						_________________________

(designated institution/Executing agency)

Other Partners:							_________________________

_________________________

Agreed by (Government): _______________________________________________________

Agreed by (Implementing partner/Executing agency):________________________________

Agreed by (UNDP):_____________________________________________________________

Notes:

UNDAF Outcome and Indicator(s)

The signature page details the UNDAF outcome(s) as well as the Outcome(s) and Output(s) related to the project.  If the UNDAF lists outcomes, they should be included in the signature page. When UNDAF outcomes are not clearly articulated, country teams may decide to either revisit the UNDAF to clarify the outcomes or leave the field blank.

UNDAF Outcome indicators should be listed here.

Expected Outcome(s) and Indicator(s)

Expected Outcomes are Country Programme (CP) outcomes. They should reflect MYFF/SRF outcomes and ACC sector, which will be in the ERP).

Outcome indicator(s) should be listed here.

Expected Output(s) and Indicator(s)

Expected Outputs are Country Programme outputs. They should reflect MYFF/SRF outputs.

Output indicator(s) should be listed here.

Implementing partner:

Same as designated institution in the simplified project document – name of institution responsible for managing the programme or project (formerly referred to as executing agency).  Implementing partners include Government, UN agencies, UNDP (see restrictions in Programming Manual Chapter 6) or NGOs.

Other partners:

Formerly referred to as implementing agencies in the simplified project document—partners that have agreed to carry out activities within a nationally executed project.  This would include UNDP when it provides Country Office Support to national execution. Private sector companies and NGOs hired as contractors would generally not be included.  The agency (i.e. Government, UN agency) that contracts with the private sector company and/or NGO is the responsible party.  ‘Other partners’ can also apply to other execution modalities.

When an NGO contributes to an output, it can be noted along with the responsible party with which it contracts (e.g., UNDP/NGO, Govt/NGO).  Consistent with current practice the rationale for selecting an NGO as a contractor, must be documented.

Programme period:  Refers to the Country Programme period

Programme component:   MYFF Goal

Project title, project code, project duration (self explanatory)

Management arrangement: Indicate NEX, AGEX, NGO Execution, DEX

Budget: Total budget minus the General Management Services Fees

General Management Services Fees:  This was formerly COA (Country Office Administrative fee) for cost sharing and UNDP Administstative Fee for Trust Funds.

Total budget:   Includes the budget and General Management Services Fees.  In-kind contributions can be listed under ‘other’ resources.  Unfunded amounts cannot be committed until funds are available.

Signatures:

The Implementing partner is the institution responsible for managing the programme or project. (The institution now commonly referred to as the “executing agency” but will now be referred to as the “implementing partner”)

UNDP is the UNDP Resident Representative.

The Government counterpart is the government coordinating authority.

# Footnotes

Typically represented by the UNDP CO

# Text boxes

Brief description

Economic activity in Ghana largely depends upon natural resources. However, Ghana’s natural resources are being depleted at an alarming rate. This degradation of the natural resource base undermines the government’s economic growth and poverty reduction strategies. As part of efforts to address the above challenges, Ghana has ratified the three Rio Conventions and taken active steps to meet its obligations. Ghanaian stakeholders recently undertook a comprehensive, participatory assessment of the capacities needed to implement the Rio Conventions. Through this process, they recognized that the three Rio Conventions have common functions and tasks, have shared resources, and face common challenges and constraints. Stakeholders in all three Conventions recognized that strengthened capacity to address these needs would lead to better management of natural resources, and in turn to better implementation of the Convention and positive impacts on the environment. Hence, the proposed project is to improve coordination structures and mechanisms, so that stakeholders in Ghana are addressing the above needs in an effective manner. The proposed project will first help the Government to merge all existing management structures at national level into one structure consisting of the Ghana Environmental Conventions Coordinating Authority (GECCA) and its Secretariat. The project will then help these mechanisms become operational by building their capacity and supporting them to perform specific tasks. Finally, the project will help these mechanisms provide support to five pilot districts, in order to build national level capacity to support districts. The result will be a far more coherent, streamlined and effective allocation of resources to meeting the Rio obligations. In turn, it is expected that this increased efficiency will attract additional investors to support Ghana as it meets its Rio Convention obligations.

Total budget:		 ____________

Allocated resources:	 ____________

- Government		 ____________

- Regular 		 ____________

- Other:

  - Donor	_________

  - Donor	_________

  - Donor	_________

- In kind contributions  _________

Programme Period:_____________

Programme Component:_________

Project Title:__________________

Project ID: _________________

Project Duration:	______________

Management Arrangement: ______

GECCA

Chaired by MLGRDE

GECCA Secretariat – housed inside and supported by MLGRDE

(All Convention and GEF Focal Points)

EPA

Other MLGRDE Divisions and Units

Other MDAs

Working Group/Unit 1

Working Group/Unit 2

Working Group/Unit etc..

Working Group/Unit etc

Environmental Desks in MDAs, and other NGO and private stakeholders