COMMUNITY RESILIENCE THROUGH EARLY WARNING (CREW) PROJECT 2013 QUARTER 1 & 2 REPORT 7/1/2013 Project Manager

|  | CREW 2013 QUARTER 1 & 2 REPORT |  |
| --- | --- | --- |

- BACKGROUND AND INTRODUCTION:

The Community Resilience through Early Warning (CREW) Project serves as the medium by which the Norwegian Government will provide both comprehensive and targeted support to GoG in delivering some of the key components from the 2013 Ghana Plan of Action for DRR and CCA. The project’s strategy is to build capacities within the country to reduce disaster risk by putting in place an integrated and scientific Early Warning System that is both scientific and people cantered.

As per the Project Document, NADMO is the Implementing Partner and United Nations Development Programme (UNDP) and Ghana Meteorological Agency (GMet) are the Responsible Party. Furthermore, the project will be implemented through partnerships with nongovernment actors, particularly with community-based NGOs and universities. The project is designed in a way that it aligns with the Hyogo Framework of Action (HFA) and the Ghana Plan of Action for DRR and CCA, and leads to tangible results in both the short-term and long-term. It also avoids EWS duplication and enhances coordination.

The goal of the project is to reduce disaster risks through better understanding of risks, reducing vulnerability to hazards, and enhancing capacities for disaster risk reduction. The main objective(s) are to develop hazard maps, enhance coordination and capacities for Early Warning Systems in 10 pilot sites by 2015. The anticipated results are:

- Economic and human losses and damages from priority hazards (i.e. floods and droughts) are reduced

- Successful Early Warning is issued and communicated for priority hazards in 10 pilot Districts

The CREW project document was successfully endorsed by NADMO and UNDP on November 24, 2012.

- PURPOSE & OBJECTIVES:

The main goals for Quarter 1 and 2 in 2013 were:

- To establish an effective Project Management structure through the recruitment of qualified professionals and essential tools/supplies,

- To conduct and complete timely and high quality implementation of the Project Inception activities, and

- To initiate the development of the Hazard and Vulnerability Mapping Methodology.

- EXPECTED OUTCOMES:

| EXPECTED OUTCOMES | KEY MILESTONES | EXPECTED OUTPUTS IN 2013 Q1 AND Q2 | OUTPUTS ACHIEVED IN 2013 Q1 AND Q2 |
| --- | --- | --- | --- |
| Atlas Activity 1: Hazard Risks Understood | Development of Hazard, Vulnerability Mapping & EWS Methodology | Hazard, Vulnerability Mapping & EWS Methodology Development Commenced: Consultant ToR to be Combined With Key Milestones Expected Outputs from Inception Workshop and Community of Practice (CoP) Meeting | -Technical Inception Workshop completed with minutes capturing inputs to Hazard and Vulnerability Mapping & EWS methodologies -International/Local Consultancy ToR developed -International/Local Consultancy Request for Proposal (RFP) for the Development of flood & Drought Risk EWS Published (Deadline: July 8-30, 2013) |
|  | 1st Community of Practice (CoP) Meeting | 1st CoP Meeting held: Minutes to include information and discussion related to pilot site selection, baseline data sources and mechanisms of measuring EWS impacts and results, scaling strategies, CoP ToR, etc. | CoP ToR Development commenced: Meeting Agenda-Pilot Sites Vetting and Validation, Discussion on Current EWS Design (Existing Activities), Baseline Data Sources (To Be Combined With Inception Report), Mechanism of Measuring EWS Impacts and Results, Discussion on Risk Data Updating (What's The Current Process?) and Scaling Strategy |
|  | Development of National Level Baseline Analysis Methodology | National Level Baseline Analysis Methodology Developed: Consultant ToR to be combined with Inputs from Inception Workshop and Community of Practice (CoP) Meeting | -International/Local Consultancy ToR developed -International/Local Consultancy Request for Proposal (RFP) for the Development of flood & Drought Risk EWS Published (Deadline: July 8-30, 2013) |
| Atlas Activity 2: Capacity for EWS for Priority Hazards Enhanced | Development of a Participatory Multi-Stakeholder EWS methodology | Stakeholder Meetings and International Consultancy Expert Consultation Sessions on EWS: Meeting(s) Including Research Institution , Donors Etc. | -CoP ToR Development commenced -International/Local Consultancy ToR developed -International/Local Consultancy Request for Proposal (RFP) for the Development of flood & Drought Risk EWS Published (Deadline: July 8-30, 2013) |
| Atlas Activity 3: Urban and Rural Vulnerabilities to Disasters Reduced | Causes of disaster vulnerabilities, and measures to reduce vulnerabilities explored and understood | Vulnerability Typology/classification Analysis Development: Participation In Multi-Stakeholder Community of Practice to Share Information and Generate Synergies | -Do- |
| Atlas Activity 4: Implementation Support | Recruitment of Project Staff | Project staff recruited: NADMO (Technical Advisor, Financial & Administrative Officer, Driver), UNDP (Administrative Assistant (50%), Project Officer, M&E Officer (50%), Technical Specialist – National, International Technical Specialist (ITS)-50%) | Hiring (Publication, Long/short Listing, Exam, Interview, Selection) process partially completed: Signed and Dispatch Offer Letters for NADMO-Technical Advisor and Finance & Administration Officers UNDP- Project Officer – hiring process underway. Offer letter to be issued and officer to start August 1, 2013. Project Admin Assistant – in progress (interviews completed) M&E Officer – due to lack of qualified candidates, the position was re-advertised. Shortlisting of the re-advertised candidates completed and written exam to take place in July. Position expected to be filled by September 2013 if qualified candidate is identified National Technical Advisor – due to lack of qualified candidate, the position was re-advertised. Shortlisting of the readvertised candidates are in progress. Position expected to be filled by September 2013 if qualified candidate is identified International Technical Advisor – The position is now vacant. Hiring process to initiate in Q3 or Q4 in accordance with UNDP policies and procedures. |
|  | Procurement of Essential Office Equipment and Supplies | Essential Office Equipment and Supplies Procured | Official Vehicle (Land Cruiser Prado TX SW), 7-Computers (Laptops) and Software-Microsoft Office, Anti-Virus, adobe Creative Suite Design Standard, and ArcGIS Advance) Purchased for Mapping, M&E reporting, Communications, and Budget & Financial Management Work through Excel and Online Platforms Office refurbishment - to be procured in Q3 once project office has been assigned |
| Atlas Activity 5: Project Inception | Inception Workshop | Inception workshop completed: covering information and discussion relating to Hazard & Vulnerability Mapping Methodologies, existing EWS related projects in Ghana-data availability and sources (i.e. reports, study) on baseline information, scaling strategies, how to establish and run effective community of practice for EWS | National technical Inception Workshop held on 24th April 2013: Workshop Report was produced which included information and discussion related to Hazard & Vulnerability Mapping Methodologies, existing EWS related projects in Ghana, data availability and sources (i.e. reports, study) on baseline information, scaling strategies, how to establish and run effective community of practice for EWS |
|  | Pilot Site(s) Selection | Ten (10) Pilot Sites Selected: Consultant ToR to be combined with key milestones expected Inputs from Inception Workshop and Community of Practice (CoP) Meetings | -Pilot site selection methodology discussed and selection process commenced: Inception Workshop Report on Criteria for Pilot Site Selection. The process will continue in Q3 as well as through the International Consultancy Report in to be delivered in Q4 |
|  | M&E Framework Development | M&E Framework Development Initiated: ToR Developed. M&E Specialist On Board and Developing The Appropriate Methodology and Gathering Data for Baseline Assessment and Developing Practical Tools and Schedule to Track Progress Throughout the Project Period. | - First Draft of the Monitoring and Evaluation Plan Completed - M&E Officer under recruitment – due to lack of qualified candidates, the position was re-advertised. Shortlisting of the re-advertised candidates completed and written exam to take place in July. Position expected to be filled by September 2013 if qualified candidate is identified |
|  | 2013 Q1 And 2 Reporting And Q3 Planning | 2013 Q1 And 2 Reporting And Q3 Planning Completed | Q1 and 2 Reporting and Q3 and 4 Planning |

- REPORTING PERIOD: Q1 & Q2 WORK PLAN AND BUDGET

| Expected Output | Planned | Actual (Achievements) | Variations (Outstanding) USD | Reasons | Recommendations |
| --- | --- | --- | --- | --- | --- |
|  | Activities | Budget USD | Activities | Disbursed USD |  |  |  |
| Outcome 1 Hazard Risks Understood |
| Updated and improved hazard maps at the national level and in 10 pilot sites | Hazard mapping methodology development in conjunction with vulnerability mapping & EWS development | 75,225.00 | International Competitive Bidding: Expert Consultation sessions | 46,479.72 | 28,745.28 | PM Hiring delayed until 2nd Quarter | Roll over to Q3 |
| Capacities built and lessons learned to better understand hazard risks | Participation in multi-stakeholder community of practice to share information and generate synergies and innovative solutions | 671.67 | Quarterly meetings | 0.00 | 671.67 | -Do- | -Do- |
| Hazard risk activities monitored, reported, and re-evaluated based on challenges and opportunities on the ground | M&E: Report on achievements, challenges, and recommendations for improvement/adjustments, next steps to be shared with Community of Practice (COP) and reflected in work plan update | 23,050.00 | Bi-annual M&E Trips. National Level assessment. Travel & DSA.1/3 of M&E Officer Salary | 0.00 | 23,050.00 | -Do- | -Do- |
| Quality of hazard risk activities assured to meet international standards and best practices | Quality assurance | 12,225.00 | Quality Assurance Includes International and national Staff salary | 28,009.40 | (15,784.40) | -Do- | For Q3 2013, all quality assurance related staff charges will be on Outcome 1 (rather than charging from all Outcomes) |
| Mechanisms to update and sustain hazard risk monitoring established | Development & implementation of hazard data updating and scaling strategy | 2,120.00 | Pre-project review report consultancy | 0.00 | 2,120.00 | -Do- | Roll over to Q3 |
|  | Total Outcome 1 Budget (ATLAS Activity 1) (2013 Q2) | 113,291.67 |  | 74,489.12 | 38,802.55 |  |  |

| Outcome 2: Capacity for EWS for priority hazards enhanced |
| --- |
| A functioning EWS for priority hazards designed and established through a participatory process in the 10 pilot sites | EWS methodology development in conjunction with hazard & vulnerability mapping development | 0.00 | International Consultancy: Expert consultation sessions with no additional costs | 0.00 | 0 | PM Hiring delayed until 2nd Quarter | Roll over to Q3 |
|  | Establish participatory multi-stakeholder EWS WG | 22,000.00 | Meeting including research institution ,donors etc. working on EWS and Stakeholder meeting | 0.00 | 22,000 | -Do- | -Do- |
| Capacities built and lessons learned to establish, improve, and sustain an effective EWS in Ghana | Participation in multi-stakeholder community of practice to share information and generate synergies and innovative solutions | 666.67 | Quarterly meetings | 0.00 | 666.67 | -Do- | -Do- |
| Quality of EWS assured to meet international standards, best practices, and local context relevance | Quality assurance | 11,916.67 | Quality Assurance Includes International and national Staff salary | 0.00 | 11,916.67 | -Do- | -Do- |
| Mechanisms to update and sustain EWS are in place | Development of sustainability and scaling strategy | 1,325.00 | Stakeholder Participation | 0.00 | 1,325.00 | -Do- | -Do- |
|  | Total Outcome 2 Budget (ATLAS Activity 1) (2013 Q2) | 35,908.34 |  | 0.00 | 35,908.34 |  |  |

| Outcome 3: Urban and Rural Vulnerabilities to Disasters Reduced |
| --- |
| Updated and improved vulnerability maps at the national level and in 10 pilot sites | Development of vulnerability mapping methodology in conjunction with hazard mapping & EWS development | 0.00 | International consultancy sessions with no additional costs | 0.00 | 0.00 | PM Hiring delayed until 2nd Quarter | Roll over to Q3 |
| Causes of disaster vulnerabilities, and measures to reduce vulnerabilities explored and understood | Vulnerability typology analysis for scaling of results to the national level | 10,166.67 | International consultancy or collaboration of academic institutions | 0.00 | 10,166.67 | -Do- | -Do- |
| Capacities built and lessons learned to reduce disaster vulnerabilities in Ghana | Participation in multi-stakeholder community of practice to share information and generate synergies and innovative solutions | 666.67 | Quarterly meeting and Training activities. | 0.00 | 666.67 | -Do- | -Do- |
| Vulnerability reduction activities monitored, reported, and re-evaluated based on challenges and opportunities on the ground | M&E: Report on achievements, challenges, and recommendations for improvement/adjustments, next steps to be shared with Community of Practice (COP) and reflected in work plan update | 6,003.33 | Includes travel costs and Technical staff salary | 0.00 | 6,003.33 | -Do- | -Do- |
| Quality of vulnerability reduction activities assured to meet international best practices and standards | Quality assurance | 11,916.67 | Quality assurance including international and national staff salary | 0.00 | 11,916.67 | -Do- | -Do- |
|  | Total Outcome 3 Budget (ATLAS Activity 1) (2013 Q2) | 28,753.34 |  | 0.00 | 28,753.34 |  |  |

| Outcome 4: Implementation Support |
| --- |
| Sufficient Human Resources for Project Management are established | Project Manager | 13,000 | Cost of Employment | 4,204.23 | 8,795.77 | April, May, Salary |  |
|  | Technical Advisor | 13,158.33 | Cost of Employment | 0.00 | 13,158.33 | Position Offered |  |
|  | Project Financial & Administrative Officer | 8,500.00 | Cost of employment | 0.00 | 8,500.00 | Position Offered |  |
|  | Project Administrative Assistant (50%) | 4,366.67 | Cost of Employment | 0.00 | 4,366.67 | Not Hired |  |
|  | Project Officer | 13,158.33 | Cost of Employment | 0.00 | 13,158.33 | Not Hired |  |
|  | Project Driver | 2,658.33 | Cost of Employment | 0.00 | 2,658.33 | Not Hired |  |
|  | M&E Officer (50%) | 0.00 | Unsuccessful Recruitment | 0.00 | 0.00 | Not Hired | Re Advertise Vacant Position |
|  | Technical Specialist - National | 0.00 | Unsuccessful Recruitment | 0.00 | 0.00 | Not Hired | Re Advertise Vacant Position |
|  | International Technical Specialist (ITS)-50% | 0.00 | ITS Hired from April-May) | 0.00 | 0.00 | ITS Related Costs (April-May) | Charged on UNDP Funds and Outcome 1 |
|  | Advertise the posts in the papers | 1,791.50 | Advertisement | 1,791.50 | 0.00 | May 8 |  |
| Sufficient Tools for Project Management are in Place | Office Supplies | 9,727.28 | Procure office supplies such as computers, desk printers etc | 7,619.03 | 2,108.25 | 7-Computers (Laptops) and Software-Microsoft Office, Anti-Virus, adobe Creative Suite Design Standard, and ArcGIS Advance) Purchased |  |
|  | Communication (Internet/Phone/Website/Software) | 863.63 | Internet, phone, website development, maintenance and software. | 0.00 | 863.63 |  | Office Accommodation to be secured ASAP |
|  | Transportation (Vehicle/Transportation Budget) | 87,500.00 | Vehicle purchase and maintenance including Fuel. | 37,208.34 | 50,291.66 | Cost of Official Vehicle (Land Cruiser Prado TX SW) | Raise Direct Payment Request for Registration of Vehicle. |
|  | Total Outcome 4 Budget (ATLAS Activity 4) (2013 Q2) | 154,724.00 |  | 50,823.10 | 101,810.50 |  |  |

| Outcome 5: Project Inception |
| --- |
| Rigorous baseline information gathered | Data collection for baseline setting | 1,250.00 |  | 0.00 | 1,250.00 |  |  |
| Stakeholder engagement & COP establishment | Inception workshops at National and local levels | 30,000.00 | National Level workshop and inception workshop in 10 pilots Districts | 5,042.63 | 24,957.37 | Inception WS (DSA, Consultancy, Venue, and supplies) at the national level held. Local level inception workshop and high level launch are yet to take place |  |
| Pilot sites determined | Selection of 10 pilot sites in view of typologies and scaling | 25,000.00 | Consultation and site visits; scaling strategy | 0.00 | 25,000.00 |  |  |
| M&E Plan and tools developed | Development of M&E Plan with baseline, indicators and tools | 2,612.50 | Consultancy and consultation for plan and tools development | 0.00 | 2,612.50 |  |  |
|  | Total Project Inception Budget (ATLAS Activity 5) (2013 Q2) | 58,862.50 |  | 5,042.63 | 53,819.87 |  |  |

4.1. Q1 & Q2 FINANCIALS

|  | Total Outcome 1 Budget (ATLAS Activity 1) | 113,291.67 |  | 74,489.12 | 38,802.55 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Total Outcome 2 Budget (ATLAS Activity 1) | 35,908.34 |  | 0.00 | 35,908.34 |  |  |
|  | Total Outcome 3 Budget (ATLAS Activity 1) | 28,753.34 |  | 0.00 | 28,753.34 |  |  |
|  | Total Outcome 4 Budget (ATLAS Activity 4) | 154,724.00 |  | 50,823.10 | 101,810.50 |  |  |
|  | Total Project Inception Budget (ATLAS Activity 5) | 58,862.50 |  | 5,042.63 | 53,819.87 |  |  |
|  |  | 391,539.85 |  | 130,354.85 | 259,094.60 |  |  |

- EMERGING ISSUES AND LESSONS LEARNT (OPPORTUNITIES & CHALLENGES)

| ISSUES AND LESSONS LEARNT | RECOMMENDATIONS |
| --- | --- |
| Getting the M&E Specialist on Board and Developing Appropriate Methodology | The Third International Conference on Early Warning (EWC III), “Developing EWS Checklist,” Recommended as the Main Structure for the M&E Methodology |
| Limited Composition and Scope of the Community of Practice (CoP) | CoP is a Climate Change Association with Limited Membership from only 6-EWS Stakeholder Institutions (NADMO, UG, G-Met, UCC, UNU, & EPA). The Implementation Partner (IP) i.e. NADMO must Exercise its Overall Responsibility to ensure Multi-Stakeholder “CoP” Participation, Mainstreaming, and Ownership of CREW EWS |

- PLANNED ACTIVITIES AND BUDGET FOR NEXT QUARTER (Q3) (in US$)

| Outcome | Outputs | Sub Activities | Responsible Party | Implementation Modality | Estimated Budget Q3 | Schedule | Deliverables |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1.0: Hazard Risks Understood | Updated and improved hazard maps at the national level and in 10 pilot sites | Risk mapping methodology development in conjunction with vulnerability mapping & EWS development | NADMO | Expert Consultation Sessions International Competitive Bidding CREW Consultancy (International+ National) | 150,450 | July 1-Sept 30 2013 July 1-Sept 30 2013 | Expert consultation session reports Signed Contract Consultant Inception report |
|  | Capacities built and lessons learned to better understand hazard risks | Participation in multi-stakeholder community of practice to share information and generate synergies and innovative solutions | NADMO | 1st CoP Meeting - discuss pilot sites vetting, existing activities, baseline data sources & mechanism of measuring EWS impacts and results | 671.67 | July 1-Sept 30 2013 | CoP Meeting minutes - capturing new information, next steps |
|  | Hazard risk activities monitored, reported, and re-evaluated based on challenges and opportunities on the ground | M&E: Report on achievements, challenges, and recommendations for improvement/adjustments, next steps to be shared with Community of Practice (COP) and reflected in work plan update | UNDP | 1st CoP Meeting - discuss pilot sites vetting, existing activities, baseline data sources & mechanism of measuring EWS impacts and results Baseline Report Development – to be combined with the International Consultancy Inception Report Quarter 3 Report & Q4 Work Plan Development | 10,000 | July 1-Sept 30 2013 | CoP Meeting minutes - capturing new information, next steps Q3 Report Q4 Work Plan Draft Baseline Report |
|  | Quality of hazard risk activities assured to meet international standards and best practices | Quality assurance | UNDP | Staff recruitment - Re-advertisement of M&E specialist & National/International Technical Specialist Quarter 3 Report & Q4 Work Plan Development | 0 | July 1-Sept 30 2013 | Signed staff contract Q3 Report Q4 Work Plan |
| Total Outcome 1 Budget (2013 – 2015): 1,281,970 | Mechanisms to update and sustain hazard risk monitoring established | Development & implementation of hazard data updating and scaling strategy | NADMO | 1st CoP Meeting - discussion on hazard data updating (what's the current process?) and scaling strategy CREW Consultancy (International+ National) | 2,650 5,000 | July 1-Sept 30 2013 | CoP meeting minutes Consultant Inception Report |
|  |  |  |  | Total Outcome 1 Budget (2013 Q3) | 168,771.67 |

| Outcome | Outputs | Sub Activities | Responsible Party | Implementation Modality | Estimated Budget Q3 | Schedule | Deliverables |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 2.0: Capacity for EWS for priority hazards enhanced | Existing status, challenges, and opportunities for EWS in Ghana identified and assessed | Existing EWS assessment and gap analysis | NADMO | CREW Consultancy (International+ National) : | (included in 1st trench payment) | July 1-Sept 30 2013 | Consultant Inception Report |
|  | EWS Master Plan developed for priority hazards | Multi-stakeholder EWS Master Plan development for priority hazards | NADMO | 1st CoP Meeting – Discussion on current design CREW Consultancy (International+ National) : | 0 0 |  | CoP Meeting Minutes Consultant Inception Report |
|  | A functioning EWS for priority hazards designed and established through a participatory process in the 10 pilot sites | EWS methodology development in conjunction with hazard & vulnerability mapping development | NADMO |  | - | July 1-Sept 30 2013 |  |
|  | Capacities built and lessons learned to establish, improve, and sustain an effective EWS in Ghana | Participation in multi-stakeholder community of practice to share information and generate synergies and innovative solutions | NADMO | 1st CoP Meeting - discuss pilot sites vetting, existing activities, baseline data sources & mechanism of measuring EWS impacts and results | 666.67 | July 1-Sept 30 2013 | Inception WS minutes/report CoP Meeting minutes - capturing new information, next steps |
|  | Quality of EWS assured to meet international standards, best practices, and local context relevance | Quality assurance | UNDP | Staff recruitment - Re-advertisement of M&E specialist & National/International Technical Specialist | 0 | July 1-Sept 30 2013 | Signed staff contract |
| Total Outcome 2 Budget (2013 – 2015): 1,137,140 | Mechanisms to update and sustain EWS are in place | Development of sustainability and scaling strategy | NADMO | 1st CoP Meeting - discussion on hazard data updating (what's the current process?) and scaling strategy | 2,650 | 1st Week of August | CoP meeting minutes |
|  |  |  |  | Total Outcome 2 Budget (2013 Q3) | 3,316.67 |

| Outcome | Outputs | Sub Activities | Responsible Party | Implementation Modality | Estimated | Schedule | Outputs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 3.0: Urban and Rural Vulnerabilities to Disasters Reduced | Updated and improved Risk maps in 10 pilot sites | Development of risk mapping methodology in conjunction with hazard mapping & EWS development | NADMO | CREW Consultancy (International+ National) | (included in first payment in Output 1) | July 1-Sept 30 2013 | Consultancy Inception Report |
|  | Causes of disaster vulnerabilities, and measures to reduce vulnerabilities explored and understood | Vulnerability typology analysis for scaling of results to the national level | NADMO | 1st CoP Meeting - discussion on hazard data updating (what's the current process?) and scaling strategy CREW Consultancy (International+ National) | 0 (included in first payment in Output 1) | 1st week of August July 1-Sept 30 2013 | CoP meeting minutes Consultancy Inception Report |
|  | Capacities built and lessons learned to reduce disaster vulnerabilities in Ghana | Participation in multi-stakeholder community of practice to share information and generate synergies and innovative solutions | NADMO | 1st CoP Meeting - discuss pilot sites vetting, existing activities, baseline data sources & mechanism of measuring EWS impacts and results | 666.67 | 1st Week of August | CoP Meeting minutes - capturing new information, next steps |
|  | Vulnerability reduction activities monitored, reported, and re-evaluated based on challenges and opportunities on the ground | M&E: Report on achievements, challenges, and recommendations for improvement/adjustments, next steps to be shared with Community of Practice (COP) and reflected in work plan update | UNDP | 1st CoP Meeting - discuss pilot sites vetting, existing activities, baseline data sources & mechanism of measuring EWS impacts and results Baseline Report Development – to be combined with the International Consultancy Inception Report Quarter 3 Report & Q4 Work Plan Development | 6,003.33 | July 1-Sept 30 2013 | CoP Meeting minutes - capturing new information, next steps Draft M&E Baseline Report Q1 & 2 Report Q3 Work Plan |
|  | Quality of vulnerability reduction activities assured to meet international best practices and standards | Quality assurance | UNDP | Staff recruitment - ToR development and hiring | - (Within Outcome 1 Budget for this Quarter) | July 1-Sept 30 2013 | Signed staff contract |
| Total Outcome 3 Budget (2013 – 2015): 1,388,120 |  |  |  |  |  |  |  |
|  |  |  |  | Total Outcome 3 Budget (2013 Q3) | 6,670 |

| Outcome | Outputs | Sub Activities | Responsible Party | Implementation Modality | Estimated Budget Q3 | Schedule | Deliverables |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Implementation Support (ATLAS Activity 4) | Sufficient Human Resources for Project Management are established | Project Manager | NADMO | Recruited | 6,262 | July 1-Sept 30 2013 | Work Plan |
|  |  | Technical Officer | NADMO | Staff recruitment - ToR development and hiring | 3,803 | August 1 - Sept 30 2013 | Signed staff contract |
|  |  | Project Financial & Administration Officer | NADMO | Staff recruitment - ToR development and hiring | 2,524 | August 1-Sept 30 2013 | Signed staff contract |
|  |  | Project Administrative Assistant (50%) | UNDP | Staff recruitment - ToR development and hiring | 2,524 | August 1-Sept 30 2013 | Signed staff contract |
|  |  | Project Officer | UNDP | Staff recruitment - ToR development and hiring | 3,803 | August 1-Sept 30 2013 | Signed staff contract |
|  |  | Project Driver | NADMO | Staff recruitment - ToR development and hiring | 1,589 | August 1-Sept 30 2013 | Signed staff contract |
|  |  | M&E Officer (50%) | UNDP | Staff recruitment – Re-advertised | - (Within Output 1) |  |  |
|  |  | Technical Specialist - National | UNDP | Staff recruitment – Re-advertised | - (Within Output 1) |  |  |
|  |  | Technical Specialist – International (50%) | UNDP | To be re-advertised | - (Within Output 1) |  |  |
|  | Sufficient Tools for Project Management are in Place | Office Supplies | NADMO | Office space request & supplies purchase | 11500 | July 1-Sept 30 2013 | Good office working environment set up |
|  |  | Communication (Internet/Phone/Website/Software) | NADMO | Office communication set up and procurement | 300 | July 1-Sept 30 2013 |  |
|  |  |  |  | Total Implementation Support Budget (2013 Q3) | 36,305.00 |

| Outcome | Outputs | Sub Activities | Responsible Party | Implementation Modality | Estimated | Outcome | Outputs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Inception (ATLAS Activity 5) | Rigorous baseline information gathered | Data collection for baseline setting | NADMO /UNDP | CoP - data availability and location to be discussed; validation of baseline information | 5,000 | By end of August | Information captured in CoP minutes |
|  | Stakeholder engagement & COP establishment | Inception workshops at National and local levels | NADMO | 1st CoP Meeting - discuss pilot sites vetting, existing activities, baseline data sources & mechanism of measuring EWS impacts and results | 8,000 | July 1-Sept 30 2013 | CoP Meeting minutes - capturing new information, next steps |
|  | Pilot sites determined | Selection of 10 pilot sites in view of typologies and scaling | NADMO | Analysis and selection of pilot sites 1st CoP Meeting - discuss and validate pilot sites | 50,000 | July 1-Sept 30 2013 | 10 pilot sites selected with rigorous methodology/justification |
| Total Outcome Budget: 185,450 | M&E Plan and tools developed | Development of M&E Plan with baseline, indicators and tools | UNDP | M&E Plan Development - Data gathering and development of M&E baseline indicators and tools | 10,450 | July 1-Sept 30 2013 | Completed Draft M&E Plan and baseline |
|  |  |  |  | Total Project Inception Budget (2013 Q3) | 73,450 |

7.0. FINANCIALS

| Total Project Budget (2013 – 2015) | 5,162,667 |  | Total Budget for 2013 Q3 | 288,513.34 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Previous Spending in 2013 (Q1 & Q2) | 130,354.85 |  |  |
|  |  |  | Estimated Spending by end of Q3 | 418,868.19 |  |  |

| 2013 Project Budget (January – December 2013) | 800,000 | Projected Delivery by end of Q3 2013 | Out of Total Project Budget (2013 – 2015) | 6.7% |
| --- | --- | --- | --- | --- |
|  |  |  | Out of Total 2013 Budget | 43.6% |

*Note: 7% General Management Service (GMS) will be added to the actual expenditure at the end of every quarter.

Budget Summary (US$) (2013 Q3)

| ATLAS |  |  |
| --- | --- | --- |
| Activity 1 | Total Outcome 1 Budget (ATLAS Activity 1) | 168,771.67 |
| Activity 2 | Total Outcome 2 Budget (ATLAS Activity 2) | 3,316.67 |
| Activity 3 | Total Outcome 3 Budget (ATLAS Activity 3) | 6,670.00 |
| Activity 4 | Total Implementation Support Budget (ATLAS Activity 4) | 36,305.00 |
| Activity 5 | Total Project Inception Budget (ATLAS Activity 5) | 73,450.00 |
|  | TOTAL | 288,513.34 |

# Footnotes

Revised - 27/07/10