BACKGROUND

The UN SSR Project Document promotes the establishment of a “technical committee for SSR support” as the “coordination mechanism.”  According to the Document, “The Technical Committee will be co-chaired by the National Security Advisor and the (UN) Senior SSR.  The co-chairs will ensure that the Committee is composed of at least 25% female members.  Meeting will take place every two weeks.  These meeting will help to establish and maintain a mapping of the various stakeholders in the sector, with a view to harmonizing and coordinating the various interventions in order to maximize the impact and avoid overlaps. In the initial phase of the project, the Senior SSR Advisor, in close cooperation with the National Security Advisor will develop the Terms of Reference of the Technical Committee and the members of the committee will be identified.”

With the December 2017 decommissioning of the Technical Working Group, tasked to assess the Security Sector, Government and the UN proceeded through all of 2018 and 2019 without the services of a Technical Committee for SSR Support.  Because meeting did not occur every two weeks, the establishment and maintenance of the mapping of the various stakeholders did not stabilize to afford for national harmonizing and coordination of the various establishing interventions.  As a consequence, there remains an absence of national coordination structure  on SSR for international partners.

In recognition and appreciation of the pledged support of numerous subject matter experts and resources from major multinational organizations, an International (SSR) Advisors Group (IAG)  formed in 2018, under the convening authority of the United Nations, as a mechanism for aligning international interventions to national SSR initiatives and activities as guided by the NSA/UN Senior SSR Advisor Project Management Unit.  The IAG is the forum where the National Security Adviser and international SSR advisers and other relevant international representatives collaborate, coordinate and deconflict on matters pertaining to the progress and technical direction of partner interventions towards SSR in The Gambia.  Generally, the IAG meets bi-weekly.

Following the completion of the SSR Assessment in December of 2017, the NSA and UNDP Senior SSR Adviser decommissioned the national key stakeholder SSR Technical Working Group.  In early 2018, the small SSR PMU identified four (4) predominantly national bodies (the SSR Institution Focal Persons Group, the Heads of Security Institutions Group, the SSR Steering Committee/Project Board, and the National Security Council) and two (2) predominantly international bodies (the International Advisers Group and the SSR International Donor Partners Group). While the PMU envisioned that each body would play a vital role in collaboration on SSR in order to enhance the coherence and coordination of the SSR support from the international community.  The data shows that none of the national bodies has met on a regular basis since the launch of SSR in 2017.  In 2019, President Barrow remarked during a meeting with the UN Technical Assessment Mission (TAM) delegation of there being too many cooks in the kitchen apparently referring to the pool of international SSR advisors.  What the President does not know is that the absence of Gambian involvement not only constricts the SSR process to the limits and competencies of the sole Gambian involved, the NSA, but also retards the collective key stakeholder visibility, collaboration and prioritization of international partner interventions.

Since April 2018, only the IAG has met consistently and regularly.  During the same time period the SSR Steering Committee/Project Board has met irregularly with near maximum participation of the members of international partners while the attendance of the participation of Gambian members of the SSR Project Board has been less than minimal, representing a self-inflicted  restraint on Gambian SSR.

OBJECTIVE

At the request of the Government, this nationally owned and maintained coordination matrix of international support contains detailed information with the specificity required to inform successively the Technical Committee for SSR Support, the SSR Steering Committee/Project Board, and National Security Council decisions on implementing activities specified in the Gambia Security Sector Reform Strategy. The Office of National Security (ONS) has the mandate to lead the coordination of international support with the assistance of the United Nations and in close consultation with the AU, ECOWAS, EU and bilateral partners. The coordination of international partners support is done against national SSR priorities identified in the Gambia Security Sector Reform Strategy 2020-2024.

- Ensure that international assistance to SSR is fully aligned to short, medium and long-term national priorities; and

- Enhance the predictability and harmonisation of the international support to SSR, including by mapping the current assistance and identifying tools and mechanisms for joint analysis, planning, implementation, as well as monitoring, reporting and evaluation.

Members of the Technical Committee for SSR Support – pending Steering Committee Action

Members of the International Advisers Group

The following multilateral and bilateral partners are represented by SSR, security and defense subject matter experts engaged in and responsible for ensuring close collaboration, coordination and deconfliction of their interventions with the ONS.

United Nations (UN)

The UNDP SSR Team is led by a senior SSR Adviser (International) who serves as Project Manager and Chief  Technical Advisor of the UN PBSO/PBF-funded SSR Project titled, “Strategic advice and support to the security reform and governance in The Gambia” developed based on the request of the Government to provide strategic advice and support to the designing and launching of the national security sector reform process. The two (2) key outcomes of the project are that (a) the SSR stakeholders benefit from the necessary strategic support to elaborate and implement an inclusive national security strategy; and (b) the SSR support of the international community is coherent and coordinated.

African Union

The AU SSR team comprises 6 military advisers and 2 civilian experts. The team is led by the Senior Defence Reform Adviser. The team was deployed based on the Government of The Gambia’s request to the AU Commission. The team has its members embedded in national institutions in order to provide and help build capacity within the institutions. Consequently, the team has two (2) advisers deployed at the ONS, one (1) at the Ministry of Defence (MOD), three (3) at the Gambia Armed Forces (GAF) Headquarters, one (1) at the Ministry of Interior (MOI) and one (1) at the National Human Rights Commission (NHRC)/Ministry of Justice (MOJ). AU SSR team members identify projects in their institutions and the projects are approved and funded by the AU based on availability of resources. Therefore, the projects captured in this matrix are not sacrosanct and new projects may be added as identified.

Economic Community of West African States (ECOWAS)

The ECOWAS recruited and deployed a Senior Defence and Security Adviser on request from government of The Gambia in early 2018. His responsibilities amongst others include but not limited to the following:

- Assist Government of The Gambia and the Special Representative of the President of the ECOWAS Commission (SRPC) by providing necessary analysis and guidance on defence and security related issues in order to review and reform the security system in The Gambia.

- Regular detailed assessments of the defence and security situation in the country.

- Plans of Action for support in the formulation of laws, policies, safe management of weapons stockpile, institutional capacity building for security sector governance.

- Regular reports on the progress made in Security Sector Reform (SSR).

- Serve as ECOWAS Adviser to the relevant Gambian Authorities on Defence and Security Sector Reform Program.

To assist the Senior Defence and Security Advisor accomplish his critical mandate, ECOWAS recruited and deployed a Project Officer, anchored at the ECOWAS Permanent Mission Headquarters. Equally, ECOWAS recruited and deployed a Communication Strategist to the Office of National Security (ONS) for sensitization and advocacy to the populace on progress of SSR implementation in The Gambia.

European Union (DAI)

The SSR Adviser, funded by the EU, is responsible for implementing State Building Contract (1) – launched in September 2018. Initial support was provided to the development of security policy. In July 2019, the EU Delegation and ONS approved a new plan called Project Trust. Activities within the project are focused on building a Security Vetting Agency, Counter Terrorism Strategy, Joint-Cross Agency working through simulation exercises, as well as continued policy development. The Project concludes in December 2020.

DCAF

DCAF’s programme in the Gambia seeks to contribute to meaningful security sector reform and greater accountability leading to improved peace and security for the Gambian population. Our work in The Gambia aims to:

- Support the global architecture of the SSR process led by the Gambian state by enhancing synergies between international stakeholders and national services involved in SSR. The project will accordingly support the government in establishing a structure dedicated to fostering information-sharing and coordination among international stakeholders around their respective engagements and interventions.

- Support an inclusive SSR process that fully takes into account the concerns and needs of all people of The Gambia, regardless of gender identity or sex, religion, ethnicity or age. DCAF will support the government of The Gambia and, notably, the Office of the National Security Adviser, in designing and implementing activities aimed at informing the population on the SSR process, and providing a forum for dialogue, consultation and information-gathering from diverse stakeholders on the needs, gaps and priorities to be considered while designing and implementing the SSR process.

- Support the legal reform process aimed at developing laws and policies governing the security sector that are fully compliant with the rule of law and human rights principles.

- Support the government of The Gambia in making strategic decisions that are based on evidence, solid analysis and best practices in SSR in order to restructure the security and defence apparatus and to adapt its workforce according to the new vision of the security sector.

- Promote and strengthen the democratic participation and oversight of the security sector by the Parliament (specifically the Defence and Security Committee), civil society, the media and citizens. The project will further aim to building bridges between civilian oversight actors and security institutions, thereby fostering the exchange of information while building confidence as an essential element to sustainable peace and security.

France

The French SSR advisor serves as Project Manager and Technical Advisor of the French-Gambian bilateral cooperation, regarding good governance and capacity building of security forces, providing strategic advice and support in the national SSR process. The main outcomes of the project are 1) the support/advise to the Office of National Security and 2) training and support on the benefit of security services (Ministries of Interior and Defence).

French Project Manager is expecting from The Gambian partner its expectations in terms of capacity building set in priorities.

MONITORING AND REPORTING

The UN PBSO/PBF-funded SSR Project titled, “Strategic advice and support to the security reform and governance in The Gambia” prescribed a UN project management unit for the UN side of work and the NSA/ONS for the host nation side of the work. In late 2017, lacking staff the Gambian National Security Adviser and UN Senior SSR Advisor agreed that they were fine on their own and declared themselves the project management unit PMU.  This two person PMU served as the collector of international assistance in the name of Gambia SSR.  In 2018 and 2019, the two person PMU received a steady stream of international delegations that later crafted assistance packages based on short term assessments absent government the SSR Strategy and time-sensitive and/or urgent prioritization.

The UN PBSO/PBF-funded SSR Project also prescribed

IAG manages the resource mobilization and coordination of international assistance, including by facilitating bi-weekly meetings among partners to exchange information as well as by updating the matrix every 3 (three) months.

The matrix is based on the prioritized activities emanating from the Gambia SSR Strategy 2020-2024. Accordingly, the matrix is structured to align with the SSR Strategic Priority Areas:

- General nationwide security reforms:

  - Addressing Post-Authoritarian Legacies to Enhance Reforms

  - Developing Overarching Security Governance Legal and Policy Frameworks

  - Reform Activities to Enable Civilian Management and Oversight Bodies

  - Reform Imperatives to Address Cross-Cutting Perennial Challenges

- Specific Reform Activities Relating to Individual Security Institutions: Gambia Armed Forces, Gambia Police Force, Gambia Immigration Department, Gambia Prison Service, Gambia Revenue Authority, Gambia Fire and Rescue Service, Drug Law Enforcement Agency – Gambia, and State Intelligence Service.

TECHINAL COMMITTEE COORDINATION MATRIX OF INTERNATIONAL

ASSISTANCE TO THE GAMBIA SSR PROCESS

Color Key For Name of Partner:

| NATIONAL SSR STRATEGY – PRIORITY AREA 1 ADDRESSING POST AUTHORITARIAN LEGACIES TO ENHANCE REFORMS |
| --- |
| Government-endorsed recommendations | SSR area | Target institution(s) | Name of the partner | SSR partners’ project activity committed | Funding (USD) | Start and end date | Progress report | Comments | Focal point |
|  |  | MOI | AU | Workshop on the review of SOP’s, Guidelines to ensure that Rule of Law (ROL) principles and modern practices are embedded in these policies and training material. | 3000 | 1 Day |  |  |  |
|  | UK Advisor to CDS and Service Chiefs. | MOD/GAF | UK |  |  |  |  |  |  |
| NATIONAL SSR STRATEGY – PRIORITY AREA 2 DEVELOPING OVERARCHING SECURITY GOVERNANCE LEGAL AND POLICY FRAMEWORKS |
| Government-endorsed recommendations | SSR area | Target institution(s) | Name of the partner | SSR partners’ project activity committed | Funding (USD) | Start and end date | Progress report | Comments | Focal point |
| To conduct terminal evaluation of the SSR project (hire and pay for consultancy) | Evaluate terminal project and document lessons and best practices | Government implementing partners including ONS | UNDP SSR Team | To conduct an evaluation of the project activity outputs and outcomes and determine “value for money investment” | 30,000 | Q-1 to Q-2 |  |  |  |
|  |  | ONS Security Sector Institutions Ministries | AU | Workshops on Implementation of National and Defence Security Sector Reform Strategy. | 6000 | 3 Days |  |  |  |
|  |  | MOI | AU | Stakeholders meeting of key strategic partners and government rule of law institutions to foster effective collaboration and consensus on the rule of law. | 2500 | 1 DAY |  |  |  |
| Vetting Act | New legislation | Ministry of Justice | DAI / EU | Creation of a Vetting Act / Classification of Information | 20 days consultancy | May – July 2020 |  |  | Chris Jagger |
| Counter Terrorism Act | New legislation | Ministry of Justice | DAI / EU | Creation of a Counter Terrorism Act to support the new CT Strategy | 15 days consultancy | July – Dec 2020 |  |  | Chris Jagger |
| NATIONAL SSR STRATEGY – PRIORITY AREA 3 REFORM ACTIVITIES TO ENABLE CIVILIAN MANAGEMENT AND OVERSIGHT BODIES |
| Government-endorsed recommendations | SSR area | Target institution(s) | Name of the partner | SSR partners’ project activity committed | Funding (USD) | Start and end date | Progress report | Comments | Focal point |
| To organise 1 day workshop on capacity building for advocacy groups on HR, and gender in relation to SSR To facilitate dialogues of rights and women’s groups to promote their advocacy and outreach work | Strengthen civilian management and oversight of SSR | Advocacy groups, HR and gender-responsive CSOs | UNDP SSR Team | To promote empowerment and capacity of oversight bodies on SSR | 13,000 | Q-1 to Q-4 |  |  |  |
|  | Security Vetting | All | DAI / EU | Mentoring the establishment of a Security Vetting Agency |  | Jan – Dec 2020 |  |  |  |
| To provide support to regular meeting of the SSR Partners Group and the SSR focal persons To support the NSA in holding coordination meetings with government’s International SSR partners To hold regular meetings at the national technical level of SSR International partners and SSR Experts and support an SSR IAG Retreat to review support strategies on SSR To support the design of a national coordination matrix, programmatic framework and SSR expert advisory to ONS; includes consultancy contract of an international expert | Support to enhance coordination of partners | SSR Partners and Impementation partners | UNDP SSR Team | Enhanced coordination, collaboration and partnerships on SSR support | 50,000 | Q-1 to Q2 |  |  |  |
|  |  | ONS NA GAF MOD MOF | AU | Seminar on Parliamentary oversight of Armed Forces between MoD, GAF and relevant civilian institutions such as the National Assembly | 2500 | 1 Day |  |  |  |
|  |  | ONS All security sector Institutions MOD MOI MOF NA | AU | Seminar on civil oversight for security sector institutions | 24000 | 3 Days |  |  |  |
| NATIONAL SSR STRATEGY – PRIORITY AREA 4 REFORM IMPERATIVES TO ADDRESS CROSSCUTTING PERENNIAL CHALLENGES |
| Government-endorsed recommendations | SSR area | Target institution(s) | Name of the partner | SSR partners’ project activity committed | Funding (USD) | Start and end date | Progress report | Comments | Focal point |
| To engage a Gender Caravan to conduct country-wide tour and sensitize on SSR and Gender -Collaborate with NCCE to conduct a nation-wide outreach activity to inform on gender-responsive SSR To visit 4 Primary/Secondary Schools in 4 regions (one each) to sensitize on SSR, Gender and Civic Education | Mainstreaming gender in SSR | all the 8 security institutions and in the rural areas | UNDP SSR Project | To enhance and promote gender-responsive SSR | 10.000 | Q-1 to Q-4 |  |  |  |
|  |  | NHRC | AU | Seminar on building the capacity of the National Human Rights Commission (NHRC) Members on the rights of vulnerable groups. | 3500 | 1 Day |  |  |  |
|  |  | NHRC | AU | Seminar on the role of National Human Rights Commissions in Transitional Justice Processes | 3500 | 1 Day |  |  |  |
|  |  | ALL | AU | Seminar on sustainable peace in The Gambia | 26000 | 3 Days |  |  |  |
|  | Counter Terrorism Strategy | All institutions | DAI / EU | The development of a whole society Counter Terrorism Strategy . 7 Workshops planned. |  | May 2020 – Dec 2020 |  |  |  |
|  | Simulations Exercises | All institutions | DAI / EU | Multi-agency working / crisis response – Counter Terrorism focus. 7 Simulations planned. |  | May 2020 – Dec 2020 |  |  |  |
| NATIONAL SSR STRATEGY – PRIORITY AREA 5 SPECIFIC REFORM ACTIVITIES RELATING TO INDIVIDUAL SECURITY INSTITUTION |
| Government-endorsed recommendations | SSR area | Target institution(s) | Name of the partner | SSR partners’ project activity committed | Funding (USD) | Start and end date | Progress report | Comments | Focal point |
| Invitation for 2 GID officers to regional conference on illicit trafficking of migrants and trafficking of persons | Capacity building | MOI | FRANCE (regional conference in Niamey) | GID |  | 21-23 May 2019 | Completed | 2 off. | Lcl Christophe POPOT |
| Train the unit commanders (PIU, platoon, section commanders) in apprehending a critical operational situation, analyzing the environment and giving proper orders to the troops in order to respond democratically and professionally | Capacity building | MOI | FRANCE | GPF - PIU |  | 10-21 June 2019 | Completed | 40 trainees | Lcl Christophe POPOT |
| Invitation for DLEAG DG to regional conference on cooperation on illicit drugs trafficking | Capacity building | DLEAG | France (regional conference in Bamako) | DLEAG |  | 1-3 October 2019 | Completed | DG | Lcl Christophe POPOT |
| Regional training on installation techniques, software knowledge, hardware maintenance, operational use of special professional devices | Capacity building | DLEAG | France (regional training in Dakar) | DLEAG |  | 6-16 October 2019 | Completed | 2 off. | Lcl Christophe POPOT |
| Invitation and to regional conference on the fight against the smuggling of migrants and trafficking in persons | Capacity building | MOI | FRANCE (regional conference in Niamey) | GID |  | 22-24 October 2019 | Completed | 3 off. | Lcl Christophe POPOT |
| Train operational officers on document security and fraud detection, which would help them to improve their capability in the execution of their functions | Capacity building | MOI | FRANCE | GID |  | 11-15 November 2019 | Completed | 20 trainees | Lcl Christophe POPOT |
| Training equipment to be delivered to the GID academy | Capacity building | MOI | FRANCE | GID | 3 300 USD | 15 November 2019 | Completed |  | Lcl Christophe POPOT |
| Train a fully operational PIU unit on command, management and crowd control tactics | Capacity building | MOI | FRANCE | GPF - PIU |  | April 2020 | To be completed | 100 trainees | Lcl Christophe POPOT |
| Professional tools for mechanic workshop | Capacity building | MOI - MOD | FRANCE | GPF – PIU / State Guard Battalion | 1 500 USD | April 2020 | To be completed |  | Lcl Christophe POPOT |
| Communication equipment to be delivered to the PIU | Capacity building | MOI | FRANCE | GPF - PIU | 13 200 USD | April 2020 | To be completed |  | Lcl Christophe POPOT |
| Training in Peace keeping Operations as ToT | Capacity building | MOI / MOD | FRANCE (training course to be conducted in Paris) |  |  | 6-20 June 2020 | To be completed | 1 or two off. | Lcl Christophe POPOT |
| Train operational officers on document security and fraud detection, which would help them to improve their capability in the execution of their functions | Capacity building | MOI | FRANCE | GID |  | September 2020 | To be completed | 20 trainees | Lcl Christophe POPOT |
| Training as company commander. Candidate must be lieutenant and pass an exam in June 2020 | Capacity building | MOD | FRANCE (training at CAOG academy in Dakar) | RNG |  | September 2020 – June 2021 | To be completed | 1 off. Must pass probation exam | Lcl Christophe POPOT |
|  |  | security institutions, Oversight bodies, ONS and Finance | AU | Training Program for Security Sector Planners on the Planning and Budgeting Process. | 6250 | 1 Day |  |  |  |
|  |  | MOD GAF PMO | AU | Workshop for Validation/Assessment of the draft structure of MoD. | 2500 | 1 Day |  |  |  |
|  |  | GAF | AU | CIMIIC workshop with GAF Officers. | 2500 | 1 Day |  |  |  |
|  |  | GAF | AU | Training Program and Battle/Operational Procedures training for Officers. | 2500 | 1 Day |  |  |  |
|  |  | GAF | AU | Support the establishment/Improvement of Operations Rooms at all levels in GAF. | 8000 |  |  |  |  |
|  |  | GAF | AU | Seminar to support the registration of biometrics/Personnel audit and reporting procedures. | 5500 | 2 Days |  |  |  |
|  |  | GAF | AU | Seminar to support the planning for Recruitment/Career progression and Exit. | 3000 | 1 Day |  |  |  |
|  |  | ONS | AU | Assistance to provide additional office space and equipment | 30000 |  |  |  |  |
|  |  | PRISON | AU | Provision of new female block | 80000 |  |  |  |  |
|  |  | NHRC | AU | Support to NHRC | 120000 |  |  |  |  |
| Human Resource Assessment of the Security Institutions |  | GAF, GPF, GID & SIS | DCAF |  |  |  |  |  |  |
| Public perception Survey on SSR and the justice sector |  | Public | DCAF |  |  |  |  |  |  |
| Gender and Security Survey |  | GPF, GAF, GID, GPS, DLEAG, GFRS & MOJ | DCAF |  |  |  |  |  |  |
| Capacity Building for the CSOs & the media on SSR |  | CSO & Media | DCAF |  |  |  |  |  |  |
| Capacity Building for the parliamentarians |  | SCDS | DCAF |  |  |  |  |  |  |
| Study tour to Ghana |  | SCDS | DCAF |  |  |  |  |  |  |
| SSR nationwide roadshow |  | public | DCAF |  |  |  |  |  |  |
| Production of arrest and detention manual |  | GPF | DCAF |  |  |  |  |  |  |
| Review of the SIS Bill |  | SIS | DCAF |  |  |  |  |  |  |
| Review of the security related provisions of the draft constitution |  | CRC | DCAF |  |  |  |  |  |  |
|  | Recruitment Policy | SIS | DAI / EU | Development of a recruitment policy for SIS |  | Feb 2020 – March 2020 |  |  |  |
|  | Training Syllabus | SIS | DAI / EU | Assistance to the SIS Academy in developing a full training syllabus |  | April – June 2020 |  |  |  |
|  | Public Visibility | ONS | DAI / EU | ONS Website |  | Jan 2020 |  |  |  |
|  | UK Advisor to CDS and Service Chiefs. No additional information | GAF | UK |  |  |  |  |  |  |
| Counter-Terrorism Senior Leader Seminar to be hosted in Mauritania as part of Exercise Flintlock. | Capacity Building | GAF | USA | GAF |  | Feb 2020 |  |  | LtCol Bryan Wilson |
| Army Leadership Summit, themed “Tomorrow’s Security Demands Leadership Today.” Successful leadership in complex security environments. | Capacity Building | GAF | USA, the summit to be held in Ethiopia | GAF |  | Feb 2020 |  |  | LtCol Bryan Wilson |
| Improving land forces capacity focusing on military planning and decision making and tactical execution through the United Accord Exercise. | Capacity Building | GAF | USA, exercise hosted in Senegal | GAF |  | June 2020 |  |  | LtCol Bryan Wilson |
| To host a Rule of Law and Military Justice exchange. Areas of will include military discipline, advancement and order by Rule of Law doctrine, societal governance in accordance with Rule of Law principles | Rule of Law, Capacity Building | GAF | USA | GAF | $20,000 | Sep 2020 |  |  | LtCol Bryan Wilson |
| Training GAF Naval forces in counter-trafficking, visit-board-search-seizure, Maritime Operations Center. 25 Gambian sailors participating in a US sponsored regional exercise. | Capacity Building | GAF Navy | USA, but training to be conducted in Dakar, Praia | GAF |  | Mar 2020 |  |  | LtCol Bryan Wilson |

# Text boxes

2020-2024

COORDINATION MATRIX OF INTERNATIONAL ASSISTANCE TO THE GAMBIAN SSR PROCESS

(information sharing on current and future support to the implementation of the Gambian security sector reform (SSR) Strategy.)

USA

UK

ECOWAS

DCAF

France

EU (DAI)

UNDP

AU