## Sheet1
00091991 - Amerindian Development Fund |  |  |  | ANNEX A
Region 1 Scoping Missions
16 April to 2 May 2015
Date | Mission Activity | Village | CDP | Key Findings | Decisions Made/Results Achieved
2015-04-16 | Joint training at Kumaka |  |  | Participants complained of sessions being too long and too boring. | ADF Team 1 agreed that joint training has its benefits. UNDP reiterated the need for the training sessions to be more interactive.
2015-04-17 |  | Koko | Shop | Site visit conducted, location of village shop was next to the scoping mission venue. Budget and workplan were created. | Bank account to be opened, CDP modified to the extension of the village shop to create a meat section. CMT created and trained at the joint training. MCGA signed.
2015-04-18 |  | Mora |  | Site visit conducted for original CDP, a fruit orchard. However, community unsure as to what their CDP should be. Members of CMT absent from public meeting. Poor attendance at the public meeting. Technical person present and input deemed valuable. | Bank account to be opened, public meeting to be rescheduled to 24th April 2015. Community to meet before, discuss and decide on new CDP. MCGA was not signed.
2015-04-19 |  | Santa Rosa | Food Processing | Potential site visit conducted before meeting. however, community unsure of the CDP they want to do and requested a specialist to consult with community on different possible projects before the community can decide on a CDP Project and its feasibility. Technical person present and input deemed valuable. | CDP changed to bakery, public meeting and letter with minutes and attendance list to be sent to MoAA requesting change in CDP. MCGA was not signed. Bank account to be opened.
2015-04-20 | Joint training at Kumaka |  |  | Training sessions to be more interactive. Practical examples and exercises need to be incorporated into all training sessions | CMT from Santa Rosa and Koko trained.
2015-04-21 |  | Parakese | Farming | Majority of villagers indicated that they do not know about FPIC. CDP modified from cassava farming to mixed crops and the potential location of the farm has been changed. The changes in CDP created the need for the CMT members identified to discuss and decide on specific crops. | CMT members to confirm details of CDP, budget to be created, bank account to be opened and MCGA was not signed
2015-04-22 |  | Wallaba | Furniture Shop | Community proactive towards the implemention of their CDP | Bank account to be set up. MCGA signed.
2015-04-23 | Joint training at Parakese |  |  | Participants deem sessions long and boring. UNDP interjected with an exercise on the marketing mix as well as helped with a better explanation of the cash book. | Parakese and Wallaba CMT members trained.
2015-04-24 |  | Mora | Poultry | Attendance at 2nd meeting was still poor. CDP changed to a poultry farm. Senior council was not present at meeting. Site visit conducted | MCGA was not signed. Village does not have a bank account.
2015-04-24 |  | Kamwatta | Aquaculture Pilot Project | See Annex C
2015-04-25 | Political Rally
2015-04-26 |  | Huradiah | Eco-Tourism | 2nd Meeting -Villagers want to change CDP to Resort/chill spot. The issue with land was stated as a matter that needed to be addressed and resolved with documentation and copies are to be sent to MoAA. Estimate for kitchen/restaurant be further worked on to include all possible costs. Members of CMT to be confirmed | Please refer to Ronald Cumberbatch's Report for Huradiah.
2015-04-27 |  | Assakata | Mixed Crop Farm | CDP to include a pond as water supply and a processing building for cassava. | Village has a bank account. MCGA signed
2015-04-28 |  | Warapoka | Cassava | CDP to include a processing plant for cassava. Equipment to be priced | Bank account not opened.
2015-04-29 |  | Santa Cruz | Coffee | Orginal CDP estimated at over $11 million and needed to be changed however, Villagers could not decide on new CDP | CMT Members invited to training despite not having chosen a CDP. Village does not have a bank account
2015-04-30 | Joint training at Warapoka |  |  | Joint Training with Assakata, Warapoka & Santa Cruz.
2015-05-01 |  | Father's Beach | Fish Project | Five (5) persons in attendance at scoping meeting. CDP not confirmed, Senior councillor not present. CMT members not chosen | Villagers to hold a public meeting to confirm details of CDP. Bank account to be opened. CMT members to be chosen
2015-05-02 | Training at Father's Beach |  |  | Training session could not be conducted due to CDP details not confirmed and minimal attendance at scoping meeting.
Prepared By: |  |  | Date:
| ________________________ |  | ______________________
Shonelle Chase-Wishart
`