|  | United Nations Development Programme | JOINT BACK TO OFFICE REPORT (BTOR) Submitted by: Jeannette Fernandez Castro & Stefanie Afonso Date Submitted: 5 May 2019 |
| --- | --- | --- |
| 1. Practice Area: Crisis Bureau, UNDP/ New York 2. Service Line: Disaster Risk Reduction and Recovery for Building Resilience (DRT) |
| Mission Period (incl. of travel days): 14-23 March 2019 |
| Type of Service/Mission Practice Building Country support mission Monitoring | 5. Client(s) n/a |
| 6. Purpose of Mission Country Support mission within the Phase II of the “Building Capacities for Resilient Recovery” (BCRRII) and identify action points to accelerate project implementation | 7. Documents, Materials, Resources from Mission. Action points |
| 8. Mission Member(s) (include consultants if any) Stefanie Afonso, Policy Analyst Jeannette Fernandez Castro, Recovery Specialist | 9. Annexes: PDNA training evaluation form Mission agenda Action points for accelerated implementation |
| 10. Summary of the Mission: The primary objective of the mission was to 1) provide a PDNA training with a case study focused on droughts 2) meet national counterparts and UNDP country office technical team. The training in Cabo Verde was very well received. A dynamic group of 29 people were trained on the PDNA methodology: a specific focus was given to the Human Impact Assessment and the drought assessment, as the country has been facing prolonged drought for the past 2 years on Santiago island. Most participants were from the Cabo Verde Civil Protection, national partner which is implementing the BCRRII. The mission was also an opportunity to meet the technical team on the ground and national government officials. Bottlenecks were identified and action points for the project implementation were identified (Annex 3). A meeting with the World Bank and UNISDR allowed for the identification of possible synergies. The annual report 2018 was shared with the Embassy of Luxembourg, donor of the phase II, and possible interactions with other projects, funded by Luxembourg, will be pursued. |
| 11. Follow-up Action Matrix |
| Actions to be taken | By Whom | Expected Completion Date |
| Details under Annex 2 |  | December 2019 |
| Follow-up on the identified action points on a monthly basis | Stefanie Afonso | December 2019 |
| 12. Distribution List (BTOR sent to): Angelika Planitz, Krishna Vatsa, Rita Missal, |

Annex 1

Summary Report: Post Disaster Needs Assessment Training

Praia – Cabo Verde 18-20 March 2019

PDNA – DRF Training in Cape Verde – Drought Assessment

More time for the training

Bring in delegates from the Ministries and Municipalities

Share materials in advance to get ready and prepare ourselves every day

I would like to participate with the government in an actual assessment, drought is a serious problem in CV

Lessons learnt from other countries

More practical examples and more field work

Use actual data from the country

Conduct more field research

Consider that some people prefer to work individually before sharing findings with a group

In my opinion, all aspects of the training were excellent

Thanks for a great training

Annex 2

Mission agenda

Cabo Verde 21-22 Março 2019

| Data | Hora | Actividade- Encontro institucionais | Objectivos |  |
| --- | --- | --- | --- | --- |
| 21 Março | 8h.30 – 16h30 | Encontro institucionais |  |  |
|  | 8h.15—10.45 | Encontro com Presidente do SNPCB | Encontro sobre a política nacional de Gestão de Riscos de Desastres, principais desafios, prioridades e lacunas Apresentação do funcionamento: desafios e constrangimentos | Confirmado Local SNPCB |
|  | 11h00-12h30 | INMG, DGASP | Conhecer as iniciativas em curso e prioridades para Cabo Verde nesse domínio de intervenção | Confirmado DGASP Local: S Filipe |
|  | 14h00-16h00 | Encontro com CM da Praia | Conhecer os desafios da gestão municipal associada a temática: Principais forças e lacunas Conhecer o programa cidades resilientes | Confirmado Local SNPCB |
|  | 17.30H-18h30 | UniCV- Reitoria | Conhecer as iniciativas em curso e prioridades para Cabo Verde nesse domínio de intervenção | Confirmado Reitoria – plateau |
| 22 Março | Encontro institucionais |  |  |
|  | 8.30-9.45h00 | Encontro com Banco Mundial | Conhecer as iniciativas em curso e prioridades e identificar possibilidades de colaboração | confirmado Escritório NU |
|  | 10h00-11h00 | INGT | Conhecer as iniciativas em curso e prioridades para Cabo Verde nesse domínio de intervenção | Confirmado Local proposto INGT |
|  | 11.15-12.30 | ANMCV | Conhecer as iniciativas em curso e prioridades para Cabo Verde nesse domínio de intervenção | Reconfirmar Escritório NU |
|  | Almoco |  |  |  |
|  | 14h0-14.h45 | Encontro Escritório do UNDP | Restituição da missão Principais prioridades, riscos, oportunidades e constrangimentos para 2019 | Confirmado Com a representante Residente Local NU |
|  | 15h00-16h00 | Encontro com a Embaixada de Luxemburgo | Visita de cortesia., avanço do Projeto e identificação de parcerias |  |
|  | 16h00-17h30 | Encontro com o Ministério da Agricultura e Ambiente (DNA) | Conhecer as estratégias / políticas nacionais na Área do Ambiente e Mudanças Climáticas, Gestão de recursos hídricos, água e saneamento e de solos e capacidade de resposta face a Seca, inundações, tempestades/ furações | Aguarda confirmação novo horário-pela DNA Local a confirmar |
| 23 Março |  | Finalização de missão |  |  |

Annex 3

ACTION POINTS CABO VERDE MISSION MARCH 2019

| Topic | Action Point | Responsible | Deadline |
| --- | --- | --- | --- |
| 2019 Work Plan | Develop a 6-month acceleration plan with clear tasks (who does what?) | CV UNDP together with Proteção Civil | 1st April |
|  | Organize Steering Committee and adopt 2019 workplan | CV UNDP together with Proteção Civil | 1st April |
|  | Launch National Recovery Platform | Council of Minister to issue a composition note | As soon as possible |
|  | Print Estratégia Nacional and Disaster Recovery Framework (DRF) | UNDP CO | As soon as possible |
|  | Organize a 1-day workshop with Recovery Platform and disseminate the law, the DRF and the 2019 Workplan | CV UNDP together with Proteção Civil (Protex) | 15th April |
|  | Discuss with Plataforma how to best share the existing data (or on IDECV) | Protex + Plataforma |  |
|  | Engage with the government and see how the emergency fund could also include a budget post-disaster recovery |  |  |
|  | Create a 1-page on the project, outlining expected results, partners etc. – see the example done for the global project in the annual report 2018 to the gov of Luxembourg |  |  |
|  | Recruitment of National UNV for project | 1 – Stefanie will check the overall budget and see feasibility 2- celeste will see with other projects in Country Office if sharing an UNV (50/50) is a possibility | 1st week of April |
| PDNA Methodology | Share templates and examples from other countries that have done their adaptation of the PDNA methodology | Jeannette | 1st April |
|  | What kind of data is needed to create scenarios and prepare for recovery | Jeannette will share the templates | 2nd April |
|  | Check recenseamento agricultura 2015 to see the data and set-up a meeting with Direcao Geral da Agricultura | Protex + Celeste |  |
|  | Check outcomes and key documents of the Forum Mundial da Agua for any innovations/new technologies that might be implemented at the Cabo Verde level | Protex |  |
|  | Check the data collected in the editions “The MID Atlantic Gateway to the world’s economy” | Protex |  |
| Partnerships/Synergies | Follow-up on Italian NGO to better understand their work at the community level | CV UNDP |  |
|  | UNISDR project “resilient cities”: receive the action plan and see which activities are similar | CV UNDP + Celestino Afonso + Protex |  |
|  | Reach out to UNI-CV again and find out which studies have been done on droughts/floods/recovery/disaster preparedness/climate change mitigation/disaster risk reduction/mobile technologies | Antero |  |
|  | Follow-up with World bank Washington D.C and discuss synergies and technical/financial support | Robert Reid and Stefanie | 2nd April, 10am NY time |
|  | INGT: see if the project can financially support the revision of legal aspects of the national territorial planning | Celeste |  |
|  | INGT is doing a detailed planning in Brava which included a risk mapping – see synergies with DURA and if project can support initiative, especially if recovery/needs indicators included in the mapping | Celeste + Protex |  |
|  | PEDS municipality level: make sure the next 13 plans include DRR and recovery strategy and see if Output 3 of project could financially support it | Celeste + Protex |  |
|  | Look at the 8 existing PEDS plan at the municipal level and how they can be reviewed/updated to include DRR and recovery issues | Protex / support from Jeannette? |  |
|  | UNISDR contact facilitation | Jeannette (with Kenya office?) |  |
|  | Share the latest Development Strategy of the Government of Luxembourg and the Programme Indicatif de Coopération IV (PIC) to better understand the positioning og the government and position DRR/recovery in the PIC V | Stefanie will share documents UNDP Co and Protex will position DRR/recovery portfolio | This week |
| Communication/Knowledge Management/Good practices from other countries | Share some blogs and links to mediums/photo essays done on recovery | Stefanie | 2nd April |
|  | Share some examples on how satellite imagery and mobile technology have been used in recovery preparing and planning + share the list of what kind of imagery is accessible for free/cost free | Stefanie | 2nd April |
|  | Create a national recovery website OR use the Protex website with a page dedicated to recovery | Protex + comm consultant to be recruited |  |
|  | PEDS municipality: write a blog on how the plans have been drafted with the local communities (if confirmed) | Dulce + ANMCV |  |
| World Reconstruction Conference https://www.gfdrr.org/en/WRC4 | Follow up with Capitao Protex if he will be joining the WRC4 – Project can provide DSA for 3 nights | Stefanie | This week |
|  | Share latest agenda and concept note with UNDP CO and Protex | Stefanie | This week |