United Nations Development Programme

Iran

PROJECT DOCUMENT

| Project Title: | Preparation of HCFC Phase-out Management Plan (HPMP) for Iran (Montreal Protocol Multilateral Fund (MLF) Project Numbers: IRA/PHA/56/PRP/188, IRA/REF/57/PRP/193, IRA/SOL/57/PRP/194 and IRA/FOA/57/PRP/195) |
| --- | --- |
| UNDAF Outcome(s): | Outcome 4.1: Global and national environmental concerns and environmentally sensitive development integrated into national development frameworks and implemented through community-based approaches to the sustainable use of natural resources, capacity building, environmental assessments and the removal of financial, economic, legal, institutional and technological barriers. |
| Expected CP Outcome(s): | Global environmental commitments integrated into national development planning and implementation capacity developed |
| Expected Output(s): | HCFC Phase-Out Management Plan (HPMP) for Iran for compliance with Montreal Protocol control targets for HCFC consumption in 2013 and 2015 |
| Executing Entity: | Department of Environment, Iran |
| Implementing Agency: | United Nations Development Programme |

Situation Analysis

1.	Objective

The objective of this project is the preparation of a comprehensive HPMP (Stage-1) for Iran, which will incorporate the strategy and action plan for Iran for compliance with the 2013/2015 control targets for HCFCs, and is targeted for submission to the Executive Committee of the Multilateral Fund, at its 60th Meeting in March/April 2010.

2.	Background

2.1 	Country profile

Iran is located at the edge of the middle east and south Asia with a land area of 1.65 million sq. km and a population of about 66 million (2008) with an estimated GDP per capita of USD 5,700 (2008). The agricultural sector accounts for 11% of GDP, the industry for 44% and the service sector for 45%. The population density is approx. 40 persons per sq km where urban population represents around 68% of the total population.

2.2	ODS phase-out activities in Iran

The table below shows the dates of ratification by Iran of the Montreal Protocol and its amendments:

| Agreement | Ratification | In Force From |
| --- | --- | --- |
| Vienna Convention | 03 October 1990 | December 1990 |
| Montreal Protocol | 03 October 1990 | December 1990 |
| London Amendment | 04 August 1997 | November 1997 |
| Copenhagen Amendment | 04 August 1997 | November 1997 |
| Montreal Amendment | 17 October 2001 | January 2002 |
| Beijing Amendment | Not yet ratified |

Iran’s Country Programme reflecting the national strategy and action plan for controlling ozone depleting substances under the Montreal Protocol was prepared and approved at the 10th Meeting of the Executive Committee of the Multilateral Fund in June 1993. The action plan presented in the Country Programme outlined policies and proposals for ODS reductions through defining ODS use quotas, taxation on ODS and ODS-based products and gradual reduction of ODS imports, supported by technological and financial interventions to ODS users for transitioning to appropriate substitutes. Subsequently, Iran made significant progress in ODS phase-out, complying with the Montreal Protocol control targets, through implementation of technology transfer investment projects, technical assistance, training, institutional strengthening and capacity building.

Iran’s National Phase-out Plan for ODS (NPP) was approved in December 2003. It aimed to eliminate the remaining consumption of 1,658 ODP metric tonnes of Annex-A Group-I substances (CFCs) and 50 ODP metric tonnes of Annex-B Group-II substances (CTC) by 2010 through a multi-year performance-based agreement, aiming to enable Iran to comply with the 2005, 2007 and 2010 control milestones of the Montreal Protocol. Iran has thus far complied with the annual phase-out targets set out in this agreement.

2.3	Evolution of HCFC Phase-out Management Plans

HCFCs, which have Ozone Depleting Potential (ODP) up to 15% of that of CFCs, are also classified as controlled substances under Annex-C, Group-I of the Montreal Protocol. HCFCs therefore, have use restrictions and would eventually have to be phased-out. Initially for developing countries, the scheduled phase-out date for HCFCs was 01 January 2040 with an interim control measure of freezing HCFC production and consumption at 2015 levels, from 01 January 2016.

During the implementation of the CFC phase-out under the Montreal Protocol, HCFCs were approved as interim substitutes for CFCs in many of the projects and activities supported by the Multilateral Fund. Considering the increasing demand for HCFCs, and considering the imminent restrictions on HCFCs, including the 2016 freeze in consumption for Article-5 countries, it was necessary to address the technology and environmental issues arising from HCFC use reductions. Moreover, it was expected that actions to reduce HCFC consumption needed to be initiated sooner rather than later. Recognizing these challenges, the ExCom approved at its 45th Meeting in 2005, funding for UNDP to carry out HCFC surveys in 12 countries, to assess the HCFC consumption and growth trends in these countries. Iran was one of the countries which requested to be a part of this activity. The key result of this survey was establishing the HCFC consumption profiles and projected growth rates in HCFC consumption in various sectors in Iran until 2015. As established in this survey, which was carried out during 2005-2007, Iran does not produce HCFCs and the domestic demand is entirely met through imports. The total imports of HCFCs in Iran during 2005 were 2,114 metric tonnes. At a conservative growth rates, this was projected to reach about 8,293 metric tonnes by 2015. Section 2.4 provides more details.

The XIXth Meeting of the Parties to the Montreal Protocol in September 2007, through its Decision XIX/6, adopted an accelerated phase-out schedule for HCFCs. The first control is the freeze on production and consumption of HCFCs from 01 January 2013, at the Baseline Level (average of 2009 and 2010 consumption levels). The second control step is the reduction of 10% from the Baseline Levels on January 1, 2015. Subsequent control steps are 35% reduction by 2020, 67.5% by 2025, 97.5% by 2030 and complete phase out from January 1 2040. The decision also directed the Executive Committee of the Multilateral Fund to assist Article-5 Parties in preparation of HCFC Phase-out Management Plans (HPMP).

The 54th Meeting of the Executive Committee in April 2008, through Decision 54/39, adopted guidelines for preparation of HPMPs. These guidelines provide an indicative outline and content of the HPMPs, with the following key elements (ExCom Decision 54/39 is attached as Annex-2):

- Adoption of a staged approach for HPMPs within the context of an overarching strategy for HCFC reductions and phase-out as per the adjusted schedule. The HPMP (Stage-1) would focus on compliance with the 2013 freeze and 2015 reduction targets. The subsequent stages would focus on HCFC phase-out in compliance with the future reduction control targets.

- Commitments to achieving the 2013 and 2015 control milestones through performance-based agreements

2.4	HCFC Survey in Iran

The ExCom approved at its 45th Meeting in 2005, funding for UNDP to carry out HCFC surveys in 12 countries, to assess the HCFC consumption and growth trends in these countries. Iran was one of the countries which requested to be a part of this activity. The survey was carried out during 2005 to 2007. The survey focused on data collection and analysis mainly from upstream suppliers of chemicals and equipment, as well as sampling of enterprise level HCFC use patterns.

Iran’s HCFC consumption increased from 240 metric tonnes in 1995 to 2,114 metric tonnes in 2005, signifying a compounded annual growth rate of 24.3%. HCFC-22 and HCFC-141b were the two main HCFCs consumed. HCFC-141b is used as a blowing agent in foam production as a replacement for CFC-11. HCFC-22 is used as a refrigerant in air conditioning and refrigeration systems, especially in comfort air conditioning units, central air conditioning chillers and industrial refrigeration. Since 2001, the HCFC consumption increased from 1,478 metric tonnes to 2,114 metric tonnes in 2005, indicating a more steady growth rate of 7.4% annually.

Based on projected annual growth rates in demand forecasted for HCFCs until 2015 in various sectors, it was estimated that the unconstrained consumption of HCFCs in Iran would reach about 8,293 metric tonnes in 2015. This was expected to lead to additional environmental impacts on ozone depletion as well as on global warming due to the ozone depleting potential and global warming potential of HCFCs.

Strategy

HCFC Phase-out Management Plan for Iran

The Government of Iran has designated UNDP to be the lead agency for the development of the HCFC phase-out management plan in Iran, considering the following:

- The early and pioneering work done by UNDP in HCFCs in several countries and the resultant accumulated experience and expertise with UNDP for specific technical and policy issues pertaining to HCFCs;

- The initial HCFC survey in Iran was carried out by UNDP;

- UNDP is the implementing agency for the Montreal Protocol institutional strengthening project for Iran through which it provides technical and policy assistance on an ongoing basis.

Germany (GTZ), UNIDO and UNEP are designated as cooperating agencies. The Government of Iran has allocated roles to various agencies as tabulated below:

Part-I:	Overarching HPMP Strategy

| Agency | Sectors/Activities | Preparation Funding (US$) |
| --- | --- | --- |
| UNDP | Overall HPMP Strategy as Lead Agency, national-level data analysis and strategy development | 113,750 |
| Germany | Technical assistance (non-investment) in the Servicing Sector and related strategy | 30,000 |
| UNEP | Policy support, information dissemination and awareness and related strategies | 30,000 |

Part-II: Investment Project Preparation for HPMP

| Agency | Sector(s) | Sub-sector(s) | Outputs | Prep. Funding |
| --- | --- | --- | --- | --- |
| UNDP | Air Conditioning | Residential, commercial, industrial and transport air conditioning | Preparation of individual and/or group projects and sector strategy | 85,000 |
|  | Refrigeration | Domestic, commercial, industrial and transport refrigeration |  |  |
|  | Foams | Systems houses |  |  |
|  | Solvents | All |  |  |
| UNIDO | Compressor Mfg. | All | Preparation of individual and/or group projects and sector strategy | 45,000 |
|  | Firefighting | All |  |  |
|  | Foams | Rigid polyurethane foam (SMEs) |  |  |
| Germany | Foams | Rigid polyurethane foam (except SMEs and systems houses) | Preparation of individual and/or group projects and sector strategy | 70,000 |
|  |  | Integral skin polyurethane foam |  |  |
|  |  | XPS/XPE foams |  |  |

In order to assist Iran in the preparation of its HPMP (Stage-1) for compliance with the 2013/2015 targets, UNDP along with the cooperating agencies, submitted requests for funding for HPMP preparation to the 56th and 57th meetings of the Executive Committee which were held respectively in November 2008 and April 2009. The ExCom approved these funding requests for various agencies as the levels indicated above. The total amount approved for UNDP is US$ 198,750 (highlighted parts of the above table), covering preparation of the overarching strategy and sectoral strategies for the sectors and sub-sectors as described above.

The proposed HCFC Phase-out Management Plan (HPMP) for Iran would need to:

- Reflect national context and priorities, national policies and country-drivenness and consequently would need the agreement of the Department of Environment, Ministry of Natural Resources and the Environment to the proposals contained herein;

- Facilitate seamless application of the proposed arrangements to the subsequent implementation stage of the HPMP, once it is approved;

- Draw upon the lessons learnt from functioning of institutional arrangements and operational mechanisms employed for CFC phase-out plans and to the extent possible integrate existing infrastructures;

- Be dynamic and evolving, and to be open for revisions and adaptation as necessary in response to evolving situations

The time available for Article-5 parties including Iran, for meeting the 2013/2015 control targets is quite limited. It is estimated that there would be maximum of about 4 years beginning 2010, to implement activities leading to compliance with the 2013 and 2015 targets. It is therefore considered imperative that the preparation of Iran’s HPMP and its submission to and approval by the Executive Committee is accomplished by mid-2010, so that adequate time as well as technical and financial assistance is available to implement actions for compliance.

HPMP Preparation Process

The preparation of the national HCFC phase-out management plan would involve the following broad activities:

- Consultation meetings for stakeholders (meetings with government agencies for policy review and meetings with industry representatives for sector-level approaches)

- Constituting the national team (recruitment of national expert (s) and project staff)

- Information dissemination and industry interaction (sector-level workshops)

- Data Collection

- Data Analysis

- Draft document preparation

- Stakeholder interactions/consultations (national workshop)

- Finalization of the HPMP (Stage-I) proposal

- Consultation Meetings with Stakeholders

The consultation meetings with government and industry stakeholders will cover review of existing policy and regulatory framework; to obtain commitment and cooperation in providing information; to ensure active participation in the HPMP preparation process and to make recommendations for meeting the 2013/2015 control targets,.

- Constituting the National Team

This would cover recruitment of a project manager and national expert(s) as required. The terms of reference of the project manager and national expert(s) are attached in Annex-3 and Annex-4 respectively.

- Information Dissemination

This would include at the minimum, the following:

- Dissemination of information on HCFC phase-out, particularly alternative technologies, their availability, feasibility, environment impact and costs

- Documentation/reports

- Data Collection

Data on industry profiles, baselines, consumption, etc. will be collected for various HCFC-consuming sectors at enterprise level, through national expert(s). This would include the development of appropriate questionnaires and formats for reporting the information and data collected. The data collected pertaining to date of establishment, Article-5 ownership and exports to non Article-5 countries, would be cross-checked and verified through NOU/DOE whenever required.

- Data Analysis

The data analysis would include the following:

- Present and historical HCFC consumption by enterprise, sector, sub-sector and application,

- List of HCFC users segregated by sector/sub-sector,

- Data on prior conversions from CFCs by sector/sub-sector,

- Projected growth trends and required reductions in HCFC consumption for meeting the 2013 freeze and 2015 reductions, by sector/sub-sector.

- Preparation of draft proposal

Based on the data collected, sector-wise draft proposals containing sector-specific challenges, opportunities and strategies for compliance with the 2013/3015 control targets, would be prepared by the national experts and submitted to NOU and UNDP for review and inputs. UNDP will collate and integrate these sector-wise strategies into a draft national HPMP (Stage-1) proposal, which will be prepared focusing on compliance with the 2013 freeze and 2015 reductions with respect to the baseline (average of 2009 and 2010) levels and would be forwarded to NOU for circulation among national stakeholders.

- Stakeholder Consultations

The draft HPMP (Stage-1) document will be circulated by NOU to the various national stakeholders for comments. In addition, a national stakeholder consultation workshop will be arranged with participation from all national stakeholders. The comments and recommendations of the stakeholders shall be collected and collated by NOU and sent to UNDP for final revisions.

In addition, periodic meetings with partner agencies and stakeholders would be held, ensuring a consultative and consensual process during the preparation of the HPMP (Stage-1).

- Finalization of the HPMP Proposal (Stage-1)

UNDP, as the lead agency will incorporate the required revisions and comments into a final draft HPMP (Stage-1) proposal, in consultation with Iran NOU. The finalized draft proposal will be sent to government for final approval.  Any further revisions, if required, would be done by UNDP.  NOU will then arrange for the final government endorsement and the final HPMP (Stage-1) document would be submitted to MLF by UNDP.

- Time Frame/Monitoring Milestones

Considering the limited timeframe available for 2013 compliance, the HPMP is targeted for submission to the 60th ExCom Meeting in April 2010. This allows for a net period of about 9 months for completing the activities needed for preparation of the HPMP, after taking into consideration the lead time of submission of 14 weeks prior to the ExCom:

| MILESTONE/TIME FRAME (In months) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Constituting the national team |  |  |  |  |  |  |  |  |
| Information dissemination/industry interaction |  |  |  |  |  |  |  |  |  |
| Data collection |  |  |  |  |  |  |  |  |  |
| Data analysis |  |  |  |  |  |  |  |  |  |
| Preparation of draft proposal |  |  |  |  |  |  |  |  |  |
| Stakeholder consultations |  |  |  |  |  |  |  |  |  |
| Finalization and submission |  |  |  |  |  |  |  |  |  |

Results and Resources Framework

The main result expected from this project is the preparation and submission of Iran’s HPMP (Stage-1) document containing the strategy and action plan for compliance with the 2013/2015 control targets for HCFC consumption.

| Applicable Goal (UNDAF): | Outcome 4.1: Global and national environmental concerns and environmentally sensitive development integrated into national development frameworks and implemented through community-based approaches to the sustainable use of natural resources, capacity building, environmental assessments and the removal of financial, economic, legal, institutional and technological barriers. Indicator: Number of national implementation plans developed and integrated into the fifth NDP. |
| --- | --- |
| ATLAS Award ID: | 000 |
| ATLAS Project ID: | 000 |
| INTENDED OUTPUTS | OUTPUT TARGETS FOR 2009 to 2010 | INDICATIVE ACTIVITIES | RESPONSIBLE PARTIES | INPUTS (US$) |
| Output 1: HPMP (Stage-1) proposal prepared Baseline: Need for strategy and action plan for compliance with the 2013/2015 control targets for HCFCs Indicator: Submission of HPMP (Stage 1) proposal | Targets (2009): Establishment of project team Targets (2010): Submission of HPMP (Stage-1) to MLF for approval Follow-up on approval of HPMP (Stage-1) proposal and awareness raising among stakeholders | Project management Technical, financial and operational management. Establishing good partnerships with ongoing projects and stakeholders. Data Collection and Analysis Collection and analysis of data Stakeholder consultation Proposal development and endorsement Information Dissemination | UNDP/NOU/DOE UNDP/NOU/DOE | 148,750 50,000 |

Annual Work Plan

| Award ID | 000XXXXX |
| --- | --- |
| Project ID | 000XXXXX |
| Project Title | Preparation of HCFC Phase-out Management Plan (HPMP) Stage-1 for Iran1 |
| Executing Agency | Department of Environment |
| ATLAS Activity | Responsible Party | Source of Funds | ATLAS Code | ATLAS Budget Description | Budget (US$) |
|  |  |  |  |  | 2009 | 2010 | Total |
| Activity 1: Project Management | UNDP | 63030 | 71200 | International experts | 5,000 | 5,000 | 10,000 |
|  | NOU/DOE | 63030 | 71300 | Technical experts | 30,000 | 15,000 | 45,000 |
|  | NOU/DOE | 63030 | 71400 | Project Manager | 18,000 | 30,000 | 48,000 |
|  | NOU/DOE | 63030 | 71600 | Travel | 10,000 | 20,000 | 30,000 |
|  | NOU/DOE | 63030 | 74500 | Miscellaneous | 5,750 | 5,000 | 10,750 |
|  | NOU/DOE | 63030 | 72800 | IT Equipment | 5,000 | 0 | 5,000 |
| Sub-total | 73,750 | 75,000 | 148,750 |
| Activity 2: Data Collection and Analysis | NOU/DOE | 63030 | 74200 | Promotional materials | 5,000 | 5,000 | 10,000 |
|  | NOU/DOE | 63030 | 74500 | Workshops | 20,000 | 20,000 | 40,000 |
| Sub-total | 25,000 | 25,000 | 50,000 |
| GRAND TOTAL | 98,750 | 100,000 | 198,750 |

Management Arrangements

Execution Modality

The project will be managed in accordance with standard UNDP procedures as support to nationally executed project (N-Ex) by the Government of the Islamic Republic of Iran through its National Ozone Unit, Department of Environment (NOU/DOE). The National Execution modality has been chosen as there is adequate capacity in the Government of Iran to undertake the functions and activities of the project. The UNDP Country Office has ascertained the national capacities during the formulation stage of this project.

UNDP will work closely with the NOU/DOE during the course of project implementation. NOU will be responsible for day-to-day management of project implementation as per Government procedures and in accordance with N-Ex guidelines, recruiting national experts and project staff, procuring equipment, establishing the project board (HPMP Coordination Group) and organizing its meetings, timely and quality preparation of annual and quarterly work plans, facilitating and responding to independent audits, implementing audit action plans, etc. UNDP Iran will be responsible for overseeing project budgets and expenditures, project evaluation and reporting, result-based project monitoring, and organizing independent audits to ensure the proper use of UNDP/MLF funds. Financial transactions, auditing and reporting will be carried out in compliance with UNDP procedures for national execution.

Institutional Framework

The following figure represents the project’s operation with the National and International bodies and agencies (governmental and non-governmental):

Legend

Existing

New

The key element of the proposed institutional arrangements is the formation of an HPMP Coordination Group (HCG) as shown above, which will comprise of main stakeholders from the government and industry to coordinate the implementation of various activities involved in preparation of the HPMP for Iran. The HPMP Coordination Group will perform overall coordination of activities related to the preparation (and at a later stage, implementation) of the HPMP. The HPMP Coordination Group shall meet once every two months for review and coordination of HPMP preparation activities.

Roles and Responsibilities

National Ozone Unit (NOU)/Department of Environment (DOE)

The Department of Environment (DOE) is the designated nodal agency responsible for implementation of the Montreal Protocol in Iran. Within the Department of Environment, the National Ozone Unit, established in 1994, serves as the national focal point for management, coordination and implementation of Montreal Protocol activities in Iran. In 1994, the National Ozone Committee, a high-level inter-ministerial body, was established to oversee the development and implementation of policies for effective implementation of the Montreal Protocol. The National Ozone Committee is constituted with representation from other ministries, such as Industries and Mines, Foreign Affairs, Oil, Commerce, Management and Planning Organization, Customs and also scientific and technical institutions. Iran has consistently sought to develop and implement policies, and within the framework of these policies, appropriate regulations for controlling and eliminating ODS. The NOU regularly seeks the advice of representatives from governmental authorities, NGOs, the private sector and academia. The NOU/DOE will have the following roles and responsibilities in the preparation of the HPMP:

- Act as the convener and chair of the HPMP Coordination Group

- Overall responsibility for monitoring and supervision of activities

- Coordination of activities among various stakeholders

- Coordination of review of policy/regulatory framework among related Government agencies

- Validation of enterprise level, sector level and national level baseline HCFC consumption data

- Facilitate industry consultation

- Communicate and disseminate public information and  conduct awareness/outreach initiatives/programmes

- Review and endorsement of draft and final HPMP document

HPMP Coordination Group

Members

- NOU/DOE (Convener and Chair)

- Implementing Agencies

- Representatives of industry (by sector)

- Representatives of scientific and technical institutions

- National Expert (s) and project staff

Functions

- Overall coordination of implementation in collaboration with DOE

- Periodic review and monitoring/evaluation of progress of activities

- Corrective interventions as and when required

- Evolve consensus on technology and policy issues

- Ensure timely achievement of HPMP preparation milestones

- Review and inputs for draft HPMP

Lead Implementing Agency

UNDP has been designated as the Lead Implementing Agency for preparation of the HPMP for Iran, by NOU/DOE.  The roles and responsibilities of UNDP during the preparation of HPMP (Stage-1) would be as below:

- Recruitment of international consultants, as may be required;

- Support NOU/DOE in ensuring an effective and smooth process in preparation of the sectoral projects/plans/activities and the integrated HPMP (Stage-1);

- Support NOU/DOE in review and endorsement process on the draft sectoral projects/plans/activities and integrated HPMP, for timely finalization and submission to the ExCom;

- Provide assistance with policy, management and technical support to NOU/DOE as and when required

- Assist NOU/DOE in the process of consultations with industries on the technical and logistical aspects of the preparation of the HPMP;

- Assist NOU/DOE and the industries on process of identification and selection of alternative technologies, technology transfer and related incremental costs;

- Work in close cooperation and coordination with NOU/DOE on finalization of the integrated HPMP;

- Submit the integrated HPMP (Stage-1) to the MLF

- Undertake consultations and clarifications with MLF Secretariat on HPMP guidelines and HPMP preparation process to facilitate effective preparation;

- Assist NOU/DOE, in responding to comments on HPMP from MLF/ExCom

Cooperating Agencies

- Prepare sector-level activities (individual/group projects and/or sector plans) with appropriate advice on technical, policy, legislative and operational aspects pertaining to the sector/activities allocated to each agency in accordance with the agreed overall work plan and timelines;

- Coordinate with NOU/DOE and UNDP to ensure adequate information sharing and consistent application of technology choices and policy actions during the preparation of the sectoral-level activities and the integrated HPMP

- Attend and participate in coordination meetings as required during the HPMP preparation process and provide comments on draft integrated HPMP as per the agreed timeframes

Representatives of Industry

The representatives of the industry in the HPMP Coordination Group would be selected from a broad spectrum of industry, ensuring representation to suppliers, manufacturers and end-users of HCFCs and HCFC-containing products. The functions of the industry representatives would be:

- To participate in the HPMP Coordination Group meetings

- To provide inputs on challenges and opportunities related to technology, availability, feasibility and costs of HCFCs and their alternatives

Representatives of Scientific and Technical Institutions

The representatives would be chosen from premier scientific and technical institutions and would be expected to perform the following functions:

- To participate in HPMP Coordination Group meetings

- Provide high quality scientific and technological advice on HCFCs and their alternatives, particularly on their environmental impacts and long term sustainability

- Share latest and cutting-edge technical information on developments related to HCFC alternatives and strategic technical advice for sectoral prioritization based on technology considerations

Project Manager and Technical Experts

The project manager and technical experts would be recruited by the NOU as needed. The technical experts and project manager would work under the supervision of NOU and be primarily responsible for interacting with industry stakeholders, enterprise and sector-level data collection and preliminary data analysis. More detailed terms of reference for the project manager and technical experts are attached as Annex-3 and 4.

Monitoring Framework and Evaluation

Monitoring and Reporting

UNDP Iran will be responsible for financial monitoring and reporting on all disbursements of the programme and will ensure continued reporting to the Government of Iran and Montreal Protocol MLF. Financial disbursements and auditing, as well as the procurement of goods and services, and the recruitment of personnel shall be based on Government procedures in compliance with N-Ex guidelines.

The reporting with respect to the project shall include the following reports:

- Annual Project Progress Report (APR) as per UNDP format to be submitted annually as of project initiation.

- Progress of Implementation of Country Programme (including HCFCs)

- Article 7 ODS Data Report (including HCFCs)

Monitoring will include a continuous and systematic review of the various activities and will be intended to (i) measure input, output, and performance indicators; (ii) provide regular and up-to-date information on the progress towards meeting the overall project objectives; and (iii) alert implementing partners to potential problems in implementation, and propose corrective measures. Milestone review will be undertaken jointly with national counterparts and all concerned stakeholders and beneficiaries.

Quality Management for Results

| Output 1: Preparation of the HPMP (Strategy and action plan for 2013/2015 compliance) |
| --- |
| Activity Result 1 | Project Management | Start Date: July 2009 End Date: December 2010 |
| Purpose | Ensure the smooth technical and operational management of the project and build partnerships with project stakeholders |
| Description | Technical, financial and operational management. Establishment of good partnership with relevant ongoing projects and stakeholders |
| Quality Criteria | Quality Method | Date of Assessment |
| Positive performance of personnel | Positive evaluation of project team | End of first quarter |
| TORs and RFQs issued | Qualified contractors/consultants selected | Second quarter |
| Capacity of stakeholders built | Stakeholder cooperation | Last quarter |
| Activity Result 2 | Data Collection and Analysis | Start Date: Sept 2009 End Date: December 2010 |
| Purpose | Collect the needed information for developing the national strategy and disseminate information on accelerated HCFC phase-out and HCFC alternatives |
| Description | Collection and analysis of data Stakeholder consultation Proposal development and endorsement Information Dissemination |
| Quality Criteria | Quality Method | Date of Assessment |
| Collection of data from reliable sources | Completed questionnaires received | First quarter |
| Analysis of data | HCFC consumption by sector/sub-sectors established | Second quarter |
| Stakeholder consultation meetings held | Stakeholder feedback received | Third quarter |
| Draft HPMP (Stage-1) proposal prepared | Timely endorsement of proposal by Govt. | Last quarter |
| Submission of proposal | Positive feedback from MLF | Last quarter |

Legal Context

For all legal matters, this project document shall be considered as an addendum to the project “Institutional Strengthening for the phase-out of Ozone Depleting Substances under the Montreal Protocol”, which is attached as Appendix-I to this document.

Annexes

Annex-1:	Risk Analysis

Annex-2:	Guidelines for preparation of HPMPs: ExCom Decision 54/39

Annex-3:	Terms of reference for Project Manager

Annex-4:	Terms of reference for Technical Expert(s)

ANNEX-1

Risk Analysis

| No | Description | Date Identified | Type | Impact and Probability (1= low, 5=high) | Countermeasures/ Management Response | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Delay in deliverable submission of recruited national consultants | Project initiation date | Operational | This will affect the project deliverables Impact = 3 Probability = 2 | Regular follow-up on the work of consultants | UNDP/NOU/DOE |
| 2 | Delay in establishing the HPMP Coordination Group (HCG) and its regular and effective meetings | Project initiation date | Operational | Inadequate coordination has adverse impact on timely decision making Impact = 4 Probability = 3 | Early identification and sensitization of stakeholders to the deliverables, advance planning for coordination meetings | UNDP/NOU/DOE |

ANNEX-2

Guidelines for development of HPMPs (Extract of ExCom Decision 54/39)

170. After having considered the revised text submitted by the contact group, the Executive Committee decided to adopt the following guidelines:

- Countries should adopt a staged approach to the implementation of an HCFC phase-out management plan (HPMP), within the framework of their over-arching-strategy;

- As soon as possible and depending on the availability of resources, countries should employ the guidelines herein to develop, in detail, stage one of the HPMPs, which would address how countries would meet the freeze in 2013 and the 10 per cent reduction in 2015, with an estimate of related cost considerations and applying cost guidelines as they were developed;

- The elaboration of stage one of the HPMP and subsequent stages should be developed as follows:

(i)	For countries with consumption in the servicing sector only:

  - To be consistent with existing guidelines for the preparation of RMPs/RMP updates pursuant to decisions 31/48 and 35/57; and, if applicable, with the preparation of TPMPs pursuant to decision 45/54;

  - To contain commitments to achieve the 2013 and 2015 HCFC control measures and include a performance-based system for HPMPs based on the completion of activities in the HPMP to enable the annual release of funding for the HPMP;

(ii) 	For countries with manufacturing sectors using HCFCs, HPMPs should contain a national performance-based phase-out plan (NPP) with one or several substance or sector-based phase-out plans (SPP) consistent with decision 38/65 addressing consumption reduction levels sufficient to achieve the 2013 and 2015 HCFC control measures and provide starting points for aggregate reductions, together with annual reduction targets;

- For countries that choose to implement investment projects in advance of completion of the HPMP:

- The approval of each project should result in a phase-out of HCFCs to count against the consumption identified in the HPMP and no such projects could be approved after 2010 unless they were part of the HPMP;

- If the individual project approach was used, the submission of the first project should provide an indication of how the demonstration projects related to the HPMP and an indication of when the HPMP would be submitted;

- Consideration should be given to providing funding for assistance to include HCFC control measures in legislation, regulations and licensing systems as part of the funding of HPMP preparation as necessary and confirmation of the implementation of the same should be required as a prerequisite for funding implementation of the HPMP;

- In cases where there were multiple implementing agencies in one country, a lead agency should be designated to coordinate the overall development of stage one of the HPMP;

- HPMPs should contain cost information at the time of their submission based on and addressing:

- The most current HCFC cost guidelines at the time of submission;

- Alternative cost scenarios based on different potential cut-off dates for new capacity if a specific cut-off date had not yet been decided, for funding eligibility of manufacturing facilities as specified in decision 53/37(k), as well as the current policy for a 25 July 1995 cut-off date;

- Alternative cost scenarios for the operational and capital costs for second conversions;

- The incremental costs of regulating import and supply to the market of HCFC dependent equipment once proven alternatives were commercially available in the country and describing the benefits to the servicing sector of associated reduced demand;

- Cost and benefit information based on the full range of alternatives considered, and associated ODP and other impacts on the environment including on the climate, taking into account global-warming potential, energy use and other relevant factors;

- Countries and agencies were encouraged to explore potential financial incentives and opportunities for additional resources to maximize the environmental benefits from HPMPs pursuant to paragraph 11(b) of decision XIX/6 of the Nineteenth Meeting of the Parties;

- HPMPs should address:

- The use of institutional arrangements mentioned in decision 53/37(e) and (f);

- The roles and responsibilities of associations of refrigeration technicians and other industry associations and how they could contribute to HCFC phase-out; and

    - HPMPs should, as a minimum, fulfill the data and information requirements, as applicable, listed in the indicative outline for the development of HPMPs, as set out in Annex XIX to the present report.

(Decision 54/39)

ANNEX-3

Terms of Reference for Project Manager

Nature of Work:	Providing managerial for preparation of Iran’s HCFC Phase-out Management Plan

Duration:		18 months

Starting Date: 	Earliest

Location:		Tehran with inland travel in Iran as required

Responsibilities:

The project manager will work under the supervision of the National Project Manager in the NOU and in close coordination with UNDP and would have specific responsibility to carry out the following main tasks:

Programme functions

- Ensuring the efficient operation of the HPMP preparation process

- Assist the NOU in providing oversight and guidance to all field activities in HPMP preparation

- Collaborate with the international experts and local consultants and implementing agencies representatives in HPMP preparation

- Ensure quality preparation and timely delivery of all field progress reports and activities

- Assist NOU in the monitoring and evaluation of the HPMP preparation activities

- Maintain regular follow-up with enterprises in the various HCFC consuming sectors

- Make logistical and administrative arrangements for information dissemination, technical assistance and awareness activities

- Follow up with UNDP on administrative and financial activities

- Maintain records, documents and work plans for monitoring progress

- Organize data and information for easy follow-up

- Compile and research background material for use in discussions and briefing sessions

- Draft correspondence relating to HPMP preparation

- Draft status reports, compile and analyze information, data and statistics on various activities

- Clarify, follow-up and respond to requests for information

Finance and administrative functions

- Analyze and monitor overall financial situation of the project

- Formulate and elaborate budgets for various activities

- Check financial reports and conformity of activities and expenditures with work plans

- Verify availability of funds for project activities

- Recommend and effect necessary budget line changes

- Ensure accuracy of supporting documents, recommending actions

- Reconcile the records of payments with activities and recommend disbursements

- Maintain and update expenditure ledgers

- Report on status of expenditures and alert on shortfalls and over-expenditures.

- Process mandatory and other budget revisions

- Process financial closure of completed activities

- Analyze and reconcile expenditure reports from UNDP and Government and recommend follow-up/remedial actions

Required qualifications and experience:

- Masters degree in management, environment, industrial management or relevant fields

- Minimum 5 years experience in managing environmental projects

- Demonstrated experience in Montreal Protocol activities in Iran preferred

- Knowledge and understanding of the Montreal Protocol programme in Iran and relevant policies and regulations

- Prior experience in working with government departments and international organizations

- Ability to communicate effectively and prepare substantive reports in a clear and concise manner in English

- Ability to work with Windows-based office, internet and email software applications

ANNEX-4

Terms of Reference for Technical Expert(s)

Nature of Work:	Providing technical support for preparation of Iran’s HCFC Phase-out Management Plan

Duration:		18 months

Starting Date:	Earliest

Duty Station:		Tehran with inland travel in Iran as required

Responsibilities:

The technical expert(s) will work under the supervision of the Manager, Iran Ozone Office and in close coordination with UNDP and would have specific responsibility to carry out the following main tasks:

- To interact with various chemical and equipment suppliers/importers and/or their representatives, relevant industry associations and relevant government departments:

- To identify all current manufacturers of HCFC-based products in the Foams (Systems Houses), Refrigeration and Air Conditioning and Solvent manufacturing sectors to maintain continuous contact with these users and maintain an updated list of all such users.

- To investigate the availability, maturity and prices of alternatives to HCFCs for each application in these sectors along with the techno-economic advantages and disadvantages of each alternative.

- To establish patterns of historical and projected unconstrained growth in HCFC consumption in various sectors/sub-sectors until 2015

- To assist NOU and UNDP in establishing an aggregate projected level of HCFC consumption by sector for 2009 and 2010

- With the prior approval of UNDP and NOU, undertake plant visits to selected users and collect enterprise baseline information and other documentation as may be required by UNDP and NOU from the users, in accordance with the pro-forma/questionnaire provided for this purpose. The HCFC consumption data from users shall be collected from 1995 or the date of their establishment, whichever is later.

- Classify the data generated from a) and b) above for these two sectors, as below:

- HCFC consumption by sub-sector and/or application

- List of HCFC users, segregated by sub-sector

- List of HCFC users who previously received assistance under the Montreal Protocol Programme

- List of HCFC users who did not receive assistance under the Montreal Protocol Programme

- Approximate population of HCFC-based equipment segregated by sector

- Collect and compile the following data on HCFCs, segregated by substance at the national level:

- Historical export data preferably from 1995 and segregated by destination countries

- Historical import data preferably from 1995 and segregated by originating countries

- In collaboration with the NOU, to prepare a draft strategy and action plan for each of the two sectors, containing the technological and financial interventions needed, in order for the sector to comply with the 2013/2015 control targets for HCFC consumption

- To assist NOU in or ensuring participation of HCFC users selected for participating in workshops/meetings

- To assist in obtaining any other confirmations, documentation or information from the identified HCFC users in these two sectors as may be required by UNDP and/or NOU from time to time.

- To arrange as required for UNDP designated international experts and/or officials/representatives, meetings with key managerial and technical personnel from the HCFC users in these sectors and for plant visits as required, in line with their mission schedules in the country.

Required qualifications and experience:

- Wide contacts and hands-on experience in the HCFC consuming sectors

- Demonstrated experience in Montreal Protocol activities in Iran preferred

- Knowledge and understanding of the Montreal Protocol programme in Iran and relevant policies and regulations

- Prior experience in working with government departments and/or international organizations preferable

- Ability to prepare substantive reports related to technology and policy in a clear and concise manner in English

- Ability to work with Windows-based office, internet and email software applications

# Footnotes

For official and legal purposes, this project shall be considered a component of the project “Institutional Strengthening for the phase-out of Ozone Depleting Substances under the Montreal Protocol” which is attached as Appendix-I to this document.

# Text boxes

PROJECT SUMMARY

The XIXth Meeting of the Parties to the Montreal Protocol in September 2007, through its Decision XIX/6, adopted an accelerated phase-out schedule for HCFCs. The first control is the freeze on production and consumption of HCFCs from 01 January 2013, at the Baseline Level (average of 2009 and 2010 consumption levels). The second control step is the reduction of 10% from the Baseline Level from 01 January 2015. The decision also directed the Executive Committee of the Multilateral Fund to assist the Parties in preparation of HCFC phase-out Management Plan (HPMP), which is expected to delineate the strategy and action plan of the respective country, for compliance with the 2013/2015 control targets for HCFC consumption. The 54th Meeting of the Executive Committee in April 2008 through Decision 54/39, adopted guidelines for preparation of HCFC phase-out management plans.

This project will cover establishment of the national team and related institutional arrangements, review of existing regulatory and policy framework, information dissemination and industry interaction, data collection on the baseline in each HCFC consuming industrial sector, data analysis, technology selection taking into account climate change impacts, prioritization of sectors for interventions, estimation of incremental costs and associated technical assistance needs and stakeholder consultations. The project will result in the preparation of a comprehensive HPMP (Stage-1) for Iran, which will incorporate the strategy and action plan for Iran for compliance with the 2013/2015 control targets, which is targeted for submission to the Executive Committee of the Multilateral Fund, at its 60th Meeting in March/April 2010.

Programme Period:	2009 - 2010

ATLAS Award ID:

ATLAS Project ID:

Start date:	01 June 2009

End Date:	31 December 2010

Total resources required:		US$ 198,750

Total allocated resources:	US$ 198,750

-MLF	US$ 198,750

Management Arrangements:	N-Ex

Agreed by Government (Department of Environment):

Agreed by Implementing Agency (UNDP):

Department of Environment (DOE)

Implementing & Bilateral Agencies

National Ozone Unit

Focal Point for Montreal Protocol

HPMP Coordination Group (HCG)

Members:	NOU/DOE, Representatives of Industry (by Sector), Representatives of scientific and technical institutions, Implementing Agencies

Technical Experts and Project Manager