# Annual Work Plan (AWP)

Annual Work Plans (AWPs) are prepared every year, on the basis of intended results, strategies, budgets and implementing partners identified in the agency’s CPAP, reflecting achievements and lessons learned of the preceding year.  They set out interventions organized around outcomes, outputs and/or implementing partners (for example, in the form of projects).

AWPs are informed by the annual programme review and should link with the Monitoring and Evaluation Plan in the CPAP. Furthermore, the AWPs are the building blocks for the annual Standard Progress Reports.

# What is the Annual Work Plan (AWP)?  - The Annual Work Plan (AWP) provides detailed activity planning and sets out what will be accomplished during the year for a result or a set of results identified in the CPAP.  The AWP contains

# the expected outputs

# the activities to be carried out towards achievement of the expected outputs

# the time frame for undertaking the planned activities

# those responsible for carrying out the activities, and

# the inputs to be provided for each activity.

# The completion of the activities should lead over time to the achievement of the Country Programme outputs, which in turn contribute to the Country Programme outcomes contained in the CPAP.  The AWP provides the basis for the requisition of inputs (cash, supplies, contracts, travel, personnel) and disbursement of funds to carry out planned activities.

- Who prepares the Annual Work Plan (AWP)? - The agency Country Office and the implementing partner (government or other) jointly prepare the AWP, usually at the beginning of a new intervention or after the annual programme review of the preceding year.  Each year, detailed AWPs are prepared based on the annual review discussions and recommendations.  Once the implementing partners agree on the proposed AWP, it is finalized and signed.

- How to prepare the Annual Work Plan (AWP)? - The AWP comprises the following:

- A cover page – This refers to the relevant UNDAF outcome(s), the Country Programme outcome(s), and Country Programme output(s).  It also includes a narrative section, a table with the name and budget code of the intervention, and a table with the estimated budget.  These remain unchanged, except for the update on resources if necessary, for the duration of the intervention.  The cover page is signed by the implementing partner as well as by the UNDG agency.

- The annual work plan is set out as a table with the following elements:

- The expected CP output(s) that the intervention is expected to contribute to as described in the CPAP.

- For each expected CP output, all related activities during the year covered by the AWP (whether funded or unfunded). Monitoring and Evaluation activities, including evaluations, field monitoring visits, technical backstopping missions, and audits should also be listed. A separate monitoring tool is attached.

- For each activity, the following:

  - Time frame

  - Responsible party

  - Source of funds

  - Budget description

  - Budget amount

# Annual Work Plan 2012

Country: __Iraq_________________

UNDAF Outcome(s):

Outcome #4: By 2014, the state has institutionalized a legal and policy framework responsive to environmental challenges and opportunities in an integrated, inclusive and participatory manner

Expected CP Outcome(s):

Outcome 4: GoI has the institutional framework to develop and implement MDG-based pro-poor, equitable and inclusive socio-economic and environmental policies and strategies.

Expected CP Output(s):

- Progress towards an Iraqi-owned framework for gender segregated data gathering and analysis, climate change indicator definition and monitoring, and organizational and institutional capacity assessment to best prepare Iraq for Climate Change, including Iraq’s reporting requirements for the UNFCCC; an organizational and institutional mapping of actors involved, highlighting capacity gaps.

- A strengthened coordination and reporting mechanism between institutional actors, including the UN country team, that will provide improved and joint action supporting Government of Iraq counterparts identified by Output 1, to be consigned in draft UNDAF Outcome #4 (Environment).

- Design and implementation of a climate change vulnerability and adaptation assessment process (involving stakeholder consultations), and a GHG inventory process, to support UNFCCC Non-Annex I reporting requirements, based on synoptic monitoring of climate change indicators, forecasting, climate change impact assessment, and monitoring of greenhouse gas (GHG) emissions and sinks in various sectors.

- Strengthened capacity in GoI (principally Ministry of Environment) to develop and implement a climate change communication strategy; implementation of a pilot public and government awareness campaign that promotes practical climate change mitigation and adaptation measures throughout Iraq.

Implementing partner: UNEP______________________

Other Partners: Ministry of Environment; Prime Ministers Advisory Council, Ministry of Foreign Affairs

Agreed by (Implementing Partner): __________________________________________

Agreed by (UNDG Agency):_________________________________________________

## Annual Work Plan

##### Year ____2012______

| EXPECTED CP OUTPUTS and indicators including annual targets | PLANNED ACTIVITIES List all activities including M&E to be undertaken during the year towards stated CP outputs | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount US$ |
| Preparatory Assistance to the Government of Iraq on Climate Change Adaptation and Mitigation Baseline: The organizational and institutional capacity of the GoI to collect and analyze gender segregated data, and translate into human rights based adaptation and mitigation policies and strategies, and activities remains weak. Indicators: A national environmental strategy is in place, and an activity plan is developed; A gender - environment approach is piloted Environmental and natural resource management issues with transboundary dimensions are translated into defined support programmes Clean Development Clean Development Mechanisms and Renewable Energy strategy framework is in place Targets 2012: A programme document for organizational development support for MoEnv has been submitted and financed, and a project has started; A pilot activity for women and environment has been formulated; Support activities for the management of the Euphrates and Tigris, Marshlands and Sandstorms have been identified and formulated; CDM pilot activities have been identified and MoEnv is aware and active on these activities | 1.0 Progress towards an Iraqi-owned framework for gender segregated data gathering and analysis, climate change indicator definition and monitoring, and organizational and institutional capacity assessment to best prepare Iraq for Climate Change, including Iraq’s reporting requirements for the UNFCCC; an organizational and institutional mapping of actors involved, highlighting capacity gaps |  |  |  |  |  |  |  |  |
|  | 1.1 National Environment Strategy and Action Plan |  |  |  |  |  |  |  |  |
|  | 1.1.1 3rd authors meeting (AMM) |  |  |  |  | UNDP | TRAC |  | 20,000.00 |
|  | 1.1.2 Validation workshop (ERB) |  |  |  |  | UNDP | TRAC |  | 40,000.00 |
|  | 1.1.3 preparation main project |  |  |  |  | UNDP | TRAC |  | 0.00 |
|  | 1.1.4 main project |  |  |  |  | UNDP | Tbd |  | 0.00 |
|  | 1.1.5 communication strategy |  |  |  |  | UNDP | Tbd |  | 0.00 |
|  | 1.2 Gender |  |  |  |  |  |  |  |  |
|  | 1.2.1 Draft concept note |  |  |  |  | UNDP | TRAC |  | 10,000.00 |
|  | 1.2.2 Informers workshop |  |  |  |  | UNDP | TRAC |  | 20,000.00 |
|  | 1.2.3 Baseline establishment and draft pilot |  |  |  |  | UNDP | TRAC |  | 10,000.00 |
|  | 1.2.4 Fundraising |  |  |  |  | UNDP | TRAC |  | 0.00 |
|  | 1.2.5. Support to the 8 March Women’s day |  |  |  |  | UNDP | TRAC |  | 10,000.00 |
|  | 2.0 A strengthened coordination and reporting mechanism between institutional actors, including the UN country team, that will provide improved and joint action supporting Government of Iraq counterparts identified by Output 1, to be consigned in draft UNDAF Outcome #4 (Environment). |  |  |  |  |  |  |  |  |
|  | 2.1 Transboundary |  |  |  |  |  |  |  |  |
|  | 2.1.1 Make ToR for E-T basin institute |  |  |  |  | UNDP | TRAC |  | 0.00 |
|  | 2.1.3 Training legal(intnl) |  |  |  |  | UNDP | TRAC |  | 20,000.00 |
|  | 2.1.4 Advice |  |  |  |  | UNDP | UNDP WGP |  | 50,000.00 |
|  | 2.1.5 Draft programme document |  |  |  |  | UNDP | TRAC |  | 10,000.00 |
|  | 2.1.6 Main project |  |  |  |  | UNDP | Tbd |  | 0.00 |
|  | 2.2.Marshlands |  |  |  |  |  |  |  |  |
|  | Seminars |  |  |  |  | UNDP | TRAC |  | 12,000.00 |
|  | 2.3 Sandstorms |  |  |  |  |  |  |  |  |
|  | 2.3.1 Symposium |  |  |  |  | UNDP | TRAC |  | 4,000.00 |
|  | 2.3.2 Travel Iran |  |  |  |  | UNDP | TRAC |  | 4,500.00 |
|  | 2.3.3 Draft project document and fund raise |  |  |  |  | UNDP | TRAC |  | 10,000.00 |
|  | 2.3.4 main project |  |  |  |  | UNDP | Tbd |  | 0.00 |
|  | 3.0 Design and implementation of a climate change vulnerability and adaptation assessment process (involving stakeholder consultations), and a GHG inventory process, to support UNFCCC Non-Annex I reporting requirements, based on synoptic monitoring of climate change indicators, forecasting, climate change impact assessment, and monitoring of greenhouse gas (GHG) emissions and sinks in various sectors. |  |  |  |  |  |  |  |  |
|  | 3.1 CDM and RE |  |  |  |  |  |  |  |  |
|  | 3.1.1 CDM workshops and support |  |  |  |  | UNEP | TRAC |  | 45,000.00 |
|  | 3.1.2 Draft project document and fund raise |  |  |  |  | UNEP/ UNDP | TRAC |  | 15,000.00 |
|  | 3.1.3 main project |  |  |  |  | UNEP/ UNDP | Tbd |  | 0.00 |
|  | 4. Strengthened capacity in GoI (principally Ministry of Environment) to develop and implement a climate change communication strategy; implementation of a pilot public and government awareness campaign that promotes practical climate change mitigation and adaptation measures throughout Iraq. |  |  |  |  | UNDP | Tbd |  | 0.00 |
|  | 5. Project Support |  |  |  |  |  |  |  |  |
|  | Project management |  |  |  |  | UNDP | TRAC |  | 42,000.00 |
|  | Common premises |  |  |  |  | UNDP | TRAC |  | 25,000.00 |
|  | Communication |  |  |  |  | UNDP | TRAC |  | 30,000.00 |
|  | M&E |  |  |  |  | UNDP |  |  | 4,000 |
|  | Security |  |  |  |  | UNDP |  |  | 8,000 |
| TOTAL |  |  |  |  |  |  |  |  | 416,500.00 |
| TOTAL WGP |  |  |  |  |  |  |  |  | 50,000.00 |
| TOTAL TRAC |  |  |  |  |  |  |  |  | 366,500.00 |
| TOTAL (other) |  |  |  |  |  |  |  |  | 0.00 |

# The Annual Work Plan (AWP) Monitoring Tool							Year__2012_____

# CP Component______________________

Implementing Partner ________________

| EXPECTED CP OUTPUTS AND INDICATORS INCLUDING ANNUAL TARGETS | PLANNED ACTIVITIES List all the activities including monitoring and evaluation activities to be undertaken during the year towards stated CP outputs | EXPENDITURES List actual expenditures against activities completed | RESULTS OF ACTIVITIES For each activity, state the results of the activity | PROGRESS TOWARDS ACHIEVING CP OUTPUTS Using data on annual indicator targets, state progress towards achieving the CP outputs. Where relevant, comment on factors that facilitated and/or constrained achievement of results including: Whether risks and assumptions as identified in the CP M&E Framework materialized or whether new risks emerged Internal factors such as timing of inputs and activities, quality of products and services, coordination and/or other management issues |
| --- | --- | --- | --- | --- |
| OUTPUT 1: Progress towards an Iraqi-owned framework for gender segregated data gathering and analysis, climate change indicator definition and monitoring, and organizational and institutional capacity assessment to best prepare Iraq for Climate Change, including Iraq’s reporting requirements for the UNFCCC; an organizational and institutional mapping of actors involved, highlighting capacity gaps INDICATOR 1.1 WITH TARGET FOR THE YEAR: A national environmental strategy is in place, and an activity plan is developed by the end of 2012; INDICATOR 1.2 WITH TARGET FOR THE YEAR: A gender - environment approach is piloted in 2012 | 1.1 National Environment Strategy and Action Plan |  |  |  |
|  | 1.1.1 3rd authors meeting (AMM) |  | Final documents for the NESAP are prepared |  |
|  | 1.1.2 Validation workshop (ERB) |  | The NESAP has been approved by Ministry, parliament and stakeholders |  |
|  | 1.1.3 preparation main project |  | A project document has been prepared, and funds have been raised |  |
|  | 1.1.4 main project |  | The organizational development project for the MoEnv has started |  |
|  | 1.1.5 communication strategy, including World Environment Day, 5 June |  | A communication strategy framework for the Ministry of Environment has been established |  |
|  | 1.2 Gender |  |  |  |
|  | 1.2.1 Draft concept note |  | A concept note on gender and environment has been drafted |  |
|  | 1.2.2 Informers workshop |  | Informers on gender and environment have explored the concept and adjusted according to insights |  |
|  | 1.2.3 Baseline establishment and draft pilot |  | A baseline on gender and environment has been established |  |
|  | 1.2.4 Fundraising |  | Funds for a pilot project have been raised |  |
|  | 1.2.5. Support to the 8 March Women’s day |  | Support is rendered to the Womens’ Day events |  |
| OUTPUT 2: 2.0 A strengthened coordination and reporting mechanism between institutional actors, including the UN country team, that will provide improved and joint action supporting Government of Iraq counterparts identified by Output 1, to be consigned in draft UNDAF Outcome #4 (Environment). INDICATOR 2.1 WITH TARGET FOR THE YEAR: Support activities for the management of the Euphrates and Tigris, Marshlands and Sandstorms have been identified and formulated, leading to pilot projects at the end of 2012; | 2.1 Transboundary |  |  |  |
|  | 2.1.1 Make ToR for E-T basin institute |  | Terms of Reference for E-T basin institute delivered to PMAC and MoFA |  |
|  | 2.1.2 Modeling workshop |  | A workshop on ‘gaming’ river basin models deleiverd |  |
|  | 2.1.3 Training legal(intnl) |  | A training on the legal dimensions of river basin management held |  |
|  | 2.1.4 Advice |  | Advice is delivered on process, and actions |  |
|  | 2.1.5 Draft programme document |  | A project document is drafted and submitted for funding |  |
|  | 2.1.6 Main project |  | The transboundary support project has started |  |
|  | 2.2.Marshlands |  |  |  |
|  | Seminars |  | 2 seminars are held on the marshlands in collaboration with the UNCT |  |
|  | 2.3 Sandstorms |  |  |  |
|  | 2.3.1 Symposium |  | A regional symposium on sandstorms is held with UNDP contribution |  |
|  | 2.3.2 Travel Iran |  | A scoping and exchange visit is made with the Iranian committee for environment |  |
|  | 2.3.3 Draft project document and fund raise |  | A project document is drafted and submitted for funding |  |
|  | 2.3.4 main project |  | A pilot project on mitigation of sandstorms is started |  |
| OUTPUT 3: 3.0 Design and implementation of a climate change vulnerability and adaptation assessment process (involving stakeholder consultations), and a GHG inventory process, to support UNFCCC Non-Annex I reporting requirements, based on synoptic monitoring of climate change indicators, forecasting, climate change impact assessment, and monitoring of greenhouse gas (GHG) emissions and sinks in various sectors. INDICATOR 3.1 WITH TARGET FOR THE YEAR: CDM pilot activities have been identified and MoEnv is aware and active on these activities | 3.1 CDM and RE |  |  |  |
|  | 3.1.1 CDM workshops and support |  | Capacity building workshops on CDM have been held with MoEnv |  |
|  | 3.1.2 Draft project document and fund raise |  | A pilot project document has been drafted and submitted for funding |  |
|  | 3.1.3 main project |  | A pilot project on mitigation and CDM is started |  |
| OUTPUT 4: 4. Strengthened capacity in GoI (principally Ministry of Environment) to develop and implement a climate change communication strategy; implementation of a pilot public and government awareness campaign that promotes practical climate change mitigation and adaptation measures throughout Iraq. INDICATOR 2.1WITH TARGET FOR THE YEAR: | Activities have been moved to output 1 and 5 |  |  |  |
| OUTPUT 5: Project support | 5.1 Project management |  | Project assistant and a project assistant are active in 2012 |  |
|  | 5.2 Common premises |  | Working space available for 2 persons |  |
|  | 5.3 Communication |  | Publication material produced and WED (5 June) supported |  |
|  | 5.4 M&E |  | Monitoring and evaluation done |  |
|  | 5.5 Security |  | Security guaranteed |  |

OUTPUT 1: Progress towards an Iraqi-owned framework for gender segregated data gathering and analysis, climate change indicator definition and monitoring, and organizational and institutional capacity assessment to best prepare Iraq for Climate Change, including Iraq’s reporting requirements for the UNFCCC; an organizational and institutional mapping of actors involved, highlighting capacity gaps INDICATOR 1.1 WITH TARGET FOR THE YEAR: A national environmental strategy is in place, and an activity plan is developed by the end of 2012; INDICATOR 1.2 WITH TARGET FOR THE YEAR: A gender - environment approach is piloted in 2012

ACTIVITIES 2012

1.1 National Environment Strategy and Action Plan

1.1.1 3rd authors meeting (AMM)

1.1.2 Validation workshop (ERB)

1.1.3 preparation main project

1.1.4 main project

1.1.5 communication strategy, including World Environment Day, 5 June

1.2 Gender

1.2.1 Draft concept note

1.2.2 Informers workshop

1.2.3 Baseline establishment and draft pilot

1.2.4 Fundraising

1.2.5. Support to the 8 March Women’s day

PARTNERS

Ministry of Environment; UNEP, WHO

DESCRIPTION

National Environmental Strategy This activity envisions the finalization of a preparatory support activity started in 2011. The Ministry of Environment requested and received assistance to develop a National Environmental Strategy and Action Plan. Senior consultants were engaged who assisted the ministry in developing the required documents. In order to implement the strategy, the Ministry requested also UNDP and UNEP’s support to develop an Organizational Development project. This project document will be finalized and will be submitted to the US Department of State for funding in the first quarter of 2012. A communication strategy has been included within the envisioned programme, and UNDP, UNEP and MoEnv expect to contribute in the celebration of the World Environment Day on 5 June 2012 Gender A concept paper is drafted that addresses the establishment of a baseline situation of women in Iraq in relation to their greatest challenges on environmental indicators. In addition a small pilot activity will be formulated that can create awareness with government and the public based on the strength and particular situation of women in the Iraqi society for submission for funding.

BUDGET 2012: 110,000 US$

OUTPUT 2: A strengthened coordination and reporting mechanism between institutional actors, including the UN country team, that will provide improved and joint action supporting Government of Iraq counterparts identified by Output 1, to be consigned in draft UNDAF Outcome #4 (Environment). INDICATOR 2.1 WITH TARGET FOR THE YEAR: Support activities for the management of the Euphrates and Tigris, Marshlands and Sandstorms have been identified and formulated, leading to pilot projects at the end of 2012;

ACTIVITIES 2012

2.1 Transboundary

2.1.1 Make ToR for E-T basin institute

2.1.2 Modeling workshop

2.1.3 Training legal(intnl)

2.1.4 Advice

2.1.5 Draft programme document

2.1.6 Main project

2.2.Marshlands

Seminars

2.3 Sandstorms

2.3.1 Symposium

2.3.2 Travel Iran

2.3.3 Draft project document and fund raise

2.3.4 main project

PARTNERS

Ministry of Foreign Affairs, Ministry of Water Resources, PMAC, Ministry of Environment, Iraq UNCT, Iraq international partners

DESCRIPTION

2.1 Support to GoI on developing a negotiation strategy for the riparian The planned activities in 2012 build on the achievements of 2011. The achievements broadly were: awareness raising on the challenges the E-T riparian is facing, the construction of rapport with the key Iraqi institutions, and the development of a strategy to address the knowledge gap. UNDP received another Note Verbale in December 2012 from the Ministry of Foreign Affairs in which an affirmation was given on the capacity building work started in 2011, and a request for continuation of this work. The following indicative results are given for 2012: A terms of reference and possibly a profile development is provided to MoFA for the establishment of a E-T Core Team and knowledge institute that will support negotiations. In addition a number of technical workshops will be held to inform identified persons of the Core Team on gaming the watershed models, on the legal regime governing the Euphrates and Tigris, and on additional activities to be identified. Upon approval from the GoI, a project document will be drafted and submitted for funding to the GoI and selected donors. Italy and US DoS have showed interest in supporting this.

2.2 Support to the GoI on developing a development policy and strategy for the Iraqi Marshlands In 2011 a conference was held in Basra, led by the RR that united key stakeholders and which explored options to come to a common strategy to address the challenges the marshlands face. The disappearance of the mandated State Ministry of the Marshlands created a vacuum that as yet has not been filled. In 2011 in a meeting with the leading UNCT members the RR accepted to hold a meeting in Baghdad for key stakeholders on national level to further develop a common policy and strategy for the marshlands. It is expected that UNDP will actively contribute in UNCT organized seminars in 2012 that address the need for a common policy on the marshlands

2.3 Support to the GoI on developing a mitigation strategy on sandstorms In 2011 the Government of Iran requested the support of UNAMI to address the challenges on the increased occurrence of sandstorms, generated in Iraq. Iran and Iraq collaborate in a number of pilot activities to mitigate sandstorms. UNDP Iraq as lead agency in the Environment Priority working Group, has collaborated closely with UNAMI, UNESCO, FAO and UNEP to intensify the dialogue, and in 2012 a UNCT visit to Iran is planned. The Ministry of Environment being the lead agency for Iraq has started an initiative for a regional symposium on sand storms, to be held in the second quarter of 2012. It is expected that in 2012 UNDP will support the regional symposium, an exchange visit will be done, and a project identified that will pilot innovative ways to mitigate sand storms.

BUDGET 2012: 137,500 US$

OUTPUT 3: Design and implementation of a climate change vulnerability and adaptation assessment process (involving stakeholder consultations), and a GHG inventory process, to support UNFCCC Non-Annex I reporting requirements, based on synoptic monitoring of climate change indicators, forecasting, climate change impact assessment, and monitoring of greenhouse gas (GHG) emissions and sinks in various sectors. INDICATOR 3.1 WITH TARGET FOR THE YEAR: CDM pilot activities have been identified and MoEnv is aware and active on these activities

ACTIVITIES 2012

3.1 CDM and RE

3.1.1 CDM workshops and support

3.1.2 Draft project document and fund raise

3.1.3 main project

PARTNERS

MoEnv and UNEP

DESCRIPTION

3.1 CDM and RE An LoA between UNDP and UNEP has been signed in 2011 to identify and encourage Clean Development Mechanisms initiatives to develop together with the Ministry of Environment. A number of project identification activities have been placed under this agreement.

BUDGET 2012: 60,000 US$

OUTPUT 4: Strengthened capacity in GoI (principally Ministry of Environment) to develop and implement a climate change communication strategy; implementation of a pilot public and government awareness campaign that promotes practical climate change mitigation and adaptation measures throughout Iraq. INDICATOR 2.1WITH TARGET FOR THE YEAR No target set for 2012

ACTIVITIES 2012

No Activities planned in 2012

PARTNERS

DESCRIPTION

BUDGET 2012: 0.00 US$

OUTPUT 5:

ACTIVITIES 2012

5.1 Project management

5.2 Common premises

5.3 Communication

5.4 M&E

5.5 Security

PARTNERS

DESCRIPTION

A Project Officer and a Project Assistant will be working for this project Desk space will be reserved for 2 persons A UNDP Climate Change communication strategy will be developed and implemented UNDP monitoring and evaluation Security is guaranteed

BUDGET 2012: 109,000 US$

# Text boxes

In case where there are more than one implementing partner responsible for an activity, all are listed with corresponding inputs/budget line and amount and sign the AWP.

Narrative

This Action Plan for 2012 builds on the gains made during 2011 in rendering assistance to the Government of Iraq on key issues on environment, climate change and natural resource management.

The gains were the following. The Iraq National Communication programme document was drafted and at the end of 2011 the document was approved by the MinEnv and was submitted to GEF. In addition an organizational scan was held for the MoEnv, and the drafting of a National Environmental Strategy was supported. This initiative will lead to an organizational development support programme in 2012. A programme document was in preparation at the end of 2011.

UNDP Iraq on request of the MoFA supported advice and debates to develop a national strategy for negotiations on the riparian. These activities equally will continue in 2012. In addition the increased occurrence of sandstorms, for which a number of hotspots have been identified in Iraq, has drawn the interest of Iran who, as neighbor and through the prevailing winds has been the recipient of sands generated in Iraq. The Iraqi Marshlands equally have dimensions that cross borders with Iran. UNDP Iraq together with the Iraq UN Country Team has been exploring ways to assist the GoI to improve the management of this unique and fragile habitat.

Estimated annualized budget:	       _______

Allocated resources:		       _______

- Government		_________

- Regular 		_________

- Other:

  - Donor	_________

  - Donor	_________

  - Donor	_________

Unfunded budget:		       _______

Programme Period:		_____2012_____

Programme Component:		_Environment__

Intervention Title:		______________

Budget Code:			______________

Duration:			______________