ACTION SHEET

NATIONAL BIODIVERSITY STRATEGY ACTION PLAN

PSC Meeting of 25 March 2015

Ministry of Water, Land, Environment and Climate Change

| # | ACTION | BY WHOM | DUE DATE | STATUS/COMMENTS |
| --- | --- | --- | --- | --- |
| 1. | Resend the invitation letter and TOR directly to all nominees of the Technical Working Group. | Dione Chambers | 03/26/15 | Feedback was received from the members of the PSC before deadline of Feb. 2. |
| 2. | Send reminder, via email, to Dr. Townsend, advising that his 3 major deliverables are to be submitted no later 30 March 2015. | Dione Chambers | 03/26/15 | Done |
| 3 | Advise the International Advisor of the likelihood of reopening the tender for a Biodiversity Specialist to replace Dr. Townsend, if he fails to submit his deliverables by Monday, 30 March 2015. | Dione Chambers | 03/26/15 | Done |
| 4. | Resend UNDP's NBSAP Inception Workshop presentation document to Mrs. Aarons Morgan. | Dione Chambers |  |  |
| 5. | Continue to follow-up with Mr. Marcus Goffe to find out if he has an interest in serving on the TWG of the NBSAP Project | Chair, NBSAP PSC |  | Done |
| 7. | Review TOR for I Integration and Coordination Specialist and submit comments to Ms. Chambers | NBSAP PSC |  | Deadline for submission of comments is Friday, 27 March 2015 |
| 8. | Send list of key tasks and cost of consultancy for the Integration and Coordination Specialist to the PSC Chair so he may approach Ms. Alicia Hayman on the likelihood of her availability and willingness to avail herself for this activity | Chair, NBSAP PSC |  | Ms. Alicia Hayman has expressed an interest in the Integration and Coordination Specialist Consultancy. The deadline for response to the expression of interest is Monday, 30 March 2015. |
| 9. | Seek clarification from Mrs. Sheries Simpson on the report that is to be produced by the Biodiversity Specialist from his consultation with the Senior Research Officer of the IOJ’s Clearing House Mechanism (CHM) | Dione Chambers |  | Dr. Townsend has advised Ms. Chambers that he has met with Dr. Davis re CHM report. He has not yet advised when he will be submitting this document |
| 10. | Apply the approved changes to Dr. Townsend's work plan and recirculate the document to the members of the PSC. | Dione Chambers |  | International Advisor has approved and signed -off on Biodiversity Specialist Work plan |
| 11. | The Chair asked that the 2nd sentence in Action # 3, from the minutes of 29 January 2015, be clarified. | Dione Chambers | 03/26/15 |  |