United Nations Development Programme

Country: Jordan

PROJECT DOCUMENT

| Project Title: |  |
| --- | --- |
| Strengthen National decision making towards Ratification of the Minamata Convention and build capacity towards implementation of future provisions |  |
| UNDAF Outcome(s): Outcome 1: Growth and development are inclusive and sustainable, incorporating productive capacities that create employment and livelihoods for the poor and excluded. Output 1.3. Solutions developed at national and sub-national levels for sustainable management of natural resources, ecosystem services, chemicals and waste. Indicator 1.3.1: Number of new partnership mechanisms with funding for sustainable management solutions of natural resources, ecosystem services, at national and/or sub-national level, disaggregated by partnership type. |
| UNDP Strategic Plan Environment and Sustainable Development Primary Outcome: Growth and development are inclusive and sustainable, incorporating productive capacities that create employment and livelihoods for the poor and excluded UNDP Strategic Plan Secondary Outcome: Countries are able to reduce the likelihood of conflict, and lower the risk of natural disasters, including from climate change |
| Expected CP Outcome(s): 5) Government and national institutions have operationalized mechanisms to develop and implement strategies and plans targeting key cultural, environmental and disaster risk reduction issues (including a transition to a green economy) at national and sub-national levels (same as UNDAF) |
| Expected CPAP Output (s) 5.2) National institutions are better able to manage integrated ecosystems, cultural and natural heritage in a sustainable and participatory manner 5.4) Government is able to operationalize national green economy action plan in a gender sensitive and inclusive manner Output 2: Key Government and non-Government actors have capacities to undertake gender-sensitive management of natural resources in a climate-resilient manner in targeted governorates |
| Executing Entity/Implementing Partner: Ministry of Environment |  |
| Implementing Entity/Responsible Partners: UNDP |  |

Brief Description

The Government of Jordan represented by the Ministry of Environment signed the MINAMATA’s binding treaty on Mercury and its compounds on 10 October 2013 and ratified the convention on 12 November 2015.

The Minamata Convention on Mercury is a global treaty to protect human health and the environment from the adverse effects of mercury. The major highlights of the Minamata Convention on Mercury include a ban on new mercury mines, the phase-out of existing ones, control measures on air emissions, and the international regulation of the informal sector for artisanal and small-scale gold mining.

The Convention draws attention to a global and ubiquitous metal that, while naturally occurring, has broad uses in everyday objects and is released to the atmosphere, soil and water from a variety of sources. Controlling the anthropogenic releases of mercury throughout its lifecycle has been a key factor in shaping the obligations under the convention.

The project’s objective is to undertake a Mercury Initial Assessment to enable the Government to determine the national requirements and needs for the implememtation of the Minamata Convention and establish a sound foundation to undertake future work towards implementing  convention provisions

Agreed by: Government

Date/Month/Year

Agreed by: United Nations Development Program (UNDP)

Date/Month/Year

Table of Contents

1.	Situation analysis	5

2.	Strategy	6

3.	Gender Dimensions:	8

4.	Project Results Framework: note:	9

5.	Total budget and workplan	14

6.	Management Arrangements	19

7.	Monitoring Framework and Evaluation	20

8.	Legal Context	25

9.	annexes	26

Annex 1: Terms of reference of project involved staff and experts	26

Annex 2 Risk analysis	28

Annex 3: Description of UNDP Country Office Support Services	29

Annex 4: Signed letter of endorsement (LOE)	31

List of acronyms

CSOs/NGOs:  Civil Society Organizations and Non-Governmental Organizations

CP: Country Program

CPAP: Country Programme Action Plan

CPD: Country Programme Document

EA: Enabiling Activity

EU: European Union

GC: Gas Chromatography

GEF: Global Environment Facility

GEF OFP: Global Environment Facility Operational Focal Point

Hg: Mercury

JSMO: Jordan Standards and Metrology Organization

MIA: Mercury Initial Assessment

MCM: Mercury Coordination/Consultation Mechanism

MoEnv: Ministry of Environment

MoH: Ministry of Health

NGOs: Non-Governmental Organizations

RSS: Royal Scientific Society

SBAA: Standard Basic Assistance Agreement

UNDAF: The United Nations Development Action Framework

UNDP: United Nations Development Program

UNDP CO: United Nations Development Program Country Office

UNEP: United Nations Environment Program

UNITAR: United Nations Institute for Training and Research

# Situation analysis

Given the dangers associated with Mercury and its compounds to public health and to the environment. The Government of Jordan represented by its Ministries and other governmental institutions has worked to target mercury and its compounds within their national legislation to reduce its risks; for instance, Mercury and its compounds were regulated and targeted in the lists of restricted chemicals that should be handeled as hazardous waste in order to be disposed in an environmentally sound management.

Ministry of Health encourage purchasing pneumatic and electronic pressure devices to replace mercury devices in all medical equipment tenders. Instructions have been also developed to monitor the mercury emissions resulting from the incineration of medical waste. Additionally, Ministry of Agriculture prevented the import and production of pesticides that contain Mercury according to Rotterdam Convention.

The Directorate of Hazardous Substances and Waste Management at the Ministry of Environment signed a $20K Memorandum of Agreement with UNITAR under which the Ministry is requested to prepare a concise road map that includes the priority actions related to the management of Mercury and its compounds. A technical committee has been established to assess the current situation pertaining to the management of Mercury.

The proposed project is consistent with Jordan’s national development priorities as well as the on-going UN operations as identified by the Country Assessment for Jordan and the United Nations Assistance Framework (UNAF).  Like the UNAF, this project is aligned with the country’s key national environmental and socio-economic plans: the National Agenda 2006-2015 and the Executive Development Programme 2015-2017 (EDP).  This project is also well aligned with the Sustainable Development Goals (SDGs) in general,

# Strategy

The proposed EA and the project framework, including envisaged activities, are entirely in line with the GEF Initial Guidelines for Enabling Activities for the Minamata Convention on Mercury (GEF/C.45/Inf.05).

Project Objective:

The project objective is to undertake a Mercury Initial Assessment to enable the Government to determine the national requirements and needs for the implementation  of the Minamata Convention and establish a sound foundation to undertake future work towards implementing convention provisions

It will do so by implementing 4 components as specified in the GEF guidelines (GEF/C.45/Inf.05 paragraph 19), as well as a fifth component on mainstreaming.

1. Undertake an assessment of legislation and policies in regard to the implementation of Convention provisions of

•	Article 3;

•	Article 5;

•	Article 7 (including legislation and policy to cover formalization, worker health and safety);

•	Article 8 (specifically in regard to relevant national air pollution/emission standards and regulations);

•	Article 9 (specifically in regard to the ability to identify and categorize sources of releases).

The policy and legislative assessment will be undertaken through a review of existing legislation on chemicals management and identification of the gaps prevalent in association to issues of mercury. In addition the legislation review will assess the necessary steps for the establishment of a National Mercury Coordination/Consultation Mechanism.

2. Undertake an initial assessment of Mercury in the following categories:

•	Stocks of mercury and/or mercury compounds and import and export procedures including an assessment of the storage conditions;

•	Supply of mercury, including sources, recycling activities and quantities;

•	Sectors that use mercury and the amount per year, including manufacturing processes, ASGM and mercury added products;

•	Trade in mercury and mercury containing compounds

3. Identify:

•	Emission sources of mercury;

•	Release sources of mercury to land and water.

4. Assess institutional and capacity needs to implement the Convention.

Institutional capacity of governmental institutions and agencies will be assessed to determine the capacity needs and gaps that exist for the implementation of the Convention and propose intervention to strengthen these institutions and capacity. The assessment will also review the systems needed to report to the Convention under article 21.

The institutional capacity gaps identified and the findings of the legislation and policy review will be used to formulate a number of priority actions, which will be included in the Mercury Initial Assessment Report. Proposed actions will be discussed and agreed upon among the key stakeholders mentioned above through several rounds of discussions.

5. Mainstream national Mercury priorities in national policies and plans to raise the importance of Hg priority interventions:

•	Identify national mercury priorities;

•	Assess opportunities for mainstreaming Hg priorities;

•	Mainstream Hg priority interventions in relevant policies/plans.

The project's key stakeholders are identified as follows:

Primary Stakeholders (among others) and their roles and responsibilities relevant to the proposed project:

- Ministry of Environment (MoEnv): Host the focal point for the Minamata Convention; Planning and policy development for implementation of the Minamata Convention; Ensure overall coordination at national level in support of the Minamata Convention, including i) Setting of national targets; ii) Support the Mercury inventory; iii) Monitor levels of contamination in environmental media and quantity of Mercury in products; iv) Coordinate with national partners such as the Ministry of Health and the Ministry of Agriculture to address national priorities related to Mercury phase-out; v) Oversee the environmentally sound disposal of Mercury containing products and materials resulting from phase-out efforts.

- Ministry of Health (MoH): Implement newly developed and adopted regulations in the health sector; Coordinate project components that pertain to the use of Mercury in the health sector; Advocate and increase awareness for the phase-out of Mercury containing devices where cost-effective alternatives exist; and, Provide advice and guidance on best practices for Mercury management in the health sector.

- Ministry of Industry and Trade: Control and support the reduction of Mercury air emissions from a number of industrial sources; Reduce or eliminate the use of Mercury in certain products and industrial processes; and, Support the reduction of Mercury use in other priority sectors.

- Jordan Standards and Metrology Organization (JSMO): Adopting EU regulations with respect to Mercury and its management; Carrying out conformity tests and market surveillance; and, Establishing specifications for the testing of laboratory equipment and their commissioning.

- Ministry of Justice: Legal entity responsible for verification of draft/proposed legislation and ensuring that proposed legislation/amendments are in line with the overall national legislative framework.

- Ministry of Agriculture: Identify and take stock of Mercury-containing agricultural chemicals that might still be present on farms in the form of old stockpiles; Collaborate with local entities on the prioritization of necessary interventions to prevent harmful releases to the environment and exposure to people.

- Royal Scientific Society (RSS): Verification of and preparation of guidance on sampling methods; Provision of sampling materials; Provide laboratory facilities and undertake tests/analysis in accordance with EU standards.

Secondary stakeholders:

- Academic and Professional Organizations: Involved in research programmes related to Mercury and its management.

- Business and Industry Organizations: Involved in various aspects of the proposed project: Private companies/industries responsible for the release of Mercury and production of mercury containing products and/or wastes; (Private) medical facilities making use of Mercury containing medical devices; Service providers involved in waste collection, disposal and treatment; Distributors and retailers of Mercury containing and Mercury-free consumer products; Laboratories for testing and certification; etc.

- Civil Society Organizations and Non-Governmental Organizations (CSOs/NGOs): Collection of data and information on the environmental and health aspects and concerns related to Mercury releases and accumulation in the environment. Dissimation of project results and raising awareness on Mercury issues (health and environment) among local communities and population groups at risk, the general public and decision makers.

# Gender Dimensions:

As mercury is passed on from mother to child, fetuses and children are most susceptible to developmental effects from mercury, the MIA will pay particular attention to assessing national capacity to keep such risk groups safe.

# Project Results Framework: note:

| This project will contribute to achieving the following Country Programme Outcome as defined in CPAP or CPD: Output 2: Key Government and non-Government actors have capacities to undertake gender-sensitive management of natural resources in a climate-resilient manner in targeted governorates |
| --- |
| Country Programme Outcome Indicators: # of strategies and plans developed and implemented for agreed key environment and DRR issues; # of relevant environmental laws reviewed; # of sustained climate change adaptation measures in place at local levels; # of sustained green economy initiatives implemented |
| Primary applicable Key Environment and Sustainable Development Key Result Area (same as that on the cover page, circle one): Support enabling activities and promote their integration into national budgets, planning processes, national and sectoral policies and actions, and global monitoring |
| Applicable GEF Strategic Objective and Program: Develop the enabling conditions, tools and environment to manage harmful chemicals and wastes |
| Applicable GEF Expected Outcomes: Outcome 2.1: Countries have undertaken Minamata Convention initial assessments activities and ratified the Minamata Convention |
| Applicable GEF Outcome Indicators: Indicator 2.1.1: Number and quality of initial assessment activities completed Indicator 2.1.2: Number of ratifications of the Minamata Convention |
|  | Indicator | Baseline | Targets End of Project | Source of verification | Risks and Assumptions |
| Project Objective Undertake a Mercury Initial Assessment (MIA) to enable the Government of Jordan to determine the national requirements and needs for the implementation of the Minamata convention and defining of national priorities for implementation of the convention (equivalent to output in ATLAS) | Initial assessment activities that will contribute to Mercury assessment | No previous Minamata assessment on mercury prepared at national level Limited information on the use of mercury and its compounds and industries that use it in addition to the emissions released from these industries. Limited national resources for the implementation of the Convention Limited information on Minamata convention’s provisions and requirements Limited preparedness to implement convention provisions | Mercury assessment for Jordan completed, public and key stakeholder consultations held, and enabling environment for the implementation of the Minamata convention established and supported A national decision-making structure on Mercury (“Mercury Coordination/Consultation Mechanism (MCM)”) established in line with national capacities and existing structures | Project implementation and technical reports Ministry of Environment reports Ministry of Planning and International Cooperation reports | Assumption: Government agencies will provide access to priority data and analysis. Assumption: Government and non-governmental project partners will be actively engaged in the project |
| Component 1: Enabling environment for the implementation of the Minamata convention. |
| Outcome 1 Establishing a national decision making structure on Mercury. (equivalent to activity in ATLAS) | NO of institutional capacity respond/comply to Minamata provisions Establishment of national decision-making structure on Mercury (“Mercury Coordination/Consultation Mechanism (MCM)”) in line with national capacities and existing structures and practices present in the project countries and where feasible will build/expand on similar structures established in support of other chemicals-related MEAs. | No mandatory identification and reporting on Mercury stocks, compounds and waste streams. No public consultations held on the Minamata Convention and its provisions | Coordination/Consultation Mechanism (MCM)”) established in line with national capacities and existing structures and practices present in the project countries and where feasible will build/expand on similar structures established in support of other chemicals-related MEAs. All stakeholders from public, private sectors and NGOs engaged in the consultation process | Workshop agendas/reports Media events on record Meeting Minutes Draft legal acts on ratification plans Structured questionnaires and/or interviews Project quarterly and progress reports Independent mid-term and final evaluation reports |  |
| Outcome 2 Conducting an assessment of the policy and regulatory framework and institutional capacity needs in regard to the implementation of the Convention’s provisions (equivalent to activity in ATLAS) | review of the structures, institutions and policies and regulations already in place | Limited number of regulatory measures to start controlling Mercury in the country No mandatory identification, and reporting on Mercury stocks, compounds and waste streams. | identifying the required policy and regulatory frame work to implement the Convention |  |  |
| Outcome 3 Raising awareness on the environmental and health impacts of Mercury (equivalent to activity in ATLAS) | Information dissemination campaigns ensure availability of Number of printed and electronic information through workshops and work with media Number of awareness workshops and training sessions conducted. | Significant gaps in knowledge about Mercury associated risks No information products published limited number of workshops held | Raising awareness workshops on the environmental and health impacts of Mercury Information products developed and published National awareness on Minamata provisions and decision making has been increased and public consultations supported |  | Assumption: Professional technical advice is ensured and the quality of information is high Assumption: Project stakeholders are receptive of the information and show interest |
| Outcome 4 Mainstreaming Hg priorities into national policies/plans (equivalent to activity in ATLAS) | Importance of Hg priority interventions at national level raised through mainstreaming in relevant policies/plans |  | National Hg priority interventions (identified in the MIA Report mainstreamed in national policies/plans.) |  |  |
| Component 2: Development of the National Mercury Profile and Mercury Initial Assessment Report. |
| Outcome 1 Building national capacity to under the Mercury Inventory | National Mercury Profile is developed by national technical experts of trained on data collection methodologies, reliability, credibility, data analysis, etc. | Analytical capacity is limited to specialized labs with GC equipment, lacks modern protocols for Mercury identification and skills for the use of such protocols. No assessment conducted to date with regard to Mercury issues, inventories | Capacity building and training conducted to commence the Mercury inventory Identification and quantification of mercury releases is upgraded through the use of UNEP Toolkit | Ministry of Environment reports to GEF/Minamata convention Secretariat Technical reports Workshop agendas/reports Ministry of Foreign Affairs reports/communique to UN depositary | Assumption: Government agencies will provide access to priority data and analysis. Assumption: Government and non-governmental project partners will be actively engaged in the project |
| Outcome 2 Conducting the Mercury Inventory and prepare the National Mercury Profile. | National Mercury Profile, including significant sources of emissions and releases, as well as inventories of mercury and mercury compounds, will be prepared for review, approval and adoption by the MCM. | No national Mercury profile and socio-economic implications of exposure to mercury prepared | Mercury profile and Assessment report drafted and reviewed by stakeholders, and submitted Identification of key sectors, municipalities, communities and other stakeholders affected by or involved with important Mercury sources and/or emissions Mercury Inventory conducted. Development of the National Mercury Profile and Mercury Initial Assessment Report |  |  |
| Outcome 3 Preparing the National MIA Report | The National MIA Report is in place to be used by decision makers | No consultation on priority action and financial resources for interventions taken place Unidentified Structures, institutions, legislation to implement the Convention. Lack of knowledge on barriers that would hinder or prevent implementation of the Convention. Lack of knowledge on the technical and financial needs for implementation of the Convention. | Consultations on socio-economic implications, product substitution, technology transfer, remediation costs and financial resources for intervention held MIA Report prepared for review, approval and adoption by the MCM during a national stakeholder workshop. |  |  |

# Total budget and workplan

| Award ID: | 00096810 | Project ID(s): | 00091779 |
| --- | --- | --- | --- |
| Award Title: | MIA Minamata |
| Business Unit: | JOR10 |
| Project Title: | Jordan: Strengthen National decision making towards Ratification of the Minamata Convention and build capacity towards implementation of future provisions |
| PIMS no | 5633 |
| Implementing Partner (Executing Agency) | Ministry of Environment |
| GEF Outcome/Atlas Activity | Responsible Party/ | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Total (USD) |  |
|  | Implementing Agent |  |  |  |  |  |  |  | Budget Notes |
| OUTCOME 1: | Ministry of Environment | 62000 | GEF | 71200 | International Consultants | 5,000 | 4,500 | 9,500 | 1 |
| Enabling environment for decision-making on the implementation of Minamata convention established. |  |  |  | 71300 | Local Consultants | 20,000 | 14,000 | 34,000 | 2 |
|  |  |  |  | 71600 | Travel | 2,000 | 1,319 | 3,319 | 3 |
|  |  |  |  | 72100 | Contractual Services companies | 1,500 | 1,500 | 3,000 | 4 |
|  |  |  |  | 74500 | Miscellaneous | 1,000 | 1,000 | 2,000 | 5 |
|  |  |  |  |  | Total Outcome 1 | 29,500 | 22,319 | 51,819 |  |
| OUTCOME 2: | Ministry of Environment | 62000 | GEF | 71200 | International Consultants | 6,000 | 11,800 | 17,800 | 6 |
| National Mercury Profile and Mercury Initial Assessment Report development |  |  |  | 71300 | Local Consultants | 30,481 | 32,000 | 62,481 | 7 |
|  |  |  |  | 72100 | Contractual services companies | 5,000 | 3,000 | 8,000 | 8 |
|  |  |  |  | 72400 | Communic & Audio Visual Equip | 700 | 1,000 | 1,700 | 9 |
|  |  |  |  | 74500 | Miscellaneous | 2,000 | 1,000 | 3,000 | 10 |
|  |  |  |  | 71400 | Contractual Services Individuals | 4,000 | 3,000 | 7,000 | 11 |
|  |  |  |  | 74200 | Audio visual and printing prod | 3,000 | 3,000 | 6,000 | 12 |
|  |  |  |  | 71600 | Travel | 5000 | 4,019 | 9,019 | 13 |
|  |  |  |  |  | Total Outcome 2 | 56,181 | 58,819 | 115,000 |  |
| Monitoring and Evaluation | UNDP/Ministry of Environment | 62000 | GEF | 71200 | International Consultants |  | 15,000 | 15,000 | 14 |
|  |  |  |  |  | Total outcome 3 |  | 15,000 | 15,000 |  |
| Project MANAGEMENT UNIT | UNDP/Ministry of Environment | 62000 | GEF | 71300 | Local consultant | 7,500 | 6,000 | 13,500 | 15 |
|  |  | 62000 | GEF | 74598 | Direct project cost | 1,000 | 1,000 | 2,000 | 16 |
|  |  | 62000 | GEF | 74100 | Professional Services – Audit |  | 2,681 | 2,681 | 17 |
|  |  |  |  |  | Total Management | 8,500 | 9,681 | 18,181 |  |
|  |  |  |  | PROJECT TOTAL | 94,181 | 105,819 | 200,000 |  |

| Budget Notes |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | GEF financing for an international technical specialist for technical advisory support |
|  | 2 | GEF financing for local specialist for reviewing regulatory framework and identification of gaps in management of mercury and national taskforce to oversee the implementation of the legal aspects of the project |
|  | 3 | GEF will finance the travel of an international consultant |
|  | 4 | GEF financing for various contractual services, such as meeting expenses , workshops and publications |
|  | 5 | GEF financing Miscellaneous expenses |
|  | 6 | GEF financing for an international technical specialist to support the national level consultations on the data analysis, national mercury profile formulation and priority setting processes for decision-making |
|  | 7 | GEF financing national taskforce and local consultancy to oversee the implementation of the technical aspects of the project. |
|  | 8 | GEF financing for various contractual services such as samples analysis and data registration |
|  | 9 | GEF financing communication and visual equipment |
|  | 10 | GEF financing Miscellaneous expenses e.g meetings expenses, stationary..etc |
|  | 11 | GEF financing for various contractual services (individuals) for technical coordinator. |
|  | 12 | GEF financing Audio visual and printing products |
|  | 13 | GEF will finance the travel of an international and local consultant |
|  | 14 | GEF financing international consultant for the terminal evaluation of the project |
|  | 15 | GEF financing for local consultant Responsible for the overall delivery of the project outputs, activities and results |
|  | 16 | GEF financing various project management cost |
|  | 17 | Audit fees |

| Summary of Funds: |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Amount Year 1 | Amount Year 2 | Amount Year 3 | Amount Year 4 | Total |
|  |  |  |  | GEF | 94,181 | 105,819 | $ | $ | 200,000 |
|  |  |  |  | TOTAL | 94,181 | 105,819 | $ | $ | 200,000 |

| Position Titles | $/ Person days | Estimated Person days | Tasks to be Performed |
| --- | --- | --- | --- |
| For EA Management (60% from PMC and 40% from technical components) | 300 | 75 | Responsible for the overall delivery of the project outputs, activities and results Responsible for planning and reporting as per UNDP standards Undertake the overall management of financial resources |
| Environmental Legal expert | 300 | 45 | Detailed review of regulatory framework and identification of gaps in management of mercury; - Development of specific recommendations on adjustments, amendments required in existing legislation; - Liaise with Ministry of Environment, Minamata focal point and relevant government agencies for development of effective proposals for regulatory framework development. |
| National experts on data collection, organization and analysis | 300 | 200 | Identification of main target areas (sites) and sources for collection of data in accordance with the rapid assessment : i) coal-fired power plants; ii) cement production; iii) mining and other metallurgical activities; iv) mercury mining; v) small-scale gold and silver mining; vi) chloral-alkali production; vii) fluorescent lamps, manometers, thermometers; viii) manufacturing of products containing mercury; and ix) waste (including medical waste) incineration; - Selection of methodology for the collection and analysis of data under each mercury source identified; - Collection of data and analysis; - Review of the rapid assessment of sources and validation (or expansion) of the list in accordance with collected data. |
| For Technical Assistance (from technical components) |
| Technical Coordinator | 300 | 30 | -Review Assessments generated under regulatory analysis and inventory; -Assessment of the impact of project outputs on specific stakeholders and general public; -Development of documentations to support stakeholder consultations as well as public awareness activities |
| International (from technical components) |
| International technical expert | 600 | 53 | UNEP "Toolkit for identification and quantification of mercury releases" - Provision of technical advisory support (with missions) to the local team on the Minamata convention as the new MEA instrument, mercury sources, data organization, collection and validation process in each related sector/sub-sector; - Support to the national level consultations on the data analysis, national mercury profile formulation and priority setting processes for decision-making; - Provision of regulatory advisory support where needed with respect existing international benchmarks - Provision of support to develop and analyze cost related to the implementation of the Convention and description of potential sources of funds, including existing bilateral sources |

# Management Arrangements

The project will be implemented over a period of two years.

The UNDP Country Office (CO) will monitor the implementation of the project, review progress in the realization of the project outputs, and ensure the proper use of UNDP/GEF funds.

The project will be nationally implemented (NIM) by the Ministry of Environment (MoEnv). The MoEnv will have the overall responsibility for achieving the project goal and objectives. The MoEnv will be directly responsible for creating the enabling conditions for implementation of all project activities. The MoEnv will designate a senior official to act as the Project Director (PD). The PD will provide the strategic oversight and guidance to project implementation.

The day-to-day administration of the project will be carried out by a national Project officer (NPO). The NPO will be technically supported by contracted national and international service providers. Recruitment of specialist support services and procurement of any equipment and materials for the project will be done in accordance with relevant recruitment and procurement rules and procedures.

A Project Steering Committee (PSC) will be constituted to serve as the executive decision making body for the project. A task force will be established to oversee the implementation of the technical and legal aspects of the project.

The NPO will produce an Annual Work Plan (AWP) to be approved by the PSC at the beginning of each year. These plans will provide the basis for allocating resources to planned project activities. Once the PSC approves the AWP, this will be sent to the UNDP Programme Specialist Technical Advisor for Montreal Protocol Unit/Chemicals for clearance. Once the AWP is cleared by, it will be sent to the UNDP/GEF Unit in New York for final approval and release of the funding. The NPO will further produce quarterly operational reports and Annual Progress Reports (APR) for review by the PSC, or any other reports at the request of the PSC.  These reports will summarize the progress made by the project versus the expected results, explain any significant variances, detail the necessary adjustments and be the main reporting mechanism for monitoring project activities.

The financial arrangements and procedures for the project are governed by the UNDP rules and regulations for National Implementation Modality (NIM). All procurement and financial transactions will be governed by applicable UNDP regulations under NIM.

# Monitoring Framework and Evaluation

The project will be monitored through the following M& E activities.  The M& E budget is provided in the table below.

Project start:

A Project Inception Workshop will be held within the first 2 months of project start with those with assigned roles in the project organization structure, UNDP country office and where appropriate/feasible regional technical policy and programme advisors as well as other stakeholders.  The Inception Workshop is crucial to building ownership for the project results and to plan the first year annual work plan.

The Inception Workshop should address a number of key issues including:

- Assist all partners to fully understand and take ownership of the project.  Detail the roles, support services and complementary responsibilities of UNDP CO and RCU staff vis à vis the project team.  Discuss the roles, functions, and responsibilities within the project's decision-making structures, including reporting and communication lines, and conflict resolution mechanisms.  The Terms of Reference for project staff will be discussed again as needed.

- Based on the project results framework and the relevant GEF Tracking Tool if appropriate, finalize the first annual work plan.  Review and agree on the indicators, targets and their means of verification, and recheck assumptions and risks.

- Provide a detailed overview of reporting, monitoring and evaluation (M&E) requirements.  The Monitoring and Evaluation work plan and budget should be agreed and scheduled.

- Discuss financial reporting procedures and obligations, and arrangements for annual audit.

- Plan and schedule Project Board meetings.  Roles and responsibilities of all project organisation structures should be clarified and meetings planned.  The first Project Board meeting should be held within the first 12 months following the inception workshop.

An Inception Workshop report is a key reference document and must be prepared and shared with participants to formalize various agreements and plans decided during the meeting.

Quarterly:

- Progress made shall be monitored in the UNDP Enhanced Results Based Managment Platform.

- Based on the initial risk analysis submitted, the risk log shall be regularly updated in ATLAS.  Risks become critical when the impact and probability are high.  Note that for UNDP GEF projects, all financial risks associated with financial instruments such as revolving funds, microfinance schemes, or capitalization of ESCOs are automatically classified as critical on the basis of their innovative nature (high impact and uncertainty due to no previous experience justifies classification as critical).

- Based on the information recorded in Atlas, a Project Progress Reports (PPR) can be generated in the Executive Snapshot.

- Other ATLAS logs can be used to monitor issues, lessons learned etc...  The use of these functions is a key indicator in the UNDP Executive Balanced Scorecard.

Bi-annual progress:

- Status Survey Questionnaires to indicate progress and identify bottlenecks as well as technical support needs will be carried out twice a year.

Periodic Monitoring:

A detailed schedule of project reviews meetings will be developed by the project management, in consultation with project implementation partners and stakeholder representatives and incorporated in the Project Inception Report. Such a schedule will include: (i) tentative time frames for Steering Committee Meetings, (or relevant advisory and/or coordination mechanisms) and (ii) project related Monitoring and Evaluation activities.

Day to day monitoring of implementation progress will be the responsibility of the Project officer based on the project's Annual Work plan and its indicators. The Project Team will inform the UNDP-CO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

Periodic monitoring of implementation progress will be undertaken by the UNDP-CO through quarterly meetings with the project proponent, or more frequently as deemed necessary. This will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

End of Project:

During the last three months, the project team will prepare the Terminal Evaluation. This comprehensive report will be elaborated by an independent evaluator and will summarize the results achieved (objectives, outcomes, outputs), lessons learned, problems met and areas where results may not have been achieved.  It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the project’s results.

Audit clause:

Audit on project will follow UNDP Financial Regulations and Rules and applicable Audit policies.

Learning and knowledge sharing:

Results from the project will be disseminated within and beyond the project intervention zone through existing information sharing networks and forums.

The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

Communications and visibility requirements:

Full compliance is required with UNDP’s Branding Guidelines.  These can be accessed at http://intra.undp.org/coa/branding.shtml, and specific guidelines on UNDP logo use can be accessed at: http://intra.undp.org/branding/useOfLogo.html. Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects needs to be used.  For the avoidance of any doubt, when logo use is required, the UNDP logo needs to be used alongside the GEF logo.   The GEF logo can be accessed at: http://www.thegef.org/gef/GEF_logo.   The UNDP logo can be accessed at http://intra.undp.org/coa/branding.shtml.

Full compliance is also required with the GEF’s Communication and Visibility Guidelines (the “GEF Guidelines”).  The GEF Guidelines can be accessed at: http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf.  Amongst other things, the GEF Guidelines describe when and how the GEF logo needs to be used in project publications, vehicles, supplies and other project equipment.  The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.

Where other agencies and project partners have provided support through co-financing, their branding policies and requirements should be similarly applied.

M& E workplan and budget

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | Project Manager UNDP CO, UNDP GEF | Indicative cost: 10,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | UNDP GEF RTA/Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | Oversight by Project Manager Project team | To be determined as part of the Annual Work Plan's preparation. | Annually and to the definition of annual work plans |
| ARR/PIR | Project manager and team UNDP CO UNDP RTA UNDP EEG | None | Not applicable for EA projects |
| Periodic status/ progress reports | Project manager and team | None | Quarterly |
| Mid-term Evaluation | Project manager and team UNDP CO UNDP RCU External Consultants (i.e. evaluation team) | None | Not applicable for EA projects |
| Final Evaluation | Project manager and team, UNDP CO UNDP RCU External Consultants (i.e. evaluation team) | $15,000 | At least three months before the end of the project |
| Project Terminal Report | Project manager and team UNDP CO local consultant | 0 | At least three months before the end of the project |
| Audit | UNDP CO Project manager and team | US $2,681 | once during project life time |
| Visits to field sites | UNDP CO UNDP RCU (as appropriate) Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses | US$ 27,681 (+/- 5% of total budget) |  |

# Legal Context

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA (or other appropriate governing agreement) and all CPAP provisions apply to this document.  Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner will put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried; as well as assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary.  Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP/GEF hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999).  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document The list can be accessed via:

http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm.

# annexes

## Annex 1: Terms of reference of project involved staff and experts

National Project Officer

Background

The National Project Officer (NPO) will be locally recruited, based on an open competitive process. He/she will be responsible for the overall coordination of the project, including the mobilization of all project inputs, supervision over project staff, consultants and sub-contractors. The NPO will report to the UNDP Environment and climate change Programme Analyst. From the strategic point of view of the project, the NPO will report on a periodic basis to the Project Steering Committee (PSC). Generally he/she will be responsible for meeting government obligations under the project, under the national implementation modality (NIM). The incumbent will perform a liaison role with the Government, UNDP, implementing partners, NGOs and other stakeholders, and maintain close collaboration with any donor agencies supporting project activities.

Duties and Responsibilities

- Supervise and coordinate the project to ensure its results are in accordance with the Project Document;

- Assume primary responsibility for daily project coordination both organizational and substantive matters budgeting, planning and general monitoring of the project;

- Ensure adequate information flow, discussions and feedback among the various stakeholders of the project;

- Ensure adherence to the project’s work plan, prepare revisions of the work plan, if required;

- Assume overall responsibility for the proper handling of logistics related to project workshops and events;

- Prepare, and agree with UNDP and ministry on, terms of reference for national and international consultants and subcontractors;

- Guide the work of consultants and subcontractors and oversee compliance with the agreed work plan;

- Maintain regular contact with UNDP Country Office and the National Project Director on project implementation issues of their respective competence;

- Monitor the expenditures, commitments and balance of funds under the project budget lines, and draft project budget revisions;

- Assume overall responsibility for the meeting financial delivery targets set out in the agreed annual work plans, reporting on project funds and related record keeping;

- Liaise with project partners to ensure their co-financing contributions are provided within the agreed terms;

- Assume overall responsibility for reporting on project progress vis-à-vis indicators in the logframe;

- Prepare GEF quarterly project progress reports, as well as any other reports requested by the Executing Agency and UNDP;

- Undertake any other actions related to the project as requested by UNDP or the National Project Director.

| Position Titles | Tasks to be performed |
| --- | --- |
| Local Consultants |  |
| Technical Coordinator | -Review Assessments generated under regulatory analysis and inventory; -Assessment of the impact of project outputs on specific stakeholders and general public; -Development of documentations to support stakeholder consultations as well as public awareness activities |
| Environmental Legal expert | Detailed review of regulatory framework and identification of gaps in management of mercury; - Development of specific recommendations on adjustments, amendments required in existing legislation; - Liaise with Ministry of Environment, Minamata focal point and relevant government agencies for development of effective proposals for regulatory framework development. |
| National experts on data collection, organization and analysis | Identification of main target areas (sites) and sources for collection of data in accordance with the rapid assessment: i) coal-fired power plants; ii) cement production; iii) mining and other metallurgical activities; iv) mercury mining; v) small-scale gold and silver mining; vi) chloral-alkali production; vii) fluorescent lamps, manometers, thermometers; viii) manufacturing of products containing mercury; and ix) waste (including medical waste) incineration; - Selection of methodology for the collection and analysis of data under each mercury source identified; - Collection of data and analysis; - Review of the rapid assessment of sources and validation (or expansion) of the list in accordance with collected data. |
| Environmental economist | -Conduct the cost benefit analysis for the mainstreaming activity; -Develop Socio-Economic Study on ASGM -Coordinate the mainstreaming activities between involved institutions -Develop the final report on Mainstreaming |
| International Expert | UNEP "Toolkit for identification and quantification of mercury releases" - Provision of technical advisory support (with missions) to the local team on the Minamata convention as the new MEA instrument, mercury sources, data organization, collection and validation process in each related sector/sub-sector; - Support to the national level consultations on the data analysis, national mercury profile formulation and priority setting processes for decision-making; - Provision of regulatory advisory support where needed with respect existing international benchmarks - Provision of support to develop and analyze cost related to the implementation of the Convention and description of potential sources of funds, including existing bilateral sources |

## Annex 2:  Risk analysis

| Identified Risks and Category | Impact | Likelihood | Risk Assessment | Mitigation Measures |
| --- | --- | --- | --- | --- |
| Political Change of the Government stand towards Convention ratification | Medium | Moderately likely | Low | The project outputs have been identified, and project activities developed, in close collaboration with the Ministry of Environment and other government institutions and stakeholders. The project will further support a Mercury Initial Assessment to enable the Government of Jordan to determine the national requirements and needs for ratification of the Minamata Convention and establish a sound foundation to undertake future work towards the implementation of the Convention |
| Institutional Difficulties in obtaining necessary data desegregated by sex. | Moderate | Low | Low | The project will work closely with different institutions and entities that collect data on different purposes and also cooperate with other initiatives that are supporting ministry of Environment on Environmental Monitoring and Information System. Also ministry of Environment will be supported to establish protocols of Information flow with different institutions serving to the project purpose. |

Annex 3

DESCRIPTION OF UNDP COUNTRY OFFICE SUPPORT SERVICES

1.	Reference is made to consultations between the Ministry of Planning and International Cooperation, the institution designated by the Government of Jordan and officials of UNDP with respect to the provision of support services by the UNDP country office for the nationally managed programme or project “Strengthen national decision making towards ratification of the Minamata Convention and build capacity towards implementation of future provisions”, project number ______.

2.	In accordance with the provisions of the letter of agreement signed and the programme support document (project document), the UNDP country office shall provide support services for the Programme as described below.

3.	Support services to be provided:

| Support services (insert description) | Schedule for the provision of the support services | Cost to UNDP of providing such support services (where appropriate) | Amount and method of reimbursement of UNDP (where appropriate) |
| --- | --- | --- | --- |
| 1. Services related to HR (including but not limited to): Recruitment of Project officer Staff HR & Benefits Administration & Management Recurrent of personnel management services: Staff Payroll & Banking | Ongoing throughout implementation when applicable | As per the attached LPL ˷$550 | UNDP will directly charge the project upon receipt of request of services from the Implementing Partner (IP) |
| 2. Services related to procurement (including but not limited to): Procurement of goods: Data show PC Printer Procurement of Services Contractual services for companies | Ongoing throughout implementation when applicable | As per the attached LPL ˷$850 | As above |
| 3. Services related to Finance (including but not limited to): Payments F10 settlements DSA | Ongoing throughout implementation when applicable | As per the attached LPL ˷$600 | As above |
| Total |  | $ 2000 |  |

4. Description of functions and responsibilities of the parties involved:

UNDP will conduct the full process while the role of the Implementing Partner (IP) will be as

Follows:

- The Implementing Partner will send a timetable for services requested annually/ updated quarterly

- The Implementing Partner will send the request to UNDP for the services enclosing the specifications or Terms of Reference required

- For the hiring staff process: the IP representatives will be on the interview panel,

- For Hiring CV: the IP representatives will be on the interview panel, or participate in CV review in case an interview is not scheduled

## Annex4: Signed letter of endorsement (LOE)

# Footnotes

For UNDP supported GEF funded projects as this includes GEF-specific requirements

Agency fee is given to UNDP as GEF Agency for implementing the project and it differentiates from Project Grant, funding given to the project

Objective (Atlas output) monitored quarterly ERBM and annually in APR/PIR

All outcomes monitored annually in the APR/PIR.  It is highly recommended not to have more than 4 outcomes.

Summary table should include all financing of all kinds: GEF financing, cofinancing, cash, in-kind, etc...

# Text boxes

Total resources required        		$200,000

2Total allocated resources:		$219,000

Project Grant - GEF	200,000 $

Agency fees			  19,000 $

Programme Period:		                2013-2017

Atlas Award ID:			00091779

Project ID:			00096810

PIMS #				5633

Start date:		     	Feb 2016

End Date			                Feb 2018

Management Arrangements		NIM

PAC Meeting Date			14 Dec 2015

Project Coordinator

Technical Expert

Project Board

Senior Beneficiary:

Ministry of Planning

Executive:

Ministry of Environment

Senior Supplier:

UNDP Country Office

Project Assurance

GEF OFP

UNDP CO

MPU/Chemicals (GEF-RCU)

Project Organisation Structure

Consultants, taskforce, Institutions, NGOs, for Specific Activities