### Reporting Agency:	UNDP

### Country:		Kazakhstan

### ANNUAL PROJECT PROGRESS REPORT

### No. and title:	101059  Improvement of the National Human Rights Protection Mechanisms and Facilitation of Effective Implementation of the International Commitments of the Republic of Kazakhstan: Phase II

### Reporting period: 	January –December 2017

### I.  PURPOSE

- Project targets to facilitate implementation of recommendations of the 2nd UPR under the National Plan for Implementation of UPR Recommendations (2016-2018) and institutionalization of new mechanisms towards implementation of international commitments on human rights. The targets reflect the Country Programme Document and Country Programme Action Plan (CPAP), specifically Outcome 2.2: Judicial and legal systems, and public institutions, are fair, accountable and accessible to all people

- Project activities contribute to the Output 3: The platform for effective implementation of Kazakhstan’s international human rights commitments has been created. Activities support improvement of national human rights protection mechanisms through revision of national human rights legislation to make it compliant to international human rights standards, introduction of national monitoring system to assess human rights implementation, and enhancement of capacity and knowledge of government bodies, including law enforcement, and civil society in international human rights standards.

- Ministry of Justice of the RK

### II.  RESOURCES

UNDP: USD 10,000

GoK: KZT 20,460,000

### III. TARGETS vs. RESULTS

Information in this section includes:

- Target 1: Assist in the formation of a holistic approach to reform policy in the field of human rights and implementation of international obligations of the Republic of Kazakhstan

Project experts reviewed the national legislation on torture investigation to assess compliance with Istanbul Protocol norms of effective torture investigation, and provided with the draft law on changes in criminal and criminal proceeding codes to fully comply with international standards of investigation process. Analysis of implementation of 2nd UPR recommendations and implementation of ICCPR has been conducted and passed to the government agencies. National experts reviewed OHCHR developed human right indicators and elaborated Meta-data for Kazakhstan to further validate with government bodies and initiate collection of data on human rights implementation. Project supported the government and civil society organized meetings on promotion of human rights mechanisms and legislative changes in Kazakhstan, including support with international expertise for UPR conference and webinar discussion of gender based violence issues.

•	Target 2: The effective implementation of policies in the field of human rights and the strengthening of institutions at all levels of execution

Training workshops have been delivered for special prosecutors, forensic experts, and police staff on Istanbul Protocol based effective investigation of torture and on GBV case management according to international standards. UNPC in Seoul provided the project with additional funding to institutionalize GBV trainings for police inspectors in Kazakhstan through the Academies of Police and Law Enforcement Academy. The study visit for the management of Academies is scheduled for 2018 to learn best practices in GBV case management and investigation. Trainings on draft law revision have been conducted for public council in Petropavlovsk and for the secretaries of regional public councils in Astana to enhance their capacity to analyze draft legislation at local government level.  National experts developed training programs for press services of government agencies on international human rights commitments of Kazakhstan to enhance their knowledge on human right treaties and skills to work with mass media on the issues of human rights implementation. The training program was developed for law enforcement bodies on management of peaceful assemblies to support next year training for police staff.

- Implementation constraints, lessons learned from addressing these and knowledge gained from evaluations and studies that have taken place in the course of the year:

Changes in the staff of the Ministry of Justice at working level put challenges in smooth project running and in-time receipt of the comments towards the project submitted analytical reports and training materials.

- Key partnerships and inter-agency collaboration: impact on results:

The training have been successfully organized with the joint efforts with OSCE and Council of Europe on Istanbul protocol. OHCHR supported the process of adaptation and validation of global indicators on human rights.

### IV.MONITORING and EVALUATION

Project monitoring and assessment has been done though quarterly check-up of results versus targets and regular meetings with the Ministry of Justice

### V.  FINANCIAL IMPLEMENTATION

Budget Overview (2017)

| Description of activity | Budgeted amount | Spent amount | Balance |
| --- | --- | --- | --- |
| Activity 1 The effective indicators and practical arrangements on implementing the new recommendations of the UPR, UN treaty bodies, Special procedures, an advisory body "Dialogue on the Human Dimension" at the Ministry of Foreign Affairs of Kazakhstan, as well as the recommendations presented in the framework of the reports of the Commissioner for Human Rights and the National Human Rights Commission under President of RK | USD 18,900 | USD 18,900 | 0 |
| Activity 2 Local authorities and civil society in the field are better informed about the reforms on the enjoyment of human rights, for the implementation of international agreements and enforcement of human rights in the process of ensuring compliance with international standards. | USD 22,680 | USD 22,680 | 0 |
| Activity 3 Effective project management | USD 9,167 | USD 9,167 | 0 |