UNITED NATIONS DEVELOPMENT PROGRAMME

SUPPORTING IMPLEMENTATION OF THE PEACE AGREEMENTS: A PROGRAMME FRAMEWORK FOR DIALOGUE AND RECONCILIATION IN KENYA IN THE AFTERMATH OF ELECTIONS- RELATED VIOLENCE

ANNUAL WORK PLAN FOR JANUARY –DECEMBER 2013

Country: Kenya

UNDAF Outcome(s):	UNDAF Outcome 2.2: Humanitarian Impact and Risk of Natural and Human –Made Disasters reduced.

Expected CP Outcome(s):	National Plans & Policies for conflict and disaster management operationalized and capacity developed at National, County and Local Levels

Expected CP Output(s):	1) Contributions by parliamentarians towards peace and reconciliation initiatives increased; 2) new institutions mandated by the peace agreements functionally established, and able to develop and implement effective frameworks and policies  for addressing the core issues behind post-electoral violence; 3) Local level conflicts resolved  through mediation, dialogue promotion and reconciliation efforts by civic and inter-faith organizations; 4) Women in affected communities visible and active roles in promoting peace in their communities; 5) Youth in affected communities, including those participating in the activities of tribal militias and other armed  groups , actively engaged in the promotion of dialogue  and reconciliation 6) Capacities of UNDP and partner agencies to support dialogue and reconciliation processes strengthened.

Executing Entity:	UNDP

Implementing Partner:	UNDP

APPROVALS:

Agreed by (UNDP Kenya):

Name		...........................................................

Title/Portfolio: ......................................................................

Signature: ..............................................................................

# Supporting Implementation of Peace Agreements: A programme framework for Dialogue and Reconciliation in Kenya in the Aftermath of Elections –related Violence -Project No: 00057987

DEX Work Plan:  January 2013 – December 2013

| Expected Output | Key Activities | Timeframe | Responsible party |  | Budget Description | BUDEGT: USD |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding source |  |  |
| Output 1: Strengthening national cohesion and integration Baseline - Initial joint efforts by parliamentarians in areas affected by violence not yet systematic, or able to achieve significant impact. - Significant acrimony on parliament floor in drafting of legislation pertinent to implementation of the reform agenda. -Current perception survey indicates frequency is about 65% of hate speech. -Baseline on level of political will extended to peace and reconciliation work in the country to be established. Indicators: Number of systematic joint efforts by parliamentarians in areas affected by violence that have yielded positive results. -% decline in the recourse to hate speech by leaders. - Increase in the level of political will extended to peace and reconciliation work in the country -Increased participation of political leaders and statutory bodies in national cohesion and integration. -Interparty mediation team in place; National level mediation team in place; Visible functioning mediation teams and active interparty platform for conflict prevention and peace building; Reports; Reconciliation strategy developed; Monitoring reports of implementation of the strategy; Peace Campaign strategy document; IEC materials; Level of use of social media; Infomercials produced; Publications; Documentaries. Targets: -Exercises on imparting skills for leadership, collaborative decision-making, and conflict resolution conducted for at least 2 Commissions/Leadership groups. - Support towards the implementation of at least one collaborative leadership initiative at national level . -At least 12 consultative meetings of leadership of political parties -Training of identified county leaders in collaborative decision making in at least 10 counties | 1.1: Training of members of Senior Media Executives and Editors, Political Parties-Youth Leadership, Informal Settlement Leaders; Cross-sectoral leaders (politicians, media and private sector) in Collaborative leadership | * | * | * | * | UNDP | UNDP-BCPR | Consultant Trainers Training Venue Transport DSA Technical support | 100,000 |
|  | 1.2 Supporting the Peace and Security Advisor for the Country Office |  |  |  |  | UNDP | UNDP-BCPR | Remuneration | 200,000 |
|  | 1.3: Monthly consultative meetings of leadership of political parties. | * | * | * | * | UNDP | UNDP-BCPR | Consultant Trainers Venue | 24,000 |
|  | 1.4: Regular reflection meetings, with Parliamentary Collaborative Leadership Caucus | * | * | * | * | UNDP |  | Venue | 50,000 |
|  | 1.5: Meetings of informal advisory group on collaborative leadership. | * | * | * | * | UNDP |  | Venue | 5,000 |
|  | 1.6: Establish High-level “insider mediation” capacity |  |  |  |  | UNDP |  | Consultancy services-Individual Experts Communication Travel Training workshops | 50,000 |
|  | 1.7: Technical support provided to partners to develop and implement a reconciliation strategy to address potential fall-out from the release of the TJRC report. | * | * |  |  | UNDP |  | Local and International Consultants Workshops | 40,000 |
| Subtotal |  |  |  |  |  |  |  |  | 504,000 |
| OUTPUT 2: Local level conflicts resolved through mediation, dialogue promotion, and reconciliation efforts by community based and civil society organizations. Baseline: - Continued high incidence of violent conflicts and insecurity at the community level, especially the Rift Valley, Northern, and Nyanza provinces. - Continued circulation, at local level, of messages intended to magnify ethnic stereotyping and resentment. - Current (perception survey) level of interaction is at 57% Indicators: -% decrease in incidence of violent conflicts in target areas. -Increased level of security in target areas. -Decrease in proliferation of messages intended to magnify ethnic stereotyping and resentment. -% increase in inter-communal interaction -Increased percentage level of perceptions on national cohesion, dialogue and reconciliation processes. -Number of community social contracts signed and implemented. Targets: -At least three community social contracts signed between communities. -% decrease in incidences of violent conflict in at least three target areas. -At least four county policy brief detailing the current peace and conflict situation and identifying possible drivers of conflict for early warning - At least 4 interfaith dialogue and two meeting with parties to drivers of conflict. | 2.1 Peace and cultural festivals and peace caravans held in 15 hot spot areas. | * | * | * |  | UNDP |  | Contractual services-Companies & individuals Travel Meetings/workshops | 45,000 |
|  | 2.2: Technical support provided and monitoring of the implementation of the process approach to reconciliation in targeted communities | * | * | * | * | UNDP |  | Travel DSA Trainers | 50,000 |
|  | 2.3 Development and publication of Amani Papers and County policy briefs on a monthly basis and specific activity reports to inform the public of practice and for CEWER purposes as well as conduct studies on implementation of devolution in Kenya | * | * | * | * | UNDP |  | Editor Layout/design Publication Dissemination Peer review | 100,000 |
|  | 2.4 Support to faith based dialogue (Muslim and Christian) to mitigate against tensions caused by new drivers of violence ( e.g. Presence of KDF in Somalia ) | * | * | * | * | UNDP |  | Consultancy Equipment Travel DSA | 80,000 |
| Subtotal |  |  |  |  |  |  |  |  | 275,000 |
| Output 3: Vulnerability of youths to criminality, armed violence and recruitment into militias reduced Baseline: - Continued high levels of youth participation in violent inter-ethnic competition and gang-related activity Indicators: No of peace divided grants provided to the youth No of training conducted to link the CDA valua chain to peace building Targets: -Training in at least ten constituencies -Technical assistance provided in at least ten constituencies | 3.1: Follow-up training of Constituency Development Associations (CDAs) in value chain addition & peacebuilding and the linkages with peace divided. | * | * | * | * | UNDP |  | Consultants Venue Transport DSA | 15,000 |
|  | 3.2: Co-ordination and provision of technical support on value chain addition and peacebuilding provided to CDAs in at least 4 constituencies. | * | * | * | * | UNDP |  | Consultants Travel | 100,000 |
| Subtotal |  |  |  |  |  |  |  |  | 115,000 |
| Output 4: Increased role and visibility of women in peacebuilding at both national and local levels Baseline: - Limited participation of women in formal peace and reconciliation processes at local levels. Indicators: -Increased level of participation of women involved in peace building initiatives at national and local levels -Number of women-led peace building initiatives at national and local level. -Level of public perception on the opportunities afforded to women in peace building and reconciliation efforts. -Increased capacity of women in Peace Building Processes Targets: - % increase of women’s participation in peace building and the CEWER mechanism in at least ten target areas. -ToT of at least 100 Law Enforcement Officers in management of electoral violence. | 4.1. County forums for women on development of conflict prevention strategies and awareness-raising on the CEWER mechanism in targeted areas. | * | * | * |  | UNDP |  | Trainers Venue | 70,000 |
|  | 4.2 Building mediative capacity of women, including women in political parties (link with IEBC). | * | * | * | * | UNDP |  | Consultant Trainers Training Venue Transport DSA | 50,000 |
|  | 4.3 Training of at least 100 Law enforcement officers at KIA on women and violence. | * | * |  |  | UNDP |  | Trainers Venue DSA | 70,000 |
|  | 4. 4 Engaging with the judicial system through consultative meetings with the community on Alternative Dispute Resolution (ADR) Mechanisms, and its application in follow-up to the research study on traditional methods of conflict resolution. | * | * | * | * | UNDP |  | Venue DSA Transport Consultants | 20,000 |
| Subtotal 210,000 |
| Total 1,069,000 |

# Text boxes

Brief Description

The Kenya Constitution promulgated in 2010 explicitly recognize the need for building systematic national and local capacities for conflict management, for establishing new national policies and institutions  including devolved government, to address critical issues such as land, reconciliation, socio-economic inequality, and for harnessing the energies of diverse groups such as women, youth, parliamentarians, tribal elders, communities of faith, and the private sector towards this end. In response to these needs, this project strives to engage with a variety of partners at the national, county and local levels to promote reconciliation, establish foundation peaceful and sustainable devolution in Kenya as well as support the implementation of the peace agreements and foster inter-communal dialogue as a means to restoring trust and confidence in the public and contributing towards healing, reconciliation, peace building, cohesion and integration in the nation.

Programme Period: 		 1 year

Key result Areas (Strategic Plan): 3.1 Enhancing conflict and disaster risk management capabilities

Atlas Award ID: 			00048014

Start date: 			01/01/2013

End date:			 31/12/2013

Management Arrangements  	DEX

Intervention Title: Consolidating the Peace Process and Establishing the Foundations for a Successful Political Transition in Kenya, 2010-2013.

Project No. 00077137

Atlas Code: 7KEN09701

Budget Code: 00061024

Duration: 	6 Months

Total resources required: USD 1,069,000

Allocated resources:  $500,000

- Regular:	      $500,000

- Unfunded budget: $569,000

- In kind Contributions-