## 2018 AWP
Project Title: | NAZAHA Institutional Strengthening Project | [18 empty] | Year |  |  |  |  | Total Budget |  | 1782157.5 | Prepared by:
Project Number: | [19 empty] | Award Number |  |  |  |  | Donor Number: |  | 145 | Certified by:
Contributing Outcome (CPD) | Governance and institutional management is efficient, transparent, accessible, competitive and accountable | [23 empty] | Fund Number: |  | 30071
Indicative Output(s): | Human development accelerated through high-caliber human capital and increased social empowerment.
[5 empty] | 2017 |  |  | 2018
Output Indicatirs, Baseline, Targets | Activities (as per Atlas AWP) | Sub activity | Status/ Progress | Action | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender | Account Code | Budget Description | Amount USD $ | Deliverable | Responsibility
[5 empty] | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable
Output 1 Kuwait anti-corruption strategy and implementation plan developed Indicators: 1.1 Level of progress achieved towards Kuwait anti-corruption strategy and implementation plan 1.2 Number of persons with enhanced capacities for the implementation, monitoring and evaluation of the national anti-corruption strategy and implementation plan Baseline: 1.1 :0 1.2 :0 Targets: 1.1 :4 1.2 :20 | 1.1 Conduct first country mission (2 from Vienna and 2 from Amman/Beirut) to establish baselines and contextual factors and agree with NAZAHA on the scope of work and the vision for its completion | [18 empty] | 2 | 28250 | [7 empty] | 56500
[20 empty] | 2 | 28250 | [7 empty] | 56500
| 1.2 Develop the necessary studies to identify related needs and priorities linking to UNCAC implementation and SDGs achievement, namely SDG 16 | [18 empty] | 1 | 9800 | [7 empty] | 9800
[20 empty] | 1 | 16025 | [7 empty] | 16025
| 1.3 Organize first national consultative workshop (40 person) to identify stakeholder perspectives on related needs and priorities | [18 empty] | 1 | 10000 | [7 empty] | 10000
| 1.4 Conduct second country mission (2 from Vienna and 2 from Amman/Beirut) to present methodology in strategy development and identify priority areas and key outcomes of the strategy | [18 empty] | 2 | 28250 | [7 empty] | 56500
[20 empty] | 2 | 28250 | [7 empty] | 56500
| 1.5 Develop the first draft of the strategy | [18 empty] | 1 | 9800 | [7 empty] | 9800
[20 empty] | 1 | 16025 | [7 empty] | 16025
| 1.6 Conduct third country mission (2 from Vienna and 2 from Amman/Beirut) to present and discuss the first draft of the strategy, and to elaborate the implementation plan (key activities, benchmarks, responsible institutions, indicative timelines, related indicators etc) | [18 empty] | 2 | 28250 | [7 empty] | 56500
[20 empty] | 2 | 28250 | [7 empty] | 56500
| 1.7 Organize second national consultative workshop (40 persons) to secure additional stakeholder inputs regarding the first draft of the strategy and way forward | [18 empty] | 1 | 10000 | [7 empty] | 10000
| 1.8 Revise the first draft of the strategy as necessary and develop the first draft of the implementation plan | [18 empty] | 1 | 9800 | [7 empty] | 9800
[20 empty] | 1 | 32050 | [7 empty] | 32050
| 1.9 Conduct fourth country mission (2 from Vienna and 2 from Amman/Beirut) to validate the strategy and implementation plan and introduce any amendments as needed | [18 empty] | 2 | 28250 | [7 empty] | 56500
[20 empty] | 2 | 28250 | [7 empty] | 56500
| 1.10 Design an outreach campaign for the launch of the strategy and implementation plan | [18 empty] | 1 | 39200 | [7 empty] | 39200
1.11 Upon securing the official approvals, organize a national conference (200 persons) to announce the strategy and implementation plan, and launch the outreach campaign
| 1.12 Execute the outreach campaign for the strategy and implementation plan | [18 empty] | 1 | 64100 | [7 empty] | 64100
| 1.13 Design the monitoring and evaluation system for the strategy and implementation plan | [18 empty] | 1 | 19600 | [7 empty] | 19600
[20 empty] | 1 | 32050 | [7 empty] | 32050
| 1.14 Organize two training sessions (20 persons) on good practices and lessons learned in implementing national anti-corruption strategies and its impact on sustainable development | [18 empty] | 1 | 10000 | [7 empty] | 10000
| 1.15 Organize two training sessions (20 persons) on monitoring and evaluating national anti-corruption strategies and implementation plans | [18 empty] | 1 | 10000 | [7 empty] | 10000
| 1.16 Provide in-house overall advisory support and quality control to carry out the activities outlined above | [18 empty] | 1 | 9800 | [7 empty] | 9800
| Sub total | [27 empty] | 750250
Total Output1 | [28 empty] | 750250
Output 2: NAZAHA Institutional capacities developed and improved for an effective organization Indicators: 2.1 Level of progress achieved towards NAZAHA’s capacity development plan 2.2 Level of progress achieved towards NAZAHA’s policies and procedures manual 2.3 Level of progress achieved towards an ICT-based knowledge management system at NAZAHA 2.4 Number of persons with enhanced capacities on good practices and lessons learned from comparative experiences of peer agencies worldwide Baseline: 2.1 : 4 2.2 : 4 2.3 : 4 2.4 : 40 Targets: 2.1 : 4 2.2 : 4 2.3 : 4 2.4 : 40 | 2.1 Conduct and validate through interviews and a dedicated internal workshop a capacity assessment of KANCOR | [18 empty] | 1 | 835000 | [7 empty] | 835000 | bar: Q1 Jan to Q4 Dec
2.2 Develop and discuss in a dedicated internal workshop the first draft of the capacity development plan in line with the priority areas and key outcomes identified under the national anti-corruption strategy | bar: Q1 Jan to Q4 Dec
2.3 Revise the capacity development plan and submit for official approval | bar: Q1 Jan to Q4 Dec
2.4 Design the monitoring and evaluation system for the capacity development plan | bar: Q1 Jan to Q4 Dec
2.5 Conduct and validate through interviews and a dedicated internal workshop the documentation and assessment of current practices in KANCOR | bar: Q1 Jan to Q4 Dec
2.6 Identify international good practices by anti-corruption agencies and adapt them to KANCOR’s context through a series of internal workshops | bar: Q1 Jan to Q4 Dec
2.7 Develop the first draft of KANCOR’s policies and procedures manual | bar: Q1 Jan to Q4 Dec
2.8 Present and discuss in dedicated internal workshops the first draft of KANCOR’s policies and procedures manual | bar: Q1 Jan to Q4 Dec
2.9 Revise KANCOR’s policies and procedures manual and submit for official approval | bar: Q1 Jan to Q4 Dec
2.10 Organize trainings for KANCOR staff on good practices and lessons learned from peer agencies worldwide including on awareness, prevention and enforcement | bar: Q1 Jan to Q4 Dec
2.11 Document and assess KANCOR’s knowledge management capacities, including use of ICT | bar: Q1 Jan to Q4 Dec
2.12 Organize internal workshop to enhance knowledge on comparative experiences on the use of ICT and knowledge management tools | bar: Q1 Jan to Q4 Dec
2.13 Present the findings and recommendations to KANCOR for approval | bar: Q1 Jan to Q4 Dec
2.14 Conduct the feasibility study for the enhancement of KANCOR’s knowledge management capacities, including the use of ICT | bar: Q1 Jan to Q4 Dec
2.15 Develop the terms of reference for the development knowledge management capacities at KANCOR, including the use of ICT and related governance frameworks | bar: Q1 Jan to Q4 Dec
2.16 Provide in-house overall advisory support and quality control to carry out the activities outlined above | bar: Q1 Jan to Q4 Dec
| Sub total | [27 empty] | 835000
Total Output 2 | [28 empty] | 835000
|  |  |  | Project Manager | [16 empty] | 10000 |  | 12 | [5 empty] | 120000
|  |  |  | Miscellaneous | [16 empty] | 5000 |  | 1 | [5 empty] | 5000
|  |  |  | Evaluation | [16 empty] | 20000 |  | 1 | [5 empty] | 20000
| Project Administration Costs |  |  | GMS | [16 empty] | 0.03 | [7 empty] | 51907.5 |  |  | x x
| Sub Total | [27 empty] | 196907.5
Total Output 5 excluding GMS and Evaluation | [28 empty] | 145000
Total Budget | [28 empty] | 1730250
Total Budget including 3% GMS | [28 empty] | 1782157.5
|  |  |  | UNDP regional Anticorruption office | Q3 Aug: 324000 |  | A |  | Travel missions-- (4 UNODC (x2 people ) + (4 UNDP regional (x2 people )) | [6 empty] | 452000
|  |  |  | UNODC including PSC | Q3 Aug: 386250 |  | B |  | 2 workshops and 4 trainings expenses (UNDP, UNODC) | [6 empty] | 40000
[5 empty] | Q3 Aug: 40000 |  | C |  | outreach campaign related activities | [6 empty] | 103300
[21 empty] | D |  | Other activities | [6 empty] | 154950
[5 empty] | Q3 Aug: 750250 | [10 empty] | 750250
[5 empty] | Q3 Aug: P-4 - one month |  | IC 90 days | SC -4months |  | T | 40% of T to C |  | 60% of T to D
|  |  |  | UNDP regional Anticorruption office | Q3 Aug: 15000 |  | 63000 | 20000 |  | 98000 | 39200 |  | 58800
[5 empty] | Q3 Aug: P-4 -4months |  | P3 -4months | G -3months |  | T | 40% of T to C |  | 60% of T to D
|  |  |  | UNODC including PSC | Q3 Aug: 73000 |  | 59000 | 28250 |  | 160250 | 64100 |  | 96150
[25 empty] | 103300 |  | 154950
Agreed by (signatures):
| Secretary General of the Supreme Council for Planning and Development |  | Acting Secretary General - Kuwait Anticorruption Authority (NAZAHA) |  | Q2 Jun: Deputy Resident Representative UNDP
| Dr. Khaled Mahdi |  | Dr. Mohammad A. Buzubar |  | Q2 Jun: Dima AL-Khatib

## ProDoc MY-WP
EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year |  | RESPONSIBLE PARTY | PLANNED BUDGET
|  | 2018 | Total |  | Funding Source | Budget Description | Amount (USD)
Output 1: | 1.1. Conduct first country mission (2 from Vienna and 2 from Amman/Beirut) to establish baselines and contextual factors and agree with KANCOR on the scope of work and the vision for its completion |  |  | KANCOR, GSSCPD, UNODC, UNDP |  | UNODC:
Kuwait anti-corruption strategy and implementation plan developed | [5 empty] | •P-4 staff for 4 months |  |  | 73000
[6 empty] | •P-3 staff for 4 months |  |  | 59000
[6 empty] | •G-staff admin for 3 months |  |  | 28250
[6 empty] | Travel -- 4 missions (x2 people) (includes PSC) | 4 | 2 | 226000
UNDP regional anticorruption agency:
[6 empty] | •P-4 staff for 1 month |  |  | 15000
[6 empty] | •IC contract (working under joint supervision of UNODC and UNDP) for 90 working days |  |  | 63000
[6 empty] | •Service contract: 20,000 for 4 months |  |  | 20000
[6 empty] | Travel -- 4 missions (x2 people) (includes PSC) | 4 | 2 | 226000
[6 empty] | 4 Workshops expenses |  |  | 40000
| 1.2 Develop the necessary studies to identify related needs and priorities linking to UNCAC implementation and SDGs achievement, namely SDG 16 |  |  | KANCOR, GSSCPD, UNDP
| 1.3 Organize first national consultative workshop (40 person) to identify stakeholder perspectives on related needs and priorities |  |  | KANCOR, GSSCPD, UNDP
| 1.4 Conduct second country mission (2 from Vienna and 2 from Amman/Beirut) to present methodology in strategy development and identify priority areas and key outcomes of the strategy |  |  | KANCOR, GSSCPD, UNODC, UNDP
| 1.5 Develop the first draft of the strategy |  |  | KANCOR, GSSCPD, UNODC
| 1.6 Conduct third country mission (2 from Vienna and 2 from Amman/Beirut) to present and discuss the first draft of the strategy, and to elaborate the implementation plan (key activities, benchmarks, responsible institutions, indicative timelines, related indicators etc) |  |  | KANCOR, GSSCPD, UNODC, UNDP
| 1.7 Organize second national consultative workshop (40 persons) to secure additional stakeholder inputs regarding the first draft of the strategy and way forward |  |  | KANCOR, GSSCPD, UNDP, UNODC
| 1.8 Revise the first draft of the strategy as necessary and develop the first draft of the implementation plan |  |  | KANCOR, GSSCPD, UNODC
| 1.9 Conduct fourth country mission (2 from Vienna and 2 from Amman/Beirut) to validate the strategy and implementation plan and introduce any amendments as needed |  |  | KANCOR, GSSCPD, UNODC, UNDP
| 1.10 Design an outreach campaign for the launch of the strategy and implementation plan |  |  | KANCOR, GSSCPD, UNDP
| 1.11 Upon securing the official approvals, organize a national conference (200 persons) to announce the strategy and implementation plan, and launch the outreach campaign |  |  | KANCOR, GSSCPD, UNDP
| 1.12 Execute the outreach campaign for the strategy and implementation plan |  |  | KANCOR, GSSCPD, UNDP, Company (tbi)
| 1.13 Design the monitoring and evaluation system for the strategy and implementation plan |  |  | KANCOR, GSSCPD, UNODC, UNDP
| 1.14 Organize two training sessions (20 persons) on good practices and lessons learned in implementing national anti-corruption strategies and its impact on sustainable development |  |  | KANCOR, GSSCPD, UNDP, UNODC
| 1.15 Organize two training sessions (20 persons) on monitoring and evaluating national anti-corruption strategies and implementation plans |  |  | KANCOR, GSSCPD, UNDP, UNODC
| 1.16 Provide in-house overall advisory support and quality control to carry out the activities outlined above |  |  | UNODC, UNDP
| Sub-Total for Output 1 | [7 empty] | 750250
Output 2: | 2.1 Conduct and validate through interviews and a dedicated internal workshop a capacity assessment of KANCOR |  |  | KANCOR, GSSCPD, UNDP |  | Consultancy firm |  |  | 835000
KANCOR’s capacities enhanced to carry out its mandate in a coordinated and effective manner | 2.2 Develop and discuss in a dedicated internal workshop the first draft of the capacity development plan in line with the priority areas and key outcomes identified under the national anti-corruption strategy |  |  | KANCOR, GSSCPD, UNDP
| 2.3 Revise the capacity development plan and submit for official approval |  |  | KANCOR, GSSCPD, UNDP
| 2.4 Design the monitoring and evaluation system for the capacity development plan |  |  | KANCOR, GSSCPD, UNDP
| 2.5 Conduct and validate through interviews and a dedicated internal workshop the documentation and assessment of current practices in KANCOR |  |  | KANCOR, GSSCPD, UNDP
| 2.6 Identify international good practices by anti-corruption agencies and adapt them to KANCOR’s context through a series of internal workshops |  |  | KANCOR, GSSCPD, UNDP
| 2.8 Develop the first draft of KANCOR’s policies and procedures manual |  |  | KANCOR, GSSCPD, UNDP
2.9 Present and discuss in dedicated internal workshops the first draft of KANCOR’s policies and procedures manual
| 2.9 Revise KANCOR’s policies and procedures manual and submit for official approval |  |  | KANCOR, GSSCPD, UNDP
| 2.10 Organize trainings for KANCOR staff on good practices and lessons learned from peer agencies worldwide including on awareness, prevention and enforcement |  |  | KANCOR, GSSCPD, UNDP
| 2.11 Document and assess KANCOR’s knowledge management capacities, including use of ICT |  |  | KANCOR, GSSCPD, UNDP
| 2.12 Organize internal workshop to enhance knowledge on comparative experiences on the use of ICT and knowledge management tools |  |  | KANCOR, GSSCPD, UNDP
| 2.13 Present the findings and recommendations to KANCOR for approval |  |  | KANCOR, GSSCPD, UNDP
| 2.14 Conduct the feasibility study for the enhancement of KANCOR’s knowledge management capacities, including the use of ICT |  |  | KANCOR, GSSCPD, UNDP
| 2.15 Develop the terms of reference for the development knowledge management capacities at KANCOR, including the use of ICT and related governance frameworks |  |  | KANCOR, GSSCPD, UNDP
| 2.16 Provide in-house overall advisory support and quality control to carry out the activities outlined above |  |  | KANCOR, GSSCPD, UNDP
| Sub-Total for Output 2 | [7 empty] | 835000
Miscellaneous: translation services, printing materials… etc. | [8 empty] | 5000
Programme Management | Project Manager |  | 10000 |  |  |  | 12 |  | 120000
Evaluation (as relevant) | EVALUATION |  | 20000 | [5 empty] | 20000
| Sub-Total for management support & Evaluation | [7 empty] | 145000
Total Excluding GMS | [8 empty] | 1730250
General Management Support (UNDP) | [8 empty] | 51907.5
TOTAL | [8 empty] | 1782157.5