## 2018 AWP
Project Title: | National Human development Report Kuwwait 2016 | [8 empty] | Award Number: |  |  |  | 98910 |  |  |  | Total Budget |  |  |  |  | 154931.7942 |  |  | Prepared by:
Project Number: | 00102107 | [8 empty] | Year: |  |  |  | 2018 |  |  |  | Fund Number: |  |  |  |  | Donor Number: |  |  | Certified by:
Contributing Outcome (CPD) | CPD Outcome# 2: Human development accelerated through high-calibre human capital and increased social empowerment CPD Output # 2.1. Institutional capacity strengthened to produce national human development policy frameworks and conduct comprehensive needs assessment for vulnerable groups.
Indicative Output(s): | Innovative knowledge, policy analysis and alternative policy options that promote human development are identified and publicly disseminated
Output Indicatirs, Baseline, Targets | Activities (as per Atlas AWP) | Sub activity |  | Status/Progress | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender |  |  |  | Deliverable | Responsibility
[6 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable |  | Account Code | Budget Description | Amount USD $
Output 1: Innovative gender-sensitive knowledge, policy analysis and alternative policy options that promote human development are identified and publicly disseminated Indicators: 1.1 A national human development report prepared and disseminated 1.2 Availability of gender sensitive indicators, data and analysis Baseline: 1.1 Two reports published 1997 & 1999 1.2 N/A | 1.1 Select the NHDR theme | Review of documentation |  | Completed | [13 empty] | 1 | 0 | [6 empty] | Workshop facilitator/Regional Centre- Travel Costs (5*accommodation@330/day + ticket) | 0 |  | UNDP/ GSSCPD
|  | Hold a multi-stakeholder workshop |  | Completed | [13 empty] | 1 | 0 | [6 empty] | Workshop Costs (Press Conference and Workshop 75 pple each) | 0
|  | Hold a press conference |  | Not required | [13 empty] | 1 | 2000 | [6 empty] | Stationary and Printing | 2000 | bar: Q2 Apr
| Sub Total | [25 empty] | 2000
| 1.2 Set up the Project Structures and Build the HDR team | Establish the Management structures |  | Completed | [13 empty] | 3 | 0 | [6 empty] | Team Leader/Lead Author (60*fees @US$750/Day | 0 |  | Project Board
|  | Select the Core report team |  | Completed | [13 empty] | 4 | 45000 |  | 6 months | IC | Deliverable |  |  | Team of Experts (Gender Expert authors/researchers) 200* Fees@ average US$ 500/Day) | 180000 | Coauthors | bar: Q1 Jan to Q3 Sep
|  | Conduct a stakeholder mapping for advisory board |  | Completed | [13 empty] | 1 | 0 | [6 empty] | External Peer Reviewers fees (3*fees @US$1000 lump sum) | 0 | Project Coordinator
|  | Set up internal partnership and consultative mechanisms |  | Completed | [13 empty] | 1 | 0 |  |  |  | National |  | 75700 | Travel Costs (assume 3 international Experts) Accommodation =140*accommodation costs @US$ 250/Day)+ 3 tickets | 0 | Project Coordinator
| Sub total | [25 empty] | 180000
| 1.3 Prepare the NHDR: Planning, Research and Analysis, Reviews and Production | Conduct an orientation session to the Project Board |  | Completed | [13 empty] | 1 | 0 |  | 1 | IC |  |  |  | Costs of statistical surveys and expertise including one training | 0 | HDRO | NHDR Core Team and Review Committees
|  | Conduct a 3 day training workshop the NHDR team |  | Completed | [13 empty] | 2 | 0 |  | 2 | IC |  |  |  | Live session was held with Mr. Adel Abdellatif in December 2017 | 0 | HDRO/Consultant
|  | Elaborate of the conceptual framework, outline of the Kuwait Report and target audience |  | Completed | [13 empty] | 1 | 0 | [6 empty] | Costs of consultation conferences/workshops/validation meetings around Kuwait (part of the methodology) | 0 | Coauthors
|  | Establish a Production Schedule |  | Completed | [13 empty] | 1 | 0 | [6 empty] | By Core team | 0 | Team Leader
|  | Commission & Prepare Background Papers |  | In Progress | [13 empty] | 5 | 7000 | [6 empty] | Costs of in country travel (local experts/project team background papers) | 35000 | Coauthors | bar: Q1 Mar to Q2 Apr
|  | HDI Training + Data assessment, surveys commissioning and HD measurement |  | In Progress | Hire Statistical Analyst | [12 empty] | 1 | 3500 | [6 empty] | TO be conducted by the Statistical Analyst when onboard. | 3500 | Project Coordinator/Coauthors | bar: Q1 Feb to Q2 Apr
|  | Undertake the research, prepare the First Draft, Internal review, Second draft, External Peer Review, Final Draft and Executive Review | [15 empty] | 2 | 5000 | [6 empty] | Stationary | 10000 | Project Coordinator
|  |  | *Reseach & First Draft | In Progress | bar: Q1 Jan to Q2 Apr
|  |  | *Internal Review | Planned | bar: Q2 May
|  |  | *Second Draft | Planned | bar: Q2 Jun to Q3 Jul
|  |  | *External Peer Review | Planned | bar: Q3 Aug
|  |  | *Final Draft & Executive Review | Planned | bar: Q3 Sep
| Sub Total | [25 empty] | 48500
| 1.4 Print, publish and distribute the report | Edit of the report in both languages | [15 empty] | 2 | 10000 | [6 empty] | Professional Editor (Two languages) | 20000 |  | Project Coordinator & Project Board | bar: Q3 Sep to Q4 Oct
|  |  | *English Editor | Planned | bar: Q3 Sep
|  |  | *Arabic Editor Following Translation | Planned | bar: Q4 Oct
|  | Tralslate to Arabic, and design of translation |  | Planned | [13 empty] | 1 | 15000 | [6 empty] | Professional Translator English Arabic | 15000 | bar: Q4 Oct
|  | Design and Print copies of the Report | [15 empty] | 1 | 10000 | [6 empty] | Design, publish and print 500 copies in each language | 10000
|  |  | *Designe Layout | Planned | bar: Q4 Nov
|  |  | *Print | Planned | bar: Q4 Nov
| Sub Total | [25 empty] | 45000
| 1.5 MONITORING | Monitor training and capacity development activities |  | In Progress | [13 empty] | 1 | 0 | [6 empty] | Monitoring and Evaluation UNDP support | 0 |  | Project Coordinator & Project Board | bar: Q1 Jan to Q3 Aug
|  | Monitor activity implementation |  | In Progress | [13 empty] | 1 | 0 | [6 empty] | Miscellaneous (stationary, cost of travel) | 0 | bar: Q1 Jan to Q3 Aug
|  | Feedback from participants |  | In Progress | [13 empty] | 1 | 0 | [7 empty] | 0 | bar: Q1 Jan to Q3 Aug
| Sub Total | [25 empty] | 0
Total Output1 | [26 empty] | 275500
Output 2: Spaces/Platforms for dialogue and advocacy on the human development paradigm and policies are established by various stakeholders Indicators: 2.1 Extent of civil society organization (CSO) and other major groups engagement in the formulation and dissemination of the NHDR 2.2 Communication and media strategy developed and implemented 2.3 No. of advocacy activities carries out by the project and/or by external stakeholders | 2.1 Develop and implement and communication and media strategy | Develop a communication and media strategy | [15 empty] | 1 | 15000 | [6 empty] | Communication and media expert (20*fee@400/day) | 15000 |  | Project Coordinator & Project Board
|  |  | *Hire communication & media specialist | Planned | bar: Q2 May
|  |  | *Set up platforms (website, social media channels ..etc) | Planned | bar: Q2 Jun
|  | Implementation of communication & media strategy | [15 empty] | 1 | 5000 | [6 empty] | Workshop (3 Day Media Training for 15 people) | 5000
|  |  | *Create video and infographics for the launch | Planned | bar: Q3 Jul
|  |  | *Prepare for Report' s dissemination events | Planned | bar: Q3 Jul
|  | Conduct one media training |  | Planned | [13 empty] | 1 | 5000 | [6 empty] | Photojournalist 10*fee@450/day) | 5000 | bar: Q2 May to Q2 Jun
|  | Prepare media material and participant and distribution lists for the launch |  | Planned | [13 empty] | 1 | 5000 | [6 empty] | Communication and Media Material | 5000 | bar: Q3 Aug to Q4 Oct
| Sub total | [25 empty] | 30000
| 2.2 Launch the NHDR | Prepare for and conduct the launch event of the NHDR |  | Planned | [13 empty] | 2 | 10000 | [6 empty] | Workshop Costs: Cost of Launch Event | 20000 |  | Project Coordinator & Project Board | bar: Q4 Oct
|  |  | *hold one post-launch regional event | Planned | bar: Q4 Oct
|  |  | *Follow-up media interviews and publich inquiries | Planned | bar: Q4 Oct
| Sub total | [25 empty] | 20000
| 2.3 Develop and implement an advocacy strategy | Conduct two workshop to develop an advocacy strategy |  | Planned | [13 empty] | 1 | 2500 | [6 empty] | Workshop facilitator (10 * workshop + prep days fees @ US$ 400/day) | 2500 |  | Project Coordinator/Follow up Committee | bar: Q4 Nov to Q4 Dec
|  | Implement the advocacy strategy |  | Planned | [13 empty] | 1 | 5000 | [6 empty] | Advocacy activities costs by the project | 5000 | bar: Q4 Oct to Q4 Dec
| Sub total | [25 empty] | 7500
| 2.4 Assess influence and Follow up (Includes Monitoring) | Pre and post assessments of participants’ knowledge |  | Planned | [13 empty] | 1 | [7 empty] | UNDP Communication and media resource people/NHDR Focal Point | 0 |  | Project Coordinator/Follow up Committee
|  | Media monitoring and documentation of any policy, position of policy decision-maker or legislative change |  | Planned | [13 empty] | 1 | [7 empty] | Consultant to develop project document | 0
|  | Develop project to build on NHDR |  | Planned | [13 empty] | 1 | [8 empty] | 0
| Sub total | [25 empty] | 0
Total Output 2 | [26 empty] | 57500
| Project Coordinator |  |  | On Progress | [13 empty] | 12 | 7300 |  | 12 Months |  |  |  |  | 12* Salary @US$ 7,500/Month | 87600
| Miscellaneous | [16 empty] | 1 | 0 | [6 empty] | 1*Pcs@1,500 + Stationary | 0
| EVALUATION | [16 empty] | 1 | 9000 | [6 empty] | Independent evaluator (20*fee@ US$ 500/Day) | 9000
| GSM | [17 empty] | 0.03 | [7 empty] | 12888
| Sub total | [25 empty] | 96600
Total Output 3 | [26 empty] | 96600
Total Budget | [26 empty] | 429600
Total Budget including 3% GMS | [26 empty] | 442488
[5 empty] | current consultant | Q2 Jun: Contract to be renewed |  |  |  | Advertised
[5 empty] | Under hiring process | Q2 Jun: prospective consultant
Agreed by (signatures):
|  |  | Secretary General of the Supreme Council for Planning and Development | [15 empty] | UNDP Deputy Resident Representative
|  |  | Dr. Khalid Mahdi | [16 empty] | Dima AL-Khatib