## 2017 AWP
Project Title: | Institutional strengthening and strategic development of Public Authority for Sports | [7 empty] | Award Number: |  |  |  | 97664 |  |  |  | Total Budget |  |  |  |  | 1042661.79 |  |  | Prepared by:
Project Number: | 00101305 | [7 empty] | Year: |  |  |  | 2017 |  |  |  | Fund Number: |  | 30071 |  |  | Donor Number: |  | 145 | Certified by:
Contributing Outcome (CPD) | Human development accelerated through high-caliber human capital and increased social empowerment.
Indicative Output(s): | Strategic plans for strengthening human capital developed with focus on building capacity and career advancement, with special attention to women and youth.
Output Indicatirs, Baseline, Targets | Activities (as per Atlas AWP) | Sub activity | LTA Company | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender |  |  |  | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable |  | Account Code | Budget Description | Amount USD $
Output 1 Restructured and more effective PAS for the promotion of an active youth community. Indicators: 1.1 Level of achievement in the institutional and business operations infrastructure 1.2 Level of improved human resources capacities performance 1.3 Level in the development of “sports for all” unit 1.4 Level of increased efficient and effective support services to clubs and federations Baseline: 1.1 :0 1.2 :0 1.3 :0 1.4 :0 Targets: 1.1 :2 1.2 :1 1.3 :3 1.4 :2 | 1.1 Improve institutional organizational structure for PAS | 1.1.1 Conduct an institutional skills audit and analysis of all PAS job descriptions to create functional job categorization and descriptions | Arup | [13 empty] | 1 | 30000 | [7 empty] | 30000 | bar: Q3 Jul to Q3 Sep
|  | 1.1.2 Support the Implementation of a new PAS organogram/structure with delegations of authority and defined lines of reporting | Arup | [13 empty] | 1 | 87207 | [7 empty] | 87207 | bar: Q1 Mar to Q2 Jun
|  | 1.1.3 Develop and Implement standard operating procedures, business/administrative processes and systems improvements | Arup | [13 empty] | 1 | 47453 | [7 empty] | 47453 | bar: Q1 Mar to Q3 Sep
| Sub Total | [24 empty] | 164660
| 1.2 Implementation of PAS Human Capital Strategy | 1.2.1 Develop and implement a new Human Resources Strategy aligned with the new PAS organogram and informed by the institutional skills audit using PAS HR database | Arup - Extra | [13 empty] | 1 | [8 empty] | 20000 | bar: Q4 Nov to Q4 Dec
|  | 1.2.2 Conduct staff capacity needs assessment and create capacity development plan including design and implementation of a skills and mentoring programme | Arup - Extra | [13 empty] | 1 | [8 empty] | 20000 | bar: Q3 Jul to Q4 Oct
|  | 1.2.3 Pilot a Performance Management System for merit based assessment of PAS staff. | Next Year | [13 empty] | 1 | 0 |  |  |  | National |  | 75700 |  | 0
| Sub total | [24 empty] | 40000
| 1.3 Support the development of a new "Sports for All" Unit within PAS' framework to promote a culture of sports entertainment in Kuwait | 1.3.1 Develop a 'Sports for All" Strategy which would strive to achieve a healthy living and Women participation in sports which are aligned with the SDG's | KPMG | [13 empty] | 1 | 40686 | [7 empty] | 40686 | bar: Q2 Apr to Q2 May
|  | 1.3.2 Develop an Action Plan and support the implementation of the "Sports for All" Strategy | KPMG | [13 empty] | 1 | 37561 | [7 empty] | 37561 | bar: Q2 May to Q3 Jul
| Sub total | [24 empty] | 78247
| 1.4 Improve PAS’ sponsorship strategy to support sports clubs and federations. | 1.4.1 Assess PAS' current holdings, assets, local investments and Facilities including its sports clubs and federation buildings to identify its needs | Arup | [13 empty] | 1 | 75911 | [7 empty] | 75911 | bar: Q2 Apr to Q2 May; Q4 Oct to Q4 Dec
|  | 1.4.2 Develop an investment strategy aiming at maximizing PAS' Use of assets and related financial resources | Decision Needed | [13 empty] | 1 | 0 | [7 empty] | 0
|  | 1.4.3 Upgrade PAS’ current automated Membership system linking it to all sports Clubs and Federations to improve monitoring and auditing. | Arup | [13 empty] | 1 | 75000 | [7 empty] | 75000 | bar: Q2 Apr to Q2 May; Q4 Nov to Q4 Dec
|  | 1.4.4 Develop a new electoral voting system for all sports clubs to improve the election process. | Arup | [13 empty] | 1 | 75000 | [7 empty] | 75000 | bar: Q2 Apr to Q2 May; Q4 Nov to Q4 Dec
|  | 1.4.5 Support PAS’ constructional developments to improve all sports facilities. | [14 empty] | 1 | 96000 | [7 empty] | 96000
| Sub Total | [24 empty] | 321911
Total Output1 | [25 empty] | 604818
Output 2: PAS’ strategy developed and improved for more effective organisation. Indicators: 2.1 Number of new formulated legislations and policies 2.2 Level of progress in establishing a knowledge centre at PAS Baseline: 2.1 : 0 2.2 : 0 Targets: 2.1 :1 2.2 : - | 2.1 Develop Sports policies and legislations to improve PAS’ standards. | 2.1.1 Review current policies and legislations to identify any unforeseen gaps. | Next Year | [13 empty] | 1 | 0 | [7 empty] | 0
|  | 2.1.2 Formulate and submit comprehensive proposals to amend current policies and legislations. | Next Year | [13 empty] | 1 | 0 | [7 empty] | 0
| Sub total | [24 empty] | 0
| 2.2 Support PAS’ conduction of researches and studies for effective strategic planning and the establishment of a knowledge centre for sports. | 2.2.1 Review PAS’ current strategy and work processes to identify discrepancies within its System. | KPMG | [13 empty] | 1 | 17929 | [7 empty] | 17929 | bar: Q2 Jun to Q3 Jul
|  | 2.2.2 Conduct analytical data search on sports to build a comprehensive database. | KPMG | [13 empty] | 1 | 26553 | [7 empty] | 26553 | bar: Q3 Aug to Q3 Sep
|  | 2.2.3 Conduct studies and statistical analysis to support the development and improvement of PAS' strategy | KPMG | [13 empty] | 1 | 16330 | [7 empty] | 16330 | bar: Q3 Aug to Q4 Oct
| Sub total | [24 empty] | 60812
Total Output 2 | [25 empty] | 60812
Output 3: Communication and outreach strategy to improve PAS’ position locally and internationally . Indicators: 3.1 Number of PAS campaigns developed and implemented 3.2 Number of new developed agreements locally and internationally 3.3 Number of implemented sport programmes Baseline: 3.1 :0 3.2 :0 3.3 :0 Targets: 3.1 : - 3.2 : - 3.3 : - | 3.1 Implement awareness campaigns and outreach programmes. | 3.1.1 Conduct surveys and studies to evaluate youth awareness, needs and satisfaction over PAS’ services. | KPMG | [13 empty] | 1 | 43607 | [7 empty] | 43607 | bar: Q3 Aug to Q3 Sep
|  | 3.1.2 Develop and implement a strategy to improve the brand identity of PAS and to assure it is consistent throughout all communication channels reflecting PAS strategy | KPMG | [13 empty] | 1 | 53597 | [7 empty] | 53597 | bar: Q3 Sep to Q4 Oct
| sub total | [24 empty] | 97204
| 3.2 Strengthen partnerships with other government entities, NGO’s, international Organizations, and the private sector to enable PAS to gain valuable knowledge | 3.2.1 Review and assess current agreements to detect potential cooperation opportunities. | KPMG | [13 empty] | 1 | 17042 | [7 empty] | 17042 | bar: Q3 Aug to Q3 Sep
|  | 3.2.2 Conduct research on potential engagement opportunities between other NGO’s and international organizations. | KPMG | [13 empty] | 1 | 28047 | [7 empty] | 28047 | bar: Q3 Aug to Q3 Sep
|  | 3.2.3 Develop new agreements (MOUs, LOA’s) to foster future partnerships. | KPMG | [13 empty] | 1 | 26540 | [7 empty] | 26540 | bar: Q3 Aug to Q3 Sep
| Sub total | [24 empty] | 71629
| 3.3 Develop Programmes for PAS to attract different members of society to participate in sports and leisure activities. | 3.3.1 Review all current local and international programmes to Identifying best practices. | KPMG | [13 empty] | 1 | 16292 | [7 empty] | 16292 | bar: Q3 Sep to Q4 Oct
|  | 3.3.2 Develop an action plan to launch effective sports programmes focusing on human development objectives and the SDG’s | KPMG | [13 empty] | 1 | 46038 | [7 empty] | 46038 | bar: Q3 Sep to Q4 Oct
| Sub Total | [24 empty] | 62330
Total Output 3 | [25 empty] | 231163
|  |  |  | Project Manager | [13 empty] | 115500 |  | 1 | [5 empty] | 115500
| Evaluation | [18 empty] | 1 | [5 empty] | 0
| Project Administration Costs |  |  | GMS | [13 empty] | 0.03 | [7 empty] | 30368.79
| Sub Total | [24 empty] | 145868.79
Total Output 4 excluding GMS | [25 empty] | 115500
Total Budget | [25 empty] | 1012293
Total Budget including 3% GMS | [25 empty] | 1042661.79
|  |  |  | current consultant | Q2 Jun: Contract to be renewd |  |  |  | Advertised
|  |  |  | Under hiring process | Q2 Jun: prospective consultancy
Agreed by (signatures):
|  | Secretary General of the Supreme Council for Planning and Development |  | Managing Director Public Authority for Sport | Q4 Oct: UNDP Deputy Resident Representative
|  | Dr. Khalid Mahdi |  | Shaikh Ahmed Mansour Al-Ahmad Al-Sabah | Q4 Oct: Dima AL-Khatib