## Slide 1: Project Board Meeting January 2013
Board Meeting presentation for the Central Statistics Bureau support project
Samir Hawana, Project Manager

## Slide 2
1
Executing Agency: | United Nations Development Programme
Country: | Kuwait
Project: | Support the development of the Central Statistics Bureau Project ATLAS ID: 81254
Project Duration: | 2011-2013
Project Budget: | $3,500,000
Reporting Period: | July–September 2012
Funds Allocated (US $): | 
Contact Persons: | UNDP Resident Representative
Project Title: Support the development of the Central Statistics Bureau
ATLAS ID: 81254
Notes: 1/14/2013
CSS2002Hello
1

## Slide 3: 1.Financial summary (until January 2013)
2
Chart: 
| Total project bujet | Total expenditure
y | 3500000 | 632592
Notes: 1/14/2013
CSS2002Hello
2

## Slide 4: Expert Roster
Expert Roster Central Statistics Office (Project 81254) | 
Pending | Project manager
Kevin Lawler | SAM
Dr. Jafar Haji pending | Economics Expert
Dr. Jasem Al Ali pending | GIS Expert
Pending | Household Income & Expenditure Surveys report evaluation
Emad Saddad Abd El-Hakeim | Executive Administrative Support
Salah Eldeen AlHaj | Demography
Hamed AlFuraih | Admin. Affairs
Pending | Sampling
Pending | IT expert
Pending | National Accounts Expert
Pending | IT expert
Khaled Affan | Economics Expert
SAM Building Project | Consultancy firm pending

## Slide 5: 2.Progress summary
EXPECTED OUTPUTS
1.4.2. National statistical tools and information systems developed Output Indicators: Presence of system for monitoring economic information and national accounts Availability of a CGE model for the SAM # of statisticians trained on newly developed IS # of training courses conducted # of CSB staff benefitting from SAM applications # of studies published on the national population census AWP Targets: 1.National SAM for national accounts developed 2.National cadres trained on applications of SAM 3. National Dynamic CGE developed 4. 50 cadres trained on applications of SAM 5. 8 studies published on the 2011 National Population and Housing Census

## Slide 6
PLANNED ACTIVITIES | 
Activity 1.4.2.1: Transition from SNA 1993 to SNA 2008 for the development of the SAM for national accounts for the period 2005-2010 | 
Activity budget lines | 
1.4.2.1.1:Identify the National Accounts and other economic data between 2005-10 for the SAM | 
1.4.2.1.2: Develop TOR for SAM RFP | 
1.4.2.1.3: Advertise RFP and select service provider | 
1.4.2.1.4: Contract SP to develop SAM | 
1.4.2.1.5: Develop composite indices and economic indicators for the SAM | 
1.4.2.1.6: Design the matrix | 
1.4.2.1.7:Implement the SAM on a statistical software | 
1.4.2.1.8: Conduct due diligence of SAM | 
1.4.2.1.9: Launch SAM | 
Activity 1.4.2.2: Dynamic Computable General Equilibrium Model (CGE) for Kuwait developed | 
Activity budget lines | 
1.4.2.2.1:Identify the National Accounts and relevant economic data | 
1.4.2.2.2: Revise and prepare detailed Social Accountability Matrix for the model | 
1.4.2.2.3: Formulate the model’s equations and utilize appropriate software to estimate the model’s variables | 
1.4.2.2.4: Train national cadres on the CGE and SAM applications | 

## Slide 7
PLANNED ACTIVITIES | 
Activity 1.4.2.3: Information technology infrastructure of the CSB developed | 
Activity budget lines | 
1.4.2.3.1:Evaluate the automation infrastructure and information network of the CSB | 
1.4.2.3.2:Develop a training plan to build the technical capacities of CSB staff after conducting a needs assessment | 
1.4.2.3.3:Procure and install licensed software for CSB network | 
1.4.2.3.4:Recruit Applications Development Specialist for the CSB | 
1.4.2.3.5: Recruit information systems specialist to develop the technical capacities of the CSB | 
1.4.2.3.6: Conduct specialized courses as per the training plan | 
Activity 1.4.2.4: A series of statistical studies and researches on the results of the National Population and Housing Census developed | 
Activity budget lines | 
1.4.2.4.1:Prepare a study on the characteristics of growth trends in the private sector in the light of the results of General Census of Establishments 2011 | 
1.4.2.4.2: Preparation of a series of population studies on the results of the census, as follows: 1.Demographic profile of the population in Kuwait 2.Gender & age composition of the population in Kuwait 3.Levels, patterns and fertility trends in Kuwait (Kuwaiti women only) 4.Patterns and trends of marriage and divorce in Kuwait 5.Assess the quality of the 2011 census data in comparison with previous censuses 6.Analysis of census databases to build a data warehouse 7.The application of an automated system for data warehouse | 
Monitoring & Evaluation Activities & Final Review | 

## Slide 8: Challenges and constraints
7
CHALLENGES/CONSTRAINTS | LESSONS LEARNED | RECOMMENDATIONS | MANAGEMENT RESPONSE STRATEGY
1- The continuity of the project outputs | Never to assume that what is planned theoretically will materialize as many intermingling factors are involved | More coordination and commitment needed | A technical training plan for capacity-building of at CSB to be developed.
2-Theneed for a PM to follow up | The PM is to be available as needs are overreaching across the whole agency with various vital departments | The CSB should recruit a PM as per the 2012 AWP . | CSB must use the TOR in the PD to announce the position.
3-The novelty of NIM is causing confusion and delays and continuous guessing. | CSB and UNDP capacity building initiatives in that respect proved helpful. | UNDP should provide NIM training sessions to CSB relevant department t. | UNDP to take the initiative to plan for NIM training of national counterparts.
Notes: 1/14/2013
CSS2002Hello
7