CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

as of 31 March 2009

| Participating UN or Non-UN Organization: | UN Office for the Coordination of Humanitarian Affairs (OCHA) | UNCAPAHI Objective(s) covered: | Objective 6: Continuity under pandemic conditions |
| --- | --- | --- | --- |
| Implementing Partner(s): | All funds disbursed will be managed by selected implementing agencies within UN country teams. |
| Programme Number: | CFIA-B11 |
| Programme Title: | Pandemic Preparedness Small Project Funding Facility for UN Resident Coordinators |
| Total Approved Programme Budget: | US$ 400,000 |
| Location: | Countries with restricted implementation capacity (humanitarian preparedness) |
| MC Approval Date: | 14 November 2008 |
| Programme Duration: | 12 months | Starting Date: | 01 February 2009 | Completion Date: | 31 December 2009 |
| Funds Committed: | US$ 340,000 | Percentage of Approved: | 85% |
| Funds Disbursed: | US$ 0 | Percentage of Approved: | 0% |
| Expected Programme Duration: | One year | Forecast Final Date: | 31 December 2009 | Delay (Months): |  |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| UN country teams support small projects which make a significant impact in stimulating greater progress in multisectoral pandemic preparedness in low capacity countries. | OCHA established an inter-agency committee to evaluate proposals under the $400,000 fund. The committee included representatives of USAID, IFRC, the Core Group, UNICEF, OCHA Dakar, and PIC Geneva. WFP were also invited to join but were unable to attend. OCHA wrote to all UN Resident Coordinators across the world explaining the concept of the fund and inviting proposals. 15 proposals were received to the value of US$ 1,271,459. The committee met by teleconference on 13 March 2009 and approved four proposals for funding: 1. Lao PDR Project title: Developing a multi-sectoral pandemic preparedness Plan for Lao PDR Project value: US$ 88,000 Implementing agency: UNDP 2. Zambia Project title: Coordinated response to pandemic induced disasters using existing disaster coordination mechanisms Project value: US$ 95,000 Implementing agency: UNDP 3. Nigeria Project title: Strengthening National Pandemic Preparedness in Nigeria Project value: US$ 80,000 Implementing agency: UNDP 4. Mozambique Project title: Strengthening readiness for critical essential services during the pandemic Project value: US$ 77,000 Implementing agency: WHO The committee also agreed that the balance of the funds should be allocated to Cambodia if Cambodia was able to provide a suitable proposal by the end of April – or failing that DPRK, if USAID confirmed that USAID was content for its funding to be used in DPRK – or failing that be offered as an expansion to one of the existing four projects if one of the existing four projects can deliver a robust case for modest expansion. | It is too early to comment on the success of the projects selected as they were selected on 13 March and are at too early a stage of implementation. |

Qualitative achievements against outcomes and results:

The CFIA has transferred the project funding to UNDP Laos, UNDP Zambia and UNDP Nigeria. OCHA’s Regional Planning Officers will keep in regular touch with project implementing agencies to keep abreast of progress.

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.