CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

As of 30 June 2009

| Participating UN or Non-UN Organization: | UN Office for the Coordination of Humanitarian Affairs (OCHA) | UNCAPAHI Objective(s) covered: | Objective 6: Continuity under pandemic conditions |
| --- | --- | --- | --- |
| Implementing Partner(s): | All funds disbursed will be managed by selected implementing agencies within UN country teams. |
| Programme Number: | CFIA-B11 |
| Programme Title: | Pandemic Preparedness Small Project Funding Facility for UN Resident Coordinators |
| Total Approved Programme Budget: | US$ 400,000 |
| Location: | Countries with restricted implementation capacity (humanitarian preparedness) |
| MC Approval Date: | 14 November 2008 |
| Programme Duration: | 12 months | Starting Date: | 01 February 2009 | Completion Date: | 31 December 2009 |
| Funds Committed: | US$ 340,000 | Percentage of Approved: | 85% |
| Funds Disbursed: | US$ 00 | Percentage of Approved: | 0% |
| Expected Programme Duration: | One year | Forecast Final Date: | 31 December 2009 | Delay (Months): |  |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| UN country teams support small projects which make a significant impact in stimulating greater progress in multisectoral pandemic preparedness in low capacity countries. | Overall, an inter agency committee has been established to take decisions on which proposals to fund. In the first round 4 proposals were supported. This left a $60,000 balance. It was decided to offer this balance to the country team in Vietnam. The urgency of dealing with the current H1N1 crisis delayed WHO in Vietnam’s capacity to finalise a detailed proposal. In the meantime, an additional tranche of funding for this small project UN Resident Coordinator multi-sector fund was allocated by DFID. As a result a second wave of proposals has been invited and received. It was decided to deposit the remaining $60,000 alongside the new resources and to consider the Vietnam proposal alongside the many new proposals for the second tranche of funds. The committee is due to meet in August to determine which projects to support from the second tranche. 1. Zambia In Zambia, UNDP as implementing agency for this project has been in discussions with the Disaster Management and Mitigation Unit (DMMU) which is the Government coordinating unit for disasters, and the Ministry of Health and Ministry of Agriculture. Discussions are ongoing with the Ministries with a view to moving the coordination of pandemic emergencies to the DMMU with the technical ministries being responsible for the technical aspects. The discussions will lead to the DMMU assuming the coordinating role for the pandemic emergency and developing a Government business continuity plan. The current national action plan focuses primarily on containment, sensitization of communities and setting up of AHI/H1N1 centres. It does not give sufficient attention to the logistics of implementation. It has become clear that there will be need to be a Government-owned BCP. Once the discussions are concluded, that is where the CFIA funding is mostly going to be applied. 2. Mozambique The Mozambique project has been delayed owing to (a) some confusion about who is responsible for requesting the funds transfer from the CFIA to enable progress, which has now been clarified and (b) ongoing attempts at country level to solicit additional funding from other UN agencies. PIC is working with the country team to expedite progress. 3. Nigeria With allocated funds (US$ 80,000) and UNDP Country Office in Nigeria as implementing agency, the following activities have so far been implemented: Building consensus on pandemic preparedness process - The Avian Influenza Technical committee appointed a small committee to work out activities and a budget to complete the pandemic preparedness and planning process - The plan was presented to the technical committee and endorsed for implementation - The financial contribution for the process was shared between the UNRC Office, Centre for Disease Control and the World Bank funded Avian Influenza Control Project. - The Ministry of Health is hosting the process and providing secretariat support through the crisis centre Expansion and re-launching of the Pandemic Preparedness and response plan - The committee that was launched in 2007 was expanded -Membership was drawn from key ministries, Departments and Agencies that provide essential services and vital supplies in Nigeria, the UN System, Red Cross and CDC Next steps - Compilation of the draft plan by a consultant hired by the RC Office and inclusion of annexes - Presentation of the plan to stakeholders, Ministries, Departments and the Technical committee. - Conducting a table top simulation exercise to test the plan - Presentation of the plan to the steering committee - Approval of the plan by the Federal executive council Challenges and constraints - The drafting committee was set up by the steering committee in 2007. Since the new government came to power, the steering committee has not been active and this may be a stumbling block in the endorsement of the plan by the Federal Executive council. - Integration of pandemic preparedness planning into the disaster management structure of the National Environment and Management Agency (NEMA) may be a challenge due to the vested interests of key stakeholders -Some key Ministries had low level representation in meetings. This may prolong the process due to back and forth consultative processes 4. Lao PDR A first candidate for the position to be funded at National Emerging Infectious Diseases Coordination Office (formerly NAHICO) became unavailable and thus the recruitment process has been delayed, due to the need for re-advertisement. The CVs of candidates are now being studied and a decision will be made in the coming days. | At present in Zambia, discussions are underway with key Government stakeholders in order to precisely define the way forward. The Mozambique project has not yet been implemented, due to ongoing attempts to raise additional funds and confusion about responsibility for transferring the CFIA money. These issues are now being resolved. Significant progress made in Nigeria during the first phase of project implementation. Implementation has been delayed owing to recruitment problems (withdrawal of selected candidate). |

Qualitative achievements against outcomes and results:

In the current global pandemic phase 6 declared by WHO, there is more urgency to ensure that UNCTs and national Governments especially in the poorest countries are better prepared than before. In Nigeria, the process adopted in pandemic preparedness and response has generated interest from the non health sectors as they now understand their role and the broader impacts of a pandemic. It is important that the different sectors start working on comprehensive sectoral plans to supplement the central government. In order to ensure expeditious progress, a lesson has been learnt that PIC Regional Planning Officers need to be in regular contact with UNDP and WHO focal points in country teams, to stimulate implementation and to identify and address bottlenecks.

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.