## ANNUAL WORK PLAN IP DoS: May 2010- December 2010

Award ID: 00059884

Revision 1: 31 May 2010

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME 2010 | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
| And baseline, associated indicatorsand annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Account code | Itemize code | Budget Description | Amount USD |
| Output 1: A clear statistics mandate is established Indicator: Availability of draft new Statistics Law; Targets: Final draft of Statistics Law is prepared and presented to National Assembly members for approval Baseline: Statistics law decree 140/PM 202 is amended and draft law is presented to the Government | 1.1: Series consultation seminars to present and share draft of law before proceed to Gov't approved (reproduction of draft of law) |  |  |  |  |  | UNDP |  | 72505 | Supply | 200.00 |
|  |  |  |  |  |  |  | UNDP |  | 74210 | Copy | 400.00 |
|  |  |  |  |  |  |  | UNDP |  | 74220 | Translation | 1,000.00 |
|  | Total: |  |  |  |  |  |  |  |  |  | 1,600.00 |
|  | 1.2. Three consultation workshops with National Assembly on Statistics Law: Northern part in Luang Prabang; Southern part in Champasak; Central part in Vientiane province. |  |  |  |  |  | UNDP |  | 71610 | ticket | 11,400.00 |
|  |  |  |  |  |  |  | UNDP |  | 71620 | DSA | 17,570.00 |
|  |  |  |  |  |  |  | UNDP |  | 71635 | travel | 10,600.00 |
|  |  |  |  |  |  |  | UNDP |  | 72505 | Supply | 600.00 |
|  |  |  |  |  |  |  | UNDP |  | 73107 | Meeting room | 10,130.00 |
|  |  |  |  |  |  |  | UNDP |  | 73410 | Car renting | 2,600.00 |
|  |  |  |  |  |  |  | UNDP |  | 74210 | copy | 1,250.00 |
|  |  |  |  |  |  |  | UNDP |  | 74525 | Misc. | 500.00 |
|  | Total: |  |  |  |  |  |  |  |  |  | 54,650.00 |
|  | Total Output 1 | 56,250.00 |
| Output 2 : Increased understanding of National Statistical Development Strategy (NSDS) through dissemination and information sharing events Indicator: Availability of communications, outreach and dissemination plan for National Statistical Development Strategy (NSDS) (2010-2015) that includes gender considerations; Availability of NSDS is Lao and English; distribution list of NSDS; report specifying the LaoInfo and NSEDP indicator metadata definitions. Target: A clear communications, outreach and dissemination plan for the National Statistical Development Strategy (NSDS) is established and implemented which includes gender considerations; NSDS is available in Lao and English and disseminated to key stakeholders; common indicators between NSEDP M&E and LaoInfo are decided on. Base line: No communication plan for National Statistical Development Strategy (NSDS) available; NSDS finalized and in process of being approved; no common indicators identified between LaoInfo and NSEDP, a list of M&E indicators for NSEDP have been indentified however, further discussion is required to finalize the list of NSEDP ME indicators. . | 2.1. User Producer Meeting (Annual Statistics Forum to discuss on AWP 2010-2011 for National Statistics System, National Statistical Development Strategy (NSDS), Statistics Law and other (subject matter)) |  |  |  |  |  | UNDP | 71600 | 71610 | Air ticket | 2,000.00 |
|  |  |  |  |  |  |  | UNDP | 71600 | 71620 | DSA | 9,000.00 |
|  |  |  |  |  |  |  | UNDP | 71600 | 71635 | Travel (petrol) | 5,000.00 |
|  |  |  |  |  |  |  | UNDP | 72500 | 72505 | Supply | 300.00 |
|  |  |  |  |  |  |  | UNDP | 73100 | 73107 | Meeting room | 5,000.00 |
|  |  |  |  |  |  |  | UNDP | 73400 | 73410 | Car renting | 1,200.00 |
|  |  |  |  |  |  |  | UNDP | 74200 | 74210 | Copy | 700.00 |
|  |  |  |  |  |  |  | UNDP | 74200 | 74220 | Translation | 500.00 |
|  |  |  |  |  |  |  | UNDP | 74500 | 74525 | Misc. | 300.00 |
|  | Total: |  |  |  |  |  |  |  |  |  | 24,000.00 |
|  | 2.2. Translation National Statistical Development Strategy (NSDS) 2010-2020 from Lao to English |  |  |  |  |  | UNDP | 74200 | 74210 | Copy | 500.00 |
|  |  |  |  |  |  |  | UNDP | 74200 | 74220 | Translation | 3,750.00 |
|  |  |  |  |  |  |  | UNDP | 72500 | 72505 | Supply | 200.00 |
|  | Total: |  |  |  |  |  |  |  |  |  | 4,450.00 |
|  | 2.3. Prepare and carry out the programme of activities for the celebration of Lao Statistics Day. |  |  |  |  |  | UNDP |  | 71610 | Air ticket | 3,000.00 |
|  |  |  |  |  |  |  | UNDP |  | 71620 | DSA | 5,100.00 |
|  |  |  |  |  |  |  | UNDP |  | 71635 | Travel (petrol) | 5,500.00 |
|  |  |  |  |  |  |  | UNDP |  | 72505 | Supply | 200.00 |
|  |  |  |  |  |  |  | UNDP |  | 73107 | Meeting room | 3,000.00 |
|  |  |  |  |  |  |  | UNDP |  | 73410 | Car renting | 500.00 |
|  |  |  |  |  |  |  | UNDP |  | 74210 | Copy | 2,000.00 |
|  |  |  |  |  |  |  | UNDP |  | 74220 | Translation | 500.00 |
|  |  |  |  |  |  |  | UNDP |  | 74525 | Misc. | 200.00 |
|  | Total: |  |  |  |  |  |  |  |  |  | 20,000.00 |
|  | 2.4. Recruit communication specialist to prepare dissemination and advocacy plans and organize workshops |  |  |  |  |  | UNDP |  | 71505 | Salary | 24,000.00 |
|  |  |  |  |  |  |  |  |  | 72505 | Supply | 200.00 |
|  |  |  |  |  |  |  | UNDP |  | 74525 | Misc. | 200.00 |
|  | Total: |  |  |  |  |  |  |  |  |  | 24,400.00 |
|  | 2.5 Support LaoInfo to be monitoring tool for MDG, NSEDP and HDI |  |  |  |  |  | UNDP |  |  |  | 3,500.00 |
|  |  |  |  |  |  |  | UNDP |  |  |  | - |
|  | Total: |  |  |  |  |  |  |  |  |  | 3,500.00 |
|  | Total Output 2: | 76,350.00 |
| Output 3: Strengthen technical and managerial capacities for Statistics through regional and international statistical cooperation meetings Indicators: Workshop reports indicating how the Lao participants have benefitted from the workshop; list of nominations to attend meetings should reflect equal opportunities for men and women. Targets: DoS staff maintains statistical networks through participation in international and regional meetings; Equal opportunity for men and women to attend the meetings. Baseline: Regular attendance of DoS staff at international and regional meetings | 3.1: Participation in meeting UN Statistical Commission Session in New York (1 person) |  |  |  |  |  | UNDP | 71600 |  | ticket, dsa, terminal | 8,000.00 |
|  | Total: |  |  |  |  |  |  |  |  |  | 8,000.00 |
|  | 3.2: Participation in Regional and ASEAN meeting |  |  |  |  |  |  |  |  |  | - |
|  | 3.2.a. ASEAN Statistical Heads of Missions (ASHOM) meeting in Vietnam for 4 pax |  |  |  |  |  | UNDP |  | 71605 | ticket | 1,000.00 |
|  |  |  |  |  |  |  | UNDP |  | 71615 | DSA | 3,100.00 |
|  |  |  |  |  |  |  | UNDP |  | 71635 | Travel | 200.00 |
|  |  |  |  |  |  |  | UNDP |  | 74525 | Misc. | 100.00 |
|  | Total: |  |  |  |  |  |  |  |  |  | 4,400.00 |
|  | 3.2.b. Statistical Commision Meeting (UN ESCAP in Bangkok) 2 pax |  |  |  |  |  | UNDP |  | 71605 | ticket | 700.00 |
|  |  |  |  |  |  |  | UNDP |  | 71615 | DSA | 1600.00 |
|  |  |  |  |  |  |  | UNDP |  | 71635 | Travel | 100.00 |
|  |  |  |  |  |  |  | UNDP |  | 74525 | Misc. | 100.00 |
|  | Total: |  |  |  |  |  |  |  |  |  | 2,500.00 |
|  | Total Output 3: | 14,900.00 |
| Output 4: Donor Coordination mechanism established and resources mobilized to support implementation of the NSDS Indicator: terms of reference of donor coordination mechanism based on the NSDS available; availability of resource mobilization plan; Targets: Coordination mechanism for donor support to DoS developed and agreed; Resource mobilization plan for the programme in support of the National Statistical System is developed. Baseline: no coordination mechanism for NSDS; no resource mobilization plan for NSDS. | 4.1. Reconvene UN Task force on Statistics |  |  |  |  |  | UNDP |  | 74525 | Misc. | 500.00 |
|  | Total: |  |  |  |  |  |  |  |  |  | 500.00 |
|  | 4.2. Develop common and agreed principles (ToR) for donor coordination mechanism |  |  |  |  |  | UNDP |  |  |  | - |
|  | Total: |  |  |  |  |  |  |  |  |  | - |
|  | 4.3. Donor consultation meeting to discuss on financing and resource mobilization for National Statistical Development Strategy (NSDS) 2010-2020) |  |  |  |  |  | UNDP |  | 73107 | Meeting room | 1,500.00 |
|  |  |  |  |  |  |  | UNDP |  | 74525 | Misc. | 500.00 |
|  | Total: |  |  |  |  |  |  |  |  |  | 2,000.00 |
|  | Total Output 4 | 2,500.00 |
| Output 5: Project Document developed and approved Indicator: LPAC minutes for project Targets: Necessary Project Documentation Completed and a Programme to Support the National Statistical System ready to start by January 1, 2011. Baseline: draft Project Document | 5.1. Finalize ProDoc |  |  |  |  |  |  |  |  |  | - |
|  | Total: |  |  |  |  |  |  |  |  |  | - |
|  | 5.2. Conduct LPAC meeting |  |  |  |  |  |  |  |  |  | - |
|  | Total: |  |  |  |  |  |  |  |  |  | - |
|  | Total Output 5 | - |
|  | Grand Total: |  |  |  |  |  |  |  |  |  | 150,000.00 |