Purpose/Description of the Quarterly Progress Report:

A quarterly project progress report should be prepared toward the end of each quarter to document the performance of each project and communicate it to appropriate stakeholders. This review will focus on the extent to which progress is being made towards production of deliverables required to generate output and identification of project issues and their solutions.

Format:

Any standard appearance to which the Deliverable must conform:

Quarterly Project Progress Report Atlas

Derivation/Inputs:

Quarterly Progress Report receives inputs from:

- Deliverable Descriptions

- Quality Log

- Issues Log

- Risks Log

Quality Control Method:

Project Assurance will review the Quarterly Progress Report and ensure that progress is properly documented including % progress towards deliverables, risks and issues.

Accountabilities:

Accountabilities for producing the Annual Review Report:

- Project Manager

Quarterly Report

| Date: June 30th 2013 Award ID: Description: Implementing Partner: UNDP Period Covered: April – 30 June 2014 1. Project Issues: |
| --- |
| Updated Project Risks: The worsening of the security situation in the country and the re-focusing from the media side on the security issues | Updated Project Issues: NA |
| 2. Project Performance |
| OUTPUT C: Conflict Sensitive Media Production Supported (Output Project 00088560) ID Description: UNDP has been working with the print and electronic media since 2008 building their capacities in conflict-sensitive reporting skills. So far, 40 mid-career journalists have been trained and they form a network that works towards a peace-oriented media coverage, both in terms of inter-community harmony within Lebanon and between the Lebanese and Syrians. Since 2012, UNDP has been supporting this network of journalists to jointly produce quarterly newspaper supplements that aim at reflecting the socio-economic impact of the Syrian crisis in a positive manner and giving peace and harmony related messages to both the hosts and the refugees. This component will support strengthening and widening of the journalists’ network and will contribute to the joint production of 4 joint quarterly news supplements. A number of ancillary visibility products such as newsletters and videos will also be produced and disseminated. |
| Activity ID: OUTPUT C: Deliverable Description: The UNDP Peace Building in Lebanon project and as planned, published its fourth joint news supplement which was distributed with the two leading national newspapers Annahar and Assafir (and which target two politically opposing audience in Lebanon, March 14th and March 8th) on Friday May 30th 2014. On May 28th 2014, two days before the publication date, UNDP through its Resident Representative, Mr. Ross Moutain, signed a Memorandum of Understanding (MoU) with both Annahar and Assafir newspapers represented by Annahar Editor-in-Chief, Mr. Ghassan Hajjar, and Assafir Managing Editor, Mrs. Hanady Salman. The signature session which was covered by the two media outlets in addition to LBCI TV channel, took place in the presence of H.E. Ambassador of Japan, Mr. Seiichi Otsuka and the First Secretary of the Japanese Embassy, Mr. Masami Ishii. The MoU aims at providing a framework of cooperation and facilitating the collaboration between the parties in regards to printing and distributing the supplements. 34,000 copies of the 4th issue of the joint news supplement where distributed for free with the two leading national newspapers, Annahar and Assafir. In addition, 2000 copies were distributed through Libanpost to all ministries, embassies, municipalities, media outlets, universities, and non-governmental organizations all over Lebanon. The supplement was also advertised on Annahar and Assafir websites and social networks, as well as on UNDP and the News Agency Websites. An episode on LBCI was broadcasted on the issue, as well as on “Radio Liban”. Journalists from Annahar, Assafir, Al Hayat newspapers, as well as Now Website and Al Modon electronic newspapers (belonging to different opposing political affiliations and communities) contributed to the supplement, sharing their views in one common space and highlighted the extraordinary resilience of Lebanese host communities and the positive impact-despite burdens- of Syrian and Lebanese living together and coping with the situation, contributing to reducing tensions between Syrians and Lebanese host communities and showing a brighter image than the one being circulated in different media outlets on the presence of Syrian refugees. This fourth issue tackled the following topics: Editorials by UNDP Resident Representative, the Japanese Ambassador, Assafir Managing Editor and Annahar Editor in Chief “Between Hermel and Homs, the Assi River…and great longing”, Bou Mediane Sahili, Al Modon Electronice Newspaper “Syrians in Achrafieh: they boosted its economy and introduced vitality and diversity”, Rayan Majed, Now Website “Arsal pays a high price for sheltering refugees; Syrians account for three times its population”, Saada Allaw, Assafir Newspaper “The Syrian displacement: economic advantages of a humanitarian crisis”, Bissan Tay, freelancer “Kin relations between Syrians and Lebanese families: do they increase family bonds or topple them?”, Michel Hallaq, Annahar Newspaper “The smell of the distant Syria comes out of kitchens in Lebanon”, Lamia Sahili, Al Hayat Website “Peace Building, the international community’s responsibility as well”, H.E. Minister of Social Affairs, Rachid Derbas “Graffiti” by Yazan Halawani The same issue was translated into English and send electronically to the international community in Lebanon, especially to those working on the Syrian crisis. As a follow up to the release of the supplement, and as planned, the project organized a discussion session on Tuesday, June 3rd 2014, which gathered the journalists who participated in writing the supplement, to present and discuss their contributions with a group of experts, journalists and civil society activists. The session was also an opportunity to collect news ideas and recommendations for the upcoming issues. The project also produced a short video explainer to brief the audience (during the MoU signature session and the discussion session) on the topics of the previous supplements and the content of the current one. This video explainer (2.18 mins) is produced by Wezank company. For each launching of the supplement and the discussion around it, the company will produce a similar video In addition, and as planned, the project is currently working on issuing the 1st newsletter which covers the activities implemented by the project during the last three months. 1000 Arabic and 1000 English copies will be printed and distributed in addition to the wide dissemination of an electronic version. Finally, some visibility materials for the project were produced as agreed. Two roll up banners were printed. 1000 commercial and 1000 luxury notebooks are being printed as well as 1000 folders. Indicators: Number of journalists engaged in the conflict sensitive reporting programme Number of joint news supplement published Current evaluation: Start and End Date: January 1st 2014- January 31st 2015 % Progress to date: 40% |
| Quality Criteria | Date | Results of Activities |
|  |  | User Perspective | Resource Status | Timeliness |
| Number of journalists engaged in the conflict sensitive reporting programme | May 2014 | “the discussion session around the supplement is important because it lets the audience know in person the journalists who wrote and it helps understand better and deeply the spirit and the angle of each article”, Khalil Khoury, editor in Chief, Al Shark newspaper During the discussion session the project had the chance to expand the circle of journalists who are involved in peace building and conflict sensitive activities. Having a wide audience was an opportunity to gather feedback from everyone and advocate for the topics the supplement is trying to spread. “This is a great initiative; this supplement enabled us to think in a new way regarding the issue of the repercussions of the Syrian crisis on Lebanon. You gave us hope and let us adopt a new angle when approaching this matter”. Nada Ouwatly, Ministry of Information and head of “Radio Liban” “it is important to give the audience the choice of suggesting new ideas”, Amer Mashmoushi, Editor in Chief, Al Liwaa newspaper These activities reminded people of the importance to foster the role of media in conveying positive messages and covering positive events, contributing this way in reducing tensions: “It is our duty to share any peace building related publication. National media should focus more on initiatives such as the supplement. It is a great project!” Laure Sleiman Saab, Head of the National News Agency | 20% | May June 2014 |
| Number of Joint news supplement published | May 2014 | “Thank you for giving me the chance to speak out loud and express my feelings regarding this issue in this supplement. Thank you for choosing me to write in the supplement, me, as a journalist coming from a remote border area (Hermel)”, Bou Mediane Sahili. Another journalist, Lamia Sahili, who contributed to the supplement, said “this supplement is like a breeze, like colors coming out of grey walls. It is a positive dose that can keep us going for some days to come”. The supplement was considered by both the journalists who contributed to it and the readers as a space for hope and a platform to convey positivity in the midst of the violent and hatred speech. | 30% | April till June 2014 |
| Financial Summary |
| Account | Fund | Donor | R. Party | Budget (USD) | Expenditure (USD) | Balance (USD) |
| 71300 | 32045 | 00141 | UNDP/PB | 22,600 | 4,769.74 | 17,830.26 |
| 72100 | 32045 | 00141 | UNDP/PB | 71,000 | US$0 | 71,000 |
| 72700 | 32045 | 00141 | UNDP/PB | 0 | 1,264.3 | - 1264.3 |
| 74200 | 32045 | 00141 | UNDP/PB | 43,005.55 | 10,381.00 | 32,624.55 |
| 74700 | 32045 | 00141 | UNDP/PB | 0 | 4,774.17 | - 4,774.17 |
| 75700 | 32045 | 00141 | UNDP/PB | 0 | 112.36 | - 112.36 |
| 71400 | 32045 | 00141 | UNDP/PB | 46,000 | 7117.96 | 38,882.04 |
| 74100 | 32045 | 00141 | UNDP/PB | 3,024.08 | 0 | 3,024.08 |
| 75100 | 32045 | 00141 | UNDP/PB | 16,370.37 | 2,329.20 | 14,041.17 |
| 74500 | 32045 | 00141 | UNDP/PB | 19,000 | 190.52 | 18,809.48 |
| 72500 | 32045 | 00141 | UNDP/PB | 0 | 504.96 | - 504.96 |
| Total |  |  |  | 221,000 | 31,444.21 | 189,555.79 |

*The amount of USD 22,677.28 has also been committed on the system through signed contracts with third parties

| OUTPUT D: Living conditions in Palestinian Refugees gatherings hosting Palestinian and Syrian Refugees improved (Output Project 00087568) Refer to the map in Annex 1 for a list of Palestinian gatherings in Lebanon. |
| --- |
| Activity ID: Activity Result 4.1: Basic urban services rehabilitation and upgrading projects identified and agreed on by the community as priority covering the areas of electricity, solid waste management, sewage and water implemented. Note: Activities below are those that fall within the timeframe of the reporting period as per the ProDoc. Activity 4.1.1: Set up community local committees within Palestinian gathering hosting Syrian refugees to monitor implementation of interventions. Indicator: Number of communities and local representatives engaged in developing collaborative mechanisms for improved service delivery. Since January 2014, UNDP has been organizing consultative meetings with local actors in the gatherings and concerned municipalities of the South Region and Beirut to identify needs in basic urban services to respond to the increased influx of Palestinian Refugees from Syria (PRS). These meetings have resulted in a list of needs and projects that local communities require in order to enhance access to basic urban services (See Annex 2). The meetings provided the basis for establishing the community local committees that will follow up on the implementation of services in the third and fourth quarter of the year. Such committees have already been established by UNDP in areas of previous implementation in South Lebanon. UNDP will continue this practice with activities implemented through the Japan contribution, providing capacity building and training to local actors. Start and End Date: January 2014 – June 2014. % Progress to date: 90% |
| Quality Criteria | Date | Results of Activities |
|  |  | User Perspective | Resource Status | Timeliness |
| Local committees formed in areas of implementation. | June 2014 | Main needs and key interventions identified by local actors. Structure for local committees’ set-up to follow-up on implementation of activities in the second half of the year. |  | 90% |
| Activity 4.1.2: Strengthening mechanisms for inclusive dialogue and transparent planning among Palestinian gathering communities and neighbouring municipal authorities. Indicator: Number of communities and local representatives engaged with developing collaborative mechanisms for improved service delivery. In March 2014, UNDP organized two workshops at AUB that hosted representatives of popular and local committees and local NGOs in the 42 Palestinian Gatherings as well as with representatives from the concerned municipalities hosting these gatherings. Participants discussed the main challenges and urgent needs in these areas, especially following the increased pressure on the urban environment exerted by the accommodation of new refugees from Syria. The workshops concluded with a set of recommendations for required interventions and ways of coordination among local actors (refer to Annex 3 for summary of recommendation). % Progress to date: 40% |
| Quality Criteria | Date | Results of Activities |
|  |  | User Perspective | Resource Status | Timeliness |
| Mechanisms for inclusive dialogue strengthened among Palestinian gathering communities and neighbouring municipal authorities | Sept 2014 | Dialogue initiated between representatives in gatherings and municipalities. List of recommendation, agreed upon by local actors, developed. |  | 50% |
| Activity 4.1.4: Implement rehabilitation projects to ensure weather proofing, proper sanitation and safe electrical connectivity. Indicators: Number of water and sanitation, solid waste management, electrical network related interventions executed in areas with high density of refugees. Number of shelter units rehabilitated in terms of weather proofing, sanitation, electricity works Basic Urban Services: In preparation of basic urban services project (to be started in Q3 as per the project document), UNDP has carried out a community participatory appraisal of remaining urgent needs in the gatherings, in coordination with concerned municipalities. This has led to the identification of a number of projects in the gatherings of South and Beirut in the sectors of water and sanitation, solid waste management and electricity (go back to Annex 2). Although implementation is not set to start until Q3, the project has responded to an urgent need in Jabal el Halib gathering adjacent to Ain el Helwe Camp in Saida aea, which was suffering from shortage in water supply. In order to address this problem, the project installed a new water pump in the gathering, benefiting some 2,100 original refugees (PRL) and more than 1,000 new refugees (PRS). In order to address problems in the electricity sector in the gatherings, technical studies were prepared to enhance electricity supply in the Gatherings of South Lebanon. These studies were developed in collaboration with the Electricite du Liban (EDL) offices in Tyr and Saida and targeted a total of 25 Gatherings. The studies will be used to guide project activities in the electricity sector. In addition to improving access to electricity in the Gatherings, this initiative would mitigate the load on the surrounding areas causing insufficient supply and regular cut-offs. For a copy of the study, refer to Annex 4. Shelter: A preliminary needs assessment was initiated in April 2014 to identify shelters housing PRS households that are in urgent need of rehabilitation. The assessment, finalized by end of May, resulted in identifying around 250 shelters in South Lebanon and Beirut in need of rehabilitation and WASH works. UNDP is currently carrying out field visits to prioritize shelters in order to start works through the Japan contribution. In July 2014, detailed BOQs will be developed per shelter to guide rehabilitation and WASH works. The description, specification and unit cost of each item of shelter works were finalized (List of shelter items attached in Annex 5); items will be selected based on the needs in each shelter unit. Start and End Date: July 2014 – December 2014. % Progress to date: 20% |
| Quality Criteria | Date | Results of Activities |
|  |  | User Perspective | Resource Status | Timeliness |
| Projects implemented (BUS and shelter) | Dec 2041 | BUS projects identified, BOQs being developed. Shelter assessment finalized. |  | 100% |
| Activity 1.4.5 Working with local NGOs to roll out hygiene awareness raising campaigns. Indicators: Number of hygiene awareness raising campaigns rolled out. Hygiene promotion: In order to promote better hygiene and viable approaches on utilizing basic urban services, UNDP developed a hygiene awareness raising campaign, to be piloted in 12 gatherings (refer to Annex 6 for brief of the pilot campaign). These include the gatherings of: Chabriha, Jal el Bahr, Qasmieh and Maachouk in Tyre; Bustan el Kods, Baraksat, Sekke, Jabal Halib and Old Saida in Saida; Mankoubin and Mouhajjarin in Beddawi in the North. The pilot campaign will primarily target 15,000 children, youth and women, equally divided between PRL and PRS, as well as active local committees in the gatherings. The campaign was developed in partnership with UN-Habitat and the local NGO Developmental Action without Borders-Nabaa, following a hygiene assessment. The purpose of the campaign is articulated in the following objectives: Promoting change in hygiene behaviour in the communities; Raising awareness on viable methods to access and use available and implemented basic urban services and environmental resources; Advocating for the right of Palestinian gatherings to healthy environments. By the end of March 2014, Nabaa has finalized the hygiene assessment the 12 gatherings using the following methods: Semi structured interviews with local committees; Focus groups with women and youth; Participatory activities with children; Field team observations. These methods aimed at discovering the unsatisfied Hygiene needs and priorities as well as investing the main finding in designing the best tools and methods to be used within the Pilot phase. The main needs that emerged from the assessment were categorized along the following sectors (refer to Annex 7 for hygiene needs assessment report): Shortage of WASH facilities and systems to provide for the increased numbers of refugees in the gatherings; Pressure on health coverage and facilities with the arrival of PRS on host communities; Lack of personal hygiene tools and items; Inadequate environmental and WASH conditions in shelters mostly inhabited by PRS households; Inadequate menstrual hygiene practices and awareness; Problems related to lice and scabies; Lack of women specific hygiene items and preventive measures against hygiene born diseases; Lack of a local reference system in the gatherings to alert NGOs on needed priorities; Increased production of solid waste; Risky behaviour in terms of using resources. Implementation of the pilot campaign has started in 24 June 2014, with a clean-up campaign that took place in the gathering of Maachouk in Tyr area. Furthermore, UNDP and Nabaaa coordinated with religious leaders in South Lebanon to include messages on water conservation and household and personal hygiene in Friday sermons during Ramadan, and distributed Ramadan calendars that include messages on hygiene and water conservation (attached in Annex 8). Start and End Date: April 2014 – December 2014. % Progress to date: 35% |
| Quality Criteria | Date | Results of Activities |
|  |  | User Perspective | Resource Status | Timeliness |
| Roll out hygiene campaign in South Lebanon | Dec 2014 | Hygiene campaign developed Implementation of pilot campaign started. |  | 100% |
| Activity 1.4.6 Provide technical assistance, monitor, evaluate and report. Indicators: Start and End Date: January 2014 – December 2014. % Progress to date: |
| Quality Criteria | Date | Results of Activities |
|  |  | User Perspective | Resource Status | Timeliness |
| Roll out hygiene campaign in South Lebanon | Dec 2014 | Hygiene campaign developed Implementation of pilot campaign started. |  | 100% |
| Financial |
| Account | Fund | Donor | R. Party | Budget (USD) | Expenditure (USD) | Balance (USD) |
| 71300 | 32045 | 00141 | UNDP/PG | 14,000.00 | 9,830.00 | 4,170.00 |
| 71400 | 32045 | 00141 | UNDP/PG | 33,662.48 | 1769.74 | 31,892.74 |
| 72100 | 32045 | 00141 | UNDP/PG | 100,000.00 | 1450.00 | 98,550.00 |
| 72400 | 32045 | 00141 | UNDP/PG | 1,500.00 |  | 1,500 |
| 72500 | 32045 | 00141 | UNDP/PG | 1,690.02 |  | 1,690.02 |
| 72600 | 32045 | 00141 | UNDP/PG | 20,000.00 |  | 20,000.00 |
| 72800 | 32045 | 00141 | UNDP/PG | 1,000.00 |  | 1,000.00 |
| 73100 | 32045 | 00141 | UNDP/PG | 4,000.00 |  | 4,000.00 |
| 73400 | 32045 | 00141 | UNDP/PG | 1,000.00 |  | 1,000.00 |
| 74200 | 32045 | 00141 | UNDP/PG | 1,500.00 |  | 1,500.00 |
| 74500 | 32045 | 00141 | UNDP/PG | 1,500.00 |  | 1,500.00 |
| 75100 | 32045 | 00141 | UNDP/PG | 14,548.20 | 1,043.97 | 13,504.23 |
| 75700 | 32045 | 00141 | UNDP/PG | 2,000.00 |  | 2,000.00 |
| 71300 | 32045 | 00141 | UNDP/PG | 8,000.00 |  | 8,000.00 |
| 71400 | 32045 | 00141 | UNDP/PG | 23,017.87 |  | 23,017.87 |
| 72100 | 32045 | 00141 | UNDP/PG | 70,000.00 |  | 70,000.00 |
| 75100 | 32045 | 00141 | UNDP/PG | 8,081.43 |  | 8,081.43 |
| Total |  |  |  | 305,500.00 | 14,093.71 | 291,406.29 |