Annual Project Review Report

Project: Strengthening Disaster Risk Management Capacities in Lebanon

Project ID: 00071806

Period covered:  January to December 2013

Table of Contents

1- List of Abbreviations	3

2- Project Background and Objectives	4

3- Project Performance 	4

1. CP outcome, indicators, baselines and targets as taken from the M&E Plan……….4

2. Update on outcomes………………………………………………………………………5

3. Annual outputs…………………………………………………………………..…………6

4. Achievements of the project in outputs …………………………………………………7

5. Reason if progress below target output and target……………………………………13

6. Update on partnership strategies reporting…………………………………………….13

7. Recommendations and proposed action……………………………………………….14

4- Project Performance  - Implementation Issues ……………………………………...15

5- Soft Assistance…………………………………………………………………………….15

6- Lessons Learnt……………………………………………………………………………..15

7- Annex1: Prime Minister’s Decision 41/2013: Formation of a committee to coordinate national disaster and crisis response………………………………………16

8- Annex 2: Press Releases of major project activities………………………………..19

9- Annex 3: TOR Consultant Table Top Exercise……………………………..………...25

- List of Abbreviations

DRM			Disaster Risk Management

PMO			Prime Minister Office

NCC			National Coordination Committee

COM			Council of Ministers

UNDP			United Nations Development Programme

DRR			Disaster Risk Reduction

NRP			National Response Plan

HFA			Hyogo Framework of Action

UNHCR		United Nations High Commissioner for Refugees

NOR			National Operations Room

MOR			Mobile Operation Room

CBRN			Chemical – Biological – Radioactive - Nuclear

BRHIA			Beirut Rafik Hariri International Airport

UN ISDR 		United Nations Office for Disaster Reduction

INSARAG		International Search and Rescue Advisory Group

CDR			Council for Development and Reconstruction

NGO			None Governmental Organizations

LAF			Lebanese Armed Forces

ISF			Internal Security Forces

CDR			Council for Development and Reconstruction

CNRS			National Council for Scientific Research

LRC			Lebanese Red Cross

NCLW			National Commission for Lebanese Women

GARD			Getting Airport Ready for Disasters

WHO			World Health Organization

SOP			Standard Operating Procedures

QPR			Quarterly Progress Report

APR			Annual Progress Report

M&E			Monitoring and Evaluation

- Project Background and Objectives

Lebanon is subject to a wide range of natural hazards, the biggest threat being of a severe earthquake and/or an associated Tsunami. Smaller-scale disasters which the country also faces include floods, forest fires, land-slides and drought. Accordingly, in May 2009, UNDP and the Lebanese Government represented by the Prime Minister signed a project document on “Strengthening Disaster Risk Management Capacities in Lebanon”. The project aims to help the Lebanese Government develop its disaster management and corresponding risk reduction strategy.

In order to achieve its outcome “mainstreaming disaster preparedness and management in national development framework strategies in Lebanon”, the project needed to evolve through two main phases to provide a stable platform for future developments.

In Phase I (2010-2011-2012), the focus was on initiating a framework at the National level as part of the following outputs:

- Disaster Risk Reduction and Management Unit Established

- National DRR strategy and systems developed and implemented

- Building National capacities at central and regional levels

- Public Awareness on DRR raised

- Gender Equality initiatives integrated into DRR Institutional framework and Regional and Local Plans.

Objectives:

The objectives of Phase II (2013-2014-2015), consist in finalizing the work previously done in addition to targeting sectoral and local levels with a particular concentration on capacity building focusing on highly vulnerable groups as part of the following outputs:

- Institutional mechanisms for DRM established with sufficient capacities to increase national resilience against disaster risks

- DRR considerations integrated into development planning of critical economic and social sectors to reduce vulnerability of development infrastructure and assets

- Local and community capacity for disaster risk reduction enhanced to reduce losses to life and property.

3- Project Performance

- Country Programme outcome, indicators, baselines and targets as taken from the M&E Plan

The project aims to help the Lebanese Government develop its disaster management and corresponding risk reduction strategy. In order to achieve its outcome “mainstreaming disaster preparedness and management in national development framework strategies in Lebanon”, the project evolved in two phases Phase I (2010-2011-2012), the focus was on initiating a framework at the National level while Phase II (2013-2014-2015), consists in finalizing the work previously done in addition to targeting sectoral and local levels with a particular concentration on capacity building focusing on highly vulnerable groups. This annual project report summarizes the results of the first year of phase II of the project.

- Update on outcomes

In 2013, the Disaster Risk Management project has made significant progress towards achieving the results of several project objectives, outcomes and activities at the national, sectoral and local levels. At the national level there has been steady increase in governmental support and a stronger engagement at the institutional level which has been reflected through the establishment and mandate of the National Coordination Committee (NCC) by the Prime Minister. The NCC was mandated in February 2013 by decision number 41/2013 under the chairmanship of the Secretary of the Supreme Council for Defense and the membership of major relief commission departments and director generals of concerned relevant ministries including the project staff. The NCC has provided a major boost for DRM at the national level, the work of this committee is very promising making it a reference in natural as well as man-made disasters and supporting increasing Lebanon's resilience.

A major breakthrough progress at the national level has been accomplished in 2013 through the finalization of the National Response Plan which has become a reference document for all concerned agencies, stakeholders and decision makers. The impact and influence of the NRP was seen with the design and implementation of the first-ever table top exercise based on the request from the Prime Minister following the explosions that took place in summer 2013 which ensured a holistic management approach and strategic coordination in response to disasters that caters to the needs and maximizes the impact in the management of resources, information and disaster mitigation. The success of the table top exercise was so evident that it triggered the PM's decision to call the NCC which includes the project to convene as a result of any major disaster and implement the National Response Plan. In 2014, the DRM project will support the government among others in equipping the much needed National Operations Room for natural and man-made disasters management so it can be fully functional and operational.

Another significant progress is reflected in the submission of the final flood assessment report by the CNRS and the valuable maps realized with data and information as well as recommendations. For the first time Lebanon has flood hazard intensity maps and flood hazard maps necessary for increasing and improving decision making capabilities in planning.

At the local level the development of response plans for the Caza of Jbeil has been achieved which has supported in strengthening regional and local level management in their response to disasters. Supporting other major municipalities such as Beirut, Tripoli and Saida in their response plans is also considered a significant progress towards building the capacities of local authorities, increasing their resilience to both natural and man-made disasters and increasing community awareness on disaster risk reduction.

Local and community awareness on DRR has been enhanced through the DRM project's collaboration with universities, NGO's and others.

Since building partnerships with various stakeholders is vital to the success of the project objective, the DRM Unit continued to build partnerships with several potential collaboration among multiple local and international agencies including the Italian Civil Protection and French Consulate who are willing to support the Lebanese government through the DRM Project to strengthen its capacities in disaster risk management and share know-how and experience.

The DRM Project looks forward to a year full of promise and potentials for DRM to become a flagship of resilience in times of crisis.

- Annual Outputs

The annual project outputs in 2013 are the achievements of the 3 intended project outputs and their respective activities as described in the original workplan, to be specific:

Output 1: Institutional mechanisms for DRM established with sufficient capacities to increase resilience against disaster risks.

1.1. Follow up on the DRM Project Operational issues

1.2. HFA progress report finalized and submitted to UNISDR

1.3. Finalize, approve and implement the National Response Plan

1.4. Finalize the National Strategy

1.5. Plan, establish and follow up on NDMA structure, regulatory and implementation

1.6. Training sessions for Parliamentarians, media, religious leaders and government officers

1.7. DRR Day related awareness activities for stakeholders

1.8. Documentary 12 episodes on TV (6 for hazards and 6 sectors)

1.9. Early Recovery Workshop with UNISDR

1.10. Regional Gender and DRR Workshop to be organized on the 8th of March

1.11. Printing and Publications

Output 2: DRR Considerations integrated into development planning of critical economic and social sectors to reduce vulnerability of development infrastructure and assets

2.1. Supporting the CNRS monitoring hazards and conducting analysis (early warning systems):

2.2. INSARAG search and rescue training with 100 members of LAF, Civil Defense, Red Cross, ISF

2.3. Expanding the E- Library on the DRM-project portal

2.4. Collaboration with the Ministry Of Public works and transportation and the CDR

2.5. Expanding the E- Library on the DRM-project portal

2.6. Elaborating a DRR Curriculum

2.7. Cultural Heritage and DRR

2.8. Collaboration with Universities

2.9. Collaboration with the Ministry of Information and Relevant Media agencies

2.10. Collaboration with the Ministry of Industry and the Association of Lebanese Industrialists

2.11. Collaboration with the Ministry of Social Affairs

Output 3: Local and community Capacity for DRR enhanced to reduce losses to life and property

3.1. Risk Assessment and DRR Integration in Municipalities

3.2. Capacity Building leading to Institutional arrangements within Municipalities

3.3. Community awareness

- Achievements of the project in outputs

2013 is the first year of the second phase of the project implementation; most of the outputs achieved are of developed nature. Solid and concrete results have been achieved with multiplier effects; major stakeholders are becoming increasingly dedicated and committed to mainstreaming DRM into national, sectoral and local plans.

Output 1: Institutional mechanisms for DRM established with sufficient capacities to increase resilience against disaster risks.

1.2. HFA progress report finalized and submitted to UNISDR

The 2nd and updated national progress report of the Hyogo Framework of action was submitted in April 2013. The report includes major results accomplished during the reporting period, strategic objectives, progress made and challenges faced as well as the way forward to accomplishing the 5 set priorities of action for 2005- 2015. The progress report supports in understanding existing gaps and challenges in disaster risk reduction as well as enhance understanding among major concerned agencies and stakeholders on disaster risk reduction. The report also supports setting up a baseline for future progress.

1.2.3. Support 18 stakeholders to attend the Global Platform in Geneva

Despite the fact of care taker government and lack of funds a Lebanese delegation of 18 major stakeholders including the Minister of Environment and DRM project manager was formed and actively participated in the Global Platform for Disaster Risk Reduction forum which was held in May 2013 in Geneva. The forum is the world's foremost gathering of stakeholders committed to reducing disaster risk and building the resilience of communities and nations.

The Lebanese delegation was very active and participated in several workshops; delegates gave presentations in the conference. The Global platform served the Lebanese delegation and DRM Project to exchange information, build partnerships across sectors and improve implementation of disaster risk reduction through better communication and coordination amongst stakeholders and share experiences.

1.3. Finalize, approve and implement the National Response Plan (NRP)

The DRM Project concluded an important task within the project through the accomplishment of the NRP which is now considered as the reference for all agencies in the event of any natural or man-made disaster. This step has paved the way for the proper implementation and endorsement of the NRF at the National level. The NRP is considered the blueprint guideline for the response plans at the sectoral and local levels. This major result that took about three years of work accomplished a significant project achievement at the national level.

1.3.2. Simulation on the NRP (LAF, UNIFIL, and other stakeholders)

Within the framework of the implementation of the national response plan and the request of the Prime Minister to implement a table top exercise for the coordination among concerned sectors. A table top exercise which is considered the first of its kind in Lebanon was prepared by the NCC's “Technical Coordination Committee” with the objective of testing the NRP in terms in inter-ministerial coordination in the event of a disaster. The table top exercise was implemented on the 30th of October 2013 at the Grand Serail with the participation of Prime Minister Mikati, President of the NCC and Secretary-General of the Supreme Council for the defense General Kheir, UNDP Country Director Mr. Luca Renda, the director generals of the concerned agencies, members of the technical committee,  Army command operations, representatives of the Internal Security Forces, Civil defense, Lebanese Red Cross, Beirut Fire Brigade, and the DRM project, consultant and team.

The importance of this exercise also lies in the cooperation and work among all concerned agencies and bodies in one place through a National Operations Room to coordinate response and unify efforts. The success of the table top exercise was so evident that it triggered the PM's decision to call the NCC which includes the DRM Unit to convene as a result of any major disaster and implement the National Response Plan.

1.3.3 / 1.3.4 Study tour for Operation Group

With the objective to enhance the capacities of the Lebanese response agencies and learn from the Italian experience which can be customized to the Lebanese context. he DRM Project with the support of TAIEX the "Technical Assistance, Information and Exchange" at the EU implemented a study visit to the Italian National Civil Protection Department in November 2013 through a delegation including the project manager of the DRM Project, a representative of the general defense council, and the director of the Remote Sensing Centre at CNRS.

The study tour which serves the project in increasing technical know-how and expertise attained its objective and set forth potential cooperation with the Italian National Civil Protection Department who is willing and able to provide support and to start a bilateral cooperation agreement with the DRM Project.

1.5 Awareness of key stakeholders and general public enhanced about disaster risks facing Lebanon and strategies to address them

1.5.1. Organize training sessions for Parliamentarians, Media, Religious Leaders and Government officers

As part of raising awareness and coordinating with different concerned entities including the public sector the DRM Project launched a series of trainings for the first time for the public sector entities and implemented two trainings the first on the 10th and 12th of and the second on the 24th and 25th of October for the staff and management within the Presidency of Council of Ministers at the Grand Serail targeting more than 80 personnel. Moreover training for the Internal security forces was launched in December targeting more than 60 members.

The DRM project liaised with the Lebanese Army, Civil Defense and Red Cross to implement the trainings which extend for two days

These pilot trainings and drills have become success models for raising awareness among both the public and private sector agencies.

These trainings add noteworthy value to project objectives as they support saving lives, protecting assets not only in the work place but in households and communities.

1.7. DRR Day related awareness activities for stakeholders

Since the IDRR includes raising awareness about the importance of DRR and encouraging every citizen and government to take part in building more disaster resilient communities and nations. The DRM project prepared several activities which were launched as of October 2013 until the end of December 2013 and which included:
a) Drills conducted in universities as mentioned in BAU and LAU Universities which included training their core groups on first aid, search and rescue, as well as securing the perimeter for response agencies to intervene and training on evacuation plans.

b) Distribution of Emergency kits: Within the context of spreading awareness on disaster risk reduction and safety measures and as part of strengthening the capacities of the personnel and management in private and public institutions to respond efficiently and effectively in the event of an emergency, the DRM Project will be distributing 300 prototype emergency kits to public and private institutions during December 2013 so they can also replicate them within their environment and help spread safety and DRR messages.

1.9. Early Recovery Workshop with UNISDR

The DRM Project in collaboration with the Prime Minister’s Office, UNISDR, IRP, UNDP implemented a workshop that was presented by UNISDR team on disaster recovery planning at the Grand Serail in Beirut, in October 2013. The workshop that was supported through EC-funded project included around 25 high-level officials from different ministries who explored options of recovery from disasters and conflicts.

Various aspects of recovery planning were discussed in the workshop. In particular, strategies and actions to “build back better” after disaster and conflict were explored using local and global cases as reference. The lessons on recovery, as compiled by IRP from different experiences around the globe provided the participants additional input to build on the existing government initiatives. The project will utilize the gained know-how and skills in its work on disaster recovery planning within the context of the project objectives.

1.10. Gender and DRR: NCLW Grant Agreement to increase level of DRR awareness in Mount Lebanon and North Lebanon

Within the project on “Gender and DRR activities” co-organized by the National Commission for Lebanese Women (NCLW) and DRM project which aims at raising awareness and improving the capabilities of women and girls in situations of natural disasters and in preparing them to prevent such situations, which ultimately supports mainstreaming gender into disaster risk reduction.

The NCLW organized three training workshops in 2013 one in Baabda, one in Tripoli and one in Zahle for its different beneficiaries. Each workshop included more than 25 participants representing NGO's and women in municipalities. The workshops included sessions by the DRM Project on DRR and DRM concepts and the role of women in DRR as well as on the Hyogo Framework of Action HFA, Briefings on natural disasters in Lebanon and the of Red Cross in relief. The DRM Project support for those workshops comes from the project objective of empowering women since they have significant contributions in building community resilience to disasters, crisis, prevention and recovery.

Output 2: DRR Considerations integrated into development planning of critical economic and social sectors to reduce vulnerability of development infrastructure and assets

2.1. Building Capacities of CNRS

2.1.7. Updating of hazard maps for all important hazards including earthquakes, floods, forest fires, tsunamis and landslides

Based on UNDP's project "Flood hazard mapping assessment for Lebanon" which aims to improve the government's capacities in disaster preparedness and to support the National Strategy for disaster risk management, relevant data was gathered and organized to get a hazard picture for different Lebanese regions. A "Flood Hazard Mapping Assessment" report was developed and submitted by CNRS to the DRM project. The report sums up all data acquisition, historical and literature review and flood plain delineation to hazard mapping. It scans through the major physical and hydrological characteristics of the Lebanese watershed.

With the completion of the report another important project objective has been attained that will serve future actions and plans for disaster risk reduction at the national, sectoral and local levels.

2.3. Collaboration with the Ministry of Public Work and Transportation in assessing BRHIA

2.3.1. Implement the GARD Plan

2.3.2. Simulation on the final GARD Plan

As part of the national response plan activities, Lebanon raised its national capacities in Getting Airports Ready for Disaster (GARD) by implementing a pioneer simulation to test its communication methods between different concerned agencies and shift work from theoretical to practical with the objective of increasing the effectiveness of response.

The simulation was implemented on the 4th of April 2013, in cooperation with GARD program at Rafic Hariri International Airport in Beirut and at Rayak military base with the participation of the Lebanese army, the General Directorate of Civil Aviation, airport security, the Directorate General of Customs, service and freight companies at the airport, civil defense, the Lebanese Red Cross and Beirut Fire Brigade. The simulation supported assessing and evaluating the situation leading to better and more effective decision making. Moreover the simulations helped in developing plans to increase the effectiveness of concerned response agencies during disasters and crises.

The evaluation meeting which followed the simulation reviewed the strength and weaknesses of the simulation and set valuable recommendations essential for the success of GARD including the need for equipment and regular GARD drills. Having practical actions within the project is necessary to prepare and equip the airport staff with the necessary skills as well as supporting effective relief, better coordination among agencies and response in case of disasters and fill in the gaps.

2.8. Collaboration with Universities

2.8.1. Drills with LAF, LRC, and Civil Defense in 5 different Universities

In accordance with project outputs to increase awareness, preparedness and emergency management of public and private institutions the Disaster Risk Management DRM Project implemented two pilot trainings and drills at LAU and in BAU in September 2013 with more than 25 participants in each training. The main targets included security, staff, management, and students. These trainings are attaining their goals with a ripple effect as they help large institutions increase their awareness on disaster risk reduction and getting prepared for disasters.

Output 3: Local and community Capacity for DRR enhanced to reduce losses to life and property

3.1.2. A plan prepared to reduce vulnerabilities of the municipal offices and services to disasters

Byblos Cooperation:

A risk assessment was implemented by the DRM Project through a Norwegian consultant. The assessment highlighted the major vulnerabilities in municipal offices as well as services in the municipality and set recommendations. Following the risk assessment a consultant from the DRM Project was appointed to support the development of the response plan for the Caza of Byblos. After four months of meetings with concerned agencies the response plan was concluded in November 2013. The results and report support project objectives at the local level by building the  capacity of local stakeholders on emergency preparedness, response and risk reduction for communities and ultimately in mainstreaming disaster risk management into overall development planning in urban areas. 
Work is currently being made for the preparation of a simulation of an earthquake associated with a tsunami and putting in place and testing the effectiveness and efficiency of the response plan put in place.

Beirut Municipality Cooperation:

The DRM Project has finalized the Beirut response plan that will be discussed with Beirut governor. Moreover, the DRM Project started cooperation with the municipality to implement a risk assessment which includes major offices and services as well as prepare for an earthquake master plan for the city of Beirut with the objective of making Beirut the nation's capital more resilient to such risks by providing pilot projects that can be replicated and by increasing awareness. The ultimate objective is making Beirut a role model city to potential natural and man-made disaster. In addition to that a project proposal has been developed and discussed with the municipality as well as concerned stakeholders.

Saida Municipality Cooperation

In accordance with supporting major Lebanese cities and based on  meetings held with the representatives and mayor of Saida municipality an agreement has been made for the drafting of the 1st draft of response plan and relevant SOP's. A consultant was assigned and the cooperation with the municipality started in July 2013, however the political situation in the city has halted the meetings nevertheless the municipality is keen to start preparing the response plan as soon as possible.

Tripoli Municipality Cooperation

Following the meetings and request of the PM the DRM Project has been actively participating in through the DRM Project and consultant in the meetings for Tripoli with the purpose of reactivating the operations room in Tripoli and preparing a response plan for Tripoli. As such the DRM Project consultant has been appointed for this purpose to help in the development of a response plan for Tripoli, the activation and equipment of the disaster management room and trainings with the objective of enhancing emergency response for all types of disasters that might happen in Tripoli.

- Reason if progress below target

Despite the progress and accomplishments achieved, several actions could not be completed during the first year of the project. A vital output that could not be accomplished in 2013 was the establishment of the national operations room, the main bottleneck is in the necessary funds required for the completion the operations room, currently UNDP has allocated a sum of 50,000USD for the operations room, more funds are expected to come to accomplish this objective.

Another challenge the DRM project faces is in having a full staff working on DRM at the local, sectoral and national level, currently the DRM Project is functioning with minimal staff with increasing need to support DRR measures at different levels.

Targets within the projects have been shifted mainly to response to disasters as a result of the political and security situation and Syrian Crisis.

- Update on partnership

Despite the fact that country is in a care talking government since March 2013 and there has been an increase in man-made disasters through explosions since summer 2013, nevertheless the work of the project has been boosted at the national and agency levels with DRM becoming a necessity uniting efforts for mainstreaming DRM at the national, sectoral and local levels. The government has increased its support by levering the work of the DRM Project and NCC through an official decree. Better coordination among agencies has been ensured mainly through the NCC which enhanced project implementation especially regarding response both to natural and man-made disasters.

Partnerships with governmental, ministry, local level authorities and academic institutions has increased as more requests for supporting them in preparing their contingency plans and increasing awareness is being reported.

The project has played an active role in supporting in day-to-day project management, coordination among donors and agencies, reporting work etc.

The DRM project's partnership with UNISDR is maintained with exchange of information, workshop activities of the project.

- Recommendations and proposed action

According to the project document the executive period of phase II of the project shall be three years. So far UNDP and SDC have financially contributed to the project implementation of the project activities and objectives.

Project activities are shifting more and more to response as a result of the current political instability the country is facing.

The main actions in line with project objectives and desired outcomes as per the annual for plan for 2014 include:

Output 1: Institutional mechanisms for DRM established with sufficient capacities to

increase resilience against disaster risks

- Supporting the establishment and set up of a fully functional and operational central National Operations Room (NOR).

- Supporting the National Coordination Committee to finalize the CBRN Response Plan and integrate it within the National Response Framework

- Developing the National Strategy for Early Recovery System

- Enhancing awareness of key stakeholders and general public about disaster risks facing Lebanon and strategies to address them

Output 2: DRR Considerations integrated into development planning of critical economic and social sectors to reduce vulnerability of development infrastructure and assets

- Supporting the CNRS monitoring hazards and conducting analysis (early warning systems

- Collaborating and support of concerned Ministries

- Supporting and setting up coordination with the Ministry of Education to develop its response plan and establish its disaster management cell

- Supporting and setting up coordination with the Ministry of Public Health/WHO/ Red Cross

- Supporting and setting up coordination with the Ministry of Social Affairs to develop its response plan and establish its disaster management cell

- Coordinating with BRHIA and military airports for logistics needs

- Introducing DRR concepts into the ENA and Military Academy Curriculums

- Collaborating with the Ministry Of Public works and transportation and the CDR to develop its response plan and establish its disaster management cell

- Supporting Cultural Heritage by implementing workshops on cultural heritage preservation and identifying different cultural sites at risk to be assessed.

Output3:  Local and community Capacity for DRR enhanced to reduce losses to life and property

- Supporting  Lebanon's 6 Mouhafazat/ Districts and for 10 Municipalities with highest influx of Syrian refugees and vulnerable area to develop their response plans

- Supporting local authorities with high influx of Syrian refugees in critical areas to adopt resilient cities

- Community awareness

- Capacity Building leading to Institutional arrangements within municipalities

4. Project Performance – Implementation Issues

- The main bottleneck remains in the necessary funds required for the completion of the set activities.

- Moreover, at the national and political level, one of the greatest challenges remains with the political instability. The country is paralyzed as Lebanon is still in a caretaker government due to political disagreements. In May 2013 the parliament voted to put off elections until November 2014 because of security concerns, no parliamentarian meetings have been held and presidential elections are near with no clear solutions in the horizons all of which add to the very much complicated situation.

- Moreover according to UNHCR 20% of Lebanon's population is now composed of Syrian refugees this increasing rate of refugees is alarming. Lebanon currently hosts 36 % of the Syrian refugees present in the area. The situation becomes even more aggravated as most of them suffer from non-adequate infrastructure or services neither for them nor for their host communities posing more threats and tensions into already vulnerable areas and communities.

5. Soft Assistance

The DRM project undertook several activities that were not envisaged in the work plan for 2013. This is mainly reflected in two actions:

- The DRM acted as the consultant for the parliamentary special commission that is discussing the DRR law.

- The DRM Project was appointed as member and technical advisor and support to the national coordination committee for response to disasters.

Main constraints in progress towards outcome that require additional soft assistance:

- The political impasse that cannot support the adoption of the DRR law and its related regulations.

Proposed elements for soft assistance strategy for the next year:

- Support for the DRR law to be approved and adopted.

- Lessons Learned

- Engagement and involvement of high and low level decision makers in DRM supports in elevating the momentum of work especially in response to man-made and natural disasters.

- International know-how and trainings mainly the training on recovery planning and how to build better, were the case studies and concrete examples that were shared can be used as models for Lebanon.

- Permanent coordination and cooperation among key stakeholders is vital

- Annex 1: Prime Minister’s Decision 41/2013: Formation of a committee to coordinate national disaster and crisis response

- Annex 2: Press Releases of major project activities

## ميقاتي افتتح مناورة حول سيناريو وقوع انفجار : لتعميم التنسيق بين مختلف الادارات تحسينا للاداء

الأربعاء 30 تشرين الأول 2013 الساعة 11:25

وطنية - أكد الرئيس نجيب ميقاتي أن "التنسيق بين مختلف الادارات اللبنانية هو أمر نحتاج الى تعميمه ليس فقط على مستوى ادارة الكوارث بل ايضا على مستوى الاشغال اليومية توفيرا للمال والوقت"، متمنيا أن "يكون هذا التنسيق نحو الأفضل دائما وفي سبيل تحسين الاداء".
كان الرئيس ميقاتي يتحدث قبل ظهر اليوم في السرايا في بداية "مناورة مكتبية حول سيناريو وقوع إنفجار" أقامتها "اللجنة الوطنية لتنسيق عمليات مواجهة الكوارث والأزمات" التي شكلها رئيس الحكومة في 18 شباط من العام الحالي برئاسة الأمين العام للمجلس الأعلى للدفاع اللواء محمد خير وعضوية المدراء العامين للوزارات المعنية وممثلين عن الادارات والهيئات اللبنانية، وذلك وفق الإطار العام لخطة الاستجابة الوطنية خلال الكوارث والأزمات على أنواعها الذي تم تطويره بالتعاون مع برنامج الأمم المتحدة الإنمائي.
وقد أعطيت هذه اللجنة صلاحية المباشرة بتطبيق الآليات المقترحة لإدارة الكوارث والأزمات، كما تنص الآلية التنظيمية على دور كل وزارة وإدارة ومسؤولياتها وآليات التنسيق والتواصل في ما بين الأجهزة المعنية لمعالجة تداعيات الأزمات والكوارث بالسرعة والفاعلية المطلوبة لإنقاذ الأرواح والمحافظة على الممتلكات. 
شارك في المناورة أعضاء اللجنة برئاسة اللواء خير، مدير برنامج الأمم المتحدة الإنمائي لوكا رندا، أعضاء اللجنة التقنية، عمليات قيادة الجيش، عمليات قوى الأمن الداخلي، عمليات الدفاع المدني، عمليات الصليب الأحمر اللبناني، عمليات فوج إطفاء بيروت وفريق عمل وحدة إدارة مخاطر الكوارث لدى رئاسة مجلس الوزراء.
اللواء خير 
بداية تحدث اللواء الركن خير فقال:"ان هذا التمرين هو الأول من نوعه في لبنان، بحيث يجتمع وللمرة الأولى ممثلون عن مختلف الوزارات والإدارات الرسمية المعنية بالاستجابة خلال الكوارث لإدارة أزمة وطنية. ويعتبر هذا التمرين فرصة لاختبار قدرة الوزارات والإدارات المعنية كافة على الاتصال والتواصل والتنسيق في ما بينها خلال أوقات الأزمات والكوارث من خلال تفعيل غرفة إدارة الأزمات المقترح أنشاؤها في الإطار العام لخطة الاستجابة الوطنية. يهدف هذا التمرين بشكل خاص الى اختبار تطبيق آلية تفعيل عمل لجنة التنسيق الوطنية لمواجهة الكوارث والأزمات المشكلة من قبل رئيس مجلس الوزراء، وتدريب المسؤولين وأركانهم على العمل المتناسق في ما بينهم، وعلى تقدير الموقف السريع واتخاذ القرار السليم في الوقت المناسب، بالإضافة إلى تدريب القادة الأمنيين على التنسيق في ما بينهم بالدرجة الأولى ومع الأجهزة الأمنية والمدنية".
برنامج الأمم المتحدة الإنمائي
ثم تحدث مدير برنامج الأمم المتحدة الإنمائي لوكا رندا فقال:"ان الحؤول دون المخاطر الطبيعية أو الدراماتيكية كالتي شهدتها الضاحية الجنوبية وطرابلس أخيرا صعب جدا، ان لم يكن مستحيلا، الا أنه يمكن الحد من تبعات هذه الكوارث من خلال الاستعداد لها واستجابة الحكومة على المستويات المحلية والاقليمية والوطنية".
أضاف :"ان مشروعنا يشمل خطة تساهم في تعزيز استجابة الحكومة أمام الكوارث أكانت طبيعية أم من صنع الانسان، الامر الذي يتلاقى مع أولويات "خارطة الطريق لتأمين الاستقرار" التي قدمتها الحكومة اللبنانية أخيرا في واشنطن".
الرئيس ميقاتي 
وتحدث الرئيس ميقاتي فقال :"في ظل الظروف الراهنة المحدقة بلبنان والمنطقة، والتطورات التي تحصل، ومن موقعي كرئيس للحكومة مؤتمن على تطبيق الدستور والتنسيق ما بين الوزارات والإدارات، ومن قناعتي بأن الحكم استمرارية وأن حياة المواطنين وممتلكاتهم هي الأولوية، دعوت لجنتكم للاجتماع في آب 2013 إثر إنفجارات الرويس وطرابلس وطالبتكم بالبدء بتطبيق الخطة الوطنية لإدارة الكوارث التي تم إنجازها والتي تعهدت بتعميمها كي تصبح معتمدة إلزاميا من مختلف الوزارات والإدارات. وقد طلبت منكم العمل على إعداد مناورة أشارك فيها شخصيا لاختبار فاعلية الخطة ومكامن ضعفها. وها نحن على موعد اليوم مع مناورة مكتبية على أن تكون في المرة المقبلة مناورة حية ميدانية.
وختم :"إن ما تحقق هو خطوة اساسية على صعيد تفعيل العمل وتنسيقه بين مختلف الادارات اللبنانية وهو أمر نحتاج الى تعميمه، ليس فقط على مستوى ادارة الكوارث، بل ايضا على مستوى الاشغال اليومية توفيرا للمال والوقت. كل ما أتمناه في هذه المناسبة أن يكون التنسيق بين الادارات اللبنانية نحو الأفضل دائما وفي سبيل تحسين الاداء وليس لادارة الكوارث، لان اللبنانيين سئموا المآسي وباتوا يتطلعون الى حياة هادئة تطوى فيها مرحلة الحرب والمآسي والتفجيرات. شعبنا يستحق الحياة ومن حقه ان يعيش بهدوء وسلام".
ثم أعطى الرئيس ميقاتي إشارة الانطلاق لبدء المناورة. 


========== ج.س

Bottom of Form

## هيئة شؤون المرأة اطلقت ورشتها الثانية للحد من مخاطر الكوارث

الخميس 29 آب 2013 الساعة 16:22

وطنية - نظمت الهيئة الوطنية لشؤون المرأة اللبنانية بالتعاون مع برنامج الأمم المتحدة الإنمائي، على مدى يومين، ورشة عمل حول "كيفية الحد من مخاطر الكوارث على ضوء اتفاقية هيوغو"، في مركز التدريب التابع للهيئة في بعبدا، في حضور مندوبات عن منظمات غير حكومية تهتم بشؤون المرأة ومندوبات عن بلديات في منطقة جبل لبنان.
وهذه الورشة هي الثانية ضمن سلسلة ورشات العمل حول "الحد من مخاطر الكوارث"، في إطار "دمج النوع الاجتماعي في خطة عمل هيوغو"، هدفها "رفع مستوى الوعي وتحسين الجهوزية لدى المرأة لمواجهة المخاطر الناجمة عن الكوارث والمخاطر الطبيعية".
وأطلقت الورشة، ممثلة الهيئة الدكتورة نجوى نصر، تلتها مديرة "وحدة إدارة الكوارث التابعة لرئاسة مجلس الوزراء اللبناني" ممثلة "برنامج الأمم المتحدة الإنمائي" نتالي زعرور.
ففي المحور الأول، قدمت الدكتورة فاديا كيوان، مفهومي إدارة مخاطر الكوارث "DRM" وتخفيف مخاطر الكوارث "DRR" من منظور النوع الاجتماعي. وتلتها في المحور الثاني سوسن بو فخر الدين التي قدمت إطار عمل اتفاقية هيوغو.
وفي المحور الأول من اليوم الثاني، قدمت المهندسة مارلين براكس، المخاطر الطبيعية التي نواجهها في لبنان، بعدها عرض شربل عيدموني نشاطات الإغاثة التي يقوم بها الصليب الأحمر اللبناني في حالات الطوارىء.

وكانت المشاركات قد توزعن على مجموعات عمل لمناقشة المواضيع المطروحة، وخلصن إلى رفع توصيات تتعلق ب"كيفية تطبيق اتفاقية عمل هيوغو والتدابير التي يجب اتباعها للتخفيف من نتائج المخاطر". 

============م.ع.ش.

## لجنة إدارة الكوارث: وفد من هيئة الاغاثة سيتوجه غدا إلى حارة حريك للاطلاع على الأضرار
الخميس 02 كانون الثاني 2014

وطنية - صدر عن اللجنة الوطنية لإدارة الكوارث والأزمات في السراي الحكومي البيان الآتي: "بتوجيهات من دولة رئيس مجلس الوزراء الأستاذ نجيب ميقاتي، عقدت اللجنة الوطنية لمواجهة الكوارث والأزمات إجتماعا طارئا في السرايا برئاسة الأمين العام للمجلس الأعلى للدفاع اللواء الركن محمد خير بحضور الأعضاء، وبحثت تداعيات الإنفجار الذي وقع حوالى الساعة الرابعة وعشر دقائق في الشارع العريض في منطقة حارة حريك - الضاحية الجنوبية، والذي أدى إلى استشهاد أربعة مواطنين وإصابة حوالى 74 آخرين، وفق إحصاءات وزارة الصحة العامة والصليب الأحمر اللبناني. كما تضرر عدد من المباني والمؤسسات والمحلات التجارية والسيارات في المكان الناتج عن انفجار سيارة غراند شيروكي سبق لقيادة الجيش أن عممت مواصفاته بتاريخ 20/12/2013. وتقوم الأجهزة الأمنية المختصة بتكليف من القضاء بضرب طوق أمني حول مسرح الجريمة للتحقيق في طبيعة الإنفجار وتطلب من المواطنين الإبتعاد عن المكان، تسهيلا لعمل الأجهزة الأمنية والعسكرية والدفاع المدني والإسعاف. وقد أوعزت وزارة الصحة العامة إلى المستشفيات والمراكز الطبية لاستقبال المصابين والحالات الناتجة من الإنفجار. كما عمدت شركة كهرباء لبنان إلى قطع التيار الكهربائي بسبب تضرر الشبكة على أن تعيد وصلها في الساعات القليلة المقبلة. هذا وتستمر اللجنة الوطنية لإدارة الكوارث والأزمات بإجتماعاتها للتنسيق ومتابعة التداعيات الناتجة من هذا العمل الإرهابي.

وسيتوجه وفد من الهيئة العليا للاغاثة إلى مكان الإنفجار لاطلاع ميدانيا على الأضرار التي سببها الإنفجار وتحديد الإحتياجات لمساعدة المواطنين المتضررين".

خير تفقد مكان الانفجار: معالجات فورية ومسح شامل للاضرار بعد انتهاء عمل الادلة الجنائية

الجمعة 27 كانون الأول 2013 الساعة 14:07

وطنية - جال الامين العام لهيئة ادارة الكوارث الامين العام للهيئة العليا للاغاثة اللواء محمد خير مكان الانفجار في الستاركو متفقدا الاضرار، وقال: "بداية الرحمة للشهداء والشفاء العاجل للجرحى".

اضاف: "بعد عقد الاجتماع الفوري في القصر الحكومي للجنة الوطنية لهيئة ادارة الكوارث، بتوجيه من الرئيس نجيب ميقاتي وفي حضور جميع اعضائها، توجهنا الى مكان الانفجار واتخذنا الاجراءات المناسبة، وتمنينا على الاجهزة كافة اتخاذ الاجراءات والمعالجات الفورية للحؤول دون اعاقة حركة المواطنين. الانفجار كبير وقد أدى الى استشهاد معالي الوزير شطح رحمه الله وخمسة آخرين و70 جريحا توزعوا على المستشفيات، وهناك 7 جرحى في وضع حرج".

وأشار الى ان "الوزارات المعنية بدأت باتخاذ الاجراءات الفورية، ووزارة الصحة اعطت توجيهاتها للمستشفيات والصليب الاحمر والدفاع المدني لان يقوموا بواجبهم".

وقال: "لقد أعطينا توجيهاتنا للهيئة العليا للاغاثة بالمسح الفوري ومساعدة وتقديم ايواء لكل مواطن بحاجة لها، لان معظم المباني سكنية، وكل الاضرار اصبحت واضحة لدينا، وبعد انتهاء الادلة الجنائية سوف نقوم بالمسح الكامل ودفع التعويضات".

واوضح ان "الجيش يمنع حاليا الدخول الى المباني المتضررة، حفاظا على الملكية الخاصة، ونحن ننفذ توجيهات الهيئة العليا للكوارث وكل التعليمات الضرورية للحفاظ على الامن واملاك الناس". 



============= ن.م

## لبنان يتحضر لمواجهة العاصفة الكسا وارشادات وقائية

الإثنين 09 كانون الأول 2013 الساعة 20:12

وطنية - بدأ لبنان الرسمي والشعبي يتحضر للعاصفة الثلجية "الكسا" التي ستضرب لبنان مساء غد الثلاثاء.
ولهذه الغاية، عقدت اجتماعات في السراي الحكومي والمحافظات والقائمقاميات والبلديات للجنة ادارة الكوارث لمواجهة تداعيات العاصفة والتي من المتوقع ان تستمر حتى يوم الاثنين المقبل وستبلغ ذروتها يوم الاربعاء.
وقد تم وضع خطط تنفيذية لمواجهة العاصفة للحؤول دون تكبد خسائر ووقوع اضرار، وارشاد المواطنين للتقيد بتعليمات القوى الامنية ورجال الدفاع المدني والاطفاء الذين سيتواجدون على الطرق مع بدء العاصفة حفاظا على سلامتهم، وطلب من أهالي طلاب المدارس متابعة وسائل الاعلام لمعرفة ما سيصدر عن وزارة التربية والتعليم العالي.

كما طلب من المواطنين "متابعة الارشادات التي ستصدر عن الاجهزة المعنية حفاظا على سلامتهم.

9 - Annex 3: TOR Consultant Table Top Exercise

Terms of Reference (TOR)

Project Name: Support to the Prime Minister Office “Strengthening Disaster Risk Management Capacities”

Reference Number: 00071806

- Subject: Procurement of a National Consultant services to implement a Table-Top Exercise for the National Committee to Coordinate Disasters Management.

- Project Description

Lebanon is subject to a wide range of natural hazards, the biggest threat being of a severe earthquake and/or an associated Tsunami. Smaller-scale disasters which the country also faces include floods, forest fires, land-slides and drought. Accordingly, In May 2009, UNDP and the Lebanese Government represented by the Prime Minister signed a project document on “Strengthening Disaster Risk Management Capacities in Lebanon”. The project aims to help the Lebanese Government develop its disaster management and corresponding risk reduction strategy. In December 2009, a Project manager and a Project assistant were appointed, leading to the establishment of a Disaster Risk Management Project located within the Prime Minister’s office for a better coordination with relevant stakeholders. Today, the project is fully operational with qualified staff and equipped offices. Recent events, such as the Haiti Earthquake (January, 2010), the Ethiopian Airlines airplane crash (February, 2010) as well as recurring earthquakes in the South of Lebanon have prompted both internal and external focus on disaster risk reduction. In order to achieve its outcome “mainstreaming disaster preparedness and management in national development framework strategies in Lebanon”, the project needed to evolve through two main phases to provide a stable platform for future developments. In Phase I (2010-2011-2012), the focus was on initiating a framework at the National level as part of the following outputs: Disaster Risk Reduction and Management Project Established National DRR strategy and systems developed and implemented Building National capacities at central and regional levels Public Awareness on DRR raised Gender Equality initiatives integrated into DRR Institutional framework and Regional and Local Plans. Phase II (2013-2014-2015), on the other hand, will consist on finalizing the work previously done in addition to targeting sectoral and local levels with a particular concentration on capacity building focusing on highly vulnerable groups as part of the following outputs: Institutional mechanisms for DRM established with sufficient capacities to increase national resilience against disaster risks DRR considerations integrated into development planning of critical economic and social sectors to reduce vulnerability of development infrastructure and assets Local and community capacity for disaster risk reduction enhanced to reduce losses to life and property In February 2013, the Prime Minister established a National Committee to Coordinate Disasters Management headed by the Secretary General of the Highest Council of Defense and the membership of Directors General of all concerned ministries. The main mandate of this Committee is to undertake all needed actions in order to activate the National Response Framework during disasters. As such, coordination meetings, trainings and simulations were identified. Under the overall guidance of the National Focal Point and the direct supervision of the Project Manager/Programme Coordinator, the consultant will perform all tasks required for the implementation of the Table-Top exercise.

- Scope of Work

Under the supervision of the Disaster Risk Management Project Manager, the consultant will work on the below: Prepare the Table-Top Exercise for the National Committee to Coordinate Disasters Management, through: Facilitate the work of the technical committee responsible for developing the scenario and logistics needed for the simulation involving the Army, Internal Security Forces, Civil Defense, Beirut Fire Brigade, the High Council of Defense and the Lebanese Red Cross. Conduct regular meetings for all concerned stakeholders to develop the Scenario. Draft the Scenario of the table-top exercise including the SOPs and roles for all concerned agencies. Coordinate the implementation of the Table-Top Exercise and provide all needed technical assistance. Evaluate the Table-Top Exercise and write a full report about it. Integrate remarks and possible changes and lessons learned from the Table-Top Exercise in the National Disasters Response Framework.

- Expected Outputs and Deliverables

The following deliverables are expected: Table-Top Exercise implemented for the National Committee to Coordinate Disasters Management. Final report of the Table-Top exercise.

| Deliverables/ Outputs | Estimated Duration to Complete | Target Due Dates | Review and Approvals Required (Indicate designation of person who will review output and confirm acceptance) |
| --- | --- | --- | --- |
| Submission of the final report of the Table-Top Exercise | 2 months | End of October | Project manager |

- Institutional Arrangement

The contractor will liaise with the Project during the course of performing his work. The DRM Project will provide the needed logistic support for the meetings of the Technical Committee.

- Duration of Contract

- Duty Station

- Qualifications and Competencies:

Title: National Consultant services to implement the Table-Top Exercise The Individual Consultant should possess the following minimum qualifications: Academic Qualifications: University degree in the area of disaster risk management or relevant field Years of Experience: 5-7 years of experience in providing similar and/or related consultancy services to UN organizations, national government and other institutions Competencies: Proven experience in emergency response and preparedness at the national and regional levels; Prior knowledge of Lebanese disaster preparedness and risk management context including relevant policy and institutional frameworks; Experience working with the Government of Lebanon on disaster preparedness and other related issues is desirable. Fluency in oral and written Arabic and English, good command of French is desirable.

- Scope of Price Proposal and Schedule of Payments

The scope of price proposal is a lump sum amount, per deliverables.

- Upon Submission of the final report of the Table-Top Exercise: 4990 USD

J. Approval

This TOR is approved by:

Signature			________________________________

Name and Designation	________________________________

Date of Signing		________________________________

# Text boxes

2 months

The contractor will be conducting the meetings at the Grand Serail .

The Contractor is not required to report regularly or be present at a certain office during the mission.